Specification

North Northamptonshire Serious mental Illness and Mental Health inequalities

Contents

1.	Executive Summary	3

2.	Introduction	3

3.	Background	3

4.	Scope	6

5.	Supplier Responsibilities and Key Functions	6

6.	Statement of Requirements	8

7.	Social Value	12

8.	Continuous Improvement	12

9.	Data Management / UK General Data Protection Regulation (UK GDPR)	12

10.	Quality Requirements	14

11.	Delivery Plan and Implementation Milestones	20

12.	Contract Management, Performance Monitoring, and Review	21

13.	Risk Management	23

14.	Corporate Social Responsibility (CSR)	25

Annexes	27

Appendix 1 – Definitions	28

## Executive Summary

  - North Northamptonshire Council is commissioning a programme to reduce mental health inequalities, prioritising improved outcomes for people with Serious Mental Illness (SMI). The initiative will strengthen community capacity and promote equitable access to health and wellbeing support.

## Introduction

  - North Northamptonshire Council seeks a delivery partner to design and implement a community-focused programme addressing mental health inequalities, with a specific emphasis on improving outcomes for people living with Serious Mental Illness (SMI).

  - Mental health inequalities remain a significant public health concern, shaped by deprivation, discrimination, and barriers to accessible care. This programme will build on local progress in SMI physical health check uptake and expand community engagement to reduce disparities across the population

  - The total available funding for this programme is £70,000, which will be divided into three separate lots to enable a flexible and targeted delivery model. Suppliers may bid for one, multiple, or all lots, depending on their expertise, capacity, and alignment with local priorities.

  - Lot 1 – community awareness and engagement (£15,000): promote mental health literacy, reduce stigma, and encourage early help-seeking.

  - Lot 2 – physical health and mental health (£30,000): initiatives that take on a system approach to strengthen understanding of Serious Mental Illness and wider mental health illness and its link to poor physical health, encouraging engagement with preventative healthcare and lifestyle services and bridging the gap between primary care and lifestyle services.

  - Lot 3 - reducing inequalities in access and uptake (£25,000): targeted approaches to improve awareness and uptake of  health checks, particularly among underrepresented groups.

## Background

  - National context

    - Mental health inequalities remain a significant public health issue, driven by social, economic, and environmental factors. People living in disadvantaged or marginalised communities experience disproportionately high rates of poor mental health, lower access to early support, and often face worse outcomes. Contributing factors include deprivation, discrimination, stigma, and a lack of culturally appropriate or accessible services.

  - Impact on People with Severe Mental Illness (SMI)

    - Individuals living with Severe Mental Illness (SMI) are among the groups most affected by poor health outcomes. SMI refers to psychological conditions that severely impair daily functioning, such as schizophrenia and bipolar disorder. Nationally, Public Health England (2018) found that people with SMI die on average 15–20 years earlier than the general population, with a 3.7 times higher mortality rate for those under 75.

    - Approximately two-thirds of these deaths are due to preventable physical illnesses including cardiovascular disease, respiratory conditions, diabetes, and hypertension .

  - Local Data and Inequalities

    - Locally, health inequalities are evident across population groups and protected characteristics in Northamptonshire. Those living with SMI are particularly vulnerable to poorer physical health and lower engagement with preventative care. While deprivation does not show a clear pattern in health check completion, inequalities are pronounced by age, gender, and ethnicity:

- Older adults have much higher completion rates of SMI health checks (70% in those aged 80–84 vs. 44% in those under 25).

- Females are more likely to complete the six core checks than males (6% higher completion).

- Lower uptake is observed in mixed and other ethnic groups (55%) compared to White British (61%), reflecting demographic and access-related differences.

  - Key Risk Factors

    - Smoking remains the most significant modifiable risk factor for premature mortality among those with SMI, accounting for around 50% of deaths in this group. Prevalence of smoking is 40.5% among people with SMI compared with 13.9% in the general population, and as high as 70% in some diagnostic groups. Public Health England (2020) estimated that one-third of all cigarettes smoked in England are smoked by people with SMI. Notably, Northamptonshire reports the highest rate of premature mortality due to respiratory disease among residents with SMI in the Midlands region, reinforcing the urgency of targeted prevention.

- Why This Matters Locally

    - Increasing engagement with annual SMI physical health checks is vital to reducing life expectancy gaps. Uptake has risen to 65%, up 5.5 percentage points in the past year, driven by strong primary care leadership and targeted outreach. However, younger adults, men, and minority ethnic groups remain underrepresented, requiring focused action.

    - As shown in Fig. 1, this procurement will build on these gains through a community-led approach—promoting awareness, early access to support, and understanding of mental and physical health links to reduce inequities and boost SMI health check uptake.

- Fig. 1. Health inequalities and local context for people with Severe Mental Illness (SMI

## Scope

  - The Supplier will be responsible for delivering a community-based programme focused on reducing mental health inequalities, with a specific emphasis on improving awareness, access, and engagement among individuals with Severe Mental Illness (SMI) and other groups experiencing the greatest health inequalities. The Supplier will work collaboratively with local partners, providers, and community networks to deliver targeted outreach, education, and capacity-building activities across North Northamptonshire.

  - The Supplier is expected to provide dedicated staff members to coordinate and deliver the programme, ensuring consistent quality, engagement, and communication across all localities. Delivery must be evidence-based, culturally competent, and aligned with local health inequality priorities.

  - Key Responsibilities Include:

- Staff Training and Capacity Building: Equip frontline staff and community organisations with knowledge of mental health inequalities, SMI, and early access to support.

- Resource Development: Create and distribute accessible and culturally appropriate materials such as leaflets, posters, and social media content to raise awareness and promote health engagement.

- Community Events and Awareness Sessions: Organise and deliver local events, workshops, and outreach sessions to increase public awareness and understanding of mental health and physical health links.

- Provider Support and Communication: Strengthen connections between community providers, health services, and voluntary sector partners to improve referral pathways and coordination of support.

- Referral Support: Assist individuals in accessing appropriate services by providing information, encouragement, and practical guidance (without managing direct referrals).

Exclusions

- Direct delivery of SMI or physical health checks.

- Formal referral management or case holding responsibilities.

## Supplier Responsibilities and Key Functions

  - The Supplier must ensure that all critical functions necessary for the successful delivery of the service are covered within their delivery model. These functions are essential for programme coordination, stakeholder engagement, and community delivery. While dedicated staff members for each role are not required, the Supplier must demonstrate how these responsibilities will be fulfilled by their team or through subcontracted arrangements. Continuity of these functions is vital to achieving the project’s objectives.

  - The following key functions must be addressed by the Supplier:

  - Project Lead Function: Provides overall programme management, delivery oversight, contract compliance, and performance reporting to the Council. Acts as the primary point of contact for the Council and partners.

  - Co-Production Function: Leads the co-design of activities with people with lived experience and community stakeholders, ensuring delivery reflects local needs, accessibility, and inclusion principles.

  - Community Engagement Function: Delivers awareness sessions, outreach, and engagement activities, maintaining direct links with community organisations, localities, and service users.

  - Communications and Resource Development Function: Develops and manages campaign materials, social media content, and information resources to promote awareness and participation.

  - Monitoring and Evaluation Function: Oversees data collection, reporting, and impact measurement to evidence outcomes against Key Performance Indicators and project objectives.

  - The Supplier must ensure that individuals or teams performing the key functions possess the appropriate qualifications, experience, and competencies relevant to their responsibilities. The Supplier must clearly outline how these functions will be delivered within their proposed model.

  - Any proposed changes to how these functions are delivered must be communicated to the Council in advance and will require Council approval prior to implementation.

  - To avoid disruption, the Supplier must ensure continuity of service when transitioning delivery arrangements. Where changes occur, a handover period of at least four (4) weeks must be built in, during which knowledge transfer, induction, and briefing activities are completed.

  - Where the Council identifies increased delivery risks, such as workforce changes, safeguarding considerations, data and reporting dependencies, or any emerging high or critical risks recorded on the Risk Register, the Council may require an extended handover period of up to six (6) weeks to ensure a safe and orderly transition.

  - The Supplier must also implement appropriate risk mitigation measures throughout any transition period. This includes maintaining and updating the Risk Register, identifying any new risks that may affect continuity of service, and putting in place proportionate controls to prevent disruption. High or critical risks must be escalated to the Council immediately in line with the agreed reporting arrangements. The Supplier must ensure that adequate staffing, supervision, safeguarding compliance, and data management standards are maintained during the transition, and must evidence contingency planning to minimise any impact on service users or partners.

  - In the event of unplanned absence or disruption affecting any key function, the Supplier must provide interim cover with suitably qualified personnel and notify the Council immediately, setting out contingency arrangements and a timeline for restoring full delivery.

  - The Supplier must also provide appropriate oversight and supervision for all personnel involved in delivering these functions and operate safe working practices, including a lone-working policy supported by dynamic risk assessment for outreach activities.

## Statement of Requirements

  - The Council is seeking a qualified and experienced supplier (or consortium) to deliver the Serious Mental Illness (SMI) and Mental Health Inequalities Project, which will focus on targeted community engagement, awareness, and education activities. The service will aim to:

- Reduce mental health inequalities across disadvantaged localities.

- Promote early access to mental health support and care.

- Increase understanding of the relationship between mental and physical health, with a focus on people with Severe Mental Illness (SMI).

- Improve awareness, confidence, and uptake of SMI Health Checks.

  - The Supplier will work collaboratively with local partners—including NHS services, voluntary and community organisations, faith-based groups, and social enterprises. To deliver measurable outcomes within a total contract value of £70,000, divided into three lots.

  - Suppliers may bid for one, multiple, or all lots depending on expertise and capacity, and are encouraged to propose innovative, locally relevant approaches.

  - Lot 1 - Mental Health Awareness and Early Access (£15,000)

    - Lot 1 -  focuses on improving mental health literacy and reducing stigma across local communities. Activities will encourage open conversations about mental health, promote early help-seeking, and strengthen knowledge of available support pathways.

    - Indicative activities include:

  - Community outreach sessions and awareness events.

  - Faith based and culturally appropriate outreach events

  - Public campaigns using social media, printed materials, and other accessible formats.

  - Co-produced initiatives that bring together residents, community organisations, and local services.

  - Activities that strengthen knowledge of available support pathways and how to access them early.

    - The emphasis should be on inclusive engagement, ensuring all materials and activities are tailored to local needs and accessible for diverse groups.

  - Lot 2 - Understanding SMI and Physical Health (£30,000)

    - Lot 2 aims to strengthen local systems and workforce capability to address the physical health needs of people with Serious Mental Illness (SMI). Activities will improve understanding of the link between mental and physical health, encourage engagement with preventative healthcare, and bridge gaps between primary care and community-based support.

    - Indicative activities include:

  - Co-production workshops with people with lived experience and stakeholders to design inclusive pathways.

  - Training for community organisations and frontline staff on mental health/  SMI and physical health risks.

  - Development of resources and tools to support engagement with lifestyle and preventative health services.

  - Initiatives that improve coordination between primary care, mental health services, and community organisations.

    - The emphasis should be on collaboration and system improvement, ensuring approaches are evidence-based, inclusive, and tailored to local needs.

  - Lot 3 – Reducing Inequalities in access and uptake (£25,000)

    - Lot 3 seeks to improve awareness, accessibility, and uptake of SMI health checks among underrepresented groups, such as younger adults, men, and ethnic minority communities. Activities will focus on building trust, reducing barriers, and supporting equitable engagement with healthcare services.

    - Indicative activities include:

  - Co-production of resources explaining what an SMI Health Check involves and how it benefits overall wellbeing

  - Peer-led outreach or ambassador programmes to promote engagement.

  - Collaborative events or workshops with local health providers to demystify the process.

  - Practical assistance to overcome barriers such as transport, appointment booking, or language needs.

  - Collaboration with local services to ensure follow-up and continuity of care.

    - The emphasis should be on equity and inclusion, ensuring approaches are tailored to the needs of those most affected by health inequalities. This should focus should be on building trust and engagement with healthcare services and ensuring people with SMI feel supported to participate in preventative health interventions.

  - Required Outputs and Outcomes

    - The Council expects the following measurable outcomes:

  - Increased awareness of mental health inequalities and the importance of early access to support within targeted communities.

  - Improved understanding of the link between mental health illness and physical health, and the role of SMI Health Checks.

  - Enhanced engagement between communities and local health and care services.

  - Increased confidence among community members and frontline workers to discuss mental health and signpost to support.

  - Improved uptake of SMI Health Checks in underrepresented groups

Required outputs

  - Provide quarterly progress and evaluation reports, including engagement data, case studies, and feedback.

  - Geographical Scope

    - The service will operate within targeted localities identified as having the highest levels of mental health inequalities within the Council area. These areas will be agreed during project mobilisation and may include neighbourhoods with high deprivation, diverse ethnic communities, or poor engagement with health services.

    - The Supplier must demonstrate an understanding of local needs and strong existing or potential community links within these areas.

  - Client Group

    - The project will engage:

  - Residents from disadvantaged and under-served communities.

  - Targeted populations such as minority ethnic groups

  - Individuals with emerging or ongoing mental health challenges.

  - People living with SMI, and their carers or support networks.

  - Local community leaders, peer supporters, and frontline workers who can act as champions for mental wellbeing.

  - Participation will be voluntary and open to all, with specific outreach to marginalised or underrepresented groups.

  - Referral Routes and Eligibility

    - This is an open-access, preventative community project, no formal referral is required. However, the Supplier will be expected to develop referral and signposting pathways to local mental health, primary care, and voluntary sector support.

    - Eligibility will be focused on residents within the identified target localities, with priority given to those facing social, cultural, or economic barriers to accessing mental health support.

  - Partnership Working and Handover

    - The Supplier must work collaboratively with:

  - Local Authority Public Health and Mental Health teams.

  - Primary Care Networks (PCNs) and secondary mental health services.

  - Local VCFSE and community organisations.

    - The Supplier must ensure all learning, materials, and evaluation data are shared with the Council and partners at project end to support sustainability and future commissioning. A structured handover plan will be required at project closure, including transfer of materials, data, and recommendations.

  - Value for money

    - The Supplier must demonstrate:

- Efficient use of resources to maximise community reach and impact.

- Leveraging of existing networks and assets to enhance delivery.

- Innovation in approach (e.g. digital engagement, peer models, or co-production).

- Transparent and auditable use of funds.

    - Innovation and exceptional performance may be recognised through opportunities for future partnership working and/or dissemination of best practice.

  - Reporting and Monitoring Requirements

    - The Supplier will be required to:

- Submit quarterly progress reports summarising delivery, outputs, spend, and outcomes achieved.

- Participate in quarterly contract review meetings with the Council.

- Provide a final evaluation report detailing quantitative and qualitative impact, learning, and recommendations.

  - Health and Safety, Equality, and Safeguarding

    - The Supplier must adhere to all relevant health and safety legislation, ensuring that all staff and volunteers are trained in safeguarding, data protection, and equality, diversity, and inclusion. They must operate in line with the Council’s safeguarding and equality policies.

## Social Value

  - Beyond the core objectives of addressing mental health inequalities, the supplier will be expected to demonstrate how their delivery approach contributes to the wider wellbeing of local communities, supports inclusive growth, and strengthens the resilience of the voluntary and community sector.

  - These include (but are not limited to):

(i) employing or training people with lived experience.

(ii) using local SMEs/VCFSEs in the supply chain.

(iii) offering volunteering or accredited training opportunities.

(iv) minimising environmental impact through digital-first approaches and low-carbon travel.

## Continuous Improvement

  - We will work with suppliers to ensure that the Supplier continues to adopt best practice, innovation, and improvement throughout the Contract term.

  - The Supplier will operate a quarterly PDSA cycle, maintain a learning log, and present a short “what changed as a result” update at each review. Participation in system learning events convened by the Council is expected

## Data Management / UK General Data Protection Regulation (UK GDPR)

  - As a data controller, we are committed to upholding the principles of UK GDPR and the Data Protection Act 2018 (UK Data Protection Legislation) to ensure:

- that any processing is lawful, fair, transparent and necessary for a specific purpose.

- that data is kept accurate, up to date and removed when no longer necessary.

- that data is kept securely and safely; and

- transparency regarding use of personal (including special category) data.

  - The data controller has overall control of the personal data that it holds. The data controller is responsible for ensuring that its data processors are competent to process personal data in line with UK GDPR requirements. Under Article 28(1) data controllers are only permitted to use data processors that can provide “sufficient guarantees” to implement appropriate technical and organisational measures, to ensure the processing complies with the UK GDPR and protects the rights of individuals.

  - There have been no data protection implications identified for the initial provision of this service.

  - If, at any stage following the commencement of services the supplier requires access to personal data held by the data controller; the data controller will ensure that the appropriate provisions are put in place and documented, to allow the processing to be undertaken in accordance with UK Data Protection Legislation.

  - In this event, in accordance with Article 28 UK GDPR, the supplier as a ‘data processor’ must adhere to the following provisions:

- 28 (3)(a) only process personal data in line with the data controller’s documented instructions (including when making an international transfer of personal data), unless it is required to do otherwise by UK law.

- 28(3)(b) the data processor and its personnel must obtain a commitment of confidentiality from anyone it allows to process the personal data, unless that person is already under such a duty by statute.

- 28(3)(c) the data processor is obligated to take all security measures necessary to meet the requirements of Article 32 on the security of processing.

- 28(3)(d) the data processor should not engage another processor (a sub-processor) without the controller’s prior specific or general written authorisation. Where authorisation is received, the sub-processor must offer an equivalent level of protection for the personal data.

- 28(3)(e) the data processor must take “appropriate technical and organisational measures” to help the data controller respond to requests from individuals to exercise their data rights.

- 28(3)(f) considering the nature of the processing and the information available, the data processor must assist the data controller in meeting its obligations to investigate and report data breaches to the ICO and data subjects, where applicable.

- 28(3)(g) upon termination of services, the data processor must delete existing copies of the personal data and confirm in writing to the data controller that it has done so, unless UK law requires it to be stored. Deletion of personal data should be done in a secure manner, in accordance with the security requirements of Article 32.

- 28(3)(h) the data processor must provide the data controller with all the information that is needed to show that the obligations of Article 28 have been met; and allow for, and contribute to, audits and inspections carried out by the data controller, or by an auditor appointed by the data controller.

- The Potential Supplier shall comply with any further written instructions with respect to processing by the Council.

## Quality Requirements

  - The Supplier will be expected to maintain and evidence robust quality management processes to ensure that all activities delivered under this contract are safe, effective, inclusive, and consistent with both local authority and NHS standards for community health and wellbeing services.

  - The Council requires that the Supplier demonstrates a strong commitment to governance, safeguarding, continuous improvement, and equity of access, ensuring that delivery meets high professional and ethical standards.

  - Staffing Levels, Training, and Experience

    - The Supplier must ensure that sufficient, appropriately skilled, and experienced staff are available to deliver all elements of the project within agreed timescales and to the required quality.

    - All delivery staff, facilitators, and community engagement workers must receive training in mental health awareness, safeguarding, data protection, and equality, diversity and inclusion (EDI). Staff and volunteers involved in direct community engagement should have relevant experience of working with vulnerable populations and, where appropriate, lived experience of mental health challenges.

    - The Supplier will be responsible for maintaining up-to-date training records and providing evidence of training completion to the Council on request.

    - Training certificates must be in-date and refreshed as per policy. All materials will meet plain-English standards and be produced in accessible formats; translations or alternative formats will be provided where reasonably required.

    - The Supplier must ensure adherence to all relevant HR and health and safety legislation, including policies for lone working, safeguarding, and incident reporting.

  - Compliance with Local and National Standards

    - The Supplier must operate in line with:

    - NHS England guidance on improving physical health for people with Severe Mental Illness (SMI).

    - NICE public health guidance related to community engagement, mental wellbeing, and health inequalities.

    - The Equality Act 2010 and Public Sector Equality Duty, ensuring equitable access to services across all protected characteristics.

    - Data Protection Act 2018 and UK GDPR requirements for the secure handling of personal information.

  - Local safeguarding policies

    - The Provider shall ensure all staff are aware of, trained to a level appropriate to their role, and abide by guidance and legislation on safeguarding children and adults).

    - This should include understanding safeguarding referral procedures and referral pathways to social care. The Provider must ensure that staff are aware of and abide by North Northamptonshire Children and Adults safeguarding procedures Home - Northamptonshire Safeguarding Children Board (northamptonshirescb.org.uk) Northamptonshire Safeguarding Adults Board | (northamptonshiresab.org.uk)

    - Local Authorities work within the legislative and procedural frameworks, in particular: Working Together to Safeguard Children (2018), the Mental Capacity Act (2005) the Care Act Guidance (2014) and other relevant legislation including the Children Act (1989), the Children Act (2004), and the Sexual Offences Act (2003). The guidance and legislation place several duties and responsibilities on relevant agencies and partner organisations to comply and work together to:

    - Cooperate with the local authorities when requested to do so.

    - To promote the safety and wellbeing of children and promote the wellbeing of adults in need of safeguarding due either to care and support needs or other vulnerabilities associated with sexual health such as Female Genital Mutilation (FGM), Child Sexual Exploitation (CSE), Victims of Human Trafficking, Domestic Abuse or other risk indicators.

    - Ensure where required adults who may appear to be vulnerable, particularly adults with care and support needs are provided with access to advocacy.

    - To inform and share information with residents and communities as required under the Care Act 2014 within the constraints of the 2018 Data Protection Act, the GDPR and the Caldicott Principles.

    - Identify children, young people and adults who are vulnerable due to care and support needs or other risk factors and who require safeguarding interventions.

    - To undertake or cause enquiries to be made where there is reason to believe that harm is occurring or likely to occur to children and vulnerable adults, who are vulnerable due to care and support needs or other risk factors that impact on their abilities to safeguard themselves.

    - Provide supervision to practitioners.

    - Work together and cooperate with partner agencies.

    - Work to ensure early identification and risk assessment of vulnerable adults at risk.

    - Keep and maintain records regarding safeguarding practice in accordance with information sharing and data protection recording protocols.

    - Inform and communicate with the public about safeguarding practice.

    - Ensure any local multi agency safeguarding pathways and referral processes are understood and adhered to.

    - The Supplier is required to submit safeguarding reports on compliance to safeguarding procedures and training. Commissioners will hold regular safeguarding quality assurance meetings to ensure that services conform with and abide with the guidance and legislation on safeguarding.

  - Safeguarding Children and Young People

    - The Supplier must ensure that practitioners are aware of the specific responsibilities that they have for sexually active young people aged 13 to 15 and for those under the age of 13. In principle, all residents under the age of 16 should be seen in a clinical setting. The Provider must ensure that those under the age of 16 are seen by a worker trained in Fraser Guidelines and Gillick Competency, to assess whether the young person is mature enough and has enough understanding to receive sexual health advice and interventions in the absence of a parent or guardian.  This is to ensure that providing sexual health advice and interventions are in the young person’s best interests, any safeguarding issues are identified and if safeguarding issues are identified that a referral to children’s social care is made.

    - The Supplier will follow the Northamptonshire Safeguarding Children Policy, Procedure and Guidance, available at. Policies and Procedures Manual - Northamptonshire Safeguarding Children Board (northamptonshirescb.org.uk).

  - Child Sexual Exploitation (CSE)

    - The Supplier shall ensure relevant staff are informed and receive appropriate training to support the identification of Child Sexual Exploitation.

    - The Supplier will develop a robust quality assurance process to ensure the “Spotting the Signs proforma” is being used and to ensure child safeguarding referrals are being made in line with local NSCB procedures

  - Safeguarding Adults

    - The Supplier will ensure that staff have received appropriate training on safeguarding vulnerable adults and be familiar with the guidance, policies and procedures available from the Northamptonshire Safeguarding Adults Board, and the procedure for raising concerns and referring, available at: Northamptonshire Safeguarding Adults Board | (northamptonshiresab.org.uk)

  - Domestic Violence and Abuse

    - The Supplier will ensure staff are trained to understand and recognise domestic abuse, carry out routine enquiry and how to respond to disclosures of abuse so that survivors feel heard and supported.

    - Where a resident discloses domestic abuse and or the Supplier suspects domestic abuse, then a full risk assessment form must be completed. High risk cases must be referred to Northamptonshire Multi Agency Risk Assessment Conferences (MARAC) and liaison with the Northamptonshire MASH in relation to vulnerable adults and children at risk of abuse, including children affected by domestic abuse.

  - Complaints and Public Interest Disclosures

    - The Supplier shall comply with the relevant regulations for complaints relating to the provision of the Services and shall have in place complaints policy and procedures that enable service users and partner organisations to make a complaint about any aspect of the service, for that complaint to be investigated, and for appropriate action to be taken. Service users should have available to them information on how to make a complaint and they should be able to do this in a variety of accessible formats. The Supplier shall use the outcomes of such complaints to inform service planning and will evidence this in the annual report to Commissioners.

    - The Public Interest Disclosure Act 1998 gives legal protection to employees against being dismissed or penalised by their employers as a result of publicly disclosing certain serious concerns. The Supplier shall have in place Policy and procedures to enable employees to raise concerns without prejudice.

    - If a complaint is received about the standard of the provision of the services, the manner in which any of the services have been supplied or work has been performed, the materials or procedures used, or any other matter connected with the performance of the Supplier’s obligations under this Contract, the Supplier must inform the Commissioner. The Authority may take any steps it considers reasonable in relation to that complaint, including investigating the complaint and discussing the complaint with the Supplier, CQC or/and any Regulatory Body. Without prejudice to any other rights the Authority may have under this Contract, the Authority may, in its sole discretion, uphold the complaint and take any action it deems appropriate.

  - Serious Incidents

    - Serious Incidents are those that have a significant impact on patient safety or the ability of the healthcare organisation to function effectively. These incidents can stem from either acts or omissions in care that lead to outcomes such as: Unexpected or avoidable death; unexpected or avoidable injury that results in serious harm, including cases where immediate treatment was required to prevent death or further serious harm or abuse. This can encompass physical, emotional, or other forms of mistreatment; incidents that threaten or prevent the organisation’s ability to deliver an acceptable level of healthcare services.

    - There are no definitive lists of Serious Incidents, and in the event of a potential Serious Incident being identified, the Supplier shall adhere to the NHS England Patient Safety Incident Framework (April 2024) The Patient Safety Incident Response Framework (ncmd.info) which sets out clearly the definition and thresholds for a Serious Incident, the principles of management of such an incident and the detailed management plan and timescales. In addition to the requirements set out in the NHSE Framework, the Supplier shall also report any Serious Incident directly to the Commissioner, via the agreed electronic communication pathway – reports to be sent to: PHincidentreporting@northnorthants.gov.uk. This must be done within 2 working days of the event occurring or earlier if immediate action is required.

    - The Supplier shall simultaneously provide the Commissioner with copies of all/any documents submitted to the Care Quality Commission (CQC) and or any other regulatory body and/ or submitted via Strategic Executive Information System (STEISS). The Commissioner shall reserve the right to request and monitor actions and shall close the Incident when Commissioners are satisfied that the investigation report and action plan meets the required standard and learning is being disseminated.

    - Where a Serious Incident is considered a safeguarding incident, or risk the Supplier shall also report and manage the incident in line with the current published Northamptonshire Safeguarding Policies and Procedures. Serious Incidents shall be closed by the Commissioner when they are satisfied that the investigation report and action plan meet the required standard.

    - Environmental, Social and Governance (ESG) and Equality, Diversity and Inclusion (EDI) standards, ensuring services are delivered responsibly, inclusively, and in accessible formats

  - Stakeholder Involvement

    - The Supplier must actively engage with key partners, including primary care, mental health services, Voluntary, Community, Faith-based and Social Enterprise sector (VCFSE organisations, and people with lived experience.

    - Co-production and community participation should be integral to programme design, delivery, and evaluation.

    - Engagement processes must ensure that voices from under-represented and marginalised groups are heard and reflected in decision-making.

  - Complaints, Feedback, and Escalation

    - The Supplier must have a clear and accessible complaints and feedback policy, outlining how issues raised by service users, staff, or partners will be acknowledged, investigated, and resolved.

    - Complaints must be logged and reported to the Council in quarterly contract monitoring returns, along with actions taken and learning outcomes.

    - The Supplier must ensure all individuals are treated with dignity and respect throughout the process and that complaints do not negatively affect access to support.

  - Monitoring and Evidence

    - The Supplier will be required to maintain detailed records of activities, engagement, outcomes, and quality checks.

    - Evidence of compliance with quality workbook standards (e.g., training logs, supervision records, safeguarding audits) must be available to the Council upon request.

    - The Supplier must contribute to local evaluation processes and performance reporting as part of continuous quality improvement.

## Delivery Plan and Implementation Milestones

  - The following section outlines the expected delivery structure and implementation timetable for the Mental Health Inequalities and SMI Project. While the appointed Supplier will be required to submit a detailed delivery plan as part of mobilisation, the milestones and core activities below represent a guideline of the project schedule.

  - Contract Duration

    - Contract period: 12 months (April 2025 –March 2026)

    - Total budget: £70,000 (inclusive of all delivery, staffing, management, materials, travel, and reporting costs)

- Table 1: Key Delivery Milestones

| Milestone | Description | Indicative Completion Date | Responsible Party |
| --- | --- | --- | --- |
| Mobilisation and Start Up Phase | Contract signing, inception meeting, submission of detailed delivery plan, risk register, and monitoring framework | Month 1 | Supplier & Council |
| Community Mapping and Engagement Planning | Identification of target communities and groups with greatest health inequalities; establishment of local partnerships and engagement venues | Month 2 | Supplier |
| Programme Launch | Delivery of initial community engagement and awareness activities; co-production of communications and outreach materials | Month 3 | Supplier |
| Quarterly Delivery Cycles | Implementation of engagement sessions, workshops, SMI awareness activities, and community champion training; quarterly monitoring reports submitted | Months 3–11 | Supplier |
| Mid-Project Review | Evaluation of progress, identification of barriers, and adjustment of delivery plan if necessary; mid-year report to Council | Month 6 | Supplier & Council |
| Final Delivery Phase | Consolidation of outreach and awareness campaigns; capture of case studies and impact data; preparation of final evaluation | Months 10–12 | Supplier |
| Project Closure and Evaluation | Submission of final project report, learning summary, and financial reconciliation; handover of all materials and documentation | Month 11-12 | Supplier & Council |

    - Mobilisation deliverables (Month 1): Detailed delivery plan, partnership map, risk register, monitoring framework, safeguarding/DBS assurance, communications plan, and branded resource templates. Progress will be tracked monthly using a RAG status against milestones.

## Contract Management, Performance Monitoring, and Review

  - The Council will adopt a Council-led contract management approach, whereby all monitoring, reporting, and performance management requirements are defined and directed by the Council. The Supplier will be required to adhere to these processes in full and provide all requested data, evidence, and reports in the format and frequency prescribed.

  - Key Performance Indicators (KPIs) outlined in this specification are provisional and will be subject to review and refinement during the contract period. A formal process for KPI development will be undertaken in collaboration with suppliers to ensure alignment with service objectives and emerging priorities.

  - Monitoring and Reporting Framework

    - Quarterly Reviews: The Supplier will be required to participate in quarterly contract review meetings led by the Council. These reviews will evaluate delivery progress, outputs, outcomes, and quality standards against agreed Key Performance Indicators (KPIs).

    - Each review will include discussion of:

    - Achievement of milestones and deliverables.

    - Financial expenditure and value for money.

    - Social value outcomes.

    - Risks, challenges, and mitigation actions.

    - Opportunities for improvement or innovation.

  - Reporting Requirements:

    - The Supplier will be required to submit a Quarterly Monitoring Report in a standard Council template, including both quantitative and qualitative data. Reports must evidence performance against Contract objectives and KPIs, provide participant demographics, and demonstrate impact in reducing mental health inequalities as set out in as detailed in Table 2 - Annex 1 (Contract Monitoring) and Annex 2 (Quality Assurance Reporting) of this specification.

  - Final Review:

    - In addition to quarterly reviews, the Council will conduct a final contract review to evaluate overall performance, assess contract compliance, and determine future commissioning priorities. The format and structure of the Final Review will be mutually agreed by the Council and the Supplier

  - Lot 1 – Community Awareness and Engagement  (Promote mental health literacy, reduce stigma, and encourage early help-seeking)

  - Key Performance Indicators (KPIs):

  - KPI 1 - Engagement delivery: at least 24 community engagements delivered though out the year.

  - KPI 2 – Extended conversations: At least 50% of participants engaged in extended conversations (≥5 minutes, tailored signposting).

  - KPI 3 - Printed materials: Develop and disseminate a minimum of 500 culturally appropriate printed materials (125 per quarter), plus evidence of digital/social engagement.

  - KPI 4 – Digital Engagement Evidence: Suppliers must provide quarterly evidence of engagement with digital versions and social media campaigns. Metrics should include reach, impressions, clicks, shares, video views, and downloads. Evidence must be recorded in the monitoring workbook and supported by screenshots or analytics reports.

  - Lot 2 - Physical Health and Mental Health (System approach to strengthen understanding of SMI and its link to poor physical health, bridging gaps between primary care and lifestyle service)

  - Key Performance Indicators (KPIs):

  - KPI 1 - Co-production Workshops: Facilitate at least 4 co-production workshops with people with lived experience and key stakeholders, leading to a minimum of 2 agreed actions or pathway enhancements that improve coordination between primary care and community lifestyle services

  - KPI 2 - Referrals to Lifestyle Services: Report on the number of people with SMI referred to lifestyle services

  - KPI 3 - Attendance at Lifestyle Services: Report on the number of people with SMI attending lifestyle services and share outcomes with primary care.

  - Lot 3 - Reducing Inequalities in Access and Uptake - Key Performance Indicators (KPIs):

    - KPI 1 - Referrals for SMI Health Checks: Report on number of people referred to SMI Health Checks among underrepresented groups (e.g., younger adults, men, ethnic minority communities).

    - KPI 2 - Referrals for SMI Health Checks: Ensure 100% of individuals signposted or supported for an SMI Health Check receive a minimum of two follow‑up contacts within four weeks. For priority groups (younger adults, men, and minority ethnic communities), make up to three outreach attempts (including at least one on a different day). Where follow‑up is not possible, record the reason (e.g., declined or uncontactable) and evidence all attempts (date/time, channel, outcome).

## Risk Management

  - The Council recognises that all projects of this nature carry inherent risks, including those related to delivery, engagement, and sustainability. Effective risk management is therefore essential to ensuring that contractual outcomes are achieved safely, efficiently, and to the expected standard.

  - The Supplier will be required to implement a comprehensive Risk Management Plan that identifies, assesses, and mitigates all known and emerging risks throughout the Contract term. This plan will be agreed at Contract initiation and reviewed quarterly as part of formal performance and contract review processes.

  - Supplier Responsibilities

    - The Supplier will be expected to:

- Maintain and regularly update a Risk Register, recording all identified risks, their likelihood, potential impact, and mitigation actions.

- Nominate a Designated Risk Lead responsible for monitoring and escalating risks to the Council.

- Report on risk status as part of quarterly contract review meetings.

- Notify the Council immediately of any emerging high or critical risks that may affect delivery, compliance, or safety. Send notifications to PHincidentreporting@northnorthants.gov.uk.

    - Demonstrate proactive mitigation and contingency planning, particularly for workforce, data, and engagement risks

    - The Risk Register will be reviewed quarterly at contract reviews. Known risks also include fraud/misuse of funds with controls covering separation of duties, spend approval thresholds, and audit trail requirements.

    - Known and Anticipated Risks - Key risks associated with this requirement include, but are not limited to:

- Engagement Risk: Difficulty engaging priority groups, including individuals with Severe Mental Illness (SMI), marginalised communities, or those less likely to access mainstream health services.

- Delivery Risk: Failure to achieve required outputs, outcomes, or milestones within agreed timescales and budget

- Workforce Capacity Risk: Insufficient staffing levels, turnover, or lack of suitably trained personnel to deliver the project to required quality standards.

- Data and Reporting Risk: Incomplete, inaccurate, or inconsistent data collection that hinders monitoring of impact and performance.

- Partnership and Coordination Risk: Lack of collaboration with local health, care, and voluntary sector partners, leading to duplication or fragmented delivery.

- Financial Risk: Inefficient use of resources or inability to demonstrate value for money, potentially impacting continued funding or contract extensions.

- Reputational and Safeguarding Risk: Failure to comply with safeguarding, confidentiality, or equality duties, resulting in harm to individuals or damage to the Council’s reputation.

## Corporate Social Responsibility (CSR)

  - The Council is committed to working only with Suppliers that uphold the highest ethical, social, and environmental standards. All Suppliers must operate in a responsible and transparent manner, in full compliance with relevant UK legislation, local authority policies, and recognised good practice in corporate social responsibility.

  - The Supplier will be required to demonstrate compliance with the following mandatory requirements throughout the duration of the Contract:

  - Equality, Diversity, and Accessibility: The Supplier must comply with the Equality Act 2010, ensuring all services are inclusive, accessible, and promote equality of opportunity. Activities must actively reduce discrimination and health inequalities across all protected characteristics and communities.

  - Human Rights, Modern Slavery, and Ethical Employment: The Supplier must comply with the Modern Slavery Act 2015 and guarantee there is no forced labour, child labour, or inhumane treatment within its operations or supply chain. Fair pay, safe working conditions, and lawful employment practices must be maintained for all staff and subcontractors.

  - Income Security and Workforce Wellbeing: The Supplier must ensure fair and timely pay, job security, and appropriate working conditions for all personnel delivering this contract. Employers are encouraged to promote staff wellbeing, professional development, and positive mental health in the workplace.

  - Environmental Sustainability: Suppliers must take reasonable steps to minimise waste, reduce carbon emissions, and operate sustainably in line with the Council’s environmental objectives. The use of eco-friendly materials, digital-first approaches, and responsible resource management is strongly encouraged.

  - Monitoring and Compliance: Compliance with these ethical and corporate, social responsibilities standards will be reviewed through the Council’s ongoing contract monitoring and quarterly performance reviews. Evidence of relevant policies, training, or due diligence may be requested, and breaches may lead to corrective action or contract termination. The Supplier will evidence compliance (policies, training logs, audits) and commit to digital first delivery and low carbon travel, using local supply chains where feasible.

## Annexes

Table 2 – Annexes

| Annex Title |  | Document |
| --- | --- | --- |
|  | KPI – Contract Monitoring V0.01 |  |
|  | QA – Reporting Workbook – V0.01 |  |

## Appendix 1 – Definitions

Table 3 – Definitions

| Term or Acronym | Definition |
| --- | --- |
| Contract | The legal agreement between the Supplier and the Council, which details the Council’s requirements, terms, and conditions. |
| Contract Year | A period of twelve (12) months, commencing on the Contract Start Date. |
| Council | North Northamptonshire Council. |
| Service and/or Works | A term used to describe the goods, supplies, service, works and/or any part, thereof and/or any other requirement to be provided and/or delivered by the Supplier, to fulfil the obligations and/or requirements of this document and all supporting documents. |
| Supplier | The organisation who wins the Contract, following evaluation of all bids received by the Council. |
| Type term or acronym SMI (Severe Mental Illness) | Long-term mental health conditions that severely impair daily functioning (e.g., schizophrenia, bipolar disorder). |
| SMI Annual Physical Health Check | Six core checks - BMI, blood pressure, blood glucose/HbA1c, lipids, smoking status, alcohol consumption. |
| VCFSE | Voluntary, Community, Faith based and Social Enterprise sector. |
| Co-production | Equal partnership with people with lived experience in design, delivery and evaluation. |
| Core20PLUS5 | Targeted approach to reducing health inequalities focusing on the most deprived 20%, locally identified “PLUS” groups, and five clinical areas including SMI physical health. |

Marmot, M. (2020) Health Equity in England: The Marmot Review 10 Years On. Institute of Health Equity, London. Available at: https://www.health.org.uk/publications/reports/the-marmot-review-10-years-on (Accessed: 7 October 2025).

Northamptonshire Integrated Care Board (2024) Serious Mental Illness (SMI) Physical Health Checks: Local Data and Performance Report 2024/25. Northamptonshire ICB, Northampton. (Unpublished internal dataset, cited with permission, accessed: 7 October 2025).

Public Health England (2020) Smoking and Mental Health: Joint Consensus Statement. Public Health England and NHS England, London. Available at: https://www.gov.uk/government/publications/smoking-and-mental-health-joint-consensus-statement (Accessed: 7 October 2025).

Northamptonshire safeguarding children partnership. (2023). http://www.northamptonshirescb.org.uk/about-northamptonshire-safeguarding-children-partnership/policies/. [Online]. northamptonshirescb.org. Available at: http://www.northamptonshirescb.org.uk/about-northamptonshire-safeguarding-children-partnership/policies/ [Accessed 01 August 2025].

Northamptonshire Adult Safeguarding Board. (2025). Northamptonshire Adult Safeguarding Board. [Online]. northamptonshiresab.org.uk. Available at: https://northamptonshiresab.org.uk/ [Accessed 01 August 2025].

National Child Mortality Database. (2022). The Patient Safety Incident Response Framework and Child Death Review. [Online]. www.ncmd.info/guidance. Last Updated: Mar 7, 2024. Available at: https://www.ncmd.info/guidance/patient-safety-incident-response-framework/#:~:text=The%20PSIRF%2C%20 [Accessed 10/02/2025].