## Hurley Schedule of Works
TITLE | PRICED RETURN - SCHEDULE OF WORKS
Client : | Environment Agency
Project: | Hurley Lock House - Internal Wall Insulation
Address: | Hurley Lock House, Mill Lane, Hurley, Maidenhead, SL6 5ND
Contract: | Minor Works
Issue Date: | 20th January 2026
Tender Return Date | Tendered on Contracts Finder TENDERS TO BE RETURNED BY WEDNESDAY 11th FEBRUARY 2026 - TO estatesresidential@environment-agency.gov.uk
Start Date: | Monday 6th March 2026 (Provisional)
Duration: | 8 weeks
Contractor: | TBC
Contents list
Section
A | Preambles
A1 - Environment Agency Priorities
A2 - General
A3 - The Site/Particulars of the Work
A4 - Contract
B | Preliminaries
C | Schedule of Work
D | Pricing Summary Page
Appendicies | Appendix A - SHEW CoP
Appendix B - Pre-Construction Information
Appendix C - Floor Plans (1:50 scale when printed at A3)
Appendix D - Asbestos Refurbishment and Demolition Survey
Appendix E - Pavadry Data Sheet
Appendix F - Pavadry Technical Manual
Appendix G - Tender Submission Form
Appendix H - Elevation Photographs & Access Information
ITEM | DESCRIPTION OF WORKS |  | Unit | Item | Rate
A | PREAMBLES
A1 | ENVIRONMENT AGENCY PRIORITIES
A1.1 | CARE OF THE ENVIRONMENT AND WILDLIFE: The Environment Agency is committed to the care and sustainability of the natural environment and its wildlife. It is essential that the greatest possible care be taken at all times to prevent any damage or pollution to the natural environment and its plant and animal wildlife. |  | - | Note | -
A1.2 | ENVIRONMENT AGENCY SITES: Most Environment Agency Sites are located near water with working lock gates and lock staff private facilities. All contractors must liaise with the lock keeper daily and at times when crossing lock gates is necessary and will be directed to work safely and within appropriate timescales |  | - | Note | -
A1.3 | PUBLIC ACCESS: Some lock sites have public footpaths across the lock gates and the island sites and the EA are committed to ensuring this access is retained safely throughout the works. It is the contractors responsibility to ensure that all works, including deliveries and transport of materials and equipment to and from site is undertaken in a safe and considerate way limiting risks to the their staff, the general public, EA staff and river users. |  | - | Note | -
A1.4 | ENVIRONMENT AGENCYS CORE HEALTH AND SAFETY VALUES ARE: All of us have the right to remain healthy and injury free at work. We are all vital to improving health and safety and we will: · work to prevent all injuries and occupational illnesses · all be responsible for health and safety · always check and learn from what we are doing · challenge and respond to challenge Remember health and safety is a way of life both at home and at work. “Constructing a better environment” applies to all works to residential properties. In all instances the principal contractor and contractor’s performance will be expected to meet or exceed the minimum standards required under the appropriate legislation. |  | - | Note | -
A1.5 | COMPETANCE AND TRAINING: TheEnvironment Agency has very specific competence and training requirements as detailed in “Safety is Paramount constructing a better environment”. The PC must ensure these are adhered to: · All operatives must hold a current CSCS card · All supervisors must hold a current SMSTS or SSSTS or CSCS Gold Card · Specific and relevant current qualifications must be held by those undertaking such tasks as erecting and checking scaffolding (CISRS) and scaffold towers (PASMA) or operating MEWP (IPAF) · Full access scaffolding must be erected by a NASC registered scaffolding company and must be tagged prior to use and regularly inspected |  | - | Note | -
A2 | GENERALLY
A2.1 | Where proprietary items are specified within this Works section and the preceding section, they must be installed in strict accordance with the manufacturer's recommendations and instructions. |  | - | Note | -
A2.2 | All proprietary items are to be installed by contractors approved by the supplier and the Contract Administrator. |  | - | Note | -
A2.3 | All provisional sums, provisional quantities and PC Sums are to be directed by the Contract Administrator. |  | - | Note | -
A2.4 | The siting of builders skips shall be agreed prior to commencement of works and the Contractor must obtain a licence for any skips deposited on the public highway and to conform to all conditions contained therein. Skips are to be removed from site promptly when full and replaced and provided with a secured cover at all times |  | - | Note | -
A2.5 | The siting of contractor's plant and stored materials within the boundaries of the premises are to be agreed with the Contract Administrator. |  | - | Note | -
A2.6 | Note: Before tendering, the contractor make a full site visit, examine the drawings, specification documents visible in Appendix to this schedule of works document, check all measurements and dimensions and ascertain all local conditions and restrictions, accessibility, the full extent and nature of the work, the supply and conditions affecting labour and the execution of the contract generally. No claims arising from failure to do so will be considered. The contractor will be responsible for contacting the owners of the Swan Public House to arrange use of their car park for any deliveries - it may be possible to park here up until 11am in order to make deliveries and clear rubbish from site making use of trollies across the weir bridge |  | - | Note | -
A3 | THE SITE/PARTICULARS OF THE WORK
A3.1 | DESCRIPTION OF THE WORK: Hurley Lock House has just become void and requires works to make it more sustainable and fit for purpose. The existing heating system is currently LPG and this is to be replaced with a modern Air Source Heat Pump. In order for this to work effectively the existing house will require thermal upgrades. The works comprise of the installation of Internal Wall Insulation which is to be a breathable system to work in harmony with the existing traditionally built solid brick external walls. The PavaDry system has been chosen as this provides a breathable system using a composite wood fibre board and subsequently less wet plastering. The house existing walls have been surveyed and are in good condition with no signs of damp or water ingress. The works will be undertaken alongside or directly prior to the installation of the ASHP Additional works that will have already been completed are the electrical works to adapt the sockets and electrical fittings on the external walls using the EA Framework contractor and this work will need to be coordinated with the IWI. Additional works that may be added is the insulation of the suspended ground floors |  | - | Note | -
A3.2 | LOCATION: Hurley Lock House is located on an island located within the River Thames. The site is reached via foot from either a small road adjacent Mill Lane, a narrow footpath and over the lock gates or a via larger car park located towards the camp site and accessed via a foot bridge. There is a potential for the contractor to hire a boat to get materials to site and access could then be arraged via the lockside and down the path - the contractor will be responsible for arranging and coordinating this with the EA (who would be open to such a solution) The house is currently empty and will become the new lock keepers residence - the lock is manned daily by EA staff The house stands within its own privave garden enclosed at the rear byt open to the towpath at the front of the property. |  | - | Note | -
A3.3 | TIMESCALE FOR COMPLETION OF THE WORKS: Ideally the works will commence in early January following the agreement of the CPP and RAMS and will be completed within 6-8 weeks. Some liason and coordination with the works being undertaken by Electrical and Heating Contractors will be necessary |  | - | Note | -
A3.4 | EMPLOYER: The Environment Agency, Estates Department, Kings Meadow House, Kings Meadow Road, Reading, RG1 8DQ |  | - | Note | -
A3.5 | CONTRACT ADMINISTRATOR: (hereinafter referred abbreviated as CA): Mrs P J Salbany, Environment Agency based at Kings Meadow House Mob 07425 620502 SECONDARY POINT OF CONTACT: Mrs Kathryn Forster, Environment Agency Mob 07795 883547 |  | - | Note | -
A3.6 | EA PERSONELLE RESPONSIBLE FOR THE LOCK SITE: Currently there is relief lock keeper on site daily |  | - | Note | -
A3.7 | EXISTING MAINS/SERVICES: Identify, protect, uphold and maintain any existing services, live drainage, ducts, water, electric, oil and other mains resources found during the carrying out of the Works. If any are damaged reinstate them before leaving site. Be liable for an indemnify The EA against any expense, liability or loss, claim or proceedings provided always that the damage is due to any negligence, omission or default of the Contractor's workpeople or sub-contractors. The mains water has been turned off to the lock house to prevent freezing during the winter months while there is no heating - temporary heaters have been installed to keep the building slightly warmer and these will need to be kept on during the works to a suitable level to prevent the building fabric from deteriorating |  | - | Note | -
A3.8 | A HEALTH & SAFETY FILE for the site is not available - however information will be passed to the contractor as part of this tender package including; EA SHEW CoP (Safety Health Environment & Wellbeing Code of Practice), Pre-Contruction Information including Asbestos Survey, Drawings including Site Plan, Existing Ground and First Floor Plans & Services Plan. |  | - | Note | -
A3.9 | RESTRICTION OF WORKING HOURS: Normal working hours will be 8am - 5.00pm, Monday to Friday - any working outside these hours must be agreed in advance with the CA Contractors are to report to the Lock Keeper daily upon arrival and departure |  | - | Note | -
A3.10 | ACCESS TO THE SITE FOR THE WORKS: The approach to the access track is through Hurley Village and Mill Lane and then via narrow pedestrian footpaths to the lock side and across the lock gates or a footbridge slightly further upstream adjacent to the public car park. During flooding high water levels can make the lock house inaccessible. This could cause delays and the contractor is advised to have additional work as back up in these situations - the EA will take no responsibliity for costs associated with no access but is aware that this can cause delays in the completion dates. Access roads are not to be blocked at any time as access for emergency vehicles is required 24/7 for other residents and river users. |  | - | Note | -
A3.11 | PARKING: Contractors and Employees vehicles - there is no designated parking for the lock house and it is advisible to make use of the public car park. There is no parking on Mill Lane and limited turning space - the contractor is responsible for delivery of materials and will need to make contact with residents if this is the route of access preferred - otherwise the public car park could be used but the contractor will be expected to obtain consent from the Parish Coundil and will require a trolly or suitable equipment to transfer materials over the footbridge and along the towpath. The contractor may be able to make private arrangements for access by boat when conditions are suitable and will be expected to make any arrangement for this with the EA Project Manager and the on site lock keeper. The contractor is responsible for ensuring suitable delivery vehicles are provided when bringing materials and equipment to site. |  | - | Note | -
A3.12 | SITE WELFARE FACILITIES/SITE ACCOMMODATION - The lock keepers mess facilties can be used as a welfare for contractors on site and provide a small space for rest, preparing food and drink - hot water is provided. These facilities are availbale for use throughout the contract if required but are shared with the lock keeper and must be kept clean and tidy and will be used by the lock keeper and other EA staff. The facility is locked outside of normal working hours and a key will be shared at the prestart meeting There are no faciltieis within the house and the water has been turned off |  | - | Note | -
A3.13 | SECURITY: Hording, Fences and Gates: There is public access on the lock side and tow path to the front of the house and the rear garden is private and enclosed by fencing. The lock area is used by boaters, walkers and other river users. It is the Contractors responsibility to keep the works secure and separate from members of the public and other personelle on site. |  | - | Note | -
A3.13 | SMOKING/VAPING: Not permitted on site |  | - | Note | -
A3.14 | NOISE: The use of radios or other audio equipment is not permitted |  | - | Note | -
A3.15 | SITE WASTE MANAGEMENT: The contractor is to separate out construction waste where possible and ensure all opportunities to reuse and recycle site waste. Making use of a licenced waste carrier that carries out recycling of waste material is essential to this project to manage finite resources and prevent waste and a Waste Transfer Note will be required for all waste removed from site. Burning of waste materials is not permitted on site at any time The contractor must take all reasonable precautions to prevent pollution The use of pesticides and/or biocides is not permitted The site is on a septic tank and as such no waste material is to be flushed down sinks, WCs or drains especially with regards to painting, all brushes are to be cleaned in contractors buckets and any cleaners and thinners are to be taken off site and not discarded down the drains or anywhere else on site. All waste material will need to be carried across the lock gates, bridge and footpath safely and taken away in contractors vans - or if a skip is required then it is the contractors responsibility to obtain the necessary permits from the highways authority or local authority - please note this will be remote from the site and on the public highway and must therefore be provided with a secure lid |  | - | Note | -
A3.16 | DEFECTS IN EXISTING CONSTRUCTION: Report to the CA without delay with possible solutions and prices for rectification where possible. Once the dry lining/plasterboard has been removed from the external walls any areas of damp or damage must be investigated, brought to the attention of the CA and rectified prior to the installation of any internal wall fittings. |  | - | Note | -
A3.17 | HOT WORKS: Hot works are not permitted without the prior approval of the CA and the issue of a Hot Works Permit which the contractor is to self manage The use of compression joints must be used prior to the need for hot works and this must be highlighted in the RAMS and PCC and discussed with the CA and PD |  | - | Note | -
A3.18 | NAME BOARDS/ADVERTISMENTS: Contractors name boards or advertisments will not be permitted except with the prior approval of the CA |  | - | Note | -
A4 | CONTRACT: JCT MINOR WORKS AGREEMENT
A4.1 | MINOR WORKS AGREEMENT: JCT Agreement For Minor Works |  | - | Note | -
A4.2 | DATE OF COMMENCEMENT OF THE WORKS: To be agreed |  | - | Note | -
A4.3 | LIQUIDATED DAMAGES: £250/week |  | - | Note | -
A4.4 | RECTIFICATION PERIOD: 12 months |  | - | Note | -
A4.5 | PERCENTAGE OF THE VALUE OF THE WORKS: 95% |  | - | Note | -
A4.6 | SUPPLY OF DOCUMENTATION: 3 months |  | - | Note | -
A4.7 | CONTRACTORS INSURANCE: Employers liability and Public Liability of £5,000,000.00 for single claim and suitable levels of insurance to cover the Insurance of the works, Employers Liabilty and Professional Indemnity Insurance to a suitable level to include design elements. Before starting works on site the Contractor is to submit documentary evidence of the insurances required |  | - | Note | -
| Sub-Contractors - The EA has appointed Heppelthwaites to install the ASHP and RAAM to undertake the electrical alterations required for IWI - the contractor is expected to liaise with them and the EA Project Manager at certain points to ensure that works are undertaken in a timely manner to prevent delays or extra costs for opening up and rectification of abortive work. The Contractor is also Air Source Heat Pump - EA Framework Contractor - Heppelthwaites Green Solutions who have already installed a number of ASHP systems in lock houses RAAM - Electrical - EA Framework Contractors Additional works to install the cabling for Prana Ecostream Vents to each habitable room will also be required and this will be progressed with Maidenhead Electrical Contractors who have already installed these vents on behalf of the EA at other Lock Houses |  | - | Note | -
B | PRELIMINARIES/GENERAL CONDITIONS
ENVIRONMENT AGENCY PROPERTIES
B1.1 | Allow for all necessary preliminaries, plant, machinery, scaffolding where required and attendance, in order to comply with the proceeding and foregoing sections. Any scaffolding erected must fall within the guidelines of NASC basic scaffolding design in line with BS EN 12811-1. And must be erected by operatives who are CISRS qualified and certified (Constrution Industru Scaffolders Record Scheme). At all times during erection and dismantling there must be at least 1no. scaffolder on site at all times with CISRS Scaffolder Tube & Fit membership. All mobile or tower access scaffolding must be erected by a PASMA certified opperator | £ | 1 | Item | -
B1.2 | CDM REGULATIONS: Allow for acting as Principle Contractor under CDM regulations, including Health and Safety in line with attached EA SHEW CoP. Include for all H&S Signage, fencing, fire extinguishers, notifications, safety plans and provide information for safety files. The contractor will need to provide details of their proposed working methods at the time of tender to ensure that they have fully considered these requirements. These will be assessed by the project team including the Client, Contract Administrator and Principal Designer/CDM Advisor as part of the overall selection procedure. The Contractor will need to provide evidence of Health and Safety Qualifications and Experience in line with the requirements of The CDM Regulations 2015 - this will include the following:- CDM Awareness accredited training (e.g. UKATA) and be current within the previous 12 months, Working at Height, Manual Handling, Asbestos Awareness, First Aid (minimum Emergency First Sid (EFA) 1 day course (First Aid at Work-FAW-would be preferable depending on risk), Where works involve breaking ground training in using a CAT & Genny and PAS128 training will also be required | £ | 1 | Item | -
B1.3 | PROJECT MANAGER - The contractor is to provide a suitably qualified and experience Project Manager and/or Site Foreman as necessary to manage the works throughout the project - With the minimum qualification of SSSTS, CSCS Gold Card. Where any management of sub-contractors is required SMSTS qualification (or equivalent e.g IOSH Managing Safely in Construction) Evidence will be requested during tender analysis and must be provided prior to any appointment | £ | 1 | Item | -
B1.4 | REPORTING: The Contactor is to allow for regular weekly reporting of progress including any issues to the CA in the form of face to face or virtual meetings. The contractor must inform the CA of any issue as they arrise to ensure they can be dealt with quickly and not cause delay to the works. Should there be any time when the CA cannot be contacted the contractor must manage the works so that progress can be maintained in alternative locations of the site | £ | 1 | Item | -
| BUILDING REGULATIONS APPROVAL - The contractor is responsible for applying for and obtaining the necessary Building Control Approval for all building works undertaken as part of these improvement works either through the Local Authority or an Approved Inspector. This will include all works where Building Regulation Approval Applies including and not excluding the following:- All additional Insulation added to the internal walls and where agreed between floor joists | £ | 1 | Item | -
B1.5 | PHOTOGRAPHS - The contractor is responsible for taking and providing as evidence all photographs relating to the installation of insulation and other works relating to the progress of each stage of construction of the work prior to covering up - these must be shared with the CA throughout the works prior to being covered up and be included in the H&S file at the end of the project | £ | 1 | Item | -
B1.6 | WORKING AT HEIGHT: The contractor is to provide safe and suitable means of working at height where required and in accordance with CDM best practice. Any use of scaffolding must be risk assessed and included in the Pre-Construction documentation for approval by the PD and CA before works start. All scaffolding contractors appointed must be NASC Registered or equivalent | £ | 1 | Item | -
B1.7 | SITE ACCESS: The contractor is to provide safe and suitable access for site operatives and materials. This will include a Site Traffic Managment Plan which must include details on deliveries and storage of materials. Safe passage across the lock gates to the island site must also be included - this could be by hand or by boat but it will be the contractor who must arrange and manage this alongside the direction of the lock keeper. Life jackets will be necessary when working close to water - this includes deliveries to and from the site across the lock gates and within 2m of the waters edge | £ | 1 | Item | -
B1.8 | SECURITY OF THE BUILDING: The contractor is responsible for ensuring the building is kept secure, wind and watertight at all times. Any damage caused to the building as a result of insufficient security, wind and weatherproofing measures during these works must be immediately remedied at the contractors cost. | £ | 1 | Item | -
B1.9 | SEPARATION OF THE WORKS: The Contractor is to include for the provision of warning barriers around the works, including areas used for storage of materials during the course of the contract, inclusive of warning notices and safety tape/bollards etc. | £ | 1 | Item | -
B1.10 | COORDINATION OF THE WORKS: Allow to arrange, coordinate and monitor a programme with each subcontractor, supplier, local authority and statutory undertaker, and obtain and supply information as necessary for coordination of the work on site. | £ | 1 | Item | -
B1.11 | GUARENTEES & WARRENTIES - The contractor must provide product guarentees and site H&S plan at end of works, including opperating and maintenance manuals for any newly installed products and materials | £ | 1 | Item | -
B1.13 | CLEANING: The site is to be kept tidy througout the building process and waste must be regularly cleared from site and not permitted to build up to excessive levels. | £ | 1 | Item | -
B1.14 | FINAL CLEAN: Prior to handover the contractor must allow for a Complete Builders Clean including all internal surfaces and internal glazing. | £ | 1 | Item | -
| CARRY FORWARD TO SECTION D (Summary Page) | £ |  | Total
C | SCHEDULE OF WORKS
C0.1 | Please note that existing plan drawings have been included in Appendix C of this tender document. Drawings are to scale when printed at A3 however it is the Contractors responsibility to ensure dimentions are checked on site prior to the submission of any prices |  | - | Note | -
C0.2 | The Contractor must, when pricing this Schedule of Works, take into consideration the requirements within all sections of this specifiation and the attached Appendicies of this tender document. Failure to do so will be at the risk of the Contractor. |  | - | Note | -
C0.3 | Not withstanding the conditions set out in the ‘National Building Specification’ guidelines and the ‘Standard Method of Measurement’ 7th Edition. The Contractor’s general cost items are to be priced in accordance with the ‘RICS New Rules of Measurement’ volume 2, 1st edition, (RICS:NRM-2 v1). |  | - | Note | -
| CARRY FORWARD TO SECTION D (Summary Page) | £ |  | Total
C.1 | DEMOLITION AND STRIP OUT WORKS
C1.1 | The Contractor is to review the asbestos refurbishment survey which is included within the PCI Document and can be found in Appendix B of this tender document. Please note - Asbestos has NOT been identified in the refurbishment survey. The Asbestos around the windows was removed prior to the last window replacement works. However, should the contractor identify anything that may contain suspected Asbestos work must stop in the location and the EA must be contacted immediately. |  | - | Note | -
C1.2 | Provide protection to all existing carpets and floor finishes | £ | 1 | Item
C1.3 | Remove and roll up existing carpets in the area where IWI works are proposed and store carefully on site for re-fitting | £ | 1 | Item
C1.4 | Remove the skirting boards to external walls to living room, dining room, kitchen, hallway, landing and bedrooms clearly name/number and set aside for alteraton and refitting following completion of the IWI Include the external walls of the pantry and the internal wall of the adjoining WC (accessed off the rear porch) The existing bathroom is not being included in these works However the external wall and area of pitched ceiling of the airing cupboard within the FF bathroom will be included in the works | £ | 1 | Item
C1.5 | Lift up an area of floor boards within the living room to allow inspection of the floor void and arrange inspection with EA Project Manager to assess whether there is a need to insulate below the GF suspended floors | £ | 1 | Item
C1.6 | Check all plaster to external walls is sound. Bring to the attention of the EA Project Manager and areas that are loose, hollow or damp | £ | 1 | Item
C1.7 | Prior to starting works the EA Electrical Contractor will have disconnected the sockets and switches on the external walls and locked these off within the fuse board |  | - | Note | -
C1.8 | Prior to works starting the EA Framework heating contractor will have removed the radiators and pipework on the external walls, removed the HWC and redundant pipework from the airing cupboard and removed the boiler from the wall in the kitchen |  | - | Note | -
C1.9 | Check depth of window sills to see if they can accommodate additional wall insulation to internal face. Remove window boards internally and all cover strips around windows and identify any areas of cold bridging or open gaps around the windows and insulate with expanding foam to prevent draughts and cold bridging. Once all gaps have been filled tape over joints prior to fitting Pavadry boards - using NBT Pavafix 60 or Pavafix WIN as appropriate | £ | 1 | Item
C1.20 | Provide 30-50mm Cellotex PIR board to underside of window sill dependent of how much the existing window frames can accommodate and allow to replace window boards with new pre-primed bull nosed boards to protrude 5mm over finished face of internal walls after IWI and skim finish | £ | 1 | Item
C1.21 | Carefully disconnect kitchen sink, WHB in downstairs cloakroom and WC on wall of downstairs WC off porch - including waste and water pipes and cap off during works. Set aside for reinstallation upon completion of IWI Carefully remove worktop and base units from external wall of kitchen and set aside for reinstallation following completion of IWI | £ | 1 | Item
C1.22 | Remove tiled surface from rear kitchen wall and external walls of WC ready to receive IWI - remove, prepare and stabilise all areas of loose or damaged plaster prior to the installation of the IWI system - allow to level the finish of all external walls prior to the installation of the wood fibre board to prevent any air gaps between the IWI and the inner face of the external walls - this will prevent interstitial condensation from forming where mould has the potential to grow | £ | 1 | Item
C1.23 | Clear all waste materials from site | £ | 1 | Item
CARRY FORWARD TO SECTION D (Summary Page)
C.2 | PREPARATION AND REPAIR
C.2.1 | Remove all wall paper to all internal walls, pitched ceilings, heads and jambs of windows including head of dormer to staircase and ceiling of bay window to dining room and perimeter of ceiling where IWI will cover these sections and wash down with sugar soap and scouring pad to remove all traces of glue. Lightly score all areas of unbreathable paint to external walls to mechanically allow moisture movement prior to the fitting of the IWI System | £ | 1 | Item
C.2.2 | Lift all floor boards around the perimter walls at first floor level to expose the floor joists. Repair areas of loose plaster as required and tape all areas where air gaps penetrate the structure from the outside or within the wall structure as detailed on the Pava Dry Technical Manual and Data Sheets | £ | 1 | Item
C.2.3 | Install PavaFlex/Sheeps Wool insulation (or other flexible natural insulation alternative) within the first floor voids. Ensure insulation is tightly fitted up against the external wall and around the timber joists. Fit insulation snuggly against the ceiling below and sufficintly bulked to fitt snuggly up agaist the underside of the floor boards as they are reinstated. Install timber noggings between the floor joists a minimum of 200mm back from the internal face of the external wall to hold the insulation in position and prevent slumping. Ensure that any amendment of pipework for radiators, waste and water pipes and any alteration of electric cabling is completed prior to this so that the plumber or electrician doesn't move the insulation away from the pipes and leave gaps that can lead to cold bridges (similarly for the electrical works) Highlight any areas where this may have occurred and make good prior to reinstating the floor boards | £ | 1 | Item
C.2.4 | Ensure all pipework is altered for new radiator positions to accommodate IWI (additional 80mm off inner face of external walls and at lengths suitable for new larger radiators NB - some radiators to be longer or in slightly different positions than than existing so pipework will need to be adapted by the heating engineer - Heppelthwaites prior to the insulation within the floor voids being completed. | £ | 1 | Item
C.2.5 | Ensure all electrics have been amended as required for IWI - including all sockets, Internet connections, Aerials and switches | £ | 1 | Item
C.2.6 | Ensure all new electrics have been installed for Prana Ecostream Vents in all habitable rooms - living room, dining room, Bedrooms 1, 2 & 3 | £ | 1 | Item
C.2.7 | Using second hand clay bricks and lime mortar to match as closely as possible the existing original colour, texture and bond of the brickwork to Hurley Lock House - fill in the existing air bricks in the kitchen - 1 large air brick at low level below the boiler in the recess of the kitchen units, the old boiler flue, the Nuair vent at low level to the right of the window to the side elevation and the hole where the extractor fan has been removed (this is likely to be in the wrong place for the new externally extracting cooker hood - which will be located above the cooker) and all holes from the airing cupboard where overflow pipes have been removed | £ | 1 | Item
CARRY FORWARD TO SECTION D (Summary Page)
C.3 | IWI Insulation - PavaDry System by Pavatex
C.3.1 | Supply and fix the 72mm Pava Dry IWI insulation system in strict accordance with manufacturers recommendations and attached PavaDry Data Sheet and Pava Dry Technical Manual - and finish flush ready to receive skim finish. Supply 60mm PavaDry wood fibre insulaton and OSB T&G Composite Boards Check walls are level and flat and fill any irregularities with NBT BAUMIT RK38 (the walls in Hurley Lock House appear to be level and free from major irregularities) Apply NBT BAUMIT RK70 5 - 8mm bonding coat to adhere Boards to wall - aligning toungs & Grooves as required (cut off toungs and fill grooves where boards butt up against return walls, ceilings and tops of floor joists & pitched rafters to ensure uniform thickness and no gaps within the insulation where condensation could form Mechanically fix boards to walls in pattern detailed in Technical Manual - using 3 or 5 fixings in alternate rows using WHO 7.5mm fixings - ensure fixing screws are a minimum depth of 60mm into masonry Ensure all corners are detailed fully to ensure the OSB boarding is not sandwiched between boards as they meet at the corners - cut back the OSB at corner junctions and ensure that only the wood fibre overlaps and ensure consistent thickness of insulating wood fibre Detail window reveals and heads as detailed in Technical Manual with as much insulation as can be accommodated with the frames of the existing uPVC windows - ensure the insulation does not impede the functionality of the windows Supply and screw fix into OSB - 12.5mm plasterboard, provide scrim tape to all joints ready to receive plaster finish Provide plaster skim finish to all walls ready to receive decoration | £ | 1 | Item
C.3.2 |  | - | - | Note | -
C.3.3 | Mechanical fixing pattern for Pavadry T&G boards to masonry wall | - | - | Note | -
C.3.4 | Window reveals and heads including splayed reveals to bay window to dining room and dormer to staircase - provide the maximum possible thickness of insulation to the window jambs and head using Cellotex TB4000 foil backed PIR insulation board (minimum 20mm) to be fixed to the existing plaster finish closely against the surface leaving no air gaps - use expanding foam contact adhesive. Discuss and agree with EA Project Manager. Stick 12.5mm plasterboard to Celotex insulation at window reveals and heads as above and finish ready to receive skim finish | £ | 1 | Item | -
C.3.5 | Staircase area - provide 20mm TB4000 Cellotex foil backed PIR board glued directly to the external wall using expanding foam grab adhesive to fix the insulation board directly to the wall as closely as possible and prevent any air gaps and potential for interstitial condensation. Ensure all joints are taped over with foil tape to ensure completeness of vapour barrier. Stick 9.5mm plasterboard to the Cellotex PIR board using expanding foam grab adhesive and ensure a good bond - use temporary screws to hold the PIR board and plasterboard in position as the glue cures - finish ready to receive plaster skim finish | £ | 1 | Item | -
C.3.6 | Insert vented soffit board externally to the rear elevation - or soffit vents every 600mm to provide sufficient ventillation to the pitched section of ceiling | £ | 1 | Item | -
CARRY FORWARD TO SECTION D (Summary Page)
C.4.0 | INSULATE PITCHED CEILINGS & ROOF TO BAY
C.4.1 | Pitched ceilings to rear of property - bedroom 1, landing and airing cupboard & flat ceiling to bay window to dining room Remove existing ceiling finish and clear debris from site Assuming rafters to house are 200mm deep - supply and fix 150mm Hemp batts (Inditherm) or Pavaflex (woodfibre insulation) between rafters and flush with the bottom edge of the rafters leaving a 50mm air gap between the top of the insulation and the underside of the felt or flat roof covering to the bay (rafters to Bay likely to be less deep (assume 100mm - in which case 50mm natural insulation to be installed leaving 50mm air gap above) Open up and agree with EA Project Manager on site Cut the insulation to be 5-10mm larger than the existing gap between the rafters to ensure it fits snugly between the rafters using the pressure of the squashable insulation to push back against the sides of the rafters using this pressure to hold in position to accommodate any contracting of the timbers during warmer weather and prevent gaps from opening up. Leave a minumum gap of 50mm between the top level of the hemp batt insulation and the underside of the existing roofing felt for ventillation. Check externally to ensure there is a vented sofit to the bay window - discuss with EA Project Manager Supply and fix 50mm GA4000 Cellotex foil backed composite board screw fixed to the underside of the rafters and finished ready to receive skim finish (narrower to baywindow depending on space between ceiling and window - allow the maximum depth that the window frame allows (to be agreed with EA Project Manager prior to installation) | £ | 1 | Item | -
CARRY FORWARD TO SECTION D (Summary Page)
NOTE | Prana Ecostream Vents
C.4.2 | Each room will be provided with an externally vented Prana Ecostream Vent (living room, dining room, kitchen, Bedrooms 1,2&3) The location of these need to be agreed with the installation contractor prior to fitting Maidenhead Electric will be appointed to undertake this work and have been trained and approved to install the new fused spur electrics for each unit prior to the installation of the IWI - they will then arrange the core drilling and the fitting of the Ecostream Vents and setting them up Decentralised MVHR Prana 160 ERP PRO mini, 350mm systems Allow an amount to liaise with Maindenhead Electric to ensure cabling is installed prior to IWI, pull through cables to ensure these are visible following skim finish, laise during core drilling Act as Principal Contractor while any EA Framework Contractors are on site and including to update your CPP to add any RAMS necessary for the works of | - | - | Note | -
C4.3 | There may be a need to provide natural ventillation in the kitchen due to the location of the wood burning stove - if this is over 7KW it will require an external air vet (awaiting confirmation of size) | - | - | Note | -
C.5 | REINSTATEMENT
C.5.1 | Allow to provide new plaster skim finish to all newly insulated surfaces - internal walls, pitched celings, heads and jambs of windows including dormer and finish ready to receive decoration | £ | 1 | Item | -
C.5.2 | Amend lengths of existing salvaged skirting boards and refix to the external walls using glue and mechanical fixings in each corner and every 1m Prepare ready to receive decoration. | £ | 1 | Item | -
C.5.2 | Fold back down and refit all underlay, refix carpet gripper strips and re-stretch and fit the carpets to the first floor rooms | £ | 1 | Item | -
C.5.3 | Fill the hole in the ceiling to the landing where the vent from the Nuair system has been removed | £ | 1 | Item | -
C5.4 | Fit new bull nosed window boards or Upvc window boards (depending on depth of existing window frame) to all windows on top of the insulated sills - to be agreed with EA Project Manager | £ | 1 | Item | -
C5.5 | Allow to refit all sanitary fittings following the completion of decoration in WC and outside WC and allow to connect up all new hot and cold water supplies and waste connections and leave all in full working order | £ | 1 | Item | -
C5.6 | Allow to refit base unit and work top in kitchen and re-fit kitchen sink including connecting up all hot and cold water supplies and connections to waste pipes and leave in full working order | £ | 1 | Item | -
C5.7 | Allow for Heppelthwaite to adapt pipework and fix radiators to external walls as required and to get heating systm up and running fully | £ | 1 | Item | -
C5.8 | Allow to supply and fit new 300-350mm high tiled splash back to external wall in kitchen - including return alongside cooker and all the way along the base unit including the window sill. Tiles to be white metro design. | £ | 1 | Item | -
C.5.9 | Allow to supply and fit new tiled splashback behind WHB in Downstairs WC to be 3 tiles high same white metro tiles used in kitchen | £ | 1 | Item | -
CARRY FORWARD TO SECTION D (Summary Page)
C.6 | DECORATION
C.6.1 | NB - The decoration is to be undertaken prior to the re-fitting of any floor fininshes | - | - | Note | -
C.6.2 | Prior to decorating, allow to loosen light fittings, switches sockets and refix upon completion | £ | 1 | Item
C.6.3 | Do not decorate new plaster without providing mist coat and ensure that all newly plastered surfaces are dry prior to painting - allow for washing down surfaces with a damp cloth prior to decoration to remove any inperfections in new plaster and all dust from other surfaces | £ | 1 | Item
C.6.4 | Allow all areas of newly finished plaster to be allowed to dry out completely prior to redecoration, prepare with 2 mist coats of 50% water 50% paint and 1 full coat prior to full redecoration | £ | 1 | Item
C.6.5 | Allow to redecorate all internal walls (except bathroom) and all new plaster over mist coat with 2 full coats of Dulux Trade Emulsion water based Matt paint in brilliant white in strict accordance with manufacturers recommendations. | £ | 1 | Item
C.6.6 | Allow to redecorate all ceilings (except bathroom) with 2 full coats of Dulux Trade Emulsion water based Matt paint in brilliant white in strict accordance with manufacturers recommendations. | £ | 1 | Item
C.6.7 | Allow to fill joints in architrave and skirtings, rub down and prepare smoothly prior to decoration. Provide 1 no. undercoat over filler prior to decoration Decorate all refitted skirting and all previously painted woodwork with 2 number full coat of Dulux Satin Wood paint in brilliant white applied in strict accordance with manufacturers recommendations including hand rail and balustrading and strings to staircase | £ | 1 | Item
CARRY FORWARD TO SECTION D (Summary Page)
C.7 | SUMMARY PAGE
C.6.1 | B -Preliminaries
| Including provision of evidence of qualifications and training relating to CDM, taking on the role of Principal Contractor and Designer (CDM Awareness, Working at Height, Manual Handling, First Aid, Asbestos Awareness, Fire Safety, SSSTS, CSCS Gold Card and SMSTS for management of any sub-contractors | £
C.6.2 | C - Schedule of Works
| C1 - Demolition and Strip out Works | £
| C2 - Preparation and Repair | £
| C3 - IWI - PavaDry System to internal face of external walls | £
| C4 - Insulate Pitched Ceilings | £
| C5 - Reinstatement | £
| C6 - Decoration | £
| TOTAL | £