Exit Strategy

| Project Number / Name: |  | PR BHFT 0745 -Supply of Dose banded compounded chemotherapy (replaces BHFT 0377) |  |  |
| --- | --- | --- | --- | --- |
| Potential Contract Value: |  | £17.25 million |  |  |
| Contracting Authority: |  | SEPPS |  |  |
| Document Owner: |  | SEPPS - Contract Manager supported by the SEPPS Senior Buyer |  |  |
| Effective Date: |  | 16th February 2026 |  |  |
| Review Cycle: |  | This Exit Strategy will be reviewed by the SEPPS Contract Management Team at least every 6 months and before each extension option date |  |  |
| Version No. | Changes made |  | Made by | Date |
| 1 | Original draft to support the business case |  | Neelan Moodley | 03/10/25 |
| 2 | Overall update following project validation review |  | Mike Pollard | 27/10/25 |
| Distribution: |  | Regional Homecare Medicines Specialist (Contract Manager) - SEPPS Data Analyst – SEPPS Team Tender Manager- BHFT Head of Procurement- BHFT Senior Buyer- SEPPS |  |  |
| Contents 1. Purpose 2 2. Procurement Act 2023 (PA23) Compliance 2 3. Contract Compliance 3 4. Exit Triggers 3 5. Exit Requirements 4 6. Exit Planning and Review 6 |  |  |  |  |

## Purpose

This Exit Strategy outlines the structured process for exiting the PR BHFT 0745 -Supply of Dose banded compounded chemotherapy (replaces BHFT 0377) contract, due to:

- discharge: including for example, where the contract obligations / deliverables are fulfilled, payments made and any disputes settled, by mutual agreement or contract frustration.  This covers the satisfaction of delivering services/supplies as a result of a call-off order.  This is a condition of planned exit.

- expiry: where the framework agreement has reached its end date (which may include periods of extension).  This is also a condition of planned exit.

- termination by a party: where one party exercises a contractual or implied right to terminate the contract (Order) or SEPPS/the Supplier takes the decision to terminate the Framework Agreement.  This is a condition of premature exit.

The aim of the Exit Strategy is to ensure continuity of patient care, compliance with regulatory obligations and minimal disruption to the operational services provided by the Participating Authorities.  The Exit Strategy provides a framework for managing the transition and ensuring accountability across all stakeholders.

## Procurement Act 2023 (PA23) Compliance

The exit process must comply with the following regulatory and contractual frameworks:

The Act implies into every public contract, grounds on which the contracting authority may terminate the contract. These grounds will apply to all public contracts, whether or not they are also expressly replicated in the contract. The three implied contract termination grounds, as set out in section 78(2) are:

- the contracting authority considers that the contract was awarded, or modified, in material breach of the Act or regulations made under it];

- since the contract was awarded, the supplier has become an excluded or excludable supplier (including by reference to an associated person;

- a sub-contractor (other than an associated person) is an excluded or excludable supplier.

This would give rise to potential premature exit and SEPPS seeking to rely on termination provisions within the contract.  In these circumstances, the SEPPS Senior Manager would seek guidance from the Tender Manager and the Head of Procurement, who may access legal guidance on how best to address such circumstances.

Terminating under any of the circumstances (implied terms) detailed above is complex and may need recourse to legal advice.  It also hinges on due diligence undertaken during the procurement project.  Ongoing review will be undertaken by the SEPPS Senior Buyer who will flag when any framework supplier becomes excluded or excludable.  Wherever possible SEPPS will seek the Supplier to ‘Self-Clean’ and take whatever interim measures necessary to mitigate any risk of continued supply.

SEPPS will issue the UK11 Contract Termination Notice should the framework agreement with any Supplier be terminated for whatever reason.

Note - Should SEPPS need to abandon the Procurement Project for whatever reason, it will issue a Procurement Termination Notice (UK12).

## Contract Compliance

The exit process must be supported by the contractual framework:

- Promote the business benefits expected and the mechanisms to measure delivery performance against Key Performance Indicators (KPIs).

- Provide protocols for supplier debarment and contract modifications.

- Includes specific exit provisions that detail the Supplier’s input against pre-determined Exit Requirements (see ITT - Schedule 7 - Appendix A - Call-off Terms and Conditions - Clause 15.9).

- Mandate MHRA licensing as the minimum benchmark for Supplier technical and quality compliance

## Exit Triggers

Exit procedures may be initiated under the following circumstances:

- Contract expiry: Planned at end of the contractual term.

- Supplier insolvency or breach: Financial failure or violation of contract terms.

- Supplier regulatory non-compliance: Failure to meet legal or clinical standards.

- Technical non-compliance (i.e. failure to maintain MHRA licensing for all compounds and manufacturing sites.

Each trigger initiates a formal review and activation of the exit plan to ensure continuity and compliance as follows.

## Exit Requirements

|  | Issue | Mitigating Action | Action Owner | Timeline | Supplier Action |
| --- | --- | --- | --- | --- | --- |
| 1. | Contract expiry: Planned at end of the contractual term | - Final Stock Reconciliation - Ongoing Patient treatment planning - Contract transition for existing patients, where applicable - UK11 Contract Termination Notice | PA / Supplier PA PA SEPPS | - 6 months prior to Term end - 6 months prior to Term end - Start UK 6 Notice date - Contract Term End Date | - Support - None - Facilitate - None |
| 2. | Supplier insolvency or breach | - Early Warning via annual economic & financial assessment review - The Supplier to maintain statutory compliance (Cl 11) - Supplier ceases to trade - Undertake risk assessment for ongoing patient treatment / care - Arrange to transition supplies to another ranked Supplier as needed | SEPPS Supplier Supplier SEPPS / PA PA | - Each 1 year anniversary date - Ongoing - 3 months notice of risk of becoming insolvent - Immediate upon notification - As needed taking guidance from SEPPS | - Support / provide adequate financial or other security and/or assurances - Maintain - Provide reasonable and proportionate up-to-date financial or other information - Support - Support |
| 3. | - Supplier regulatory non-compliance (Supplier becomes excluded or excludable) - Supplier maintains transparency of all sub-contractors involved in Services / Supply - Supplier fails to declare issues which may make it excludable | - Early Warning via regular review of the Central Digital Database - Review Supplier response to ITT Appendix 1 - Procurement Specific Questionnaire - Ensure all responses to the ITT Appendix 1 - Procurement Specific Questionnaire are up to date | SEPPS SEPPS Supplier | - At least quarterly - At ITT evaluation - At ITT submission | - Support - Maintains absolute transparency in respect of sub-contracts to service all Orders against the framework - Supplier tender quality control |

|  | Issue | Mitigating Action | Action Owner | Timeline | Supplier Action |
| --- | --- | --- | --- | --- | --- |
| 4. | Failure to meet clinical standards | - Compliance confirmed at the time of ITT - Accurate and complete ITT Specification Appendix 3 completion - Ongoing communication of MHRA inspection and NHS QA inspection/audit - Ongoing communication of MHRA inspection letter, NHS QA audit report together with the action plan submitted in response to any issues raised - Ongoing communication of any of the Suppliers manufacturing sites has been referred to the MHRA’s Inspection Action Group (IAG) or Compliance Management Team (CMT) and the reasoning for such referral - Suspend the supply of particular mAb compounds, or supply from effected manufacture sites - Undertake risk assessment for ongoing patient treatment / care - Arrange to transition supplies to another ranked Supplier as needed | Supplier / SEPPS Supplier Supplier Supplier Supplier PA / SEPPS SEPPS / PA PA | - At ITT submission - At ITT submission - Ongoing over the framework Term - Ongoing over the framework Term - Ongoing over the framework Term - Immediate following Supplier communication should license be suspended - Immediate upon notification - As needed taking guidance from SEPPS | - Supplier tender quality control - Supplier tender quality control - Maintain - Maintain - Maintain - Support - Support - Support |
| 5. | Broader supplier performance | - Supplier provides monthly performance against contract KPIs - Supplier Contract Manager supports quarterly review meeting with SEPPS and PA personnel (as required) | Supplier Supplier | - Monthly - Two weeks prior to the Performance Meeting | - Support - Respond to an issues raised and provide such management information as requested |
|  | Issue | Mitigating Action | Action Owner | Timeline | Supplier Action |
|  | Broader supplier performance continued | - Communicate any dispute in accordance with Clause 22 of the Contract. - Issue a Breach Notice and request a Remedial Proposal in accordance with Clause 15.3 of the Contract. - Issue a Termination Notice in accordance with Clause 15.4 and 15.5 of the Contract. | Supplier / SEPPS / PA Supplier / SEPPS / PA Supplier / SEPPS / PA | - As needed - As needed - As needed | - Support - Support - Support |

## Exit Planning and Review

In accordance with ITT -	Schedule 7 - Appendix A - Call-off Terms and Conditions - Clause 15.9, within three months of the Commencement Date, the Supplier shall develop and agree an exit plan with SEPPS consistent with the Exit Requirements, which shall ensure continuity of the Services on expiry or earlier termination of the Contract.  The Supplier shall provide a first draft of an exit plan within one (1) month of the Commencement Date.  SEPPS and each Supplier shall review and, as appropriate, update the exit plan on each anniversary of the Commencement Date of this Contract to ensure it adequately addresses exit triggers and requirements.  If SEPPS and the Supplier cannot agree an exit plan in accordance with the above timescales (such agreement not to be unreasonably withheld or delayed), such failure to agree shall be deemed a Dispute, which shall be referred to and resolved in accordance with the Dispute Resolution Procedure set out in the Contract.