## Introduction
CDM REGULATIONS 2015 - PRE-CONSTRUCTION INFORMATION
CDM WORKBOOK CONTENTS
No. | Sheet | Description
1 | Project Information | Provides summary of project details including description of works, key duty holders, programme.
2 | Client Site Rules | Identifies any specific client site rule requirements.
3 | Client Management Requirements | Identifies any specific client management requirements.
4 | Design Hazard Register | To be completed by Principal Designer to record significant construction phase hazards and any control measures to eliminate or reduce the risk. Needs to incorporate all significant hazards/risks highlighted by other disciplines.
5 | Access & Maintenance Strategy | Records access and maintenance strategy for finished structure (for inclusion in Health & Safety File).
6 | Site Assessment | Identifies client site occupation requirements / considerations during construction phase.
7 | Construction Phase Plan Checklist | To assess adequacy of Principal Contractor's construction phase plan on behalf of client.
8 | Health & Safety File Checklist | To assess adequacy of Health and Safety File documentation.
Other | Pre-Construction Information Template (Separate Word Document) | On larger projects involving more than 30 days of construction work or involving significant/complex risks the separate Pre-Construction Information template should also be completed.

## 1. Project Info
CDM REGULATIONS 2015 - PRE-CONSTRUCTION INFORMATION
PROJECT INFORMATION
SITE: | Hazelwood Neighbourhood Centre, Gainsborough Road, Corby NN18 0QF
PROJECT: | Internal Alterations & Kitchen installation
COMPLETED BY: | Paul Wilson
REVIEWED BY:
DATE: | 3rd February 2026
PROJECT DETAILS
Description of Works: | Internal alterations including the blocking up and creation of new openings and installation of kitchen units, oven and extractor.
Site Occupancy: | The site is a multi use community asset with a Day nursery attached.
Programme: | Start on site: | TBC | Construction Wks: | 4 Weeks
| Mobilisation: | 4 Weeks
CLIENT
Organisation: | North Northamptonshire Council
Contact Name: | Baz Kelsi |  | Telephone No: | 01536 534463
PRINCIPAL DESIGNER
Organisation: | Principle Contractor
Contact Name: | TBA |  | Telephone No:
PRINCIPAL CONTRACTOR
Organisation: | To be appointed
Contact Name: |  |  | Telephone No:
F10 NOTIFICATION
Notification Required: | NO
A project is notifiable if the construction work is scheduled to: - last longer than 30 working days with more than 20 workers working simultaneously; or - exceed 500 person days of work.
OTHER KEY SUPPORTING DOCUMENTATION
Document |  |  | Reference No. / Additional Info.
Client Site Rules
Client Considerations & Management Requirements
Design Hazard Register
Mains Service Record Plans
Portfolio Record Plans
Site Assessment Document
Asbestos Management Plan
Arboricultural Report
Note on B6: Type details here and then information will auto-populate onto the other sheets

## Master Template Project (hidden)
Lincolnshire County Council, County Offices, Newland, Lincoln, LN1 1YL
Kier Business Services Ltd, County Offices, Newland, Lincoln, LN1 1YL
To be appointed
Lincolnshire County Council, County Offices, Newland, Lincoln, LN1 1YL
Fully occupied school site
Works planned for school holiday period when site will be unoccupied
Occupied office accommodation
Accommodation to be vacated for duration of works
YES
NO
Pre-Construction Information compiled by CDM Advisor
Client Site Rules
Client Considerations & Management Requirements
Design Hazard Register
Site Assessment Document
Portfolio Record Plans
Mains Service Record Plans
GRPS Services Scan
Historic Record Drawings
Asbestos Management Plan
Asbestos Refurbishment & Demolition Survey
Ground Investigation
Other (please type here)
1 Week
2 Weeks
3 Weeks
4 Weeks
5 Weeks
6 Weeks
7 Weeks
8 Weeks
9 Weeks
10 Weeks
11 Weeks
12 Weeks
13 Weeks
14 Weeks
15 Weeks
16 Weeks
17 Weeks
18 Weeks
19 Weeks
20 Weeks
21 Weeks
22 Weeks
23 Weeks
24 Weeks
25 Weeks
26 Weeks
27 Weeks
28 Weeks
29 Weeks
30 Weeks
31 Weeks
32 Weeks
33 Weeks
34 Weeks
35 Weeks
36 Weeks
37 Weeks
38 Weeks
39 Weeks
40 Weeks
41 Weeks
42 Weeks
43 Weeks
44 Weeks
45 Weeks
46 Weeks
47 Weeks
48 Weeks
49 Weeks
50 Weeks
51 Weeks
52 Weeks

## 2. Client Site Rules
CDM REGULATIONS 2015 - PRE-CONSTRUCTION INFORMATION
CLIENT SITE RULES |  | The Principal Contractor's Site Rules must incorporate the following client requirements:
01 | Compound and work areas to be kept secure to prevent authorised access
02 | Contractor vehicles and plant to be limited to 5mph within the curtilage of the site.
03 | Contractor vehicles and plant to have trained banksman guidance during reversing operations.
04 | Plant and Equipment is to be inspected before use.
05 | Plant and Equipment is only to be used by trained and competent operatives.
06 | All activities to be undertaken in a professional and courteous manner.
07 | Written, spoken or implied abuse of anyone to anyone will not be tolerated.
08 | Fraternising with occupants of the premises is not permitted.
09 | The playing of music on occupied sites is not permitted
10 | Smoking is not permitted anywhere on the site.
11 | Possession of recreational drugs and solvents or alcohol on site is not permitted.
12 | As a minimum at all times site standard PPE requirements must be adhered to.
13 | Operatives to be appropriately dressed at all times (including no bare chests).
14 | The lighting of fires is strictly prohibited on site.
15 | The site must be kept clean and tidy and waste must not be left to accumulate.
16 | Contractor to maintain emergency provisions on site.
17 | Permit to work systems are to be enforced for higher risk operations including all hot works.
18 | Cartridge tool fixing operations only permitted with prior consent of Principal Designer.

## 3. Client Management Req.
CDM REGULATIONS 2015 - PRE-CONSTRUCTION INFORMATION
CLIENT CONSIDERATIONS & MANAGEMENT REQUIREMENTS |  | To be read in conjunction with 'Client Site Rules'
In order to ensure the works are managed and delivered safely the client expects that the Principal Contractor will introduce measures to ensure the following items are addressed.
1.0 HEALTH AND SAFETY BASICS
1.1 | All Contractors must at all times comply with the provisions of The Health and Safety at Work Act 1974 and all other relevant legislation including the CDM Regulations 2015.
1.2 | Contractors must take all necessary measures to ensure the health and safety of their own employees, others working on site, the general public and persons using or entering the place of work whether authorised or otherwise, who may be affected by their activities.
1.3 | The Principal Contractor must ensure that at all times there is a named responsible person on site to manage the works from a Health and Safety perspective.
1.4 | The Principal Contractor must hold an SSIP accreditation for the duration of their appointment. Site Managers must hold an SMSTS level qualification or equivilant and Site Supervisors must hold an SSSTS level qualification or equivilant.
2.0 COOPERATION, COMMUNICATION AND COORINATION
2.1 | The principal objectives relating to Health and Safety on the project rely on cooperation, communication and coordination between all parties.
2.2 | The Principal Contractor will be required to confirm their arrangements for facilitating this including: - Named responsible person on site - Site inductions & tool box talks - Regular liaison with the head of the establishment
2.3 | If applicable the Principal Contractor must make additional arrangements to communicate with workers who have poor literacy skills or who are not fully literate in English.
3.0 SEGREGATION OF THE WORKS
3.1 | The Principal Contractor must ensure that at all times safety clearance zones are maintained between the construction activity and the construction site boundary.
3.2 | All compound, storage and external working areas of the site must be within a securely fenced enclosure to prevent unauthorised access.
3.3 | Fencing should not be less than 2m high solid hoarding or narrow gauge anti climb design.
3.4 | All fencing must be adequately braced and supported and appropriately designed to ensure it remains stable.
3.5 | In vulnerable areas (such as adjacent to public footpaths / play areas) additional measures should be incorporated for example solid hoarding or additional debris mesh protection.
3.6 | Internal works areas must also be fully segregated to provide security, dust protection and 1/2 hour fire segregation as necessary.
3.7 | Protective coverings must be flame retardant i.e. comply with the appropriate Loss Prevention Standard (LPS1207 (Internal floor coverings etc.) & LPS 1215 (External sheeting for scafffolds etc).
3.8 | Materials must be stored in a safe manner. Particular care must be taken in relation ot stacked items to ensure they remain stable.
3.9 | Access into occupied areas will only be permitted with the prior consent of the head of the establishment.
4.0 SAFEGUARDING REQUIREMENTS
4.1 | Safeguarding arrangements need to be in place on all projects which provide contractors with the opportunity for regular contact with children.
4.2 | In such circumstances the Principal Contractor will be provide an enhanced DBS certificate for all members of their site team.
4.3 | At all times construction works must be segregated from occupied areas and operatives must not be unaccompanied in areas outside of the defined site parameters.
5.0 SITE ACCESS / PARKING
5.1 | Vehicular movements / deliveries must be planned to avoid peak traffic times.
5.2 | Parking arrangements are to be agreed with the head of the establishment.
5.3 | Vehicles must not be parked where they pose a hazard or obstruction to other road users.
5.4 | Trained banksman guidance to be used to supervise deliveries and reversing manoeuvres.
5.5 | The Principal Contractor must ensure that the compound and buildings are left secure and all equipment, tools and plant are secured, immobilised and/or cleared away at the end of each working day.
6.0 LIFTING OPERATIONS
6.1 | All lifting operations must be undertaken in accordance with LOLER 1998.
6.2 | Lifting operations beyond the confines of the site boundary / over occupied buildings are strictly prohibited.
6.3 | Where necessary temporary barriers must be utilised to provide segregation.
7.0 WORKING AT HEIGHT
7.1 | All work at height operations must be undertaken in accordance with the Work at Height Regulations 2005.
7.2 | A sufficient safety distance must be maintained between all work at height operations and the boundary of the site.
7.3 | Where a safety distance can not be achieved additional overhead safeguards must be provided to prevent the fall of materials onto persons below.
7.4 | All scaffolding to be assembled/modified in accordance with a recognised standard (e.g. NASC TG20:21 for tube and fitting scaffolds) by trained operatives. Where a non-standard configuration is required this must be subject to a bespoke design with supporting calculations by a competent person.
7.5 | Scaffold erection/dismantling will only be permitted within a segregated works area.
7.6 | If existing access to a roof is available its suitability should be considered prior to adopting it as the preferred route of access.
7.7 | When working at height suitable access to the work area shall be made available, an assessment shall be carried out to determine the associated risk and should be based on: - the height of the access point to the working location, - the number of users, - the number of times it is used on a daily basis - the duration of the work - the nature of the work
7.8 | The lifting of materials, tools and plant onto an elevated work area must be carried out in compliance with LOLER 1998
7.9 | No materials, tools or plant shall be carried up ladders.
7.1 | All mechanical and manual lifting aids shall be fitted with a suitable emergency braking system to prevent fall back in the event of failure.
7.11 | Where lifting appliances are used they should be properly installed, maintained, inspected and, at all times, operated within its safe working load
7.12 | Access to the area below a lifting point should be controlled when the lifting equipment is in use, eg by temporary fencing.
8.0 TEMPORARY WORKS
8.1 | All tempoary works must be undertaken in accordance with the requirements of BS5975:2019
8.2 | The Principal Contractor will be required to ensure that all temporary works required are designed, authorised, managed and inspected by a competent qualified person.
8.3 | All temporary works proposals are to be submitted to the design team in advance for comment.
9.0 MOBILE PLANT, TOOLS AND EQUIPMENT
9.1 | All mobile plant, operating tools and equipment must be properly maintained, serviced, inspected and tested as required by statutory requirements.
9.2 | All operators must be trained, competent and authorised to use equipment.
9.3 | Priority must be given to the use of either battery powered or low voltage 110v tools.
10.0 WELFARE & EMERGENCY ARRANGEMENTS
10.1 | The Principal Contractor will be required to maintain welfare provisions in accordance with Schedule 2 of the CDM Regulations 2015.
10.2 | The Principal Contractor will be required to provide their own emergency provisions during the contract period including first aid and fire fighting.
10.3 | The Principal Contractor is to develop an Emergency Plan confirming their management arrangements in the event of an emergency evacuation.
10.4 | The Principal Contractor must liaise with the Head of the Establishment in order to coordinate the emergency arrangements during the works including method of raising the alarm.
10.5 | The Principal Contractor must implement accident/incident reporting procedures including the requirements of RIDDOR 2013.
11.0 LONE WORKING
11.1 | Lone working on site should be avoided and must only be permitted for low risk activities.
11.2 | Lone working at unoccupied premises is strictly not permitted for any medium/high risk activities including working at height, working with plant/machinery, working with electricity.
11.3 | If lone working is required then the Principal Contractor must ensure suitable management procedures are in place. This should include the provision of an automated monitoring system (such as a Lone Working App).
12.0 COVID-19
12.1 | Principal Contractors will be required to ensure they have suitable and sufficient arrangements in place to manage the risks associated with COVID-19 and enable works to continue in a safe manner in accordance with the latest Government guidance.
12.2 | Details of these arrangements must be included within the Construction Phase Plan and be regular reviewed on site.
END OF DOCUMENT

## 4. Design Hazard Register
CDM REGULATION 2015 - PRE-CONSTRUCTION INFORMATION DESIGN HAZARD REGISTER
SITE: | North Northamptonshire Council - Hazelood Neighbourhood Centre Internal Alterations & Kichen Installation
PROJECT: | Internal Alterations
COMPLETED BY: | Paul Wilson
REVIEWED BY: | 0
DATE: | 3rd Febuary 2026 |  | REVISION:
To be read in conjunction with the 'Client Consideration and Management Requirements' and 'Client Site Rules'.
ELEMENT | ANTICIPATED HAZARDS | DESIGN CONSIDERATIONS TO REDUCE / MINIMISE RISK | FURTHER ACTION / INFO
Site Access | Moving Vehicles | Site plan indicates proposed access / fencing route.
| Interface with Public Routes | Restrict vehicles access and movements to avoid busy periods
| Highway Traffic | Car park on site to be used for contractor vehicles
| School Traffic / Pedestrians | N/A to this project
Occupant / Visitor Access | Moving Vehicles | Careful planning required and avoidance of bussiest time.
| Pedestrians | Pedestrian barrier to be provided to segregate vehicular and operative pedestrian routes
Works in Occupied Areas | Occupants | Scaffolding to be assembled / disassembled outside of occupied hours
| Electrocution | N/A to this project
| Asbestos Materials | N/A to this project
| Slips, Trips, Falls | N/A to this project
All access/egress routes to be remain clear at all times. Restrict unauthorised site access. Good site housekeeping.
Fire Procedures - Existing Occupants Arrangements | Fire | Ensure fire exits are kept clear | BB100 - Design for Fire Safety in Schools
Burns
Entrapment
Explosion
Fire Procedures - Contractors Arrangements | Fire |  | HSG168 - Fire Safety in Construction
Burns
Entrapment
Explosion
Fire Procedures - Timber Framed Structures | Fire | N/A to this project - No timber framed structures included within scheme | STA - 16 Steps to Fire Safety Guidance
Burns
Entrapment
Explosion
Screening & Protection | Unauthorised Access | N/A to this project
Dust / Debris
Ground Investigation | Chemical Contamination | N/A to this project - No excavation works planned
Infill / Made-up Ground
Asbestos | Carcinogenic Material | N/A to this project - Works do not affected any existing structures
Lead in Paint | Toxic Material | N/A to this project - Works do not affected any existing structures
Inhalation, Ingestion
Coal Tar in Tarmac | Carcinogenic Material | N/A to this project - Works do not affected any existing tarmac surfaces
Existing Underground Services | Live Underground Services | Mains service record plans sourced from utilities providers
Electrocution Explosion Fire
Existing Overhead Services | Arcing of Cables | N/A to this project - No overhead services present on site
| Electrocution Explosion Fire | N/A to this project - No overhead services present on site
General Excavations | Collapse of Excavations | N/A to this project - No excavation works planned
| Falls into Excavations | Area of excavation to be CAT scanned and all identified services to be highlighted on site
Underground Services
Structural Considerations | Collapse of Structure | N/A to this project | For further details refer to Structural Engineers DRA
Noise / Vibration
Manual Handling
Work at Height | Falls from Height | N/A to this project
| Fall of Materials | N/A to this project
Mechanical & Electrical Services/ Lighting Protection System |  | N/A to this project
Control of Dust & Noise | Dust | N/A to this project
Noise
Fire
Manual Handling | Sprains | Principal Contractor required to make his own assessment of the procedures to be adopted when handling certain heavy items.
| Internal Injuries | Principal Contractor required to make his own assessment of the procedures to be adopted when handling certain heavy items.
| Back Injuries | Principal Contractor to include provision for mechanical lifting to reduce manual handling on site.
Slips, Trips, Falls
COSHH | Fumes Vapour | N/A to this project
Burns
Skin Irritations
Welfare & Emergency Provisions |  | Existing toilet facilities will be available for use by the contractor | Provision to include: Toilets, Washing Facilities (inc. Hot Water), Drinking Water, Facilities for Rest (Chairs / Tables / Heating)
Contractor to respect cleanliness of facilities made available to them
Any Other | Safeguarding | N/A to this project - No children present on site
| Hazardous Substances | Fuel tank located away from the premises, used / spent oil in bunded tank at the end of the premises

## Master Template DHR (hidden)
ELEMENT | DESIGN CONSIDERATIONS
Site Access
N/A to this project
Form new separate access route for contractors vehicles
Contractor access route to be shared with main vehicular entrance onto site
Proposed access route discussed with Head of Establishment
Restrict vehicles access and movements to avoid busy periods
Site plan indicates proposed access route / fencing lines (Ref Drwg No. xxx)
Contractor to provide warning and directional signage and provide trained banksman assistance
Other (Please Type Here)
Occupant / Visitor Access
N/A to this project
Works to be undertaken during holiday period hence fewer occupant will be present on site
Designated crossing point to be formed
Pedestrian barrier to be provided to segregate vehicular and pedestrian routes
Movement of plant/material to be strictly prohibited during key times
Alternative temporary access route onto site to be established
Suitable pedestrian barrier protection to blind corners to be provided along vehicular access routes
Other (Please Type Here)
Works in Occupied Areas
N/A to this project
Agree phasing and timescales with Head of Establishment to enable areas directly affected by works to be vacated
Utilise holiday periods when site is less busy
The new extension has its own external access enabling contractor to have dedicated access directly into work area
Ensure complete segregation of working areas from occupants of buildings
Keep adjoining occupied routes clear from the storage of materials and equipment
No works to be undertaken prior to receipt of Refurbishment/Demolition Asbestos Survey
Principal Contractor to maintain permit to work systems where necessary for electrical testing, hot works and the like.
Scaffolding to be assembled / disassembled outside of occupied hours
Other (Please Type Here)
Fire Procedures - Existing Occupants Arrangements
N/A to this project - No existing occupants on site
The works / compound area do not affect any exiting fire exit routes
Works will affect some fire exits but adequate alternatives available to ensure compliance with BB100 (Travel Distances - 18m (one direction only) 45m (more than one direction))
Site Fencing to be located to maintain existing fire exit routes adjacent to works area
Contractor to provide clear signage indicating fire exit routes
Works to Fire Alarm to be undertaken outside of occupied hours
Works will affect access to existing Fire Alarm Panel
Other (Please Type Here)
Fire Procedures - Contractors Arrangements
Contractor to liaise with Head of Establishment and produce Emergency Plan outlining their arrangements in event of evacuation
Contractor to maintain 30mins fire resistant segregation between construction works and occupied areas
Protective coverings must be flame retardant i.e. comply with the appropriate Loss Prevention Standard (LPS1207 Internal & LPS 1215 External).
Temporary accommodation / skips etc. to be located over 6m from existing buildings / construction works. Temporary accommodation to have 30mins fire resistance.
Contractor to utilise existing emergency lighting and fire alarm system during construction
Existing emergency lighting and fire alarm system to be tested prior to use
Additional break glass point to be installed in works area to enable Contractor to raise school alarm in emergency
Temporary Emergency lighting to be installed by Principal Contractor if the existing system cannot be maintained during construction
Temporary Fire Alarm measures and controls to be installed by Principal Contractor if the existing system cannot be maintained during construction
Other (Please Type Here)
Fire Considerations - Timber Framed Structure
N/A to this project - No timber framed structures included within scheme
Consideration of fire resistance and fire protection during the construction stages and the effects on adjacent buildings neighbouring residential premises and land.
Consultant appointment to prepare a Site Fire Risk Assessment Report to determine protection measures for the timber frame (i.e. – fire resistance treatment of the timber frame, pre clad areas)
Carry out an initial Consultation with the timber frame manufacturer regarding site accessibility, space separation, methods of compartmentation and techniques to maintain fire safety during construction
Follow the guidance in the Structural Timber Association guidance 16 steps to fire safety
Screening and Protection
N/A to this project
Existing glazing adjacent to works area to be protected with suitable screening
Solid hoarding to be erected adjacent to pedestrian routes / play areas
Solid hoarding to be erected internally to provide dust protection, security and fire protection
Debris mesh to be fitted to fencing adjacent to pedestrian routes / play areas
2m safety exclusion zone to be created using pedestrian barrier adjacent to overhead roofing works
Ball guards to be fitted at base of fencing adjacent to play area
Other (Please Type Here)
Ground Investigation
N/A to this project - No excavation works planned
Consultation with Building Control to confirm local ground conditions and suitable foundation design
On site investigation undertaken by Structural Engineer
Full Ground Investigation Report commissioned
Ground Investigation Report information sourced from previous scheme
Known history of previous manufacturing / industrial process either on or adjacent to proposed site hence risk of migrating contaminants
Other (Please Type Here)
Asbestos
N/A to this project - Works do not affected any existing structures
N/A to this project - All structures affected by works were constructed after year 2000
Management Asbestos Survey undertaken in 20XX identifies:
Demolition/Refurbishment Survey of areas affected commissioned
Proposed Mechanical and Electrical service routes have been included within the survey area
No works to existing structure permitted prior to receipt of Demolition/Refurbishment Survey
No works with Asbestos Containing Materials permitted without demonstration of necessary training
Asbestos containing materials to be removed by licensed contractor
Other (Please Type Here)
Lead in Paint
N/A to this project - Works do not affected any existing structures
N/A to this project - All structures affected by works were constructed after year 1988
No planned works to disturb existing painted window/door/timber surfaces
Existing painted window/door/timber surfaces to be removed in entirety hence painted surface will not be worked upon as part of scheme
Lead in paint sampling required and commissioned
Principal Contractor to ensure authorised disposals of lead painted items
Where work with lead in paint cannot be avoided contractor to follow the HSE and DEFRA guidance regarding working practices
Coal Tar in Tarmac
N/A to this project - Works do not affected any existing tarmac surfaces
N/A to this project - Works do not affected tarmac surfaces which pre-date 1985
Core sampling of tarmac surface required and commissioned (record service information provided)
Contractor to be advised and take all necessary protection measures, wearing of PPE and the like during the removal of affected areas
All contaminated tarmac to be taken to licensed tip for authorised disposal
Existing Underground Services
N/A to this project - No excavation works planned
Mains service record plans sourced from utilities providers
Record drawings sourced from archived information
GPRS site services scan commissioned
On site investigation undertaken to locate and expose existing services
Underground services within vicinity of piling operations hence guidance sought from utility companies (requirement for vibration alleviation trench?)
Other (Please Type Here)
Existing Overhead Services
N/A to this project - No overhead services present on site
The following overhead services have been identified in the area affected by the works:
The following overhead services have been identified crossing the proposed access route:
Utilities service provider contacted for guidance
Other (Please Type Here)
General Excavations
N/A to this project - No excavation works planned
Provide Ground Investigation and Services Information (as above)
Foundation design to minimise excavation
Area of excavation to be CAT scanned and all identified services to be highlighted on site
The scheme includes the following deep excavations:
Other (Please Type Here)
Outreach Excavations
N/A to this project - No outreach excavation works planned
Outreach excavations (beyond confines of site) will be required for:
Head of establishment to be consulted with regard to programming of outreach works
Works to be segregated from occupants of building at all times
Other (Please Type Here)
Demolition / Alteration Works
N/A to this project
Refer to record information relating to services / asbestos / lead in paint
Head of Establishment to be consulted with regard to programming of works
Works to be segregated from occupants of building at all times
Consider unauthorised access - potential for sharps/syringes, vagrant within
Contractor to prepare written plan for the safe management of site works
Other (Please Type Here)
Temporary Works
All Temporary Works are to be undertaken in accordance with the requirements of BS5975:2019
Significant Temporary Works associated with this scheme include:
Structural Engineer to survey site to assess structural stability and risk of uncontrolled collapse
Structural Engineer to advise on any foreseeable loadings that may be imposed upon the temporary works and transferred to the permanent structure
Principal Contractor to issue proposed method statement to Structural Engineer for comment
Principal Contractor to appoint named Temporary Works Co-ordinator to ensure the contractor's procedures for control of Temporary Works are implemented on site
Other (Please Type Here)
Structural Considerations
N/A to this project
Sequential 'hit and miss' bay foundation specified owing to proximity of adjacent foundations
Underpinning requirements
Any bracing requirements
Specific sequence of erection outlined by structural engineer
Requirements for temporary stability of frame outlined by structural engineer
Piling diameter kept to minimum to reduce noise/vibration issues and reduce size of plant required
Mix design for substructure concrete and gas protection measures informed by Ground Investigation report
Individual concrete block weights kept below 20kg (XXkg/m3, 440x140x215mm blocks)
Lifting Operations
N/A to this project
Define lifting zones and clearance areas in liaison with client and produce corresponding site plan
Strictly no lifting operations permitted over occupied buildings
Consider additional impact protection where crane located adjacent to roadway
Assessment of ground conditions including CRB (compression) test has been completed
Underground services within vicinity of works hence approval sought from utility companies
Overhead Services within vicinity of works - Ref existing overhead services section
Contractor to prepare risk assessment for safe management of works
Sequences of erection including temporary bracing requirements provided by Structural Engineer
Works are within 6km of an Airfield hence Airfield Manager to be given 1months notice of any craning operations
Other (Please Type Here)
Work at Height
N/A to this project
Staircase to be pre-cast hence providing good access to first floor work area.
Works above occupied area will not be permitted
Existing roof lights to be covered / protected during works
Assessment of integrity of light fittings/diffusers beneath roofing operations to be undertaken
Contractor to be aware of existing fragile roof structure adjacent to proposed extension
Other (Please Type Here)
Mechanical & Electrical Services
N/A to this project
Additional loadings to existing structures from new M&E services has been considered
Oil tank removal to be programmed and managed by appointed contractor including vapour testing
New service runs to be installed to appropriate depth with sand surround and tracer warning tape min 300mm above
Requirements for Outreach Works associated with new service runs outlined above
Requirements for Asbestos survey and precautions associated with new service runs outlined above
Other (Please Type Here)
Lightning Protection System
N/A to this project
Client requirement for lightning protection system to be installed
Existing Lightning Protection System in place and to be extended
Specialist consultant to undertake risk assessment and provide recommendations on requirements
New system to be designed and installed by specialist consultant
System to incorporate external (structural) and internal (surge and over-voltage protection) elements
Control of Dust and Noise
N/A to this project
Principal Contractor will be required to pay all due regard to the need to control dust and noise. Utilise damping down measures, suppression equipment and the like.
Discuss timing and operation of any disruptive works with the school.
Works phased to minimise disruption to the school
Other (Please Type Here)
Manual Handling
N/A to this project
Principal Contractor required to make his own assessment of the procedures to be adopted when handling certain heavy items.
Principal Contractor to include provision for mechanical lifting to reduce manual handling on site.
Mechanical Equipment to be employed where possible to reduce manual handling on site however it must noted that owing to the location of the new build access for large machinery is restricted.
The Principal Contractor will be required to make his own assessment of the following items:
Other (Please Type Here)
COSHH
N/A to this project
The contractor should be aware of the following items specified with in this project:
The construction materials generally are common place. The Principal Contractor is to obtain copies of COSHH or other health and safety information, when ordering materials from suppliers
All solvents, fuels, paints and the like must be stored in accordance with the manufacturer’s instructions within a secured store in the compound area. No such materials are to be left or stored within the building.
Other (Please Type Here)
Unexploded Ordnance
N/A to this project - no excavation works planned
Preliminary risk assessment undertaken considering site location, previous site developments, wartime bombing records etc.
Site considered to be low risk hence no further action required
Site considered to be medium / high risk hence detailed risk assessment to be completed by UXO specialist and risk mitigation plan to be established
Principal Contractor to implement risk mitigation plan and emergency procedures
Other (Please Type Here)
Other Safety Risks
No specific additional safety hazards identified in relation to this project
POTENTIAL HAZARD: Fragile Surfaces (roof glazing / lightweight sheeting / canopies) identified on site
POTENTIAL HAZARD: No flame zones associated with roofing works identified on site and indicated on project drawings
POTENTIAL HAZARD: Presence of water course adjacent to works area
POTENTIAL HAZARD: Hazardous materials known to be stored on site
POTENTIAL HAZARD: Damage / instability of existing structures on site
POTENTIAL HAZARD: Confined space identified on site
Other (Please Type Here)
Other Health Risks
No specific additional health hazards identified in relation to this project
POTENTIAL HAZARD: Trace anthrax presence within horse hair plaster present within existing historic buildings refer to English Heritage guidance documentation
POTENTIAL HAZARD: Leptospirosis (weils disease) from direct contact with urine from infected rats or from contaminated water
POTENTIAL HAZARD: Significant quantity of Guano (pigeon droppings) present on site
POTENTIAL HAZARD: Infection from discarded hypodermic needles - appropriate management arrangements to be implemented to clear and dispose of sharps and deal with any injuries
POTENTIAL HAZARD: Contaminants from previous users of accommodation - minor chemical spills etc.
POTENTIAL HAZARD: Legionella risk within vacant buildings - testing to be commissioned and system flushed out / chlorinated
Principal Contractor to ensure site operatives are made aware of potential health hazards on site
Good standard of welfare provision and PPE (including gloves, boots, face masks and overalls) to be employed on site to reduce risks associated with potential health hazards
High standard of personal hygiene to be promoted on site
Other (Please Type Here)
Welfare Provision
N/A to this project
Contractor to provide full welfare provision to satisfy requirement of Schedule 2 of CDM Regulations
Temporary site accommodation and storage facilities to be located within the designated compound area
Connections to existing water / electric services will be made from:
Existing facilities available on site to be designated for use by contractor
Contractor to respect cleanliness of facilities made available to them
Contractor to maintain his own provisions for First Aid & Fire Fighting Equipment on site
Any Other
N/A to this project - No children present on site
Works taking place on an unoccupied, vacant site hence Principal Contractor to ensure suitable arrangements are in place to avoid lone working.
Enhanced DBS checks required for Principal Contractor site team members
Enhanced DBS checks required for all operatives working on site

## 5. Access & Main. Strategy
CDM REGULATIONS 2015 - PRE-CONSTRUCTION INFORMATION ACCESS & MAINTENANCE STRATEGY
SITE: | North Northamptonshire Council - Hazelwood Neighbourhood Centre Corby
PROJECT: | Internal Alterations & Kitchen installation
COMPLETED BY: | Paul Wilson
REVIEWED BY: | 0
DATE: | 29th January 2026 | REVISION:
For inclusion within Health and Safety File documentation
ELEMENT | DESIGN CONSIDERATIONS / MAINTENANCE PROCEDURES | FURTHER INFORMATION
Roof Access
N/A to this project
Roof Lights | N/A to this project
Gutters & Downpipes
N/A to this project
Window Access (Internally)
N/A to this project
Window Access (Externally)
N/A to this project
External Decoration | N/A to this project
Internal Decoration / Cleaning / Maintenance
N/A to this project
Specialist Equipment |  | Refer to Equipment List for details of warranty / servicing agreements
N/A to this project
N/A to this project
Plant and Equipment |  | Refer to Mechanical & Electrical O&M Manuals
N/A to this project
Flooring |  | Refer to manufacturers product information
N/A to this project
Organisation of Traffic Routes | N/A to this project
Other Details

## Master Template AMS (hidden)
ELEMENT | DESIGN CONSIDERATIONS
Roof Access
N/A to this project
Perimeter access maintained around building for erection of scaffold / mobile elevated works platform (MEWP) access
The roof is enclosed by a parapet wall at a height of at least 1100mm
Secure barriers (1100mm high) to provide protection to exposed edges
A roof access hatch has been incorporated with gated barrier to prevent falling back through hatch
Access onto the roof is gained via strategic ladder access points (with eye bolt fixings to secure ladders) located around the building.
A permanent fall restraint system has been incorporated onto the roofs allowing access to the:
A proprietary walkway system in contrasting colour clearly defines the working area on the roof
Access onto the roof is anticipated as being infrequent for annual routine maintenance, clearing of unwanted debris, roof light cleaning.
Other (Please Type Here)
Roof Lights
N/A to this project
Individual roof lights to be of non-fragile construction and sizes kept to a minimum to reduce risk of fall through
Roof lights to have upstand detail (to minimise possibility of inadvertently walking onto roof light)
Velux style roof lights specified which can be cleaned internally from tower scaffold
Roof lights to have automated opening with rain sensors
Other (Please Type Here)
Gutters & Downpipes
N/A to this project
All gutters are located at the eaves enabling access from the perimeter via a suitable mobile lifting platform
Access to gutters is to be made from the roof (Ref Roof Access Section)
Access to for gutters above areas of roof-wall abutments will be:
Ladder access - max. 9m but requires fixing points if over 6m
Downpipes designed to be straight (without swan neck detail) reducing maintenance issues
Other (Please Type Here)
Window Access (Internally)
N/A to this project
Cleaning of high level internal glazing / roof lights to be undertaken from suitable tower scaffold
Mechanical winding gear incorporated for opening high level windows / windows in front of fixed benching
Window poles incorporated for opening high level windows / windows in front of fixed benching
Other (Please Type Here)
Window Access (Externally)
N/A to this project
Cleaning of windows to be undertaken from ground level with the use of a telescopic 'pump fed' hose and brush attachments.
Windows designed to open internally enabling cleaning to undertaken from within the building
Openable windows to be restricted to prevent them projecting where persons could collide
Access to clerestory glazing will be:
Access to windows above areas of roof-wall abutments will be:
Ladder access - max. 9m but requires fixing points if over 6m
Other (Please Type Here)
External Decoration
N/A to this project
Perimeter access around the building has been maintained for mobile elevated working platform access
Alternatively scaffold could be utilised to provide access to external areas.
Internal Decoration / Cleaning / Maintenance
N/A to this project
Where high level internal access is required it is anticipated this will be made via a tower scaffold
Suspended light fitting incorporated reducing need for high level access
Wall lights incorporated in stairwells for ease of access
Underfloor Heating - Care must be taken to ensure point loads are not transferred to the floor (for example erect tower scaffolds off plywood boards)
Other (Please Type Here)
Specialist Equipment
N/A to this project
Scheme incorporates lightning protection system which will require annual inspection including access onto roof
Employ specialist contractors for all servicing, maintenance and repair of lifting equipment in accordance with H&S Regulations
Isolate electricity supplies and lock off
Ensure fixed barriers, guards and warning notices are erected before works commence
Other (Please Type Here)
Plant and Equipment
N/A to this project
No plant or equipment requiring regular maintenance has been incorporated within high level areas
Level access into plant room enabling safe delivery of plant/equipment
Permanent staircase provided to access first floor plant room
Fixed ladder included to provided access to plant
Designated ladder access point provided with fixing points to secure ladder
Scheme incorporates safe access, walkways, handrails, lighting to plant and equipment in roof voids
Scheme incorporates method for lifting of tools / maintenance equipment to high level areas
Other (Please Type Here)
Flooring
N/A to this project
Slip resistant safety flooring specified in wet areas
Where necessary floor includes an effective means of drainage
Care & Maintenance of flooring to be in accordance with manufacturers recommendation
Organisation of Traffic Routes
N/A to this project
Scheme incorporates separation of vehicles from doors, gates and pedestrian routes
Scheme incorporates crossing points for pedestrians
Scheme incorporates suitable signage and road markings
Scheme incorporates turning area for delivery vehicles / buses
Other (Please Type Here)
Other Details

## 6. Site Assessment - General
CDM REGULATIONS 2015 - PRE-CONSTRUCTION INFORMATION
SITE ASSESSMENT
SITE: | Hazelwood Neighbourhood Centre, Gainsborough Road, Corby NN18 0QF
PROJECT: | Internal Alterations & Kitchen installation
COMPLETED BY: | Paul Wilson
REVIEWED BY:
DATE: | 3rd February 2026
COVID-19 - Given the ongoing and evolving COVID-19 situation it must be noted that stated client occupancy levels and any identified key times may be subject to change. Further updates will be provided as they become available and the Pre-Start Meeting will provide the opportunity to further clarify details with the client prior to works commencing.
INFORMATION | NOTES / COMMENTS
LOCATION Neighbouring accommodation / adjacent users | The Council Depot is located in a densely populated industrial estate
OCCUPANTS No. of occupants Age of occupants Any vulnerable user groups etc.
GENERAL USE OF PREMISES Primary use of premises Breakfast / after school clubs Lettings (weekend / evening) Holiday clubs Other users (childrens centre / nursery / library etc.)
PREMISES CONTACT Main contact on site during works Out of hours access arrangements | Baz Kelsi
PROGRAMMING / SEQUENCING Project specific phasing requirements Works to be undertaken during holiday periods Holiday dates
EXISTING ACCESS Main access Secondary access Grounds maintenance / emergency access Local restrictions (size / weight) / safety zones outside site School buses / taxis Daily deliveries - kitchen etc Pedestrian access on to site Visitor access affected by works
CONTRACTOR ACCESS Peak times to be avoided Proposed access route
SITE COMPOUND / WELFARE Compound location Parking arrangements Welfare arrangements (Consider COVID-19 requirements) Temp water & electric connections | The contractor may make use of the toilet and welfare facilities at the Depot. An allocated area will be assigned for the Contractors Vehicles.
LIFTING / PILING OPERATIONS Access to site for large equipment Proximity to occupied areas | N/A
ACTIVITIES NEAR TO SITE Location of works in relation to occupied areas Access requirements into occupied areas (alterations / service connections / window replacement etc) Will works above occupied areas be required Pedestrian diversions Segregation/screening requirements including glazing Other restrictions (break times etc)
FIRE CONSIDERATIONS Do work affect fire exit routes Fire alarm panel location Fire assembly area Site specific restrictions on hot works | The fire assembly point is indicated on the Site Block Plan.
EXISTING SERVICES Mains services present on site Other service positions (sub-mains, sub-stations, adjacent buildings, cctv, fire alarms, manholes, drainage runs) Any overhead services (crossing construction site or access route) | Utility services plans are provided.
PROPOSED SERVICES Will any service diversion be required and if so when can this be completed Will outreach trench excavations beyond construction site by required
ASBESTOS Asbestos Management Survey Refurb & Demo Asbestos Survey Requirement for removal of known asbestos containing materials | N/A
VANDALISIM RISK Does site suffer from unauthorised access / vandalism issues Is there security / CCTV coverage | The area does not appear to experience vandalism problems.
OTHER CONSIDERATIONS Any other planned construction works separate from this project Any other planned maintenance activities which may impact (e.g. decoration / boiler servicing / electrical testing) Any examination periods during contract period. Relationship with neighbours and consideration of impact of works (dust / noise / scaffolding - privacy) Smoking/Vaping - Policy to be adopted during construction works. Any other items to highlight to Principal Contractor | There are no other planned works on site during period of August 2025. Smoking is only permitted in the designated smoking area.
Disclaimer: The information contained herein has, so far as is reasonably practicable, been gathered from reputable sources however the accuracy and sufficiency of this information is not guaranteed by the Employer or the Employer's representative. Additionally the nature and condition of the site cannot be fully and certainly determined before it is opened up. Before tendering the contractor is to satisfy themselves of the nature of the site, access thereto and all local conditions and restrictions likely to affect the execution of the works. Should any gaps or omissions be identified within the information provided please advise the Employer or Employer’s representative who will seek to clarify any issues.

## 6. Site Assessment - SEND Sch (hidden)
CDM REGULATIONS 2015 - PRE-CONSTRUCTION INFORMATION
SITE ASSESSMENT
SITE: | Hazelwood Neighbourhood Centre, Gainsborough Road, Corby NN18 0QF
PROJECT: | Internal Alterations & Kitchen installation
COMPLETED BY: | Paul Wilson
REVIEWED BY: | 0
DATE: | 3rd February 2026
COVID-19 - Given the ongoing and evolving COVID-19 situation it must be noted that stated client occupancy levels and any identified key times may be subject to change. Further updates will be provided as they become available and the Pre-Start Meeting will provide the opportunity to further clarify details with the client prior to works commencing.
INFORMATION | NOTES / COMMENTS
LOCATION Neighbouring accommodation / adjacent users
OCCUPANTS No. of occupants Age of occupants Broad needs of pupils / conditions school caters for Awareness of procedures should pupils go into crisis Storage of medicines / oxygen and accessibilty during works
GENERAL USE OF PREMISES Primary use of premises Breakfast / after school clubs Lettings (weekend / evening) Holiday clubs Residential Use Other users (childrens centre / nursery / library / health care professionals etc.)
PREMISES CONTACT Main contact on site during works Out of hours access arrangements
PROGRAMMING / SEQUENCING Project specific phasing requirements Works to be undertaken during holiday periods Holiday dates
EXISTING ACCESS Main access Secondary access School buses / taxis - How this operates & consider pupil needs Grounds maintenance / emergency access Daily deliveries - kitchen etc Pedestrian access on to site Visitor access affected by works Local restrictions (size / weight) / safety zones outside site
CONTRACTOR ACCESS Peak times to be avoided Proposed access route Visual / Audible warning for vehicular movements
SITE COMPOUND / WELFARE Compound location Parking arrangements Specific Fencing Requirements (Anti-climb, solid hoarding, visibilty panels etc) Welfare arrangements (Consider COVID-19 requirements) Temp water & electric connections
LIFTING / PILING OPERATIONS Access to site for large equipment Proximity to occupied areas
ACTIVITIES NEAR TO SITE Location of works in relation to occupied areas and pupil movements Access requirements into occupied areas (alterations / service connections / window replacement etc) Impact on existing secure areas of site (gate controls etc) Will works above occupied areas be required Pedestrian diversions Segregation/screening requirements including glazing Other restrictions (break times etc)
FIRE CONSIDERATIONS Do work affect fire exit routes Fire alarm panel location Fire assembly area School evacuation procedure inc. req for any supporting equipment Site specific restrictions on hot works
EXISTING SERVICES Mains services present on site Other service positions (sub-mains, sub-stations, adjacent buildings, cctv, fire alarms, manholes, drainage runs) Any overhead services (crossing construction site or access route)
PROPOSED SERVICES Will any service diversion be required and if so when can this be completed Will outreach trench excavations beyond construction site by required
ASBESTOS Asbestos Management Survey Refurb & Demo Asbestos Survey Requirement for removal of known asbestos containing materials
EXISTING ROOFS Are works in vicinity of roof lights / fragile surfaces that require protection
TEMPORARY WORKS Are there any elements of temporary works required that will impact on the users of the site
VANDALISIM RISK Does site suffer from unauthorised access / vandalism issues Is there security / CCTV coverage
OTHER CONSIDERATIONS Contractor induction by school - Safeguarding / DBS etc Any other planned construction works separate from this project Any other planned maintenance activities which may impact (e.g. decoration / boiler servicing / electrical testing) Any examination periods during contract period. Relationship with neighbours and consideration of impact of works (dust / noise / scaffolding - privacy) Smoking/Vaping - Policy to be adopted during construction works. Any other items to highlight to Principal Contractor
Disclaimer: The information contained herein has, so far as is reasonably practicable, been gathered from reputable sources however the accuracy and sufficiency of this information is not guaranteed by the Employer or the Employer's representative. Additionally the nature and condition of the site cannot be fully and certainly determined before it is opened up. Before tendering the contractor is to satisfy themselves of the nature of the site, access thereto and all local conditions and restrictions likely to affect the execution of the works. Should any gaps or omissions be identified within the information provided please advise the Employer or Employer’s representative who will seek to clarify any issues.

## 6. Site Assessment - Fire St. (hidden)
CDM REGULATIONS 2015 - PRE-CONSTRUCTION INFORMATION
SITE ASSESSMENT
SITE: | Hazelwood Neighbourhood Centre, Gainsborough Road, Corby NN18 0QF
PROJECT: | Internal Alterations & Kitchen installation
COMPLETED BY: | Paul Wilson
REVIEWED BY: | 0
DATE: | 3rd February 2026
COVID-19 - Given the ongoing and evolving COVID-19 situation it must be noted that stated client occupancy levels and any identified key times may be subject to change. Further updates will be provided as they become available and the Pre-Start Meeting will provide the opportunity to further clarify details with the client prior to works commencing.
In the event that any plant or equipment is tampered with or unintentionally damaged, it MUST be reported immediately via the out of hours procedure and to the Client . Control measures and procedures for such events should be clearly documented within the Principal Contractors / Contractors Construction Phase Health & Safety Plan and that of the Induction provided
INFORMATION | NOTES / COMMENTS
LOCATION Neighbouring accommodation / adjacent users
OCCUPANTS No. of occupants On call station / 24/7 Station / Both Third Party on Site (Red Cross, Police, Ambulance) No. of vehicles and vehicle type Business Support Occupants
GENERAL USE OF PREMISES Primary use of premises
PREMISES CONTACT Main contact on site during works Out of hours access arrangements Out of hours procedure
PROGRAMMING / SEQUENCING Project specific phasing requirements
PROGRAMMING / SEQUENCING Project specific phasing requirements
CONTRACTOR ACCESS Times to be avoided Proposed access route Refer to Contractor access & Handbook
SITE COMPOUND / WELFARE Compound location Parking arrangements Welfare arrangements Temp water & electric connections
LIFTING / PILING OPERATIONS Access to site for large equipment Proximity to occupied areas
ACTIVITIES NEAR TO SITE Location of works in relation to occupied areas Access requirements into occupied areas (alterations / service connections / window replacement etc) Will works above occupied areas be required Pedestrian diversions Segregation/screening requirements including glazing Other restrictions (break times etc)
FIRE CONSIDERATIONS Do work affect fire exit routes Fire alarm panel location Fire assembly area Site specific restrictions on hot works
EXISTING SERVICES Mains services present on site Other service positions (sub-mains, sub-stations, adjacent buildings, cctv, fire alarms, manholes, drainage runs, solar panels, tannoy systems, fire hydrant, fuel & water storage systems (including isolation points, boiler (inc. fuel type) communications mast, emergency lighting) Communication Systems (telephone, broadband, tannoy systems, other communication networks) Any overhead services (crossing construction site or access route)
BREATHING APPARATUS (location of oxygen, access times required) Location of BA Compressor Location of Cylinder Storage
PROPOSED SERVICES Will any service diversion be required and if so when can this be completed Will outreach trench excavations beyond construction site by required
ASBESTOS Asbestos Management Plan Refurb & Demo Asbestos Survey Requirement for removal of known asbestos containing materials
EXISTING ROOFS Are works in vicinity of roof lights / fragile surfaces that require protection
TEMPORARY WORKS Are there any elements of temporary works required that will impact on the users of the site
VANDALISIM RISK Does site suffer from unauthorised access / vandalism issues Is there security / CCTV coverage
OTHER CONSIDERATIONS Any other planned construction works separate from this project Any other planned maintenance activities which may impact (e.g. decoration / boiler servicing / electrical testing) Any examination periods during contract period. Relationship with neighbours and consideration of impact of works (dust / noise / scaffolding - privacy) Smoking/Vaping - Policy to be adopted during construction works. Any other items to highlight to Principal Contractor
Disclaimer: The information contained herein has, so far as is reasonably practicable, been gathered from reputable sources however the accuracy and sufficiency of this information is not guaranteed by the Employer or the Employer's representative. Additionally the nature and condition of the site cannot be fully and certainly determined before it is opened up. Before tendering the contractor is to satisfy themselves of the nature of the site, access thereto and all local conditions and restrictions likely to affect the execution of the works. Should any gaps or omissions be identified within the information provided please advise the Employer or Employer’s representative who will seek to clarify any issues.

## 7. CPP Checklist
CDM REGULATIONS 2015 - CONSTRUCTION PHASE PLAN REVIEW CHECKLIST
SITE: | Hazelwood Neighbourhood Centre, Gainsborough Road, Corby NN18 0QF
PROJECT: | Internal Alterations & Kitchen installation
COMPLETED BY: | Paul Wilson
DATE: | 29th January 2026
Identifies the essential items that the client will expect to see addressed within the Construction Phase Plan (note list may not be exhaustive).
INFORMATION |  | INCLUDED | COMMENTS
01. GENERAL PROJECT INFORMATION General description of the type of work activities involved in project. Statement of project timescales or programme. Details of client / occupier, CDM Advisor, Principal Designers and other consultants, Principal Contractor and sub-contractors.
02. H&S MANAGEMENT / LIAISON ARRANGEMENTS Outline of principal contractors management structures. Details of specific responsibilities of named individuals regarding health and safety. Arrangements for regular liaison between parties. Arrangements for passing information to non-English speaking operatives. Safeguarding / Arrangements for DBS checking. Policy relating to lone working (and controls if applicable).
03. MONITORING Arrangements for monitoring health and safety on site. Site Inspections – Who will undertake them, how frequently, who will findings be reported to.
04. SUB CONTRACTOR SELECTION Arrangement for selection of competent sub-contractors. Method of control and management of sub-contractors.
05. SITE RULES Details of site rules including: - Client requirements - Permit to work systems (particular hot works) - Policy regarding P.P.E. on site - Requirements for enhanced DBS checks (on sites with children present)
06. WELFARE PROVISIONS Description of welfare provisions (toilets and washing facilities, drinking water, rest facilities, facilities to change and store clothes).
07. TRAFFIC PLAN Description (and where necessary plan) of access arrangements / parking / signage and any delivery restrictions.
08. SEGREGATION OF WORKS Description of how works will be segregated from occupants of the buildings / public. Details of any requirements for pedestrian crossing points / fencing / solid hoarding / glazing protection. 30mins fire segregation between construction site & occupied areas. Temporary sheeting/polythene fire performance LPS1207 (Internal) LPS1215 (External)
09. EMERGENCY PROVISIONS Detail of emergency procedures. Availability of fire fighting equipment and first aid provisions. Arrangements for accident reporting RIDDOR 2013. Nearest Hospital.
10. ASBESTOS Detail of what surveys have been undertaken and summary of their findings. Detail of where the information will be available on site. Detail of who will ensure information is passed to operatives. Detail of how any potential asbestos hazard will be managed on site.
11. UNDERGROUND SERVICES Detail of what record information has been sourced and any known services identified. Detail of where the information will be available on site. Detail of who will ensure information is passed to operatives. Detail of how any potential known service runs will be managed on site. Detail of checks for unknown service runs (CAT etc.).
12. PLANT AND EQUIPMENT Arrangements for maintenance, inspection and recording. Detail of training and certification of operatives.
13. TEMPORARY WORKS Requirement for temporary propping highlighted: Temporary supports and propping of the structure, Excavation and trench support or shoring Structural formwork, falsework or propping None standard scaffolding Arrangements for designing, authorising and inspecting by competent qualified person.
14. OTHER SIGNIFICANT SITE RISK - SAFETY Arrangements for controlling any other significant safety risks including: Work at height, lifting operations, deep excavations, storage of hazardous materials.
15. OTHER SIGNIFICANT SITE RISK - HEALTH Arrangements for controlling any other significant health risks including: Manual handling, contaminated land, reducing noise, vibration & dust.
16. COVID 19 Arrangements for managing risks associated with COVID-19. Reference to following latest Government Guidance to enable works to be undertaken in a safe manner. Confirmation of who will be responsible for monitoring arrangements are being adhered to.
17. ADDITIONAL COMMENTS

## 8. H&S File Checklist
CDM REGULATIONS 2015 - HEALTH & SAFETY FILE REVIEW CHECKLIST
SITE:
PROJECT:
COMPLETED BY:
DATE:
Identifies the essential items that the client will expect to see included within the Health & Safety File documentation (note list may not be exhaustive).
REF | ITEM | STANDARD REQUIREMENT | STATUS | COMMENTS
1.0 CONSTRUCTION DETAILS
1.1 | Project Team Details | Client and design team
1.2 | Construction Team Details | Principal contractor and sub contractors
1.3 | Description of Works | Project description including key dates
1.4 | Architectural | As built drawings Design statement
1.5 | Structural | As built drawings Design statement (key structural principals / floor & roof design loads)
1.6 | Residual Hazards Information | Asbestos - Details of any works affecting asbestos materials together with associated certification (waste consignment notes / certificates of reoccupation etc.)
Fire strategy - Design philosophy / compartmentation . Fire stopping / fire alarm zoning / fire fighting equipment
Underground services - Including drawing showing new service positions
Underground drainage - Including drainage strategy and drawing showing drainage layout
Service isolation points - Including drawing showing main isolation points
Ground contamination - Including details of any remiation undertaken
1.7 | Specification summary | Materials & suppliers
1.8 | Manufacturers product literature | User guides / cleaning & maintenance guides
1.9 | Other Details
2.0 MAINTENANCE PROCEDURES
2.1 | Access & Maintenance Strategy | Strategy for finished building to include: Plant / Equipment
2.2 | Equipment List | Itinerary schedule of all equipment requiring regular serviing / maintenance
2.3 | Other Details
3.0 ELECTRICAL / MECHANICAL / SPECIALIST EQUIPMENT
3.1 | Electrical | Test certificates User manuals As installed drawings
3.2 | Mechanical | Test certificates User manuals As installed drawings
3.3 | Specilist Equipment / Guarantees | Lift (user manual / commissioning certificate / EC declaration)
Lighting protection (user manual / commissioning certificate / as installed drawing)
PV array (user manual / MCS certificate / as installed drawing)
Automatic doors / roller shutters (commissioning certificates)
Kitchen equipment (user manuals / commissioning certificates / layout drawing)
Drainage pump (user manual / commissioning certificate)
Roof guarantee
Access equipment e.g. safety line / restraint points (user manual / commissioning certificate)
Hoist / lifting equipment
Other

## Amendments & Issue
CDM REGULATIONS 2015 - PRE-CONSTRUCTION INFORMATION
CDM WORKBOOK TEMPLATE AMENDMENTS & ISSUE
Version | Date | Description of Changes | By | Approved
1
2
3
4
5
6
7
8

## Master Template - H&S File (hidden)
COMPLETE
IN PROGRESS
OUTSTANDING
N/A