## Sheet1
Project Risk & Opportunity Register
(Holistic risk register containing a complete set of risks and opportunities for all project stakeholders)
Name of Project
Isles of Scilly - Belonging and Inclusion hub
| Key Stakeholders |  | (name of organisation) |  |  |  | Date Risk Register last updated
Employer Team | Nicola Stinson |  | Council of the Isles of Scilly |  |  |  | 2026-02-05
| Keith Grossett |  | Council of the Isles of Scilly
| Kanchan Jadeja |  | Council of the Isles of Scilly
| Laura Thompson |  | Council of the Isles of Scilly
Employer Representatives | Andrew Chaplin |  | KTA Architects
| Aidan Irving |  | Clough Management
| Evelyn McBarnet |  | Currie & Brown
| Danielle Hill |  | Collaton Safety
| Steve Rysdale |  | EDP
| Chris Hitchock |  | EDP
| Mark Harris |  | StructureHaus
| Sam Curran |  | KTA Architects
|  |  |  | Consequence of risk/opportunity |  |  | Pre Mitigation Rating |  |  |  |  | Post Mitigation Rating
ID | Status (open / closed) | Risk or opportunity Classifier | Risk or opportunity descriptor | Cost | Time | Qlty | Likelihood (L) | Impact (I) | Total Risk Score (L x I) | Cost | Risk mitigation or opportunity development presently in place | Likelihood (L) | Impact (I) | Total Risk Score (L x I) | Risk Owner
Time
1 | Open | Risk | Weather disruption; prevents designers attending Islands to carry out investigations, design meetings etc. | Y | Y |  | 4 | 4 | 16 |  | Ensure enough time allowed for unforeseen delays due to weather within the design period; | 4 | 2 | 8 | Project Manager
2 | Open | Risk | Weather disruption; prevents client team attending progress meetings | Y | Y | Y | 4 | 2 | 8 |  | Risk is mitigated through the use of Teams. | 4 | 1 | 4 | Project Team
3 | Open | Risk | Weather disruption; delays the delivery of materials onto the Island | Y | Y | Y | 4 | 4 | 16 |  | Ensure enough time allowed for unforeseen delays due to weather within the construction period | 4 | 2 | 8 | Contractor
4 | Open | Risk | Design and tender process takes longer than programmed due to unforeseen complexities | Y | Y |  | 2 | 4 | 8 |  | Ensure there is enough time and float within the design and tender process to deal with unknowns | 1 | 4 | 4 | Project Manager
5 | Open | Risk | Tenderers request longer to return tenders due to complexity of work or lack of sub contract resource etc. | Y | Y |  | 3 | 4 | 12 |  | Discuss with market prior to tender the period provided and get buy in before tender is issued | 2 | 4 | 8 | QS
6 | Open | Risk | Tenderers are returned late | Y | Y |  | 2 | 4 | 8 |  | Set realistic tender return target period. | 1 | 4 | 4 | QS
7 | Open | Risk | Interface with stakeholders/building users | Y | Y |  | 1 | 4 | 4 |  | Provide sufficient notice of works so any potential de-cant problems are known early and can be worked through | 1 | 4 | 4 | Client
8 | Open | Risk | No tenders are returned | Y | Y |  | 3 | 5 | 15 |  | Engagement with local market to ensure tenderers are interested and want to carry out the works | 2 | 4 | 8 | QS
9 | Open | Risk | Construction period identified in tender is unachievable | Y | Y |  | 2 | 4 | 8 |  | As above, engagement with market to ensure time periods are suitable | 1 | 4 | 4 | QS
10 | Open | Risk | Unknowns found during construction; delay works | Y | Y |  | 2 | 4 | 8 |  | If possible, provide float within the construction period to take account of any potential delays. Carry out pre contract surveys | 2 | 3 | 6 | Project Manager
11 | Open | Risk | Lack of interest / capacity by on island / mainland contractors. | Y | Y |  | 3 | 5 | 15 |  | Early communication with both on island and mainland contractors so that they are aware the work is coming up. | 3 | 3 | 9 | Project Team
12 | Open | Risk | Potential for delays and higher costs due to possible need to move the footpath and secure necessary permissions. | Y | Y |  | 3 | 4 | 12 |  | Early engagement with necessary parties (diocese) to understand the processes involved and whether movement of the footpath is necessary. | 3 | 4 | 12 | Project Team
12 | Open | Risk | Delay in meeting planning deadline and approval | Y | Y |  | 2 | 4 | 8 |  | Early engagement through regular DTM with the client and project team. Aiming for the March committee meeting | 2 | 3 | 6 | Project Team
13 | Open | Risk | Service providers delaying the project as unable to get to site due to long lead times. | Y | Y |  | 3 | 4 | 12 |  | Early engagement with service providers such as National Grid to avoid time delay and cost increases. | 3 | 3 | 9 | Project Team
14 | Open | Risk | Acoustician not been able to get to island and provide report before tender | Y | Y |  | 4 | 2 | 8 |  | Acoustician to do early assessments remotely to mitigate the risk of unknowns. Add the report as a tender addendum when visit to island is possible. | 3 | 2 | 6 | Project Team
15 | Open | Risk | Long lead in tme for Velfac windows |  | Y |  | 4 | 4 | 16 |  | Early procurement when tender is awarded | 3 | 3 | 9 | Contractor
16 | Open | Risk | Long lead in times for MVHR and small vent units upto 12wks |  | Y |  | 4 | 4 | 16 |  | Early procurement when tender is awarded | 3 | 3 | 9 | Contractor
17 | Open | Risk | Insufficient on-island resource | Y | Y |  | 3 | 4 | 12 |  | Engagement with the local contractors, | 2 | 3 | 6 | QS
Cost
18 | Open | Risk | Tender returns are higher than allowances made within the budget. | Y | Y |  | 3 | 4 | 12 |  | Provide robust cost updates against the original budget during design; if this shows any potential overspend then look at some value engineering | 2 | 3 | 6 | QS
19 | Open | Risk | Unknowns found during construction which result in increased costs. (M&E) | Y | Y |  | 3 | 4 | 12 |  | Allow for a contingency within the costs. | 3 | 3 | 9 | Design Team
20 | Open | Risk | Construction costs higher than expected, including the potential for more extensive ground works | Y | Y |  | 4 | 4 | 16 |  | Work with team to ensure planning approval is obtained as early as possible. Ground investigation surveys to be undertaken so that the extent is known and mitigation can be costed. | 3 | 4 | 12 | Design team
21 | Open | Risk | Lengthy approvals delay project and inrease costs. | Y |  |  | 3 | 5 | 15 |  | Early discussions to be had with stakeholders to ensure visibility and reduce risk. | 2 | 4 | 8 | Project Team
22 | Open | Risk | Delay in organising drainage, results in survey showing crossover with foundations of new build. | Y | Y |  | 4 | 5 | 20 |  | C&B have tried but unable to pull survey forward. Leave an element of drainage in abeyance and include as a tender addendum. | 3 | 4 | 12 | Project Team
23 | Open | Risk | Risk that connecting to existing services is more complex than initially thought | Y | Y |  | 3 | 4 | 12 |  | Early assessments of connecting to existing services done to reduce risk. | 3 | 3 | 9 | Project Team
24 | Open | Risk | Radon risk | Y | Y |  | 3 | 4 | 12 |  | Ground investigation surveys to be done to determine levels of risk of radon. | 3 | 3 | 9 | Project Team
25 | Open | Risk | Drainage systems at full capacity risking surface water run off and requirements for attenuation tank | Y | Y |  | 3 | 3 | 9 |  | Likleyhood is felt to be low. Architect to ensure infiltration systems are clear on designs. | 2 | 3 | 6 | Design Team
26 | Open | Risk | Risk that the structural integrity of the curent building is not as previously thought | Y | Y |  | 1 | 4 | 4 |  | A low risk - to monitor | 1 | 4 | 4 | Project Team
27 | Open | Risk | Movement of the reception desk and services proves to be costly. | Y |  |  | 3 | 3 | 9 |  | M&E to establish current services that requie movement to estabish whether reception desk movement is required | 3 | 2 | 6 | Design Team
28 | Open | Risk | Increased cost due to Velfac windows unable to be sent to island by manufacturers. | Y |  |  | 4 | 3 | 12 |  | Architects to look at alternatives which may provide cost saving. | 3 | 3 | 9 | Design Team
29 | Open | Risk | Scope creep increase costs | Y | Y |  | 2 | 4 | 8 |  | Strong change management procedure to be implemented. | 1 | 3 | 3 | Project Manager
Quality
30 | Open | Risk | Not enough time to conduct approporiate investigatory works | Y | Y | Y | 3 | 3 | 9 |  | Aim to allow for sufficient time to carry out necessary surveys. C&B additional resource to assist | 2 | 3 | 6 | Client
Governance/Operational/business
31 | Open | Risk | Limited stakeholder engagement early on in the project |  |  | Y | 2 | 5 | 10 |  | Continued and early consultation- to be undertaken during planning period. | 1 | 5 | 5 | Client
32 | Open | Risk | Changes or lack of the correct personnel to deliver the project as planned. Loss of continuity leading to delays in meeting Delivery Application deadline | Y | Y | Y | 2 | 5 | 10 |  | Strong governance in place mitigating any impact if any staff leave. | 1 | 3 | 3 | Client
33 | Open | Risk | Late changes to client brief. Changes lead to abortive work and delays to the project whilst re-design is undertaken; cost forecasts are at risk of being too low if changes increase costs. Potential impact on programme. | Y | Y | Y | 2 | 5 | 10 |  | All changes to the brief or scheme to be reviewed with the project team first to understand potential implications. Project governance requirements are to be factored in to the programme to ensure decisions for change can be captured. Strong project plan in place. | 1 | 5 | 5 | Client
34 | Open | Risk | Project work taking place during peak holiday season and term time, causing disruption to project. |  | Y |  | 3 | 5 | 15 |  | Strategic programme shared with the project team for awareness of target dates for construction. Clear signage and communication to be upheld during project to minimise disruptions. | 2 | 3 | 6 | Project Team
|  |  | Impact Descriptions | Sc. |  |  | Risks to be Ranked on Total Risk Score |  |  |  |  | Risks to be Ranked on Total Risk Score
|  |  | Slight | 1 |  |  | grouped as high/med/low (see below) |  |  |  |  | grouped as high/med/low (see below)
|  |  | Minor | 2 | [6 empty] | Risk/Opportunity Identification
|  |  | Moderate | 3 |  |  | High Scores - 12.00 to 25.00 |  |  |  | ↓ | High Scores - 12.00 to 25.00
|  |  | Severe | 4 |  |  | Medium Scores - 6.01 to 11.99 |  |  |  | Risk/Opportunity Assessment | Medium Scores - 6.01 to 11.99
|  |  | Very Severe | 5 |  |  | Low Scores - 1.00 to 6.00 |  |  |  | ↓ | Low Scores - 1.00 to 6.00
Risk/Opportunity Response
|  |  | Likelihood Descriptions | Sc. | Wgt | [5 empty] | ↓
|  |  | Very Unlikely | 1 | 10% | [5 empty] | Risk/Opportunity Action Plan
|  |  | Unlikely | 2 | 20% | [5 empty] | ↓
|  |  | Possible | 3 | 40% | [5 empty] | On-going Management
|  |  | Likely | 4 | 60% | [5 empty] | (Implement Actions/Review Risks/Opportunity)
|  |  | Very Likely | 5 | 80%