## SUMMARY
PRENTON RUFC COMMUNITY HUB
SCHEDULE OF WORKS: SUMMARY
ITEM | DESCRIPTION | QUANTITY | UNIT | RATE | TOTAL (£)
| GENERAL |  |  |  | 0
| PRELIMS |  |  |  | 0
| DEMOLITION & ALTERATIONS |  |  |  | 0
| CHANGING ROOM SUPERSTRUCTURE |  |  |  | 0
| CORRIDOR SUPERSTRUCTURE |  |  |  | 0
| COMMUNITY HUB SUPERSTRUCTURE |  |  |  | 0
| CHANGING ROOM FINISHES |  |  |  | 0
| CORRIDOR FINISHES |  |  |  | 0
| COMMUNITY HUB FINISHES |  |  |  | 0
| MECHANICAL, ELECTRICAL & SANITARYWARE | 1 | PS |  | 100000
| BUILDERSWORK & FIRE STOPPING | 1 | PS |  | 15000
| SUMMARY |  |  |  | 115000

## General
PRENTON RUFC COMMUNITY HUB
SCHEDULE OF WORKS: GENERAL
ITEM | DESCRIPTION | QUANTITY | UNIT | RATE | TOTAL (£)
REFERENCE DOCUMENTATION
ALL TO BE READ IN ACCORDANCE WITH THE FOLLOWING DRAWINGS AND INFORMATION:
DRAWINGS
Architectural
2025 007 300 000 02 Proposed Site & Roof Plan
2026 007 300 001 02 Existing Floor Plan, Roof Plan, Site Plan & Elevations
2025 007 300 001 02 Proposed Ground Floor Plan
2025 007 300 002 02 Proposed Elevations
2025 007 300 003 02 Proposed Part Ground Floor Plan 1
2025 007 300 004 02 Proposed Part Ground Floor Plan 2
2026 007 300 005 02 Proposed Part Ground Floor Plan 3
2026 007 300 007 02 Key Section AA
2027 007 300 008 02 Key Section BB & CC
2028 007 300 009 02 Proposed Fire Strategy
2029 007 300 010 02 Door & Window Schedule
2030 007 300 011 02 Building Regulations Specification
2031 007 300 012 02 Proposed Ceiling Layouts
Drainage
25039-AJF-ZZ-ZZ-DR-D-001B-R7 PROPOSED FW & SW DRAINAGE PLAN
21663-AJF-ZZ-ZZ-CA-DR-002-R8-Drainage Calculations
21663-AJF-ZZ-ZZ-DR-D-003 R1 - Drainage Standard Details - Sheet 1
21663-AJF-ZZ-ZZ-DR-D-004 R1 - Drainage Standard Details - Sheet 2
21663-AJF-ZZ-ZZ-DR-D-005 R1 - Drainage Standard Details - Sheet 3
21663-AJF-ZZ-ZZ-DR-D-006 R1 - Drainage Standard Details - Sheet 4
21663-AJF-ZZ-ZZ-DR-D-007 R1 - Drainage Standard Details - Sheet 5
21663-AJF-ZZ-ZZ-DR-D-008 R1 - Drainage Standard Details - Sheet 6
25039-AJF-ZZ-ZZ-DR-D-009-R1 MANHOLE SCHEDULES
25039-AJF-ZZ-ZZ-DR-D-010-R1 MANHOLE SCHEDULES
Updated Drainage Drawings
25039-AJF-ZZ-ZZ-DR-D-001-R8 PROPOSED FW & SW DRAINAGE PLAN
25039-AJF-ZZ-ZZ-DR-D-001A-R8 PROPOSED FW & SW DRAINAGE PLAN
25039-AJF-ZZ-ZZ-DR-D-001B-R8 PROPOSED FW & SW DRAINAGE PLAN
Structural
ZZ-ZZ-DR-S-001 T04 Structural Details A1
| General Page 1 |  |  |  | 0
PROJECT DETAILS
CLIENT
Prenton RFU
PRINCIPAL DESIGNER / DESIGNER
DPC Consultants Ltd
PRINCIPAL CONTRACTOR / CONTRACTOR
TBD
CONTRACT DETAILS
CLIENT PROJECT MANAGER
Gareth Knapman
CLIENT CONTRACT ADMINISTRATOR
Tony Campbell
CONTRACT FORM
JCT Minor Works
LIQUIDATED DAMAGES
N/A
DEFECTS LIABILITY PERIOD
12 MONTHS
RETENTION
N/A
PROGRAMME
Start Onsite End May / Beginning of June 2025
SITE INFORMATION
ADDRESS
Prenton RUFC
Prenton Dell Road
Birkenhead
CH43 3BS
ACCESS RESTRICTIONS
The site is located down a shared access track with multiple pinch points. The site is located in a residential area off a B road
SITE WORKING HOURS
8am to 5pm Monday to Friday
| General Page 2 |  |  |  | 0
PLANNING CONSTRAINTS
To be confirmed upon receipt of planning approval
WELFARE
Welfare to be established externally.
Principal Contractor to provide toilet facilities, mess facilities for all onsite contractors and workers , running hot & cold water, access to drinking water and a location for storage and laydown
PPE
Minimum requirement is steel toe capped work shoes with ankle protection (rigger boots or similar are not allowed). Light eye protection, tear resistant gloves and hardhats to be worn if the task dictates. High visibility clothing required during any external working
WASTE DISPOSAL
Principal contractor to provide segregated waste disposal skips within the laydown area
HEALTH & SAFETY HAZARDS
Principal Designer and Principal Contractor to carry out a construction risk analysis prior to works commencing onsite
| General Page 3 |  |  |  | 0

## Prelims
PRENTON RUFC COMMUNITY HUB
SCHEDULE OF WORKS: PRELIMS
ITEM | DESCRIPTION | QUANTITY | UNIT | RATE | TOTAL (£)
The Contractor shall allow for all items necessary to deliver the works
Project & Site Management
1 | Project Management
2 | Site Management
3 | Quantity Surveyor
4 | Quality assurance
Progress Management
5 | Monthly site meetings
6 | Weekly progress photographs
7 | The contractor shall ensure that any works carried out are open for inspection prior to covering up
8 | Enter other items as necessary
Welfare
9 | Site Cabin / Mess Facility
10 | Toilets / Washing Facilities
11 | Drying / Locker Room
12 | Enter other items as necessary
Waste Disposal
13 | Skips
14 | Enter other items as necessary
Access Equipment
15 | Scaffolding
16 | Hop ups / Pop Ups / Scissor Lifts
17 | Cherry pickers / MEWPs
18 | Enter other items as necessary
Small Tools & Equipment
19 | Small tools
20 | Tackle & Equipment
21 | Enter other items as necessary
| Prelims Total |  |  |  | 0

## Demolition & Alterations
PRENTON RUFC COMMUNITY HUB
SCHEDULE OF WORKS: DEMOLITION & ALTERATIONS
ITEM | DESCRIPTION | QUANTITY | UNIT | RATE | TOTAL (£)
The Contractor shall allow for all items necessary to deliver the works
CHANGING ROOMS
1 | Strip back the existing roof over the existing gym and dispose offsite | 1 | Item |  | 0
2 | Demolish gable wall to gym for changing room extension | 1 | Item |  | 0
COMMUNITY HUB
3 | Form new opening in existing structure for lounge extension (B1) | 1 | Item |  | 0
4 | Form new openings in existing structure for D01 (B2) | 1 | Item |  | 0
5 | Strip back existing walls back to brick where required | 1 | Item |  | 0
6 | Strip out existing flooring ready for construction | 1 | Item |  | 0
7 | Demolish internals walls no longer required for the new layout | 1 | Item |  | 0
8 | Strip out bar and ceilings in preparation for the works | 1 | Item |  | 0
9 | Strip out kitchen and any other FF&E for the works | 1 | Item |  | 0
| DEMOLITION & ALTERATIONS PAGE 1 |  |  |  | 0

## Changing Room Superstructure
PRENTON RUFC COMMUNITY HUB
SCHEDULE OF WORKS: CHANGING ROOM SUPERSTRUCTURE
ITEM | DESCRIPTION | QUANTITY | UNIT | RATE | TOTAL (£)
The Contractor shall allow for all items necessary to deliver the works
Site Set Up & Enabling Works
1 | Heras fencing to segregate the construction site | 1 | Item |  | 0
2 | Check the setting out of the foundations | 1 | Item |  | 0
External Walls
3 | Construct new external walls; 100mm block internal skin, 150mm cavity with full fill dritherm 32 insulation and outer skin of facing brickwork. For tender purposes allow 75p per brick; masonry to be tied into existing using suitable wall starter system | 192 | m2 |  | 0
4 | Construct new external walls; 140mm block to separate changing room from existing gym; masonry to be tied into existing using suitable wall starter system | 32 | m2 |  | 0
5 | Supply & install lintel L2 | 4 | Nr |  | 0
Internal Walls
6 | Supply & install 100mm blockwork internal walls | 346 | m2 |  | 0
7 | Supply & install lintel L1 | 16 | Nr |  | 0
8 | Supply & install lintel L3 to suit existing wall thickness; for tender purposes assume 2Nr lintels required | 2 | Nr |  | 0
9 | Infill existing internal wall openings with new masonry walls to suit; masonry to be tied into existing using suitable wall starter system | 4 | Nr |  | 0
Roof
10 | Supply & install new structural timberwork to changing rooms and gym extension as shown on the structural drawings | 1 | Item |  | 0
11 | Supply & install new roof to achieve 0.15w/m2K; adhered single ply roofing membrane, kingspan 150mm thermaroof TR27 insulation on 18mm OSB roof deck on timber firrings to achieve min 1:40 fall | 375 | m2 |  | 0
12 | Build up plinth brickwork to suit new roof level | 1 | Item |  | 0
External Windows & Doors
13 | Supply & install new steel external door inc frame & all associated ironmongery (D15) | 2 | Nr |  | 0
14 | Supply & install new Window W-01 | 1 | Nr |  | 0
| CHANGING ROOM SUPERSTRUCTURE PAGE 1 |  |  |  | 0

## Corridor Superstructure
PRENTON RUFC COMMUNITY HUB
SCHEDULE OF WORKS: CORRIDOR SUPERSTRUCTURE
ITEM | DESCRIPTION | QUANTITY | UNIT | RATE | TOTAL (£)
Site Set Up & Enabling Works
1 | Heras fencing to segregate the construction site | 1 | Item |  | 0
2 | Check the setting out of the foundations | 1 | Item |  | 0
External Walls
3 | Supply & install new SIPS wall panels from SIPCO; contractor to update quotation SIPCO-1778 | 1 | Item |  | 0
4 | Supply & install Eurobrick 25mm x-clad system with external brick slip cladding | 79 | m2 |  | 0 | 48.62
| Internal Walls |  |  |  |  | 39.79
5 | Supply & install new SIPS wall panels from SIPCO; contractor to update quotation SIPCO-1778 | 1 | Item |  | 0
7.48
6 | Supply & install 100mm blockwork internal walls | 8 | m2 |  | 0
7 | Supply & install lintel L1 | 4 | Nr |  | 0
8 | Infill existing internal wall openings with new masonry walls to suit; masonry to be tied into existing using suitable wall starter system | 1 | Nr |  | 0
Roof
9 | Supply & install new structural timberwork to corridor and entrance porch as shown on the structural drawings | 1 | Item |  | 0
10 | Supply & install new roof to achieve 0.15w/m2K; adhered single ply roofing membrane on 18mm OSB roof deck on timber firrings to achieve min 1:40 fall; 150mm Celotex XR4150 in between joists and Celotex GA4040 under joists | 65 | m2 |  | 0
External Windows & Doors
11 | Supply & install new external door inc frame & all associated ironmongery (D02) | 1 | Nr |  | 0
12 | Supply & install new external door inc frame & all associated ironmongery (D03) | 1 | Nr |  | 0
13 | Supply & install new Windows W-04 | 2 | Nr |  | 0
| CORRIDOR SUPERSTRUCTURE PAGE 1 |  |  |  | 0

## Community Hub Superstructure
PRENTON RUFC COMMUNITY HUB
SCHEDULE OF WORKS: COMMUNITY HUB SUPERSTRUCTURE
ITEM | DESCRIPTION | QUANTITY | UNIT | RATE | TOTAL (£)
The Contractor shall allow for all items necessary to deliver the works
Site Set Up & Enabling Works
1 | Heras fencing to segregate the construction site | 1 | Item |  | 0
2 | Check the setting out of the foundations | 1 | Item |  | 0
External Walls
3 | Construct new external walls; 100mm block internal skin, 150mm cavity with full fill dritherm 32 insulation and outer skin of facing brickwork. For tender purposes allow 75p per brick; masonry to be tied into existing using suitable wall starter system | 44 | m2 |  | 0
4 | Supply & install lintel L2 | 1 | Nr |  | 0
Structural Steelwork
5 | Supply & install 2Nr Beam 1 inc padstones | 1 | Item |  | 0
6 | Supply & install Beam 2 inc padstones | 1 | Item |  | 0
Internal Walls
7 | Supply & install 100mm blockwork internal walls | 10 | m2 |  | 0
8 | Supply & install lintel L1 | 1 | Nr |  | 0
9 | Infill existing internal wall openings with new masonry walls to suit; masonry to be tied into existing using suitable wall starter system | 2 | Nr |  | 0
Roof
10 | Supply & install new structural timberwork to lounge & kitchen as shown on the structural drawings | 1 | Item |  | 0
11 | Supply & install new roof to achieve 0.15w/m2K; adhered single ply roofing membrane, kingspan 150mm thermaroof TR27 insulation on 18mm OSB roof deck on timber firrings to achieve min 1:40 fall | 48 | m2 |  | 0
12 | Build up plinth brickwork to suit new roof level | 1 | Item |  | 0
External Windows & Doors
13 | Supply & install new bi-folding door D01 | 1 | Nr |  | 0
14 | Supply & install new Window W01 | 3 | Nr |  | 0
15 | Supply & install new external door D13 | 1 | Nr |  | 0
| COMMUNITY HUB SUPERSTRUCTURE PAGE 1 |  |  |  | 0

## Changing Room Finishes
PRENTON RUFC COMMUNITY HUB
SCHEDULE OF WORKS: CHANGING ROOM FINISHES
ITEM | DESCRIPTION | QUANTITY | UNIT | RATE | TOTAL (£)
The Contractor shall allow for all items necessary to deliver the works
Internal Walls & Ceilings
1 | Supply & install new Armstrong PRELUDE 24 suspended ceiling system with Armstrong Hydroboard 600x600mm ceiling tiles | 40 | m2 |  | 0
2 | Supply & install aquaboard wall panelling to shower room walls; silicone to joints; white tile trim to edges | 135 | m2 |  | 0
3 | Paint blockwork walls white | 950 | m2 |  | 0
Joinery
4 | Supply & install internal door D17 including frame, architrave & ironmongery | 2 | Nr |  | 0
5 | Supply & install internal door D18 including frame, architrave & ironmongery | 5 | Nr |  | 0
6 | Supply & install internal door D19 including frame, architrave & ironmongery | 2 | Nr |  | 0
7 | Supply & install internal door D20 including frame, architrave & ironmongery | 5 | Nr |  | 0
8 | Decoration of architraves; oil based eggshell | 140 | m |  | 0
9 | Supply & install new mdf window board | 1 | Nr |  | 0
10 | Decoration of window board; oil based eggshell | 1 | Nr |  | 0
Floor Finishes
11 | Supply & install new polysafe altro flooring; skirtings capped and coved; colour to be determined | 231 | m2 |  | 0
12 | Supply & install new polysafe hydro flooring; skirtings capped and coved; colour to be determined | 40 | m2 |  | 0
External Works
13 | Supply & install fascia & soffit in black u-pvc | 60 | m |  | 0
14 | Supply & install new rainwater goods in black u-pvc | 1 | Item |  | 0
| CHANGING ROOM FINISHES PAGE 1 |  |  |  | 0

## Corridor Finishes
PRENTON RUFC COMMUNITY HUB
SCHEDULE OF WORKS: CORRIDOR FINISHES
ITEM | DESCRIPTION | QUANTITY | UNIT | RATE | TOTAL (£)
The Contractor shall allow for all items necessary to deliver the works
Internal Walls & Ceilings
1 | Supply & install new British Gypsum CasoLine MF Suspended Ceiling System with moisture resistant plasterboard | 57 | m2 |  | 0
2 | Board out SIPS panels with 12.5mm plasterboard | 91 | m2 |  | 0
3 | Dot & dab new internal blockwork walls with 12.5mm plasterboard | 16 | m2 |  | 0
4 | Tape & joint plasterboard with skrim, apply 3mm skim to all new plasterboard | 164 | m2 |  | 0
5 | Decoration of all newly plastered surfaces; mist coat of emulsion diluted 50/50 with water and minimum of 2Nr finishing coats; scrubbable matt emulsion; colour to be determined | 164 | m2 |  | 0
6 | Allowance for M&E access hatches where required | 1 | Item |  | 0
Joinery
7 | Supply & install internal door D06 including frame, architrave & ironmongery | 3 | Nr |  | 0
8 | Decoration of architraves; oil based eggshell | 30 | m |  | 0
9 | Supply & install new mdf window board | 2 | Nr |  | 0
10 | Decoration of window board; oil based eggshell | 2 | Nr |  | 0
Floor Finishes
11 | Supply & install new polyflor commercial; promenade oak; ref 9038, substrate self levelled and DPM layer if required due to screed drying times | 57 | m2 |  | 0
External Works
12 | Supply & install fascia & soffit in black u-pvc | 40 | m |  | 0
13 | Supply & install new rainwater goods in black u-pvc | 1 | Item |  | 0
14 | Supply & install new concrete access ramp and handrail | 1 | Item |  | 0
15 | Supply & install new illuminated signage | 1 | Item |  | 0
| CORRIDOR FINISHES PAGE 1 |  |  |  | 0

## Community Hub Finishes
PRENTON RUFC COMMUNITY HUB
SCHEDULE OF WORKS: COMMUNITY HUB FINISHES
ITEM | DESCRIPTION | QUANTITY | UNIT | RATE | TOTAL (£)
The Contractor shall allow for all items necessary to deliver the works
Internal Walls & Ceilings
1 | Supply & install new Armstrong PRELUDE 24 suspended ceiling system with 600x600 Armstrong Ceramaguardceiling tiles | 245 | m2 |  | 0
2 | Supply & install new British Gypsum CasoLine MF Suspended Ceiling System with moisture resistant plasterboard | 45 | m2 |  | 0
3 | Dot & dab new internal blockwork walls with 12.5mm plasterboard | 80 | m2 |  | 0
4 | Dot & dab walls stripped back to brick | 74 | m2 |  | 0
5 | Line internal face of external wall; CLS timber studwork set off the existing wall with visqueen lining, 100mm Celotex GA4100 PIR insulation fitted inbetween timber joists, vapour barrier stapled to the timbers; 12.5mm plasterboard over | 55 | m2 |  | 0
6 | Allowance to overskim any other internal walls impacted by the works | 170 | m2 |  | 0
7 | Tape & joint plasterboard with skrim, apply 3mm skim to all new plasterboard | 209 | m2 |  | 0
8 | Decoration of all newly plastered surfaces; mist coat of emulsion diluted 50/50 with water and minimum of 2Nr finishing coats; scrubbable matt emulsion; colour to be determined | 379 | m2 |  | 0
9 | Allowance for M&E access hatches in solid ceiling where required | 1 | Item |  | 0
Joinery
10 | Supply & install internal door D04 including frame, architrave & ironmongery | 1 | Nr |  | 0
11 | Supply & install internal door D07 including frame, architrave & ironmongery | 3 | Nr |  | 0
12 | Supply & install internal door D08 including frame, architrave & ironmongery | 1 | Nr |  | 0
13 | Supply & install internal door D09 including frame, architrave & ironmongery | 1 | Nr |  | 0
14 | Supply & install internal door D10 including frame, architrave & ironmongery | 1 | Nr |  | 0
15 | Supply & install internal door D11 including frame, architrave & ironmongery | 1 | Nr |  | 0
16 | Supply & install internal door D12 including frame, architrave & ironmongery | 1 | Nr |  | 0
| COMMUNITY HUB FINISHES PAGE 1 |  |  |  | 0
Joinery (cont'd)
17 | Supply & install internal door D14 including frame, architrave & ironmongery | 1 | Nr |  | 0
18 | Supply & install internal door D16 including frame, architrave & ironmongery | 1 | Nr |  | 0
19 | Decoration of architraves; oil based eggshell | 114 | m |  | 0
20 | Supply & install new mdf window board | 4 | Nr |  | 0
21 | Decoration of window board; oil based eggshell | 4 | Nr |  | 0
22 | Supply & install new mdf skirting boards | 100 | m |  | 0
23 | Decoration of mdf skirting board; oil based eggshell | 100 | Nr |  | 0
Floor Finishes
24 | Supply & install new polyflor commercial; promenade oak; ref 9038, substrate self levelled and DPM layer if required due to screed drying times | 189 | m2 |  | 0
25 | Supply & install new polysafe altro flooring; skirtings capped and coved; colour to be determined | 56 | m2 |  | 0
External Works
26 | Supply & install fascia & soffit in black u-pvc | 20 | m |  | 0
27 | Supply & install new rainwater goods in black u-pvc | 1 | Item |  | 0
28 | Supply & install new illuminated signage | 1 | Item |  | 0
| COMMUNITY HUB FINISHES PAGE 2 |  |  |  | 0

## Schedule of Rates
PRENTON RUFC COMMUNITY HUB
SCHEDULE OF WORKS: SCHEDULE OF RATES
ITEM | DESCRIPTION | QUANTITY | UNIT | RATE | TOTAL (£)
The Contractor shall list below rates as detailed
Labour
1 | Labourer
2 | Tradesman
3 | Craftsman
4 | Supervisor
Management
5 | Project Manager
6 | Site Manager
7 | Quantity Surveyor
8 | Designer
Equipment
9 | Small tools
10 | Tackle & Equipment
Welfare
11 | Site Cabin / Mess Facility
12 | Toilets / Washing Facilities
13 | Drying / Locker Room
14 | Enter other items as necessary
Access Equipment
15 | Scaffolding
16 | Hop ups / Pop Ups / Scissor Lifts
17 | Cherry pickers / MEWPs
18 | Enter other items as necessary
Mark Up
19 | Materials
20 | Equipment
21 | Subcontractors
22 | Enter other items as necessary
| Schedule of Rates Total |  |  |  | 0