## Sheet1
Attendances Schedule Stage Right Package | Revision 1
CCaM
Item | Main contractor | Stage contractor | Client-CIoS | Notes
Site Inductions & Health/Safety Briefings | Y
Provision of RAMS |  | Y
Vetting/commenting on RAMS | Y
Explanation of RAMS to workforce |  | Y
Safe Access to site Areas | Y
Birdcage access to 2nd fix high level auditorium, only whilst main contractor scaffold is in position | Y | Y |  | Details for agreement
All other access, scaffolding, MEWPs required |  | Y
Space for storage | Y- 2nr pallet spaces + lockable tool box only |  | Y | For discussion-CIoS to provide off site storage area for SR contractor containers. SR to minimise components stored on site
Power Supply transformers- temporary power 110v on site | Y
Safety lighting | Y
Task Lighting and all power leads etc. |  | Y
Power for testing and commissioning | Y |  |  | Details/dates to be agreed, to ensure power is available
Welfare Facilities during main contract construction period | Y
Welfare facilities following main contract handover |  |  | Y
Waste disposal during main contract construction period | Y | Y |  | Stage contractor to cart waste to skip provided outside by Main Contractor
Waste disposal following main contract construction period |  |  | Y
All lifting, hoisting etc. |  | Y
Provision of accommodation for workforce or visitors | Y |  | Y | This will be provided by the main contractor, unless pod accommodation is full, in which case the client will provide this.
Transport of plant and materials to Penzance Docks |  | Y
Shipping of plant and materials to St Mary's |  | TBC | TBC | Provisional sum at this stage for discussion
Transport of plant and materials from St Mary's docks to site/off-site storage area |  | TBC | TBC | Provisional sum at this stage for discussion
Transport of plant and materials from off-site storage area to site |  | TBC | TBC
Movement of all plant and materials around site |  | Y