# Annex C: Service Levels, Service Credits and KPIs

Lot 1 – Business Design and Data and Business Change

| Service Level Performance Criterion | Service Level Performance Measure (target) | Service Level threshold | Measurement | Service Credit for each Service period (Service Credit % calculated applied to be based on worst SLA failure) |
| --- | --- | --- | --- | --- |
| - Business Design and Data – Completion of the following outputs against the delivery plan: - End to end business maps (L1-L4) - Data materials such as Data Protection Impact Assessments - Identification and update of operational risks including operational impact assessments | 95% | At least 90% at all times | Per above | Service Credit % = Service level threshold – Actual monthly service level. Worked example – monthly actual of 80%: 92% - 80% = 12% of the calculated Contract Charges for that month to deducted from the next invoice payable by the Customer. |
| - Change Management - Delivery of upskilling and SMR sessions vs agreed delivery plan timelines | 95% | At least 90% at all times |  | As above |
| - Change Management – Development and implementation of a comprehensive change management strategy across deployment drops in line with agreed delivery plan timelines | 95% | At least 90% at all times |  | As above |
| - Develop and manage change governance forums in line with agreed delivery plan timelines covering: - Management reporting - Risk and issue management - Facilitating approvals of key change documentation and activities | 95% | At least 90% at all times | Per above | As above |
| - Communication and Engagement – Development and roll out of communications and engagement plan covering: - supporting comms materials and events - tailored to user groups, ahead of each individual ‘drop’ Go-Live. | 95% | At least 90% at all times | Per above | As above |
| - Business Transition – Develop and deliver deployment approaches for each drop and manage business implementation of each of the drop solutions in line with the agreed plan | 95% | At least 90% at all times | Per above | As above |

Service Credit worked example:

For a given calendar month, the pre-Service Credit calculated Contract Charges were £20,000. The Provider reported the following results against the SLAs:

- Completion of outputs against delivery plan – 90%

- Upskilling and SMR sessions – 100%

- Change management strategy – 98%

- Change governance forums – 85%

- Comms and engagement plan – 98%

- Deployment approaches – 95%

The worst performing SLA related to the delivery of the requirements within Lot 1 – Business Design & Data, and Business Change Services, at 85%. This results in a Service Credit % of (92-85) = 7%, which will result in a credit being applied to the next monthly Contract Charge of (£20,000*7%) = £1,400.

Lot 2 – Training Services

| Service Level Performance Criterion | Service Level Performance Measure (target) | Service Level threshold | Measurement | Service Credit for each Service period (Service Credit % calculated applied to be based on worst SLA failure) |
| --- | --- | --- | --- | --- |
| - Training feedback score: Candidate feedback score collected and recorded by the Supplier up to one week after the conclusion of Command and Control Training, with feedback score on a whole number scale from 1-5 per the below assessment methodology; Score of 1 – Poor Score of 2 – Requires improvement Score of 3 – Satisfactory Score of 4 – Good Score of 5 - Excellent | 5.00 | 4.00 | Supplier monthly SLA report. The MPS shall retain the right to audit and or conduct spot checks. | - |
| - Training feedback score – resulting from Train the Trainer cohorts: Candidate feedback score collected and recorded by the Supplier up to one week after the conclusion of Command and Control Training, with feedback score on a whole number scale from 1-5 per the below assessment methodology; Score of 1 – Poor Score of 2 – Requires improvement Score of 3 – Satisfactory Score of 4 – Good Score of 5 - Excellent | 5.00 | 4.00 | Supplier monthly SLA report. The MPS shall retain the right to audit and or conduct spot checks. |  |
| - Attendance rates The number of candidates invited to training vs attendance | 95% | At least 90% at all times | Per above | Service Credit % = Service level threshold – Actual monthly service level. Worked example – monthly actual of 80%: 92% - 80% = 12% of the calculated Contract Charges for that month to deducted from the next invoice payable by the Customer. |
| - Skills improvement rate – measured through pre and post training assessments or line management assessment of skill development | 95% | At least 90% at all times | Per above | As above |
| - Number of candidates to receive training vs training delivery plan | 95% | At least 90% at all times | Per above | As above |
| - Learning assessment pass rates | 95% | At least 90% at all times | Per above | As above |

Service Credit worked example:

For a given calendar month, the pre-Service Credit calculated Contract Charges were £20,000. The Provider reported the following results against the SLAs:

- Training feedback score – 4.75

- Training feedback score – 4.50

- Attendance rates – 90%

- Skills improvement rate – 100%

- Training received vs training plan – 98%

- Learning assessment pass rates – 85%

The worst performing SLA related to the delivery of the requirements within Lot 2 – Training services, at 85%. This results in a Service Credit % of (92-85) = 7%, which will result in a credit being applied to the next monthly Contract Charge of (£20,000*7%) = £1,400.