## GENERAL
Raynes Park High School & Rutlish School
6th Form Block Externals Package
Contractor Pricing Document
Note: Contractor to note that the Schedule of Works, drawings and appendices take precedence over the descriptions provided in this document and as such these should be priced. This document has been provided in editable format to make it easier for the contractor to insert their costs.
Ref Nr | Item/Description | Item/PC | Cost (£)
Section 1 | Preliminaries
Section 2 | Schedule of Works |  | (price within breakdown below)
1 | GENERAL
A | External remedials package of work to the 6th Form Blocks at Raynes Park High School and Rutlish School, to be undertaken between late August to late October 2025, in the London Borough of Merton. Contractor MUST erect high level access, provide site setup and brise soleil opening up investigations prior to the 2nd September 2025 when school returns. Works to the windows and brise soleil will be undertaken both out of hours and over October half term in order to ensure no disruption to the school. Raynes Park High School, Bushey Road, London, SW20 0JL Rutlish School, Watery Lane, London, SW20 9AD Nature: Works largely involve remedial works to remedy defects to the 2 identical two storey modular blocks constructed some 12 years ago at each school site. These include but are not limited to; - Replacement of cappings to ridge line and roof edge - Overlay of the metal insulated roof panels with new high performance liquid system - Overhaul of existing outlets and rainwater goods - Replacement of coxdome rooflights inc kerb details to surround - Renewing detailing around windows including sealants - Investigations to brise soleil’s and works to ensure secured back to frame correctly -Erection of high level access to safely access working areas.. Close liaison with the end user throughout will be required. Scaffolding cannot be erected, adapted or struck during normal working hours when the school is in use/incase works over run into September. ALL operatives must hold a valid Enhanced DBS Certificate to be provided to the CA/End-User in good time prior to works commencing. These should be provided for management inc site supervision at issue of tender returns.
Contractor will be required to design and erect/dismantle suitable high level access as detailed within the document.
The works involve a variety of roofing and external fabric repairs in order to address identified defects which are causing internal water ingress issues, in addition to preventing further disrepair and full replacement of the fabric. As works will be carried out whilst school holiday clubs are on-site the Contractor will need to take particular care and attention when planning works to ensure that risks are mitigated. All operatives must hold valid DBS enhanced certificates. Proof of which should be provided upfront in good time prior to works commencing. Should scaffold remain come the start of term the Contractor will need to allow for striking outside of term time hours, i.e. 8.30am-3.3pm Monday to Friday. Contractor should allow this within their pricing return.
The Contractor will be required to develop a suitable Construction Phase Plan and RAMS to mitigate risk and make sure that the prescribed works are executed in a safe and professional manner. These documents are to be submitted for review to the Principal Designer before works commence on site.
The Contractor will need to provide their own welfare facilities in a location to be agreed by the Principal Designer and which is practical so that works can be effectively executed. The Main Contractor will be provided with a section of the car park nad/or playground as shown within the Logistics Plan. Contractor to develop and provide as part of their tender submission for review.
Note: Any area made available to the Contractor for site set up and storage, including external areas, must be cleaned and returned to the Client in the same condition in which it was found prior to works commencing on site. On completion of all works and prior to the Practical Completion Certificate being issued, the Contractor will be responsible for removing all waste resulting from the works and thoroughly cleaning down all working/site setup areas to ensure tidy and left in condition as prior to works commencing.
Services
B | The Contractor will be provided access to the sites water and electrical supply. Meter readings will be taken on the day of works commencing and on completion of works. Although energy will be FoC to the Contractor they will be responsible for utilising efficiently. | Item
Protection
C | All site personnel to wear appropriate PPE and the Contractor is to make an allowance for site protection / access restriction as identified by site RAMS. | Item
D | Waste Materials
| Remove all rubbish and debris from the site from time to time as it accumulates and at the completion of the contract, particularly given the tight confines of the site and setup area. Leave the site neat and tidy to the satisfaction of the Contract Administrator. A skip may be placed on site to the compound area and also car park providing outside of term time when assume main strip will be undertaken, in a location to be agreed with the Contract Administrator. | Item
Cleaning
E | The Contractor is expected to leave works areas clean and tidy upon completion of each day’s work. | Item
Parking/ Storage
F | The Contractor will be provided with parking on-site during the summer holiday period. Should works extend into the term time they will NOT be allowed to park on-site. The Contractor will be given a fob to access the site and will be responsible for ensuring secure at all times. The Client will not be reimbursing the Contractor for parking. Street parking around the site is a mixture of restricted and unrestricted. | Item
Access
G | The sites are located within urban residential areas in close proximity within the Raynes Park/South Wimbledon area, with various amenities nearby. Access to the sites and direct working area can be made from main roads and residential roads, with both national rail and underground stations within a 5 minute walk. | Item
The Contractor will be responsible for timing deliveries in order to limit disruption to the neighbours, schools and surrounding roads. Both during holidays and term time, no major deliveries should be made between 8.30-9.30am and 2.30-3.30pm. Particular effort should be made to ensure that deliveries avoid the busy morning and late afternoon rush hour periods in order to appease the neighbours. Where required a Banksman should be used by the Main Contractor for particular deliveries with details to be provided within their Construction Phase Plan prior to works commencing. This is of particualr importance with regards to the scaffolding delivery and collection given use of large lorries.
The Contractor will be responsible for developing the Construction Phase Plan following appointment to detail how they will safely execute the works and manage the site, with both schools being consulted with.
Note: As such it is paramount that the Contractor ensures the access into the neighbouring properties and schools is not obstructed at any time during the course of the works.
Note: The Client will NOT be expected to take deliveries on behalf of the Contractor.
Handover Documents
H | The Contractor must collate all required Handover Documentation as the work proceeds, submitting to the Contract Administrator all information requested by McBains by the completion date to enable Practical Completion to be issued. | Item
| Working Hours | Item
I | As previously detailed, given the Client’s requirements for works to be completed within a quick timeframe, Contractors are expected to price the works on the basis of normal working hours however if unable to strike scaffolding in full before the start of term in early September, the Contractor will need to allow for striking outside of term time hours of 8.30-3.30 Mon-Friday at their own cost.
Normal working hours are expected to be Monday to Friday 7.30am – 6.00pm. It is expected that the Contractor will be given keys to access the property. As such the Contractor will be responsible for securing the site on commencement of works and upto issue of the PC Certificate.
With regards to noisy works the Contractor will need to try and warn the neighbouring properties in advance as to ensure relations are maintained throughout the project. The Contractor will need to allow for adapting their activities to reflect where required.
Welfare Facilities
J | The Contractor will be responsible for developing the appended Logistics Plans to ensure a practical approach can be taken. Contractor will need to price for providing their own welfare facilities within the area shown in the Logistics Plan. | Item
Note: The Contractor is expected to develop the site logistics plan at tender return stage so that this can be assessed as part of the qualitive tender return. This is to ensure that a practical and acceptable approach is provided.
The Contractor will be able to make use of existing services on sites but will however be responsible for making all connections and ensuring these have been carried out safely (no trip hazards etc).
Health and Safety
K | It is considered that due to the nature of the works and anticipated contract period these works WILL BE notifiable under the CDM Regulations 2015. As such the Contractor is to allow for providing all necessary information for the compilation of the Health and Safety Folder, in addition to providing a Construction Health and Safety Plan to the satisfaction of the Principal Designer prior to works starting on site. The Contractor is to review any existing building plans/health & safety documentation prior to starting the works. Asbestos information has been appended to the tender documents. A Pre-Construction Information Document will be issued to all tendering Contractors during the tender period. | Item
During the Construction phase and as works progress, the Contractor is expected to act as Principal Contractor and supply all required method statements/obtain from sub-contractors where applicable, to the satisfaction of the Principal Designer, including collation of information from the named underpinning sub-contractor. The Principal Contractor will be responsible for amending their Construction Phase Plan if required during the progress of works and the collation and submission of Health & Safety File on completion of the works to the satisfaction of the Principal Designer. The Principal Designer will be responsible for issuing all F10 notices to the HSE and distributing to all relevant parties.
Security
L | The Contractor shall ensure that the building is left secure at all times. Should there be any security issues during the scheme the Contractor should notify the end-user, assume Caretaker, in the first instance. | Item
The Contractor will be responsible for ensuring the site/compound is secure throughout the duration of the works, including buildings where welfare/storage is provided and will be responsible for any loss of materials from site. As such it is advised that materials/items of value be brought to site on day of install etc.
Note: The Client will not be responsible for any loss or damage caused where utilising existing buildings for these purposes.
Preliminaries
M | Allow here for all contractors’ preliminary costs for undertaking these works. Please append a breakdown to reflect breakdown in terms of site management, contracts management, H&S supervision, welfare, IT, allowance for consumables etc. | Item
Qualifications
N | Please provide details of at least 2 recent school roof refurbishment projects you have delivered as Main Contractor.
1 | TOTAL

## Raynes Park
Raynes Park High School & Rutlish School
6th Form Block Externals Package
Contractor Pricing Document
Note: Contractor to note that the Schedule of Works, drawings and appendices take precedence over the descriptions provided in this document and as such these should be priced. This document has been provided in editable format to make it easier for the contractor to insert their costs.
Ref Nr | Item/Description | Item/PC | Cost (£)
Section 1 | Preliminaries
Section 2 | Schedule of Works - RAYNES PARK HIGH SCHOOL |  | (price within breakdown below)
1 | ACCESS
A | The Contractor is to design and provide appropriate means of access in order to undertake all required high level works suitably and in a safe manner to access the working areas as highlighted within the appended site access plan, which the Contractor will need to develop as part of their tender return and provide an access method plan. Given the scope of works proposed it is assumed that the Contractor will either fully scaffold the building with lifts at levels to ensure windows can be safely accessed for the scope proposed, or provide a scaffold staircase complete with hoist, edge protection, with works at high level to windows being undertaken from mobile access towers and/or MEWPS. Given the scope of works to be undertaken it is assumed that the Contractor will provide full scaffolding to all working areas, with herras fencing provided to prevent access by intruders. The Contractor is ultimately responsible for designing. If scaffolding is still in-situ come the start of the term Contractor will need to remove post 3.30pm or at a weekend at their own cost. It is assumed that the Contractor has reviewed this against site access constrains when attending the sites to determine and design their high level access, in addition to temporary edge protection and netting where deemed necessary. The Contractor will need to provide fans over each external door to ensure that building users are protected at all times. Should the Contractor have any concerns with being able to complete the necessary works on the below basis they should inform the CA at their earliest convenience prior to returning their tender. Note: Contractor to allow for liaising closely with the School Caretaker in order to arrange access. | Item
B | Means of access should be suitable for the scope works as outlined within the Specification. Particular attention should be paid to;
Avoid physical damage during the undertaking of high level works.
The Contractor is to ensure that all entrances, exits and fire exits are not in any way obstructed by the use of scaffold whilst undertaking high level works and that they are left operational at all times. Contractor to review prior to submitting their return.
C | Should the Contractor proceed with scaffolding this should be boarded and netted, inc means of alarm activated at the end of each working day. Contractor to allow for adapting scaffold access over exits and entrances to ensure these are not impacted by the works. This should be through use of netted fan lights etc. Also advisable to not undertake works over entrances/exits during term time. Contractor to provide out of hours details in the event alarm is activated outside of construction hours. Ladders are to be secured out of reach at the end of each working day to prevent access. | Item
D | Contractor to determine means of access appropriate for the scope works as outlined within this document. Particular attention should be paid to; Avoid physical damage during the undertaking of high level works. The Contractor is to ensure that all fire exits are not in any way obstructed by the use of scaffold whilst undertaking high level works and that they are left operational at all times. | Item
E | The Contractor is to ensure that all areas outside of the working area are kept unobstructed at all times throughout the works and that means of alarm is provided and activated at the end of each working day. Contractor to provide out of hours details in the event alarm is activated outside of construction hours. | Item
F | Working areas are to be fully protected at all times by the installation of herras fencing or equal and approved. Fencing is to be erected to all site boundaries and suitably screened off. | Item
G | Contractor will need to allow for providing a crash deck or alternative when working the brise soleil. | Item
2 | STRIP OUT
i | Prior to works commencing the Contractor is to allow for isolating all services to the working areas to minimise hazards and providing temporary services to working areas in a safe manner, ensuring no trailing leads or cables that can be accessed by pupils. | Item
ii | Contractor to allow for the strip up and correct disposal of all external fabric to be renewed as part of the works detailed in this document, such as existing rooflights, rainwater goods, joinery etc, ensuring that adjoining surfaces being retained are not damaged as far as reasonably practical. | Item
3 | ROOF
A | Prior to works commencing, the Contractor will be expected to remove for inspection and reinstate all existing transition sheets over the bay joints to the modular units allowing re-secure on completion to the satisfaction of the CA, securing where fixings are currently missing.
B | To the ridge line Contractor is to allow for installing new standard top hat flashing with powder coated finish in white to direct surface water away from the ridge line. Overlaps of min 200mm should be provided in accordance with manufacturers details before being applied with Giromax Roof Coat System to ensure warranty for the roof in full. Contractor to allow for external grade sealant and Butyl tape to seams. | Item
C | To the surround of timber cladding provided to vent hatches, Contractor is to allow for instlaling new pre formed flashing kit to extend min 200mm above the roof surface, secured with stitch screws back to substrate and sealed using external grade sealant and butyl tape. | Item
D | To the roof edge where parapet has been retrofitted with a grating preventing drainage of surface water, Contractor is to allow for renewing with new perforated powder coated aluminium trims screwed back to the coping flashing in order to allow drainage of surface water whilst preventing the concealed box gutters from being blocked by foliage. | Item
E | The existing insulated metal roof sheets are to be overlaid using a high quality reinforced cold liquid system in accordance with the appended manufacturers specification and drawings. Contractor to overlay utilising a Giromax Roof Coat Metal System inc of encapsulation and Giromax Cut Edge application (equal and approved), providing a 25 year insurance backed independent warranty on completion of the works (Giromax Roofcoat Elite waterproofing system guarantee). Warranty is to be made out to the Client and be job specific. As part of the warranty, the manufacturer is required to inspect progress of works and on completion to ensure they are satisfied that works have been carried out in accordance with their warranty requirements. | Item
Prior to commencing works, Contractor is to allow for thoroughly preparing the existing metal roof sheets in accordance with the manufacturer specification to ensure suitable for repair and liquid application, allowing to secure all existing fixings and detail in all loose surfaces to ensure integrity. Contractor to allow for ensuring minimum 150mm upstands are provided to all junctions. Contractor to allow for liaising with Giromax or equal and approved manufacturer (Mark Cotton - 07407 615098) at all times to ensure reps can attend to review quality and compliance of works so that a completion certificate and guarantee can be provided. Any deviation from the manufacturers specification MUST be authorised and approved by the CA and system manufacturer in good time prior to works taking place. On completion of the works a 25 year manufacturers insurance backed warranty is to provided for the new installations to certify workmanship and lifespan of the product.
Works MUST be undertaken by one of the following manufacturer approved Contractors given the type of warranty which will be provided on completion;
Nationwide Decorators & Spray finishing Ltd Unit 8 Asquith Avenue Business Park Morley Leeds LS27 7RZ Tel: 0113 2523211 Contact: Stephen Email. stephen@nwdecs.co.uk Stark 218 Milton Keynes Business Centre Foxhunter Drive Linford Wood Milton Keynes MK14 6GD Raj Gohil – 07951 497556 Email - raj@starkconstruct.com
Smart Spray Solutions Ltd Unit 10 The Old Railworks Dumfries Street Darlington DL1 1LB Tel: 0800 2335656 Contact: Daniel Roberts Mobile: 07896 981465 Email: daniel@smartspraysolutions
F | Should any further repairs or replacement be required to the roof sheets and detailing, the Contractor is to allow the Provisional Sum of £5,000.00 to be instructed by the CA. | PROV SUM | 5000
G | Contractor to allow for removing all debris/growth to outlets before suitably jetting out and installing new preformed outlet kits as per manufacturers specification, ensuring detailed to surrounds to prevent ingress to system. | Item
H | Contractor to allow for replacing the coxdome rooflights inc 2.nr roof access hatches with hydraulic opening, using new high performance triple skin units inc preformed kerbs. Contractor to detail in at parapets before installing new termination bars as per manufacturers requirements and drawings. | Item
I | Contractor to allow for thoroughly overhauling all existing rainwater goods such as the downpipes and box gutters following renewal of outlets, to ensure they are correctly working, free of any blockages, debris etc, allowing to jet out twice on completion. Contractor to allow for taking capping off the parapet in order to expose gutters, allowing to removal any blockages and debris, before reinstating, ensuring suitably secured, replacing any missing or defective fixings on completion to the satisfaction of the CA. | Item
J | Contractor to allow Provisional Sum of £750 for any further repairs/isolated replacement to rainwater goods to be instructed by the CA. | PC SUM | 750
4 | WINDOWS & FAÇADE
A | To the existing timber sills of all windows the Contractor is to fabricate PPC aluminium capping's provided with a fall of 15 degrees minimum to direct surface water away from the glazing. Contractor to allow for cutting down sheets of the PPC aluminium in order to form to suit openings. Drip detail to be provided to ensure surface water is directed away from the facade. Units are to be finished in light grey to closely match the window finish. Contractor to secure back to substrate mechanically and detail to all surrounds with waterproof external grade sealant to prevent ingress of water to substrate. | Item
B | To the surround of all window units, Contractor will be required to remove all existing sealants given these have largely failed and been renewed on an ad-hoc basis on several occasions. Contractor to ensure junctions and substrate are free of debris, clean and dry prior to applying bead of external grade silicone sealant to all surrounds in a light grey finish to match existing. On completion Contractor to ensure that all beads are smooth and continuous to satisfaction of the CA. | Item
C | To the surround of all penetrations to the facade, such as rainwater goods, pipework, flues, Contractor will be required to apply new external grade silicone sealants. Contractor to ensure junctions and substrate are free of debris, clean and dry prior to applying bead of external grade silicone sealant to all surrounds in a clear finish to match existing. On completion Contractor to ensure that all beads are smooth and continuous to satisfaction of the CA. | Item
D | To isolated window units where gaskets to glazing panes have failed the Contractor is to allow for renewing with new EPDM gaskets to suit frame bead in black. Contractor to allow for removing glazing before stripping out defective sections and renewing with new. For pricing purposes Contractor to allow for removing 5.nr panes of glass and renewing 4lm per window under the direction of the CA. | PC QUANT
E | Contractor to allow the Provisional Sum of £2,000.00 for any further works to be instructed by the CA in relation to the windows. | PC SUM | 2000
5 | BRISE SOLEIL
i | To all locations where brise soleil's are provided, namely to the East and South elevations, the Contractor is to allow for carefully removing the timber cladding to surround and setting aside for reinstatement, so that sufficient access to the fixing of the units can be provided for review and remedial works. Contractor to allow for reinstating cladding on completion of remedial works. | Item
ii | Contractor to allow the Provisional Sum in relation to required remedial works to the brise soleil's following opening up works and review by the CA, to be instructed by the CA. | PC SUM | 16000
iii | On completion and reinstatement of the cladding, Contractor to allow for applying flexible movement sealant to the surround of all brise soleil's to ensure there are no open voids as is currently the case, in clear finish. | Item
6 | MISCELLANEOUS
A | Contractor to allow for a builders clean and sparkle clean on completion of all working areas and externals to ensure that sufficient cleanliness is provided at handover to the Client. Contractor to also allow for thorough clean of all associated external areas in relation to site setup/access on completion. Contractor to make good all soft and hardstandings following dismantling of scaffolding and site setup to ensure in the same condition as prior to works undertaken. | Item
On completion of all works the Contractor is to make good all surrounding/landscaped areas such as existing surfaces so that areas are left tidy and presentable on completion.
Note: It is advised that the Contractor undertakes a Schedule of Condition prior to commencing works to use a reference at a later date.
B | As part of the works the Contractor will need to ensure that the lightning protection system is not damaged by the works. The LPS system is currently compliant as demonstrated by the most recent report appended. Should any damage occur to the LPS then the Contractor will need to rectify at their own cost. As such we advise that you review the LPS condition and record any damage prior to commencing works. | Item
C | Following completion of works, the Contractor will need the schools incumbent LPS contactor to undertake a survey/test to ensure the system is still operational and compliant. A quote has been appended from the Named Sub-Contractor. Please allow for their quote plus your attendance and OHP. Note quote currently awaited and will be issued shortly. | Item
D | Contractor to allow for the Contingency Sum to be expended by the Contract Administrator. | PROV | 6000
2 | RAYNES PARK HIGH SCHOOL EXTERNALS PACKAGE |  | £
SUMMARY
1 | ACCESS
2 | STRIP OUT
3 | ROOF
4 | WINDOWS
5 | BRISE SOLEIL
6 | MISCELLANEOUS
2 | RAYNES PARK HIGH SCHOOL TOTAL

## Rutlish
Raynes Park High School & Rutlish School
6th Form Block Externals Package
Contractor Pricing Document
Note: Contractor to note that the Schedule of Works, drawings and appendices take precedence over the descriptions provided in this document and as such these should be priced. This document has been provided in editable format to make it easier for the contractor to insert their costs.
Ref Nr | Item/Description | Item/PC | Cost (£)
Section 1 | Preliminaries
Section 2 | Schedule of Works - RUTLISH SCHOOL |  | (price within breakdown below)
1 | ACCESS
A | The Contractor is to design and provide appropriate means of access in order to undertake all required high level works suitably and in a safe manner to access the working areas as highlighted within the appended site access plan, which the Contractor will need to develop as part of their tender return and provide an access method plan. Given the scope of works proposed it is assumed that the Contractor will either fully scaffold the building with lifts at levels to ensure windows can be safely accessed for the scope proposed, or provide a scaffold staircase complete with hoist, edge protection, with works at high level to windows being undertaken from mobile access towers and/or MEWPS. Given the scope of works to be undertaken it is assumed that the Contractor will provide full scaffolding to all working areas, with herras fencing provided to prevent access by intruders. The Contractor is ultimately responsible for designing. If scaffolding is still in-situ come the start of the term Contractor will need to remove post 3.30pm or at a weekend at their own cost. It is assumed that the Contractor has reviewed this against site access constrains when attending the sites to determine and design their high level access, in addition to temporary edge protection and netting where deemed necessary. The Contractor will need to provide fans over each external door to ensure that building users are protected at all times. Should the Contractor have any concerns with being able to complete the necessary works on the below basis they should inform the CA at their earliest convenience prior to returning their tender. Note: Contractor to allow for liaising closely with the School Caretaker in order to arrange access. | Item
B | Means of access should be suitable for the scope works as outlined within the Specification. Particular attention should be paid to;
Avoid physical damage during the undertaking of high level works.
The Contractor is to ensure that all entrances, exits and fire exits are not in any way obstructed by the use of scaffold whilst undertaking high level works and that they are left operational at all times. Contractor to review prior to submitting their return.
C | Should the Contractor proceed with scaffolding this should be boarded and netted, inc means of alarm activated at the end of each working day. Contractor to allow for adapting scaffold access over exits and entrances to ensure these are not impacted by the works. This should be through use of netted fan lights etc. Also advisable to not undertake works over entrances/exits during term time. Contractor to provide out of hours details in the event alarm is activated outside of construction hours. Ladders are to be secured out of reach at the end of each working day to prevent access. | Item
D | Contractor to determine means of access appropriate for the scope works as outlined within this document. Particular attention should be paid to; Avoid physical damage during the undertaking of high level works. The Contractor is to ensure that all fire exits are not in any way obstructed by the use of scaffold whilst undertaking high level works and that they are left operational at all times. | Item
E | The Contractor is to ensure that all areas outside of the working area are kept unobstructed at all times throughout the works and that means of alarm is provided and activated at the end of each working day. Contractor to provide out of hours details in the event alarm is activated outside of construction hours. | Item
F | Working areas are to be fully protected at all times by the installation of herras fencing or equal and approved. Fencing is to be erected to all site boundaries and suitably screened off. | Item
G | Contractor will need to allow for providing a crash deck or alternative when working the brise soleil. | Item
2 | STRIP OUT
i | Prior to works commencing the Contractor is to allow for isolating all services to the working areas to minimise hazards and providing temporary services to working areas in a safe manner, ensuring no trailing leads or cables that can be accessed by pupils. | Item
ii | Contractor to allow for the strip up and correct disposal of all external fabric to be renewed as part of the works detailed in this document, such as existing rooflights, rainwater goods, joinery etc, ensuring that adjoining surfaces being retained are not damaged as far as reasonably practical. | Item
3 | ROOF
A | Prior to works commencing, the Contractor will be expected to remove for inspection and reinstate all existing transition sheets over the bay joints to the modular units allowing re-secure on completion to the satisfaction of the CA, securing where fixings are currently missing.
B | To the ridge line Contractor is to allow for installing new standard top hat flashing with powder coated finish in white to direct surface water away from the ridge line. Overlaps of min 200mm should be provided in accordance with manufacturers details before being applied with Giromax Roof Coat System to ensure warranty for the roof in full. Contractor to allow for external grade sealant and Butyl tape to seams. | Item
C | To the surround of timber cladding provided to vent hatches, Contractor is to allow for instlaling new pre formed flashing kit to extend min 200mm above the roof surface, secured with stitch screws back to substrate and sealed using external grade sealant and butyl tape. | Item
D | To the roof edge where parapet has been retrofitted with a grating preventing drainage of surface water, Contractor is to allow for renewing with new perforated powder coated aluminium trims screwed back to the coping flashing in order to allow drainage of surface water whilst preventing the concealed box gutters from being blocked by foliage. | Item
E | The existing insulated metal roof sheets are to be overlaid using a high quality reinforced cold liquid system in accordance with the appended manufacturers specification and drawings. Contractor to overlay utilising a Giromax Roof Coat Metal System inc of encapsulation and Giromax Cut Edge application (equal and approved), providing a 25 year insurance backed independent warranty on completion of the works (Giromax Roofcoat Elite waterproofing system guarantee). Warranty is to be made out to the Client and be job specific. As part of the warranty, the manufacturer is required to inspect progress of works and on completion to ensure they are satisfied that works have been carried out in accordance with their warranty requirements. | Item
Prior to commencing works, Contractor is to allow for thoroughly preparing the existing metal roof sheets in accordance with the manufacturer specification to ensure suitable for repair and liquid application, allowing to secure all existing fixings and detail in all loose surfaces to ensure integrity. Contractor to allow for ensuring minimum 150mm upstands are provided to all junctions. Contractor to allow for liaising with Giromax or equal and approved manufacturer (Mark Cotton - 07407 615098) at all times to ensure reps can attend to review quality and compliance of works so that a completion certificate and guarantee can be provided. Any deviation from the manufacturers specification MUST be authorised and approved by the CA and system manufacturer in good time prior to works taking place. On completion of the works a 25 year manufacturers insurance backed warranty is to provided for the new installations to certify workmanship and lifespan of the product.
Works MUST be undertaken by one of the following manufacturer approved Contractors given the type of warranty which will be provided on completion;
Nationwide Decorators & Spray finishing Ltd Unit 8 Asquith Avenue Business Park Morley Leeds LS27 7RZ Tel: 0113 2523211 Contact: Stephen Email. stephen@nwdecs.co.uk Stark 218 Milton Keynes Business Centre Foxhunter Drive Linford Wood Milton Keynes MK14 6GD Raj Gohil – 07951 497556 Email - raj@starkconstruct.com
Smart Spray Solutions Ltd Unit 10 The Old Railworks Dumfries Street Darlington DL1 1LB Tel: 0800 2335656 Contact: Daniel Roberts Mobile: 07896 981465 Email: daniel@smartspraysolutions
F | Should any further repairs or replacement be required to the roof sheets and detailing, the Contractor is to allow the Provisional Sum of £5,000.00 to be instructed by the CA. | PROV SUM | 5000
G | Contractor to allow for removing all debris/growth to outlets before suitably jetting out and installing new preformed outlet kits as per manufacturers specification, ensuring detailed to surrounds to prevent ingress to system. | Item
H | Contractor to allow for replacing the coxdome rooflights inc 2.nr roof access hatches with hydraulic opening, using new high performance triple skin units inc preformed kerbs. Contractor to detail in at parapets before installing new termination bars as per manufacturers requirements and drawings. | Item
I | Contractor to allow for thoroughly overhauling all existing rainwater goods such as the downpipes and box gutters following renewal of outlets, to ensure they are correctly working, free of any blockages, debris etc, allowing to jet out twice on completion. Contractor to allow for taking capping off the parapet in order to expose gutters, allowing to removal any blockages and debris, before reinstating, ensuring suitably secured, replacing any missing or defective fixings on completion to the satisfaction of the CA. | Item
J | Contractor to allow Provisional Sum of £750 for any further repairs/isolated replacement to rainwater goods to be instructed by the CA. | PC SUM | 750
4 | WINDOWS & FAÇADE
A | To the existing timber sills of all windows the Contractor is to fabricate PPC aluminium capping's provided with a fall of 15 degrees minimum to direct surface water away from the glazing. Contractor to allow for cutting down sheets of the PPC aluminium in order to form to suit openings. Drip detail to be provided to ensure surface water is directed away from the facade. Units are to be finished in light grey to closely match the window finish. Contractor to secure back to substrate mechanically and detail to all surrounds with waterproof external grade sealant to prevent ingress of water to substrate. | Item
B | To the surround of all window units, Contractor will be required to remove all existing sealants given these have largely failed and been renewed on an ad-hoc basis on several occasions. Contractor to ensure junctions and substrate are free of debris, clean and dry prior to applying bead of external grade silicone sealant to all surrounds in a light grey finish to match existing. On completion Contractor to ensure that all beads are smooth and continuous to satisfaction of the CA. | Item
C | To the surround of all penetrations to the facade, such as rainwater goods, pipework, flues, Contractor will be required to apply new external grade silicone sealants. Contractor to ensure junctions and substrate are free of debris, clean and dry prior to applying bead of external grade silicone sealant to all surrounds in a clear finish to match existing. On completion Contractor to ensure that all beads are smooth and continuous to satisfaction of the CA. | Item
D | To isolated window units where gaskets to glazing panes have failed the Contractor is to allow for renewing with new EPDM gaskets to suit frame bead in black. Contractor to allow for removing glazing before stripping out defective sections and renewing with new. For pricing purposes Contractor to allow for removing 5.nr panes of glass and renewing 4lm per window under the direction of the CA. | PC QUANT
E | Contractor to allow the Provisional Sum of £2,000.00 for any further works to be instructed by the CA in relation to the windows. | PC SUM | 2000
5 | BRISE SOLEIL
i | To all locations where brise soleil's are provided, namely to the East and South elevations, the Contractor is to allow for carefully removing the timber cladding to surround and setting aside for reinstatement, so that sufficient access to the fixing of the units can be provided for review and remedial works. Contractor to allow for reinstating cladding on completion of remedial works. | Item
ii | Contractor to allow the Provisional Sum in relation to required remedial works to the brise soleil's following opening up works and review by the CA, to be instructed by the CA. | PC SUM | 16000
iii | On completion and reinstatement of the cladding, Contractor to allow for applying flexible movement sealant to the surround of all brise soleil's to ensure there are no open voids as is currently the case, in clear finish. | Item
6 | MISCELLANEOUS
A | Contractor to allow for a builders clean and sparkle clean on completion of all working areas and externals to ensure that sufficient cleanliness is provided at handover to the Client. Contractor to also allow for thorough clean of all associated external areas in relation to site setup/access on completion. Contractor to make good all soft and hardstandings following dismantling of scaffolding and site setup to ensure in the same condition as prior to works undertaken. | Item
On completion of all works the Contractor is to make good all surrounding/landscaped areas such as existing surfaces so that areas are left tidy and presentable on completion.
Note: It is advised that the Contractor undertakes a Schedule of Condition prior to commencing works to use a reference at a later date.
B | As part of the works the Contractor will need to ensure that the lightning protection system is not damaged by the works. The LPS system is currently compliant as demonstrated by the most recent report appended. Should any damage occur to the LPS then the Contractor will need to rectify at their own cost. As such we advise that you review the LPS condition and record any damage prior to commencing works. | Item
C | Following completion of works, the Contractor will need the schools incumbent LPS contactor to undertake a survey/test to ensure the system is still operational and compliant. A quote has been appended from the Named Sub-Contractor. Please allow for their quote plus your attendance and OHP. Note quote currently awaited and will be issued shortly. | Item
D | Contractor to allow for the Contingency Sum to be expended by the Contract Administrator. | PROV | 6000
2 | RUTLISH SCHOOL EXTERNALS PACKAGE |  | £
SUMMARY
1 | ACCESS
2 | STRIP OUT
3 | ROOF
4 | WINDOWS
5 | BRISE SOLEIL
6 | MISCELLANEOUS
2 | RUTLISH SCHOOL TOTAL

## PRICING SUMMARY
Raynes Park High School & Rutlish School
6th Form Block Externals Package
Contractor Pricing Document
| PRICING SUMMARY | £
1 | Preliminaries
2 | Raynes Park High School Schedule of Works
3 | Rutlish School Schedule of Works
TOTAL