Specification and Schedule of Works Rous Road Car Park, Newmarket, Suffolk, CB8 8LX

| A1 - SPECIFICATION & SCHEDULE OF WORKS Provision of Works Rous Road Car Park, Newmarket, Suffolk, CB8 8LX | £ | p |
| --- | --- | --- |
| Preliminaries Carry out site specific Risk Assessment and Method Statement and submit to Contract Administrator for approval prior to commencement on site. Attention is drawn to the Council’s Safety and Environmental requirements for Contractors and Sub-contractors (appended to this document). Allow for providing safe system of work, welfare facilities and compound area as determined by the Risk Assessment and for removal from site and reinstatement upon completion. All drain locations and pipe runs to be identified and recorded. Any services not shown on plan to be traced and recorded before works commence. NOTE: The car park will be operational whilst the works are being carried out. Phasing works to take place, closing off sections and then reopening once works have been completed. (To be agreed with winning Contractor) Waste removal to approved sites will be provided by the contractor. Contract commencement date will be within eight weeks of the date for the receipt of quotation. Contract period will be 4 weeks. The Contractor does not commence work until the commencement date and does the work so that completion is on or before the dated provided in this Tender Document. Payment will be made on completion of the works. A retention sum of 5% of the contract price will be held for the 12 months defects period. Accreditation for Street Works Under the New Roads and Street Works Act (1991) (NRSWA), Chapter 8, the installation, renewal, maintenance and inspection of underground apparatus in any street or road must be under the control of competent people. Works in this project will be required to be supervised by a qualified street works “supervisor”. In addition, whether the street is excavated or not, a “trained operative, with an “operative” qualification must be present on site at all times when works are in progress. Contact is to be made to Highways Officer, Cheryl Froud – contact (01284) 757319 or 07964 919303 or Adam Warnes, Parking and Highways Services Manager (01284) 757423 for site inspection as this is a mandatory condition of submitting a bid. The dates for the site inspections are: Wednesday 30 July 2025 at 10am Wednesday 6 August 2025 at 10am. NOTE: The road marking works will be completed separately and will be organised by West Suffolk Council. Previous experience Please provide evidence of previous experience to similar works, within the past 3 years together with the value of the works. Carried to Summary Schedule of Works: Site Boundary area – 5738m2 - To carry out all preparation and site enabling works as per Drawing Number 397/2024/011 P1. - Existing surface is to be swept and fully prepared and any soft spots are to be made good before the bond coat is applied. - Carriageway patching, prior to 40mm resurfacing. (areas in blue). Drawing Number 397/2024/011 P1 - Existing concrete areas to be removed and replace with asphalt construction (areas in purple) Drawing Number 397/2024/011 P1 - Overband and fill crack sealant joint repairs (area shown as green lines) Drawing Number 397/2024/011 P1 - Existing surface water drainage channels to be removed within the car park. Asphalt to be laid with appropriate falls to convey water to the gullies. Drawing Number 397/2024/010 P2. Existing gullies to be retained. - All existing chamber covers within the car park extent to be reset to match new levels following resurfacing works – Please see Drawing Number 397/2024/010 P2. - New 56m length of kerb line to be installed along the back of the proposed parking bays – West to South. Drawing Number: 397/2024/010 P2 - 0-40mm 2m Plane out and inlay (areas shown in green). Depth of planing varies respective to distance from kerb. Drawing Number 397/2024/011 P1. - 40mm Surfacing Overlay ONLY (areas shown in red). Entire area to be resurfaced (including planing, patching and concrete removal). Drawing Number 397/2024/011 P1 DRAINAGE - within the car park - (Gullies/interceptors/soakaways) - cleaning the whole of the system, removing root ingress and then apply a liner to the system – please see Drainage report included with the tender documents and Drawing Number 397/2024/010 P2. 12. To reposition a barrier around 1 x street column within the car park. 13. Traffic Management for vehicles and public footways Including (barriers, signage and personnel) for users of the car park whilst works are being carried out. Carried to Summary | £ £ £ £ £ £ £ £ £ £ £ £ £ £ £ £ |  |
| Temporary works |  |  |
| Provide all temporary protection to prevent unauthorised access to working area from public Carried to Summary |  |  |
| Completion of the Works |  |  |
| Remove all temporary works, sweep through and clear all debris, leaving sites if good condition, including reinstatement of compound area. Carried to Summary | £ £ |  |
| SUMMARY |  |  |
| Preliminaries Schedule of Works | £ £ |  |
| Temporary Works | £ |  |
| Completion of the Works | £ |  |
| TOTAL | £ |  |