## Slide 1: Invitation to participate Refinement and deployment phase team structure and timeline Lot 1: Design and Business Change Lot 2: Training annex h – team structure and timeline

## Slide 2: Lot 1 and Lot 2 Resource Split
External Resource (Lot 1)
External Resource (Lot 2)
MPS Resource
Business Change Programme Leadership
Training Content Design
Training Content Designers
Training Content Designers incl BAU training
Training
Training method, content scheduling, logistics and tech Mgt. and support
Training method, content scheduling, logistics and tech Mgt. and support
Comms and Engagement
Comms & Engagement Mgt. and support
Comms & Engagement Mgt. and support
End to end Design and Business Change Strategy and Leadership
End to end Design and Business Change Strategy and Leadership
Lot 1: Design and Business Change
Business Change Delivery Management
Management across the four areas of Change: Business Readiness, Transition, and Comms and Engagement
Management representation across the four areas of Change: Business Readiness, Transition, and Training
Business Transition
Transition Mgt. and support
Transition Mgt. and support
Business Readiness
Business Readiness Mgt. and support
Business Readiness Mgt. and support
Data and Design
Management across Design and Data
Product Owners
Data analysts
Business analysts
Lot 2: Training
Training Delivery
External Trainers
Internal Trainers (inc. business process and context)
An end to end Design, Data, Change and Training approach is required, to ensure the business is ready to use the new Command & Control Solution
A “two in a box” model is required, where external professional Data, Design, Change & Training skillsets work collaboratively with MPS Subject Matter Expertise
A consistent end to end Design and Business Change Leadership will set the strategic direction, lead the blended teams and maintain end to end consistency and standards across all deployments.
The Training Workstream is a key part of the overall Business Change strategy, so is managed and governed by the Business Change Leadership to ensure strong alignment with Design, Data and Change (also close working with testing). Trainers and Content Designers will focus on each deployment

## Slide 3: Command and Control Provisional Delivery Timeline and Impact
Drop | Overview of functionality delivery | Expected business transition | Business Change Impact expected (Numbers of users and level of change)
1. LifeX for Despatch | Replacing ICCS with a standalone LifeX system for Despatch Users only | Q4 2025 | Moderate
2. First Contact | Replacing CHS with OnCall for First Contact Operators and introducing PowerBI reporting | 2026 | Significant
3. Despatch+ | Replacing CAD with OnCall for Despatch Users, Replacing MetOps with OnCall OPR for Event Management, and Mobile Responder for all Frontline Officers | 2027 | Most Significant
Within the Refinement and Deployment phase, C&C will deliver functionality across three defined capability “drops”.
Each drop has a unique approach and schedule for training and transitioning. The detailed deployment approach and timing of each drop is subject to consultation. In advance of each training and go-live, an end-to-end design, data and change approach is required to enable each Go-Live. Testing is also a key part of this value chain.
Indicative schedule for delivery of drops:
Drop 1: LifeX for Despatch
Drop 2: First Contact
Drop 3: Despatch+
Training & Go-live
Training & Go-live
2025 |  |  |  |  |  |  |  |  |  |  |  | 2026 |  |  |  |  |  |  |  |  |  |  |  | 2027 |  |  |  |  |  |  |  |  |  |  |  | 2028 |  | 
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 1 | 2 | 3
Training & Go-live
Business Deployment
All timelines are subject to ongoing consultation

## Slide 4: External resource requirements across programme lifespan
A consistent leadership will build the teams in line with the demand for each deployment.
There is a requirement to maintain consistency in the management to build experience between deployments, with resources expected to increase with the complexity of each deployment.
The indicative resource estimates below are intended to demonstrate increasing resourcing over time and not constrain resourcing decisions.
Business Areas | Drop One: LFD | Drop Two: First Contact | Drop Three: Despatch
Lot 1: Design and Business Change |  |  | 
Business Change | c.5 FTE | (increasing over time) | c.15 FTE
 | April 2025 – January 2028 |  | 
Data and Design | c. 5-10 FTE (plus managing c.5-10 additional specialist policing SMEs – contracted directly to MPS) April 2025 – January 2028 |  | 
Business Areas | Drop One: LFD | Drop Two: First Contact | Drop Three: Despatch
Lot 2: Training |  |  | 
Training Content Design | c. x2 FTE April 2025 – December 2025 | c. x4 FTE January 2026 – January 2027 | c. x6 FTE February 2027 – November 2027
Training Delivery | c. x10 per training day August 2025 – November 2025 | c. x12 per training day March 2026 – November 2026 | c. x35 per day December 2026 – October 2027