Municipal Building:

Design element for the

cultural and creative transformation works to the Passmore Edwards Building, Falmouth

May 2023

Key Contract Conditions Data provided by the Client

Introduction

Set out below are the specifics which will be applicable.

Contract Data Provided by the Client

| Contract Data | Contract Specific Details |
| --- | --- |
| The law of the contract is | England and Wales |
| The period for reply is Except the period for reply for | One week accepting particulars of design is two weeks |
| The period for retention following completion or earlier termination is | Twelve years |
| The key dates and conditions to be met are | To be agreed |
| The consultant prepares forecasts of total expenses at intervals no longer than | Monthly |
| The consultant submits revised programmes at intervals no longer than | Monthly |
| The completion date for the whole of the service is | The date of issue of the making good defects certificate of the construction works contract |
| The period after the contract date within which the consultant is to submit a first programme for acceptance is | Two weeks |
| Payment |  |
| The currency of the contract is | Pound Sterling |
| The assessment interval is | A month |
| The expenses stated by the Client are | Payment of fees to Statutory Authorities and Utilities Suppliers |
| The interest rate is | 2% above the Bank of England base rate |
| The period within which payments are made is | Twenty eight days |
| Compensation events | Does not apply |
| Collaborative working | Does not apply |
| Health and Safety | Applies |
| Cost savings and value improvements | Applies |
| Sustainable development and environmental considerations | Applies |
| Performance Indicators and monitoring | Does not apply |
| Liabilities and Insurance |  |
| The minimum amount of cover and the periods for which the consultant maintains insurance are | As stated in Volume 1 |
| Resolving and avoiding Disputes |  |
| The tribunal is | Arbitration |
| The arbitration procedure is | To be agreed |
| The senior representative of the client is | Jackie George (Project Manager) |
| The adjudicator is | To be appointed by the adjudicator nominating body |
| Price adjustment for Inflation |  |
| The proportions used to calculate the price adjustment factor are The base date for indices is These indices are | Non-adjustable Not Applicable Not Applicable |
| Delay damages for completion of the whole of the service is | £100 per day |
| Performance Bond | Not Applicable |
| Limitation of Liability: The end of liability date after the completion of the whole service is | Twelve Years |