## Title
Issue Date
2025-08-01
Contractors Proposals
Project Reference
C2086
Project Title
Swanspool Pavillion
Project Address
Swanspool Parade, Wellingborough NN8 9SR
Project Description
Refurbishment of existing Grade II listed pavilion
Note to tenderers:
1. Please complete the tabs below as necessary for your works.
2. These documents are tracked and recorded. Any changes to the document will be the sole responsibility of the tenderer
3. Tenderers are responsible for satisfying themselves with all formulas and calculations within this document.

## Qualifications
Swanspool Pavillion
C2086
Tender Clarifications / Qualifications
Ref. | Work Item / Description
Allowances & Assumptions:
In preparation of this offer we have allowed and assumed that:-
1.01 | It has been assumed that we can use the existing facilities for welfare during the Works. Existing Meeting Room, Office and external Accessible WC to be used. Works to be sequenced accordingly to facilitate the use of these areas.
Remainder of Qualifications & Exclusions to be completed by tendering contractor.
1.02
1.03
1.04
1.05
1.06
1.07
1.08
1.09
1.1
1.11
1.12
1.13
1.14
1.15
Exclusions:
In preparation of this offer we have excluded the following:-
1.16 | Site Security; Guard / monitored surveilance
1.17
1.18
1.19
1.2

## CSA
Swanspool Pavillion
C2086
Contract Sum Analysis
Ref | Description | Value
1 | Preliminaries / Fees Etc.
1.1 | Preliminaries / General Conditions | 0
1.2 | Fees | 0
| Preliminaries, Fees et. Sub-total | 0
2 | Measured Works
2.1 | Enabling Works | 0
2.2 | External Walls & Roof | 0
2.13 | BWIC | 0
| Measured Works Sub-total | 0
3 | Provisional Sums | 0
| Provisional Sums Sub-total | 0
| TOTAL - Tender Sum c/f to Form of Tender - exc. VAT | 0

## Prelims
Swanspool Pavillion
C2086
1.1 | Preliminaries / General Conditions
Ref | Description | Qty | Unit | Rate | Total (£)
Enabling Works Contractor to be assigned as Principle Contractor for the Works; Please allow for the following items to achieve CDM compliance for 14 week duration
1.1.1 | Management and staff | 14 | weeks |  | 0
1.1.2 | General Labour | 7 | weeks |  | 0
1.1.3 | Safety, fire, and environmental protection | 1 | item |  | 0
1.1.4 | Hoarding; Allowance for 50m heras fencing; 1no vehicle gate and 2no pedestrian gates for duration of the Works | 1 | item |  | 0
1.1.5 | Site records; Permits etc | 1 | item |  | 0
1.1.6 | Completion and post-completion requirements; O&M Manual | 1 | item |  | 0
1.1.7 | Rubbish Removal; Allowance for fully enclosed 12 yard skips | 10 | no |  | 0
1.1.8 | Other (Contractor to state) | 1 | item |  | 0
0
| Any other works the contractor deems necessary for the Works: |  |  |  | 0
1.1.9 | Allowance to work alongside, and supervise 2no colledge students on day release. Cost per day to be advised | 1 | day |  | 0
To Collection |  |  |  |  | 0

## Fees
Swanspool Pavillion
C2086
1.2 | Fees
Ref | Description | Qty | Unit | Rate | Total (£)
Any other works the contractor deems necessary for the Works:
To Collection |  |  |  |  | 0

## SOW (1)
Swanspool Pavillion
C2086
2.1 | Enabling Works
Ref | Description | Qty | Unit | Rate | Total (£)
2.1.1 | Remove existing fitted furniture throughout | 1 | item |  | 0
2.1.2 | Remove existing floor finishes throughout | 257 | m2 |  | 0
2.1.3 | Remove existing doors, frames & architraves; As per plan | 7 | no |  | 0
2.1.4 | Remove existing chair rails throughout | 13 | m |  | 0
2.1.5 | Remove existing skirting boards throughout | 165 | m |  | 0
Remove existing ceilings throughout
2.1.6 | Suspended ceiling grid | 75 | m2 |  | 0
2.1.7 | Plasterboard ceilings | 190 | m2 |  | 0
2.1.8 | T&G timber ceilings | 46.8 | m2 |  | 0
2.1.9 | Remove non-loadbearing internal partitions | 45 | m |  | 0
2.1.10 | Clean out & jetwash existing gutters & downpipes | 1 | item |  | 0
Form new opening in masonry walls
2.1.11 | D8; 1143w x 2105h | 1 | item |  | 0
2.1.12 | ID3; Form new opening within masonry walls; 2105h x 1000w | 1 | item |  | 0
2.1.13 | ID9; 4705w x 2430h | 1 | item |  | 0
Widen existing openings to doorways in masonry walls
2.1.14 | D1; Widen from 943 to 1147mm; Works to both sides; External masonry wall | 1 | item |  | 0
2.1.15 | D5; Widen from 905 to 1147mm; Works to one side; External masonry wall | 1 | item |  | 0
2.1.16 | ID8; Widen from 885 to 1000mm; Works to both sides; Internal masonry wall | 1 | item |  | 0
2.1.17 | Allowance for temporary works | 1 | item |  | 0
Lintels to above; In accordance with Structural Engineers design
2.1.18 | D1; 1450mm | 1 | no |  | 0
2.1.19 | D5; 1450mm | 1 | no |  | 0
2.1.20 | D8; 1450mm | 1 | no |  | 0
2.1.21 | ID3; 1300mm | 1 | no |  | 0
2.1.22 | ID8; 1300mm | 1 | no |  | 0
2.1.23 | Steel beams to ID9; In accordance with Structural Engineers design | 1 | item |  | 0
2.1.24 | Padstones to above; In accordance with Structural Engineers design | 1 | item |  | 0
2.1.25 | Remove glass roof to canopies; Set aside for re-use | 1 | item |  | 0
2.1.26 | Clean and re-instate glass roof to canopies | 1 | item |  | 0
2.1.27 | Survey existing roof for defects; Report to identify scope of repairs | 1 | item
Any other works the contractor deems necessary for the Works:
To Collection |  |  |  |  | 0

## SOW (2)
Swanspool Pavillion
C2086
2.2 | External Walls & Roof
Ref | Description | Qty | Unit | Rate | Total (£)
2.2.1 | Make good pointing to external brickwork; Rake back existing mortar and apply mortar to match existing; Provisional Quantity | 10 | m2 |  | 0
2.2.2 | Clean all elevations; External brickwork and canopies | 496 | m2 |  | 0
2.2.3 | Jetwash external areas, including paving's, ramps and steps; Provisional Quantity | 50 | m2 |  | 0
Any other works the contractor deems necessary for the Works:
To Collection |  |  |  |  | 0

## SOW (13)
Swanspool Pavillion
C2086
2.13 | BWIC
Ref | Description | Qty | Unit | Rate | Total (£)
2.13.1 | BWIC with M&E | 1 | item |  | 0
2.13.2 | Mastic to skirtings, architraves, vanity units, kitchen worktops & window cills | 1 | item |  | 0
2.13.3 | Builders clean | 1 | item |  | 0
Any other works the contractor deems necessary for the Works:
To Collection |  |  |  |  | 0

## Prov Sums
Swanspool Pavillion
C2086
Provisional Sums
Ref | Description | Qty | Unit | Rate | Total (£)
External Works
| Perennial bedding | 1 | Psum |  | 0
| Electronic gate closures for garden gates; 2no adjacent to Pavillion | 1 | Psum |  | 0
| Path way redressing; Extent unknown | 1 | Psum |  | 0
| Replacement of litter bins with TC logo | 1 | Psum |  | 0
| New signage for park with TC logo and bowls green | 1 | Psum |  | 0
| Picnic benches | 1 | Psum |  | 0
| Survey and make good roof | 1 | Psum |  | 0
To Collection |  |  |  |  | 0

## Thank you
Thank you.
Please feel free to get in touch at any time.