## Sheet1
CLARIFICATION LOG
Tender: | Municipal Building: Design element for the cultural and creative transformation works to the Passmore Edwards Building, Falmouth
Tender Reference: | 02(07/2025)
Published Date: | 2025-08-22
Version number: | 0.5
Number | Clarification | Response | Reply date
1 | Although the tender documentation has been revised and re-issued, the submission date has remained the same on 29 August 2025. This is of course the August Bank Holiday week and we have many staff taking leave. In addition, this is a complex tender requiring inputs from a large design team. Could we therefore request and extension of the submission date to either the 5th or preferably the 12th September to allow us to provide the Council with a rigorous and detailed tender? | Although we appreciate the complexities of this tender, we are being driven by funding timescales and therefore we are unable to offer an extension. | 2025-08-05
2 | Could you please confirm the scope and budget of the exhibition design and installation works proposed for the upgraded gallery and facilities? Can you also confirm if these costs are in addition to the construction costs outlined in Para 2.12 which amount to £5.1m? | The scope of works is detailed in the Design brief. 2.12. For the purposes of this tender the estimated overall budget range is External construction cost of works £2.6m (exc. VAT) Internal construction cost of works £2.5m (exc. VAT) Apologies, there is a typo/ misleading word in the document. | 2025-08-05
3 | In addition to the MEND funding could you confirm the sources anticipated for the balance of the project funding and have applications been discussed and initiated with the funding agencies concerned and taken into account in the programme outlined in Para 3.3? | A number of funding applications are being considered and communication with the funders are at different stages. We will confirm the funders to the successful tenderer. The Programme is partly driven by these funding applications. | 2025-08-05
4 | Can you confirm the proposed team must include an AABC Registered accredited conservation architect and a CARE accredited conservation engineer given the Passmore Edwards Building is a prominent listed building? | No this is not essential. We will be looking for teams which have a successful track record of working with prominent listed buildings and may seek references to confirm this. | 2025-08-05
5 | Para 2.4 requires the design team to have access to all the required services to support this project and then lists those anticipated. Could you confirm if the costs of the consultants providing these services have to be included in the tender submitted or will the lead consultant just be required to assist in obtaining tenders for these works for the client to appoint direct? | The costs of the consultants providing these services have to be included in the tender submitted. | 2025-08-05
6 | Are the construction works to be carried out as a single contract or do we have to allow for the MEND funded works to the external fabric to be carried out as a separate contract to the internal works and upgrading? | It is anticipated that the internal and external construction works will be separate contracts. However, the appointed team will be responsible for advising the client accordingly. | 2025-08-05
7 | Para 2.5 indicates the successful bidder will be ‘required to undertake the necessary project management. Could you confirm if this is management is restricted to the construction elements of the project and that you will retain your existing overall project manager Jackie George or if we have to allow for the overall project management including the role currently provided by Jackie George? If so could you please provide a scope for this service? | This is project and contract management of the construction elements. Jackie George will be retained to support the client the costs of which are separate to this commission. | 2025-08-05
8 | Can you advise on a word limit or page count for the quality question responses? | 3 page limit for each question , arial 11 font. Relevant but proportional and succinct appendices will be allowed as long as also clearly cross referenced. | 2025-08-05
9 | Do you want the completed price schedule to be submitted in excel or as a PDF | Please submit as a separate Excel document. | 2025-08-05
10 | The price schedule notes ‘please submit a breakdown of cost per consultant and pre RIBA stage’ a. How would you like this formatted? One table with multiple columns – one per consultant? b. Or copy the whole table out for each consultant? | Apologies this should read "Please submit a breakdown of cost per RIBA stage". A revised Price Schedule sheet has been uploaded to Find a Tender | 2025-08-05
11 | Are you able to share your budget for consultant fees for both internal and external elements? For example the cost plan for the MEND works shows professional fees at 15%, equating to £234k, are you expecting a similar % rate / allowance for the internal works? | We have an indicative construction cost of £2.5m for the internal element. We expect to receive design fees proportionate to this budget. | 2025-08-05
12 | The sample marking table on page 22 of the tender brief includes fees for each sub-criteria – are these in the region of the expected fees? | No. This is an example to explain how the weightings will work. | 2025-08-05
13 | Can you confirm the construction estimate for the external works? The OCE notes £1.9m, while the MEND cost breakdown shows £1.5m | The costs will need to be updated as part of this work. As a separate commission, a costed condition survey is being procured. Based on previous work, we are assuming construction costs to be circa £2.1m | 2025-08-05
14 | Regarding the method statements questions, can we please use our own template to respond to the 5 method statements questions so we can best illustrate our experience & team? We will submit the document in pdf format. | We would ask all bidders to use the documents provided as part of the tender pack. We will, as set out in response to question 8, accept relevant and proportional appendices. | 2025-08-05
15 | We recently saw the Invitation to Tender for design services related to the refurbishment of the Passmore Edwards Municipal Building (on Find-a-tender, and also the Glenigan planning portal) and wanted to express our keen interest in supporting Falmouth Town Council with the delivery phase. | All details regard to this tender can be found in the accompanying documents with the Tender Notice – please see here: | 2025-08-05
|  | Municipal Building: Design element for the cultural and creative transformation works to the Passmore Edwards Building, Falmouth - Find a Tender | 2025-08-05
16 | Can you please share the Council’s full Terms & Conditions? | Please note section 2.4 of the Invitation to Tender Part A - it is proposed that this tender would be formed on JCT Consultancy Agreement (Public Sector) (CA 2024) - https://www.jctltd.co.uk/product/consultancy-agreement-2024 | 2025-08-08
17 | Does each sub-consultant need to complete their own questionnaire (ITT Part B) or are you expecting to review their details within our response only (Part 2B – list of all intended sub-contractors)? | We would expect the Lead design organisation to complete Part 2A, and 2B completed by all other key suppliers who would be supporting on this project, for example with a minimum of 15% input on the overall work. | 2025-08-08
18 | Can you define the scope of service for the building surveyor | The bidding organisation is to determine this, informed by the scope of works set out in the accompanying brief, drawings and documents with this tender pack. | 2025-08-08
19 | Can you define the scope of service for the acoustic consultant | The bidding organisation is to determine this, informed by the scope of works set out in the accompanying brief, drawings and documents with this tender pack. | 2025-08-08
20 | Can you define the scope of service for the exhibition designer | The bidding organisation is to determine this, informed by the scope of works set out in the accompanying brief, drawings and documents with this tender pack. | 2025-08-08
21 | What is the construction budget allowance for the exhibition design? | The scope of the internal works is set out in the brief and an indicative overall budget of £2.5m (exc. VAT) construction cost of works. We would be seeking that the design is included within this budget alongside any structural changes. Please also refer to responses to questions 2 and 9 above. | 2025-08-08
22 | In response 2 you refer to the scope of the exhibition work being set out in Para 2.12 of the Design Brief. The Design Brief for Lead Design Consultant does not have a Para 2.12 and does not define the scope of the exhibition work. Para 2.12 of the Invitation to Tender Part A only refers to the construction costs and does not define the scope of the exhibition work. Are we missing a document or could you provide an alternative reference? | The scope of works is detailed in the design brief. Exhibition design is to be considered throughout and therefore an integral part of the internal work. Para 2.12 details the budgets which was the second part of the question. Please also see responses to questions 2, 9 and 21 | 2025-08-12
23 | Are the interpretation and exhibition works costs included in the construction costs for internal works of £2.5m indicated in Para 2.12 of the Invitation to Tender Part A. If so, could we please have a breakdown of the internal costs so we can identify the anticipated exhibition costs? | There is not a breakdown of costs for the internal works. No design has been done to date - therefore no breakdown of costs. The appointed team will design and cost. £2.5m is an indicative construction cost so we can evaluate tenders on a like for like basis. Interpretation should be included where deemed most suitable ie design or construction. Exhibition design would be included in both design and construction. Please also see responses to questions 2, 9 and 21 | 2025-08-12
24 | One of our potential subconsultants may not meet the £10m public liability insurance requirement (note that they will meet all other insurance requirements). Would it be acceptable a) for them to be insured at £5m as they are not the lead consultant, b) for our insurance as lead consultant to be extended to cover them. | In principle we would be amenable to this but would require clarity that any split arrangement where the lead consultant acts in effect as guarantor from an insurance perspective is legally binding under the contract and does not expose the Council to risk. | 2025-08-12
25 | Public conveniences | Note that the public conveniences located on Webber Street are owned by FTC. They are currently not used as PCs. This area can also be considered as part of the project to increase the footprint of the project. | 2025-08-12
26 | Based upon the Key Contract Conditions document, it appears that the proposed form of contract is an NEC Professional Services Contract. Please can you confirm that this assumption is correct and also that there are no Z clauses. | The form of contract is to be JCT Consultancy Agreement (Public Sector) (CA 2024) as set out in Part A (para 2.14). Appendix 3 sets out the key Contract Conditions which would apply within that | 2025-08-12
27 | Within the Contract Data (Appendix 3), reference is made to Volume 1. Please can you provide a copy of Volume 1. | Apologies this should read "Part A: Invitation to Tender" - and specifically para 2.15 and 3.3. | 2025-08-12
28 | A key item within NEC Contract Data Part One is confirmation of the Consultant's total liability under the contract. There does not appear to be a corresponding item within the Key Contract Conditions. Please confirm the proposed value of the Consultant’s total liability. | We would seek that Consultant's total liability limits aligns to the Professional Indemnity Limit of £2m. As noted the form of Contract is JCT Consultancy Agreement (Public Sector) (CA 2024). | 2025-08-12
29 | I am looking at the fee and want to clarify that I am proposing a team that consists ONLY of the consultants listed in the tender: 2.4.1. Architectural Services (including acting as Principal Designer) 2.4.2. Exhibition design 2.4.3. Mechanical and Electrical Consultant (including fire expertise) 2.4.4. Energy assessor (Simplified Building Energy Model calculations) 2.4.5. Structural Engineer 2.4.6. Acoustic Consultant 2.4.7. Building Surveyor 2.4.8. Cost Consultant / Quantity Surveyor 2.4.9. Conservation Specialist 2.4.10. Contract Management My point being, there are other consultants you will need, Access, Fire, Lighting design, Interpretation, that will impact on the fee. If I include them, and other bidders don’t, my bid will be at a disadvantage. | Section states 2.4. The Supplier would be required to ensure that the professional services design team has access to all the required professional services to support this project and would include (but not limited to):…. We are therefore seeking the full design team required to take this from Stage 0 through to 6 . Specialisms should be considered and included where deemed required and costed for accordingly. The Council would not look to accept additional claims for consultancy costs where, based on the information supplied and the nature of the works required, it is reasonable and appropriate that those cost should have been included at the time of submitting the tender. | 2025-08-12
30 | Do you have any more information about the programme? Most of the key dates are ‘tbc’ on the schedule? | At this stage we do not have a firmed up programme as some of the dates will depend on how quickly designs can be progressed. Others are dependent on funding programmes. | 2025-08-12
31 | With the exact scope of works and final construction value unknown, are we to provide our price response based on the two estimates given for the external and internal works (£2.6m and £2.5m respectively) to allow all tender returns to be assessed equally? | Yes please. | 2025-08-12
32 | The tender documents break the scoring pricing response into two parts, 30% for RIBA 1-2 price and 70% for RIBA 3-6 price. Is this still the case or is this related to the first version of the tender issued? | Due to funding still to be confirmed the Council is seeking to undertake stages 1 & 2 at risk and hence seeking that this is fixed price. The evaluation therefore remains as set out in Part A Para 3.38 to 3.41 and therefore remains split as to evaluation 30% for RIBA 1-2 and 70% RIBA 3-6. PLEASE NOTE: Price Schedule has been revised in making a submission please use Price Schedule 1_Version 2_ 15.08.2025 | 2025-08-12
33 | Committee presentations | To enable the evaluators to compare tenders on a like for like basis, please allow for quarterly, face to face committee presentations. | 2025-08-12
34 | Will you accept more than 3 pages for the response, this is a complex project and with bullet point breakdowns of key actions per RIBA Stage, it will be difficult to achieve this. | We require responses within 3 pages per each question. Appendices are allowed, but please be thoughtful with regards to the size of these. All pertinent information should be in the question responses. | 2025-08-12
35 | Are we expected to provide methodology for stage 3-6 for internals, with the associated pricing and programme? Even though it is out of the scope of this agreement. | It is in scope of this appointment. However, as the design (and costs) have yet to be developed, we are assuming a total (internal) project cost of £2.5m and fees should reflect this. | 2025-08-12
36 | The Internal and external works are broken down in stages: o Internal works  Stage 1: RIBA 0-2: Strategic Definition through to the end of Concept Design (by end of December 2025)  Stage 2: RIBA 3 – 4: Spatial Co-ordination and Technical Design  Stage 3 RIBA 5 – 6: Construction to Use o External Works  Stage 1: RIBA 3 – 4: Spatial Co-ordination and Technical Design  Stage 2: RIBA 5 – 6: Construction to Use Which implies that RIBA 0-2 internal is concurrent with RIBA 3-4 of external (Stage 01). Can you confirm if these stages will run concurrently from October 25 or will the Stage 3 external start after the MEND funding determination in March. I note mention of an initial contract end in December. | Stages 0-2 for the internal works must be completed by December to comply with funding conditions. The external works are currently at RIBA 3 - and planning and Listed Building approvals gratned - with conditions. We anticipate a decision in March for MEND so detailed design (RIBA 4) should begin after the decision. | 2025-08-22
37 | Can you please confirm what time the tender submission deadline is on the 29th August please? In the ITT Part A doc, you state 2pm but in the ITT Part B document, you state 12pm. Please advise. | Thank you for highlighting this error. We will accept submissions up to the later time of 2pm (14:00 hrs). | 2025-08-22
38 | In the ITT Part B doc, section 2.2 (second statement), we are proposing to subcontract the PD services to a different consultant instead of providing the services ourselves as the lead consultant, would that be acceptable please or will we be disqualified? | It is acknowledged that it is unlikely that any one supplier will have all the necessary skills and experience to deliver the total package of works. Accordingly, subcontracting of any elements of the work will be permissible as one of the means of delivering this contract. What the Council will be looking for will be assurances as to how any commercial package which includes more that one legal entity be acheived, in a manner that does not put the Council at a commercial risk. In essence the Council would look to contract with a single legal entity (or individual lead consultant) and for that single legal entity to provide assurances as to the robustness of the onward legal relationship with those partner organisations / sub contractors etc. | 2025-08-22
39 | There doesn’t appear to be a way to register an interest in the bid on the Find a Tender site so we would like to register our interest by e-mail in leading and submitting a bid for this opportunity. | No specific register of interest is set out. If a register of interest is considered to apply please state that as part of the tender submission. All details on how to submit a bit are included in the tender pack that accompanies the notice on Find a Tender, including where to email any submisison to and by when (see also response to question 37). | 2025-08-22
40 | Please confirm whether the closing date for submission is 12:00 or 14:00 on 29/08/2025? (there are two documents in the ITT pack suggesting different times) | Thank you for highlighting this error. We will accept submissions up to the later time of 2pm (14:00 hrs). | 2025-08-22
41 | Is there a comprehensive schedule of structural repairs required available? | Please refer to the condition survey which was included in the tender pack. | 2025-08-22
42 | A review of the Tender documents suggests there are no major structural interventions such as removal of floors, slabs, walls or columns required, nor the introduction of any new similar elements. Please can you confirm if this is correct? | The appointed team are to consder the building as a whole and if the removal of floors, slabs, walls or columns are required to meet the scope of the brief. | 2025-08-22
43 | Should provision be made for structural inspection and appraisal of items that have been mentioned as requiring closer inspection in the ITT information pack and planning documents? | A strucutural engineer is most likely required as part of the team. The condition survey is being updated as a separate appoitment. | 2025-08-22
44 | Could guidance be provided on the upper bound loading criteria to consider for the exhibition space, storage areas and loading bay if any non-standard loads are anticipated? | No, this would need to be an overall consideration of the design and as noted a strucutural engineer is most likely required as part of the team to provide information on this. | 2025-08-22
45 | Is any archive information available on the material properties (mechanical characteristics) of the building structure? | The condition survey is being updated as a separate appoitment and not available at the time of this tender. | 2025-08-22
46 | Could any archive information relating to previous works that involve structural repair, refurbishment, modifications, extensions be made available? | Background documents like this will be provided to the appointed team as part of mobilisation and familiarisation. | 2025-08-22
47 | Has any further survey of bat activity/roosting been undertaken, which the last ecological survey recommended? | No bat survey or any other ecological assessments have been carried out at this stage. | 2025-08-22
48 | As part of the design development, we assume that architectural interventions impacting the external appearance of the building should be avoided. However, could you please confirm whether there is scope to explore architectural interventions affecting the internal spaces that may require additional listed building consent? | Correct, architectural interventions to external spaces where possible should be avoided but we can confirm there would be scope to explore architectural interventions affecting the internal spaces, but note that may require additional listed building consent. | 2025-08-22
49 | Public Toilet Block – It was noted that the public toilet block adjacent to the accessible entrance is under the ownership of Falmouth Council and that clearance of this structure may be possible. Has consideration been given to a replacement facility as part of this proposal? Or should any such considerations be left to individual bidder proposals? | Any such considerations be left to individual bidder proposals. | 2025-08-22
50 | We understand that public consultation will form part of the appointed services. Could you clarify whether a PR company or external consultant will be engaged to support this process, or whether this responsibility lies entirely with the appointed party? Additionally, could you outline the expected level of involvement in community engagement activities? | A PR company or external consultant will be engaged to support this process but it is expected that the design team will be present and provide materials to support this. The end user must be front and centre of design. Consultation will take place throughout the design process. | 2025-08-22
51 | Could you provide a list of the current stakeholders involved in this project, together with any potential future stakeholders we should be aware of? | We are not able to provide this at this stage. | 2025-08-22
52 | Could you confirm who will hold ultimate responsibility for the decision-making process in relation to the tender outcome and subsequent project development? | A Council appointed panel will appraise the returns in line with the criteria set out in the tender pack and the award decision will be taken to committee to appoint the identified preferred supplier. The works themselves will be managed as part of a Council appointed project team. | 2025-08-22
53 | We understand that Part B: Above Threshold Tender Response Document is the principal document required for submission, and that it permits the inclusion of supporting information and documentation. Could you confirm whether any additional forms or mandatory documents are required as part of the tender submission? | No additional forms, other than those stated are required. Therefore, for avoidance of doubt the completed tender submission should be the Part B Above Threshold Reponse Document (with any clearly referenced, relevant and proportional appendices) along with the completed Price Schedule. | 2025-08-22
54 | Can we use our own template for the submission? | No. We would ask all bidders to use the documents provided as part of the tender pack. We will, as set out in response to question 8, accept relevant and proportional appendices - and please also refer to response to question 53. | 2025-08-22
55 | Will the Stage 3-6 works relating the External Fabric repairs be commissioned under the same contract as the Internal works (stages 1-6)? | Yes | 2025-08-22
56 | Will it be possible to visit the site with a member of the procurement team prior to the 29th? | No the opportunity for formal site visits has ended. Design teams can visit the public spaces during open hours but no further set site visits can be accommodated | 2025-08-22
57 | Assuming a full measured survey been undertaken to procure the plans provided in the ITT. Please can you confirm how this information was developed and are you able to provide the original survey information in .dwg format? | The .dwg docs will provided to the successful team. | 2025-08-22
58 | Was a photogrammetry model also procured as part of the survey? | No this is not anticipated | 2025-08-22
59 | Does the council have any employers requirements in terms of improvements to the energy rating of the building, u values etc? | The Council has the aspiration to be net zero by 2030. | 2025-08-22
60 | Does the council wish to include for the design of modern digital infrastructure (augmented reality, blue-tooth audio wayfinding etc) as a method to attract modern and diverse audiences? | This is for the design team to consider and make recommendations given the scope of the project. | 2025-08-22
60 | We understand that there is a requirement for the Lead Designer to appoint a Fire Engineer. We’re experienced in the recommendation, management and co-ordination of fire engineers, however, the terms of our Professional Indemnity Insurance now preclude us from appointing anyone providing fire advice. This is a typical arrangement for PII across the industry in the wake of the Building Safety Act. Therefore would you consider direct client appointment of the fire engineer? | Please included as a sub contractor. The Council is seeking to appoint solely with a Lead Consultant who then brings the to the table the other necessary consultants / professionals and as such the Council will not appoint direct beyond the Lead Consultant. | 2025-08-22
60 | In absence of a fixed design for specialist consultant information such as commercial kitchen design and CCTV, are you happy for us to exclude these design costs at this stage or otherwise provide a provisional sum based on our industry experience? | We would be seeking all anticipated costs to be included as part of the bid submisisons. Therefore in such situations please include as a provisional sum, otherwise additional fees may not be claimed in the future. | 2025-08-22
Clarifications will be published against the Tender Notice on Find a Tender.
If interested in tendering for this project please ensure you add a "watch this notice" for alerts as from time to time additional information or clarifications may be published related to this tender.
It will be the responsibility of Bidders to ensure they are aware of all published clarifications and ensure that their bid has taken these into account.
In the event of any queries please contact: procurement@falmouthtowncouncil.com