## GENERAL
Hollymount Primary School, LB of Merton
LPS Remedials & Footpath Renewal
Contractor Pricing Document
Note: Contractor to note that the Schedule of Works, drawings and appendices take precedence over the descriptions provided in this document and as such these should be priced. This document has been provided in editable format to make it easier for the contractor to insert their costs.
Ref Nr | Item/Description | Item/PC | Cost (£)
Section 1 | Preliminaries
Section 2 | Schedule of Works |  | (price within breakdown below)
A
1 | GENERAL
A | Works relate to the LPS and footpath renewal at Hollymount Primary School. Isolated repairs to the lightning protection system in order to provide a compliant system in accordance with the appended report by the incumbent and replacement of footpath following termination of conductors. Works are expected to take over the October half term 2025.
Should the Contractor believe these timescales cannot be achieved they should provide an alternative programme for each site for review/comment by the CA and Client.
Note: All operatives working within the schools where must hold a valid enhanced DBS Certificate. Evidence will need to be provided and included within the Contractors CPP, with daily records provided to the school on a weekly basis once works are on-site. Contractor will be responsible for developing site logistics plan to ensure segregation with school holiday club.
The Contractor is to note that works are expected to commence by the 18th August 2025 and complete no later than the 29th August 2025.
If this is not possible the Contractor is to provide an alternative achieve programme with their tender return clearly stating the programme length and any long lead-in items which may impact on this being achieved. Likewise if the Contractor believes they are able to complete within a quicker timeframe they should confirm this on the Tender Form and covering letter.
Contractor to allow for developing a sufficient Construction Phase Plan in order for the works to be executed in a safe and professional manner. The Contractor will need to allow for making safe the working areas and compound through use of herras fencing and barriers. Contractor to allow for liaising closely with the site managers of each site on a daily basis. Given scope of works it is assumed that either a floating site supervisor or working foreman will be employed.
The Contractor will NOT be acting as Principal Contractor under the CDM Regulations 2015 and must allow for liaising with the Principal Contractor throughout the project. It is paramount that the Contractor allows for developing a sufficient Construction Phase Plan for the works to be executed in a safe and professional manner.
Services
B | The Contractor will be provided access to the sites water and electrical supply. Meter readings will be taken on the day of works commencing and on completion of works. Although energy will be FoC to the Contractor they will be responsible for utilising efficiently. | Item
Protection
C | All site personnel to wear appropriate PPE and the Contractor is to make an allowance for site protection / access restriction as identified by site RAMS. | Item
D | Waste Materials
| Remove all rubbish and debris from the site from time to time as it accumulates and at the completion of the contract. Leave the site neat and tidy to the satisfaction of the Contract Administrator. A skip may be placed on site in addition to a compound area, in a location to be agreed with the Contract Administrator. | Item
Cleaning
E | The Contractor is expected to leave works areas particularly external areas clean and tidy upon completion of each day’s work. Contactor to lay protection to working areas and where doors are transported across. Providing partial cover over flooring will NOT be acceptable. The Contractor is deemed to have included projection within costs. | Item
Parking/ Storage
F | The Contractor will be provided with the area highlighted on the appended logistics plan for parking and storage. The surrounding roads to each site are a mixture of restricted, no parking costs incurred on these roads will be reimbursed to contractors or subcontractors. The Contractor must not block vehicles movements or fire escapes at any time and must move their vehicles as necessary upon any reasonable request from the Client, other contractors or maintenance teams working on site. | Item
Access
G | The site is located in a residential areas of Wimbledon, South London, with major roads and public transport network within close vicinity. The Contractor is to undertake a full photographic record of the site access, delivery and communal areas, including the route to the work site and submit to the Contract Administrator prior to commencement. | Item
Contractor to allow for developing a sufficient Construction Phase Plan in order for the works to be executed in a safe and professional manner. The Contractor will need to allow for making safe the site from the adjacent school site through use of herras fencing.
The Contractor will be responsible for developing the Construction Phase Plan following appointment to detail how they will safely execute the works and manage the site.
Note: As such it is paramount that the Contractor ensures the access into the site is not obstructed at any time during the course of the works.
Note: The end-user will NOT be expected to take deliveries on behalf of the Contractor.
Handover Documents
H | The Contractor must collate all required Handover Documentation as the work proceeds, submitting to the Contract Administrator all information requested by McBains by the completion date to enable Practical Completion to be issued. | Item
| Working Hours | Item
I | Normal working hours are expected to be Monday to Friday 7.30am – 6.00pm. It is expected that the Contractor will be given keys to access the working areas/site and as such will be responsible for locking up at the end of each working day.
With regards to noisy works the Contractor will need to undertake within normal working hours Monday to Friday to ensure no disruption to adjoining properties at weekends.
Welfare Facilities
J | Contractor will be provided with a designated toilet and room for welfare within the school. Contractor will be responsible for ensuring it is left clean and tidy at all times. | Item
Note: The Contractor is expected to develop the site logistics plan at tender return stage. This is to ensure that a practical and acceptable approach is provided.
The Contractor will be able to make use of existing services on site but will however be responsible for making all connections and ensuring these have been carried out safely (no trip hazards etc).
Health and Safety
K | It is considered that due to the nature of the works and anticipated contract period these works will NOT be notifiable under the CDM Regulations 2015. As such the Contractor is to allow for providing all necessary information for the compilation of the Health and Safety Folder, in addition to providing a Construction Health and Safety Plan to the satisfaction of the Principal Designer prior to works starting on site. The Contractor is to review any existing building plans/health & safety documentation prior to starting the works. Asbestos information has been appended to the tender documents. A Pre-Construction Information Document will be issued to all tendering Contractors during the tender period. | Item
Security
L | The Contractor shall ensure that the building is left secure at all times. Should there be any security issues during the scheme the Contractor should notify the Client. | Item
The Contractor will be responsible for ensuring the site/compound is secure throughout the duration of the works, including buildings where welfare/storage is provided and will be responsible for any loss of materials from site. As such it is advised that materials/items of value be brought to site on day of install etc.
Note: The Client will not be responsible for any loss or damage caused where utilising existing buildings for these purposes.
Preliminaries
M | Allow here for all contractors’ preliminary costs for undertaking these works. Please append a breakdown to reflect breakdown in terms of site management, contracts management, H&S supervision, welfare, IT, allowance for consumables etc. | Item
Qualifications
N | Main Contractors must be able to demonstrate experience of acting as Main Contractor within the education sector, providing case studies and references upon request to satisfy the CA's tender evaluation. | Item
| PRELIMINARIES TOTAL | £

## HOLLYMOUNT
Hollymount Primary School, LB of Merton
LPS Remedials & Footpath Renewal
Contractor Pricing Document
Note: Contractor to note that the Schedule of Works, drawings and appendices take precedence over the descriptions provided in this document and as such these should be priced. This document has been provided in editable format to make it easier for the contractor to insert their costs.
Ref Nr | Item/Description | Item/PC | Cost (£)
Section 1 | Preliminaries
Section 2 | Schedule of Works |  | (price within breakdown below)
B | HOLLYMOUNT PRIMARY SCHOOL
1 | STRIP OUT
i | Prior to works commencing the Contractor is to allow for isolating all services to the working areas to minimise hazards. | Item
ii | Following suitable access being provided, Contractor is to allow for stripping and disposing of all existing concrete pavings along the footpath beneath the flank of the building to be resurfaced, circa 90m2 as shown on the plans. | Item
iii | Contractor to allow for stripping out and disposing of defective conductors and rods to the lightning protection system where required. | Item
iv | Contractor to allow for removing and setting aside with care all existing loose street furniture to the footpath prior to working and then reinstating on completion. Protection to be provided around all fixed furniture which cannot be removed such as balustrade posts prior to commencing works and removing on completion, ensuring that no damage is caused. | Item
2 | LIGHTNING PROTECTION SYSTEM
A | In accordance with the appended report provided by Cuttings, the Contractor is to allow for undertaking repairs to the Lightning Protection System, in order to provide a compliant and operational LPS. | Item
To 3.nr locations (6,7 & 9) along the flank of the pitched roof, allowing to renew earthing rods and termination within the ground inc new termination pit/box, in accordance with report from incumbent Cuttings, allow to renew rods inc termination within ground, in accordance with BS EN 62305.
Contractor to employ an LPS specialist to undertake works and provide evidence of their accreditation.
B | Contractor to provide a cost for providing surge protection to the mains incoming electrical supply through installation of a Type 1 device in accordance with BS EN 62305. | Item
C | Contractor to allow the Provisional Sum in relation to any further works to the LPS to be instructed by the CA. | PC SUM | 1500
D | On completion of remedial works, Contractor to allow the incumbent LPS provider, Cuttings, to attend site and test the rectified system to ensure pass if given. | Item
3 | RENEWAL OF FOOTPATH
A | Prior to excavating, Contractor to undertake CAT scan to the working area in order to determine if any buried services are located beneath. | Item
B | Should any buried services be located beneath Contractor to allow Provisional Sum for instruction by the CA. | PC SUM | 1500
C | Following Contractor to excavate down 125mm to provide a level surface, ensuring compact using wacker plate and laid to slight fall away from building towards new pin kerb/to suit existing falls/drainage on-site. Pin Kerb to only be provided where soft surface is provided adjacent, i.e. not where brick planters and brick dwarf walls are etc. | Item
D | To the edge of the new footpath opposite the elevation Contractor to lay new concrete flat edge pin kerbs, 150mm x 50mm x 915mm, to the perimeter in full. Contractor to make good excavated areas to surround following install and ensure soft ground is compacted sufficiently. | Item
E | Contractor to lay new 125mm tarmac system inc of 75mm sub base, 30mm binder and 20mm wearing course, allowing to detail upto the brickwork of building elevation, new pin kerbs and around the tree planter. To be laid to suit existing falls provided to the footpath to suit ground levels/drainage. Contractor to note new surface extends to areas currently paved only. Note: Hot lay asphalt to be used with roller, cold lay will not be accepted! | Item
F | To the surround of the trees the Contractor is to lay a flexible resin system complete with galvanised trim in black in order to allow movement without compromising either the tree's health or the condition of the new tarmac surface. Contractor to supply and install Rose Garden 2.5mm blend aggregate manufactured by Resco Resin in accordance with manufacturers recommendations, ensuring that a fluish surface is provided on completion, neatly detailed within the planter bed and against the trim. | Item
4 | MISCELLANEOUS
A | Contractor to allow for a builders clean and sparkle clean on completion of all working areas and external areas to ensure that sufficient cleanliness is provided at handover to the Client. Contractor to also allow for thorough clean of all associated external areas in relation to site setup/access on completion. Contractor to make good all soft and hardstandings following dismantling of access and site setup to ensure in the same condition as prior to works undertaken. | Item
On completion of all works the Contractor is to make good all surrounding/landscaped areas such as existing surfaces so that areas are left tidy and presentable on completion.
Note: It is advised that the Contractor undertakes a Schedule of Condition prior to commencing works to use a reference at a later date.
B | Contractor to allow for the Contingency Sum to be expended by the Contract Administrator. | PROV | 3000
| SCHEDULE OF WORKS |  | £
SUMMARY
1 | STRIP OUT
2 | LIGHTNING PROTECTION SYSTEM
3 | FOOTPATH RENEWAL
4 | MISCELLANEOUS
HOLLYMOUNT SOW TOTAL
1 | PRELIMINARIES TOTAL | £
2 | SOW TOTAL | £
| TOTAL | £