## GENERAL
Singlegate Primary School and Abbotsbury Primary School
Structural and External Repairs
Contractor Pricing Document
Note: Contractor to note that the Schedule of Works, drawings and appendices take precedence over the descriptions provided in this document and as such these should be priced. This document has been provided in editable format to make it easier for the contractor to insert their costs.
Ref Nr | Item/Description | Item/PC | Cost (£)
Section 1 | Preliminaries
Section 2 | Schedule of Works |  | (price within breakdown below)
1 | GENERAL
A | The works relate to the proposed structural and external remedial works to be undertaken at Singlegate Primary School and Abbotsbury Primary School, over and around the October half term 2025. Works at Singlegate relate to isolated underpinning and helical bar repairs to remedy subsidence issues. Works at Abbotsbury relate to rectifying a damp slab to the main Office and repairs to the retaining dwarf brick walls to the rear entrance. Works will be undertaken both during and after the October half term however there will be children on-site due to holiday activity clubs so the Contractor will need to pay particular attention to developing the logistics plan to ensure risks are mitigated. Close liaison with the end user throughout will be required. ALL operatives must hold a valid Enhanced DBS Certificate to be provided to the CA/End-User in good time prior to works commencing. These should be provided for management inc site supervision at issue of tender returns.
Contractor will be required to design and erect/dismantle suitable high level access as detailed within the document.
All operatives must hold valid DBS enhanced certificates. Proof of which should be provided upfront in good time prior to works commencing. Should scaffold remain come the start of term the Contractor will need to allow for striking outside of term time hours, i.e. 8.30am-3.3pm Monday to Friday. Contractor should allow this within their pricing return.
The Contractor will be required to develop a suitable Construction Phase Plan and RAMS to mitigate risk and make sure that the prescribed works are executed in a safe and professional manner. These documents are to be submitted for review to the Principal Designer before works commence on site.
The Contractor will be provided with use of welfare facilities at each site which they must protect and give back in the same condition on completion. Contractor to allow for providing a condition survey prior to works commencing. The Main Contractor will be provided with a section of the car park and/or playground as shown within the Logistics Plan for waste, storage etc. Contractor to develop and provide as part of their tender submission for review.
Note: Any area made available to the Contractor for site set up and storage, including external areas, must be cleaned and returned to the Client in the same condition in which it was found prior to works commencing on site. On completion of all works and prior to the Practical Completion Certificate being issued, the Contractor will be responsible for removing all waste resulting from the works and thoroughly cleaning down all working/site setup areas to ensure tidy and left in condition as prior to works commencing.
Services
B | The Contractor will be provided access to the sites water and electrical supply. Meter readings will be taken on the day of works commencing and on completion of works. Although energy will be FoC to the Contractor they will be responsible for utilising efficiently. | Item
Protection
C | All site personnel to wear appropriate PPE and the Contractor is to make an allowance for site protection / access restriction as identified by site RAMS. | Item
D | Waste Materials
| Remove all rubbish and debris from the site from time to time as it accumulates and at the completion of the contract, particularly given the tight confines of the site and setup area. Leave the site neat and tidy to the satisfaction of the Contract Administrator. A skip may be placed on site to the compound area and also car park providing outside of term time when assume main strip will be undertaken, in a location to be agreed with the Contract Administrator. | Item
Cleaning
E | The Contractor is expected to leave works areas clean and tidy upon completion of each day’s work. | Item
Parking/ Storage
F | The Contractor will be provided with parking on-site during the summer holiday period. During term time only 2 parking bays per site will be provided. The Contractor will be given a fob to access the site and will be responsible for ensuring secure at all times. The Client will not be reimbursing the Contractor for parking. Street parking around the site is a mixture of restricted and unrestricted. | Item
Access
G | The sites are located within urban residential areas around 2 miles apart within the Morden area of South London, with various amenities nearby. Access to the sites and direct working area can be made from main roads and residential roads, with both national rail and underground stations within a 5 minute walk. | Item
The Contractor will be responsible for timing deliveries in order to limit disruption to the neighbours, schools and surrounding roads. No major deliveries should be made between 8.30-9.30am and 2.30-3.30pm. Particular effort should be made to ensure that deliveries avoid the busy morning and late afternoon rush hour periods in order to appease the neighbours. Where required a Banksman should be used by the Main Contractor for particular deliveries with details to be provided within their Construction Phase Plan prior to works commencing.
The Contractor will be responsible for developing the Construction Phase Plan following appointment to detail how they will safely execute the works and manage the site, with both schools being consulted with.
Note: As such it is paramount that the Contractor ensures the access into the neighbouring properties and schools is not obstructed at any time during the course of the works.
Note: The Client will NOT be expected to take deliveries on behalf of the Contractor.
Handover Documents
H | The Contractor must collate all required Handover Documentation as the work proceeds, submitting to the Contract Administrator all information requested by McBains by the completion date to enable Practical Completion to be issued. | Item
| Working Hours | Item
I | As previously detailed, given the Client’s requirements for works to be completed within a quick timeframe, Contractors are expected to price the works on the basis of normal working hours however if unable to strike scaffolding in full before the start of term in early September, the Contractor will need to allow for striking outside of term time hours of 8.30-3.30 Mon-Friday at their own cost.
Normal working hours are expected to be Monday to Friday 7.30am – 6.00pm. It is expected that the Contractor will be given keys to access the property. As such the Contractor will be responsible for securing the site on commencement of works and upto issue of the PC Certificate.
With regards to noisy works the Contractor will need to try and warn the neighbouring properties in advance as to ensure relations are maintained throughout the project. The Contractor will need to allow for adapting their activities to reflect where required.
Welfare Facilities
J | The Contractor will be responsible for developing the appended Logistics Plans to ensure a practical approach can be taken. Contractor will be provided with a designated toilet at each site which they must hand back in the same condition as prior to works commencing and clean on a regular basis, provide protection etc. | Item
Note: The Contractor is expected to develop the site logistics plan at tender return stage so that this can be assessed as part of the qualitive tender return. This is to ensure that a practical and acceptable approach is provided.
The Contractor will be able to make use of existing services on sites but will however be responsible for making all connections and ensuring these have been carried out safely (no trip hazards etc).
Health and Safety
K | It is considered that due to the nature of the works and anticipated contract period these works will NOT be notifiable under the CDM Regulations 2015. As such the Contractor is to allow for providing all necessary information for the compilation of the Health and Safety Folder, in addition to providing a Construction Health and Safety Plan to the satisfaction of the Principal Designer prior to works starting on site. The Contractor is to review any existing building plans/health & safety documentation prior to starting the works. Asbestos information has been appended to the tender documents. A Pre-Construction Information Document will be issued to all tendering Contractors during the tender period. | Item
During the Construction phase and as works progress, the Contractor is expected to act as Principal Contractor and supply all required method statements/obtain from sub-contractors where applicable, to the satisfaction of the Principal Designer, including collation of information from the named underpinning sub-contractor. The Principal Contractor will be responsible for amending their Construction Phase Plan if required during the progress of works and the collation and submission of Health & Safety File on completion of the works to the satisfaction of the Principal Designer. The Principal Designer will be responsible for issuing all F10 notices to the HSE and distributing to all relevant parties.
Security
L | The Contractor shall ensure that the building is left secure at all times. Should there be any security issues during the scheme the Contractor should notify the end-user, assume Caretaker, in the first instance. | Item
The Contractor will be responsible for ensuring the site/compound is secure throughout the duration of the works, including buildings where welfare/storage is provided and will be responsible for any loss of materials from site. As such it is advised that materials/items of value be brought to site on day of install etc.
Note: The Client will not be responsible for any loss or damage caused where utilising existing buildings for these purposes.
Preliminaries
M | Allow here for all contractors’ preliminary costs for undertaking these works. Please append a breakdown to reflect breakdown in terms of site management, contracts management, H&S supervision, welfare, IT, allowance for consumables etc. | Item
Qualifications
N | Please provide details of at least 2 recent school roof refurbishment projects you have delivered as Main Contractor.
1 | TOTAL

## SINGLEGATE
Singlegate Primary School & Abbotsbury Primary School
Structural and External Repairs
Contractor Pricing Document
Note: Contractor to note that the Schedule of Works, drawings and appendices take precedence over the descriptions provided in this document and as such these should be priced. This document has been provided in editable format to make it easier for the contractor to insert their costs.
Ref Nr | Item/Description | Item/PC | Cost (£)
Section 1 | Preliminaries
Section 2 | Schedule of Works - SINGLEGATE PRIMARY SCHOOL |  | (price within breakdown below)
1 | ENABLING WORKS
i | Prior to works commencing the Contractor is to allow for isolating all services to the working areas to minimise hazards and providing temporary services to working areas in a safe manner, ensuring no trailing leads or cables that can be accessed by pupils. | Item
ii | Contractor to allow for carefully removing and setting aside for later re-planting any plants to the border to the working area prior to removing and setting aside soil, inc kerbs. | Item
iii | Contractor to allow for appointment of incumbent lightning protection contractor () in terms of attending site, carefully taking up existing conductors and termination bars and for reinstating on completion with new pit. NOTE QUOTE TO BE ISSUED DURING TENDER PERIOD. | Item
iv | Contractor to allow for all plant and protection in connection with the works, inc herras fencing and barriers to working areas. | Item
2 | STRUCTURAL WORKS
A | In connection with the initial design indicated within the appended drawings provided by the Structural Engineer, the Contractor is to allow for developing the design and undertaking the proposed underpinning works to the Edgware Classroom in order to address the movement issues. Contractor to allow for all works as indicated within the appended drawings. Contractor should allow cost here for devleoping the design to Construction for review/approval by the Structural Engineer. | Item
B | Contractor to allow for excavating and removing from site all soil and debris. | Item
| Contractor to allow for temporary supports and shoring as part of the works. | Item
C | Undertake underpinning works using mass concrete using hit and miss sequencing as per the Structural Engineers details. | Item
D | On completion of underpinning works Contractor to allow for making good tarmac to using hot melt mix and thoroughly compacting and existing falls are reinstated away from the building. Contractor to reinstate planter inc brick kerbs, soil and existing plants. | Item
E | Contractor to allow for undertaking helical bar repairs to the affected areas of brickwork to working area in accordance with Structural Engineers details and manufacturers recommendations. For pricing purposes Contractor to allow for 12lm of helical bar repairs. | PC QUANT
F | Should any further masonry repairs be required, Contractor to allow for raking out defective brickwork joints as directed on site by the Contract Administrator and repoint using a cement mortar mix (1 part cement to 3 parts sand), to match existing colour and profile. Areas of repointing will be identified once full access has been provided. For pricing purposes, allow to repoint 5m2 of defective pointing to brickwork in isolated areas. | PC QUANT
G | On completion allow to thoroughly clean down brickwork, glazing in frames and hardstanding to working areas to the satisfaction of the CA. | Item
H | Contractor to rake out defective brickwork joints as directed on site by the Contract Administrator and repoint using a cement mortar mix (1 part cement to 3 parts sand), to match existing colour and profile. Areas of repointing will be identified once full access has been provided. For pricing purposes, allow to repoint 10m2 of defective pointing to brickwork in isolated areas. | PC QUANT
I | Contractor to allow PC Sum for any further external repairs identified. | PC SUM | 1500
3 | DRAINAGE
A | Contractor to allow appointing the Named Sub Contractor DW Solutions Ltd in relation to their CCTV drainage report and corresponding quotation appended. Contractor to allow for their appointment, managing them, making payment and reviewing their work as progresses. Contractor to allow for OHP on top of their appended quote. | Item
B | Should any further works be required Contractor to allow PC Sum to be expended by the CA. | PC SUM | 1500
C | Contractor shall ensure that all manholes are safely removed and reinstated particularly where the astroturf surface is proved so that no damage is caused. | Item
D | On completion provide clean CCTV report to confirm repairs completed. Ensure the Contractor cleans down all working areas and hardstanding on completion. | Item
4 | MISC
A | Internally Contractor will be require to undertake redecoration to affected wall surfaces such as to the Classroom and Hall. For pricing purposes Contractor to allow for filling all cracks and redecorating using an undercoat and 2.nr finishing coats of Dulux Trade Emulsion to the 2.nr external wall surfaces within the Edgware Classroom and 1.nr external wall within the Hall. Contractor to allow for providing protection to floor, display boards etc. Ensure surfaces left clean on completion. | Item
B | Contractor to allow the PC Sum of £1,000.00 for any further works internally to be instructed by the CA. | PC SUM | 1000
C | Should the existing bush be unable to be replanted, Contractor to allow PC Sum to be expended by the CA in relation to new planting to the border to be reinstated. | PC SUM | 750
D | Contractor to allow for the Contingency Sum to be expended by the Contract Administrator. | PROV | 4000
2 | SINGLEGATE PRIMARY SCHOOL ROOFING REMEDIALS |  | £
SUMMARY
1 | ENABLING WORKS
2 | STRUCTURAL WORKS
3 | DRAINAGE
4 | MISCELLANEOUS
2 | SINGLEGATE TOTAL

## ABBOTSBURY
Singlegate Primary School & Abbotsbury Primary School
Structural and External Repairs
Contractor Pricing Document
Note: Contractor to note that the Schedule of Works, drawings and appendices take precedence over the descriptions provided in this document and as such these should be priced. This document has been provided in editable format to make it easier for the contractor to insert their costs.
Ref Nr | Item/Description | Item/PC | Cost (£)
Section 1 | Preliminaries
Section 3 | Schedule of Works - ABBOTSBURY PRIMARY SCHOOL |  | (price within breakdown below)
1 | ENABLING WORKS
i | Prior to works commencing the Contractor is to allow for isolating all services to the working areas to minimise hazards and providing temporary services to working areas in a safe manner, ensuring no trailing leads or cables that can be accessed by pupils. | Item
ii | Prior to works commencing on site Contractor will be required to undertake a GPR survey of the floor in the Office to determine if there are any buried pipes or redundant pipes within which may be contributing to the issues identified, with survey results to be shared with the CA. Contractor to allow for removing the desk and reinstating on completion, ensuring that equipment is removed prior. | Item
iii | Following appointment Contractor to allow for instructing an Arboculturalist to survey the front of the site, say 12.nr trees in total, for review and instruction. | Item
iv | Contractor to allow PC Sum of £1,500 in relation to recommendations of the Arb consultant. | PC SUM | 1500
2 | WORKS TO OFFICE
A | Prior to undertaking works Contractor to allow for safely disconnecting all electrical equipment prior to removing all desks, equipment, storage units and chairs etc, allowing to set aside within adjoining area and reinstating on completion of works. | Item
ii | Contractor to allow for stripping up and disposing of existing carpet tiles and breaking out existing screed. | Item
iii | Should any services within the slab be identified Contractor to allow PC Sum to be expended by the CA. | PC SUM | 1500
iv | Contractor is to allow for preparing existing concrete floor surface prior to applying new DPM screed to ensure that a level finish free of moisture is provided. Contractor will be required to demonstrate floor surface is free of moisture prior to applying latex to ensure level. | Item
V | On completion allow to renew carpet tiles with matching new supplied by Heckmondwike Supacord. Install in accordance with manufacturer instructions and include for adhesive wastage, stainless steel transition and threshold strip bars. Colour to be confirmed. Include for all adhesives and the like and threshold strips as required. Allow for all cutting and waste, for dressing the flooring upto the existing skirting boards. | Item
vi | Allow to apply 2.nr finishing coats of Dulux Trade Diamond Gloss in white to the skirtings. | Item
3 | BRICK WALL REPAIRS
i | To the dwarf brick wall to the secondary entrance footpath, the Contractor will be required to remove and set aside for reuse the brick on edge detail prior to works being undertaken in order to put into a good state of repair. Contractor to allow for cleaning and removing excess mortar and staining from brick surfaces, using suitable methods to restore appearance without damaging the bricks. | Item
ii | To all junctions of the wall where this a change in height, the Contractor will be required to install new flexible movement joint and correctly detail to the satisfaction of the CA. | Item
iii | Contractor to allow for chasing out new weep holes to the brickwork where staining is present in order to allow passage of water within the ground above. Contractor to allow for providing weep holes at 600-800mm intervals to either side of the footpath laid to a slight fall towards tithe footpath. | Item
iv | Contractor to allow for reinstating brick on edge bull nose bricks on completion laying a new bed of cement. Contractor to allow for renewing all damaged bricks with matching new. | Item
v | Contractor to rake out defective brickwork joints as directed on site by the Contract Administrator and repoint using a cement mortar mix (1 part cement to 3 parts sand), to match existing colour and profile. Areas of repointing will be identified once full access has been provided. For pricing purposes, allow to repoint 8m2 of defective pointing to brickwork in isolated areas. | PC QUANT
vi | Contractor to provisionally allow for undertaking helical bar repairs to areas where movement is identified in accordance with the engineers details appended. For pricing purposes Contractor to allow for undertaking 6lm of helical bar repairs and repoint on completion using matching mix. | PC QUANT
vii | On completion of works Contractor to allow for redecorating the nosing's of all steps using an external grade reflective road line marking paint. Contractor to thoroughly clean down existing surfaces before applying 3.nr coats. | Item
viii | Contractor to allow PC Sum to be expended by the CA in relation to any additional masonry repairs deemed required. | PC SUM | 2000
4 | MISCELLANEOUS
A | Contractor to allow for a builders clean and sparkle clean on completion of all working areas and externals to ensure that sufficient cleanliness is provided at handover to the Client, inc intern al areas where isolated works have been undertaken. Contractor to also allow for thorough clean of all associated external areas in relation to site setup/access on completion. Contractor to make good all soft and hardstandings following dismantling of scaffolding and site setup to ensure in the same condition as prior to works undertaken. | Item
On completion of all works the Contractor is to make good all surrounding/landscaped areas such as existing surfaces so that areas are left tidy and presentable on completion.
Note: It is advised that the Contractor undertakes a Schedule of Condition prior to commencing works to use a reference at a later date.
B | Contractor to allow for the Contingency Sum to be expended by the Contract Administrator. | PROV | 2000
3 | ABBOTSBURY PRIMARY SCHOOL |  | £
SUMMARY
1 | ENABLING WORKS
2 | WORKS TO OFFICE
3 | BRICK WALL REPAIRS
4 | MISCELLANEOUS
3 | ABBOTSBURY TOTAL

## PRICING SUMMARY
Singlegate Primary School & Abbotsbury Primary School
Structural and External Repairs
Contractor Pricing Document
| PRICING SUMMARY | £
1 | Preliminaries
2 | Singlegate Primary School Schedule of Works
3 | Abbotsbury Primary School Schedule of Works
TOTAL