# Annex A

| Title of Project | Wyville Thomson Ridge (0924S) Imagery Analysis |
| --- | --- |
| Date and Time for Return of Bids | 10 November 2025 @09:00/14:00 Hours (UK) |
| Contract Reference Number | Provided by Procurement team C25-0877-2114 |
| Address for Bid Submission | 1 electronic copy to be sent to TenderResponse@jncc.gov.uk PLEASE DO NOT SEND BIDS DIRECTLY TO (name of project officers) OR A MEMBER OF THE JNCC PROCUREMENT TEAM VIA THEIR WORK EMAIL ADDRESSES AS THIS WILL INVALIDATE YOUR BID. Bids must be less than 10 MB in size. On receipt of your bid, you will receive an automated e-mail to confirm receipt by the JNCC Support Co. If you do not receive this automated email, please contact the number below; (00 44 1733 866 988) |
| Contacts for Technical Information relating to this Project Specification | Procurement Team Joint Nature Conservation Committee Email: contractqueries@jncc.gov.uk Telephone: 01733 562626 |
| Contact for Queries Regarding the Procurement Procedure | Procurement Team Joint Nature Conservation Committee Email: contractqueries@jncc.gov.uk Telephone: 01733 562626 |
| Proposed Start Date | 20th November 2025 |
| Proposed End Date | 16th March 2026 |

Wyville Thomson Ridge (0924S) Imagery Analysis

Contents

1.	Joint Nature Conservation Committee	3

2.	Project Aims	3

3.	Project Background	4

4.	Project Objectives	9

5.	Project Objectives: Detailed Tasks	10

6.	Outputs	17

7.	Product Specification	18

8.	Dissemination	19

9.	Timescale	19

10.	Health and Safety	20

11.	Project Management	21

12.	Instructions for Bid Submission	21

13.	Evaluation Criteria	23

14.	Payment	25

15.	Additional Requirements	25

16.	Procurement Timetable (which may be subject to change)	25

Appendix A: BIIGLE still image protocol (adapted from Cefas BIIGLE protocol)	26

Appendix B: Stony Reef Analysis	29

Appendix C: Non-indigenous species (after Curtis et al, 2020)	32

## Joint Nature Conservation Committee

The Joint Nature Conservation Committee (JNCC) is the statutory adviser to the UK Government and devolved administrations on UK and international nature conservation

Our role is to provide scientific evidence, information, and advice to inform decisions to  protect the natural environment. Our specific role is to work on nature conservation issues that affect the UK as a whole and internationally, by:

advising Government on the development and implementation of policies for, or affecting, nature conservation in the UK and internationally;

providing advice and disseminating knowledge on nature conservation issues affecting the UK and internationally;

establishing common standards throughout the UK for nature conservation, including monitoring, research, and the analysis of results; and

commissioning or supporting research which it deems relevant to these functions.

Background to JNCC can be found on JNCC’s website at: https://jncc.gov.uk/about-jncc/

## Project Aims

JNCC wishes to commission a contract to undertake the analysis of seabed imagery (still images and video) collected on the 0924S survey from a drop-frame camera. Seabed imagery will be analysed using the image and video annotation software BIIGLE. During 0924S, imagery data was collected for MPA monitoring purposes.

The total number of sampled drop-camera stations was 80; circa 38 hours of high-definition video. Due to technical difficulties, the camera had to be restarted during 4 transects, resulting in multiple videos for these transects, giving a total of 85 videos to be analysed. Videos from one transect should be analysed together. A total of 3,530 still images were collected across 79 of the drop-camera stations.

More detailed metadata will be provided including information from logs and the survey report. Throughout the tender process, guest access to the 2024 BIIGLE project will be provided to allow review of the available images. The successful contractor will be provided with access to the 2024 BIIGLE project and the annotated 2018 WTR seabed imagery to aid with identification.

Please note that experience in the identification of deep-sea taxa is required to complete this contract.

The bid submission should clearly state which of the following options are being bid for, please provide a quote for either option 1, 2 or 3:

Option 1

Video analysis, please provide a quote for the cost and breakdown per video hour

Option 2

Stills analysis, please provide a quote for the cost and breakdown of the number of stills

Option 3

Video analysis and stills analysis, please provide a quote for complete analysis of all imagery (video and stills), breaking down the costs as per options 1 and 2.

## Project Background

JNCC and the Marine Directorate of the Scottish Government (MD) conducted a survey aboard MRV Scotia (0924S) in 2024 to gather evidence to monitor Wyville Thomson Ridge Special Area of Conservation (WTR) (Figure 1) and inform assessment of the extent and condition of the designated features of the site. A survey of WTR was conducted in 2017/18, but the 0924S survey will form the first monitoring point (T0) in the time series at WTR.

WTR is located to the northwest of mainland Scotland at the northern end of the Rockall Trough, with the closest land approximately 77 km away at Rona, Scotland. The site has an area of 1,740 km2 and a depth range of 350 m to 1000 m. The designated features of WTR are listed in Table 1. Further information on WTR can be found at the JNCC site information centre https://jncc.gov.uk/our-work/wyville-thomson-ridge-mpa/.

Figure 1. Map showing Wyville Thomson Ridge SAC boundary and bathymetry data from EMODnet 2022.

Table 1. Designated features of Wyville Thomson Ridge SAC.

| Feature | Feature type |
| --- | --- |
| 1170 Reefs | Annex I Habitat |

### Annex I Reef

Reefs are formed by biogenic concretions or non-biogenic substrata, which arise from the seafloor and so are topographically distinct from their surroundings (European Commission 2013a). They are generally found in the subtidal zone but may extend in a broken transition into the intertidal zone. Annex I reefs include biogenic reefs, bedrock reefs and stony reefs.

The UK has a greater range and extent of rocky reefs than biogenic reefs, and rocky reefs are extremely variable in their structure and in the communities they support (Brown et al. 1997). They range from vertical rock walls to horizontal ledges, sloping or flat bed rock, broken rock, boulder fields, and aggregations of cobbles. A variety of invertebrates can inhabit rocky reefs, including sponges, corals, and sea squirts, which attach to the rock surface. Mobile species, such as fish, lobsters and crustaceans, may also use rocky reefs for shelter. Both types of rocky reefs – bedrock reefs and stony reefs – are protected features within WTR.

### Bedrock reef

Bedrock reef occurs where the bedrock that underlies surface sediments on the seafloor arises from the surrounding seabed, creating a habitat that is colonised by many different marine animals and plants. Bedrock is consolidated rock and can be composed of most rock types (granite, limestone, sandstone etc.).

### Stony reef

Stony reef occurs where 10% or more of the seabed substratum are composed of particles greater than 64 mm across, i.e. cobbles and boulders (European Commission 2013a). The remaining supporting ‘matrix’ could be of smaller sized material. The reef may be consistent in its coverage or it may form patches with intervening areas of finer sediment. Epifaunal species dominate biological cover. Stony reef should be topographically distinct from the surrounding sea floor with a minimum area of 25 m2 (this also applies to the total area of a patchy reef) (Irving, 2009).

Iceberg ploughmarks can be considered as a special type of stony reef. They occur along the UK continental shelf edge off northern and western Scotland, including in WTR (Irving 2009). Iceberg ‘ploughmarks’ consist of ridges of boulders, cobbles and gravel where finer sediments have been winnowed away by high energy currents at the site, interspersed with finer sediment troughs up to 5 -10 m deep (Masson et al., 2000). They are thought to have been formed by the ploughing movement of icebergs through the seabed at the end of the last ice age. The iceberg ploughmarks in WTR are stable and consolidated and have been classified as stony reef (Irving 2009).

Although the Irving (2009) stony reef criteria can be applied in WTR, as iceberg ploughmark Annex I Reef is a special case of Annex I stony reef, regardless of the substrate present, the area identified as iceberg ploughmarks is considered to be Annex I Reef. The patchy nature of stony substrate within the wider iceberg ploughmark area results in a small-scale mosaic of stony and non-stony substrate of the seabed. Hence, small scale variation in the presence or absence of stony reef substratum can occur within the wider Annex I Reef area.

### Biogenic reef

Biogenic reefs are made up of hard matter, formed by animals themselves. The reef structure can be composed of the reef-building organism (including its tubes or shells), or it may also be composed of sediments, stones and shells that the organism has bond together. In the deep sea, the main species that form biogenic reefs include cold-water corals (e.g. Lophelia pertusa, Madrepora oculata and Solenosmilia variabilis). Biogenic reefs can provide complex habitats for species assemblages, such as for sponges, bryozoans, and sea squirts.

### WTR 2024 Survey (0924S)

The 0924S survey departed from Aberdeen on the 23rd of July 2024 and returned to Aberdeen on the 12th of August 2024. Data from this survey will form the first time point (T0) of a monitoring series. The monitoring aims and objectives of survey 0924S relating to seabed imagery are:

  - Collect evidence to inform type one (sentinel) monitoring of the structure and function of Annex I Reef at WTR SAC.

  - Collect evidence to inform the physical extent and distribution of the Annex I Reef within WTR SAC.

Imagery was collected with a drop-frame camera (DC) system, towed by the vessel at a target speed of 0.5 knots and a target altitude of 1 m.

The following instruments were mounted on the drop-frame camera:

- Kongsberg OE 14-408 digital stills camera (10 MP) mounted in a planar (downwards facing) orientation

- High definition SubC 1 Alpha video camera in a planar orientation

- Four-point (green) laser-scaling with the bottom two set to 67 mm spacing

- Additionally: four SEALED lamps, Valeport CTD, Ultra-short Baseline (USBL) acoustic positioning beacon

Sampling during the 0924S survey was stratified by zones and depth. Seven zones were selected for the purposes of sampling design, with seven depth contours chosen from within these zones (Figure 2).

Figure 2. Map showing the seven zones at Wyville Thomson Ridge SAC, depth contours from EMODnet Bathymetry, and the planned DC sampling stations.

Video and stills imagery were collected from 80 stations across the seven depth bands. The 300, 400, 450 and 800 m depth bands were prioritised and all stations at these depths, across all zones, were sampled. It was not possible to sample the 500, 600 and 700 m depth bands in all zones during the survey (Figure 3).

Figure 3. Summary of successfully attempted camera stations at Wyville Thomson Ridge SAC 0924S survey.

At each station, the camera tow was continued until a suitable number of images had been collected. As a result, the length of video tows varies. In total, 38 hours and 13 minutes of video and 3,530 still images will be analysed (Table 2). All imagery will be made available via a BIIGLE project. Access to the imagery via the BIIGLE project can be provided on request to aid in the tendering process (see contacts for technical information on page 1) and more detailed metadata will be provided to the successful contractor following contract award.

The following will be provided to the successful contractor:

- Access to the 2024 BIIGLE project with all stills, videos and label trees.

- Associated metadata including USBL positions

- 2024 WTR cruise report

- Epibiota Quality Assurance Framework Proforma spreadsheets

- Access to the 2017/18 WTR annotation catalogue in BIIGLE

Table 2. Summary of the number of still images and length of video imagery collected on 0924S to be processed as part of this contract.

| Survey site | Equipment type | Stations (n) | Imagery type | Still images (n) | Video length (hh:mm) |
| --- | --- | --- | --- | --- | --- |
| Wyville Thomson Ridge SAC | Drop Camera | 80 | Video and stills | 3,530 | 38:13 |

## Project Objectives

JNCC wishes to commission a contract to undertake the analysis of seabed imagery including video and still imagery from the 0924S survey as set out in the sections below. Analysis of video should be completed first as a priority. The successful contractor will:

- Undertake the analysis as set out below, adhering to the NMBAQC Epibiota interpretation guidelines (Turner et al., 2016).

- Use BIIGLE to annotate video and still images as described below. Alternative image annotation software may be used subject to agreement with the project officer.

- Ensure that still images and video references used in analysis outputs are identical to those used in the naming of the original media to enable future reconciliation between data and media. If identical naming is not possible, a suitable alternative should be sought with JNCC.

- Produce a final analysis report including, at a minimum, sections detailing the methodology, results including results of Annex I Stony Reef analysis, and details of all QA work undertaken with any remedial action deemed necessary. The report should be no longer than 15,000 words including all tables and appendices and be provided electronically via email as a Microsoft Word document.

- Provide substrate and taxonomic image reference collections for each substrate type and taxon identified from imagery.

- (Costed extra) Create a subset of still images annotated in a way suitable to act as training data for artificial intelligence model training as described below

Some information, where specified, may be recorded directly into the proformas provided. The majority will be recorded first into BIIGLE and then used to populate the proforma. No analysis additional to what is described in this document is required. Any deviation from this methodology should be approved in writing by the project officer.

## Project Objectives: Detailed Tasks

### Video Processing

Video should be analysed in BIIGLE using the label trees shown in Table 3. A high-level review should be conducted as described in section 2.1 of Turner et al (2016). Annotations can be added to videos as either tier 1 or tier 2 annotations depending on the label tree used. More details on the video annotation tiers and how they should be applied are provided in Appendix A.

Table 3. Label trees for video annotation and the annotation type which should be used for each label tree.

| Video analysis label tree | Video annotation type |
| --- | --- |
| Segment | Tier 1 |
| Habitat Directive Annex 1 Reef subtypes | Tier 1 |
| Marine Habitat Classification of Britain and Ireland | Tier 1 |
| JNCC image quality | Tier 1 |
| NMBAQC image quality | Tier 1 |
| Annex I Stony Reef Elevation | Tier 1 |
| Annex I Stony Reef Composition | Tier 1 |
| Annex I Stony Reef Presence | Tier 1 |
| Priority Marine Feature Habitats | Tier 1 |
| Stony Reef | Tier 2 |
| Biota | Tier 2 |
| Litter | Tier 2 |
| Anthropogenic | Tier 2 |

Video will be analysed to extract the following information (all information should be recorded using the provided BIIGLE label trees, unless specified otherwise):

- Video should be segmented into areas of continuous seabed habitat type greater than or equal to 5 m which is the equivalent of 1 minute. The segment label should be used to delineate these segments and labels from other trees should be attached to each segment using the “add label” tool in BIIGLE.

- Each segment will be assigned an image quality using labels from two label trees. Further analysis of video segments will be dependent on the image quality score. For example, if a segment is given a score of zero, no further analysis should be carried out for that segment.

  - JNCC image quality, a summary of these labels is shown in Table 4.

  - NMBAQC image quality, a summary of these scores is shown in Table 5 but described in more detail in section 2.1 of Turner et al, (2016).

- A combination of three habitat classifications should be used and a new segment should be started only if either of these habitat classifications changes.

- Habitat Directive Annex 1 Reef subtypes. This label tree contains three labels, Bedrock, Potential Stony, Stony reef, or Not reef. Stony reef replaces Potential Stony after doing a stony reef analysis. See Appendix B for more details on stony reef analysis.

- Marine Habitat Classification of Britain and Ireland level 3 (Broad-scale Habitat). This label tree should be used to assign broad-scale habitats at a minimum of level 3 of the Marine habitat classification of Britain and Ireland hierarchy.

- Use the Marine Habitat Classification of Britain and Ireland to assign biotopes up to level 6 in accordance with Parry (2019)

- Areas classified as potential stony reef will require analysis using the Irving criteria (Appendix B). Two label trees are used to assign the Irving criteria and one label tree to determine the result of the assessment:

- Annex I Stony Reef Elevation. This label tree contains four labels (high elevation, medium elevation, low elevation, elevation is not reef)

- Annex I Stony Reef Composition. This label tree contains four labels (high composition, medium composition, low composition, composition is not reef)

- Annex I Stony Reef Presence. This label tree contains four labels (high, medium, low and not a stony reef) and should be assigned using the conclusions of the Elevation and Composition labels as part of the stony reef analysis.

- Use the Priority Marine Feature Habitats label tree to identify any habitat segments containing the Priority Marine Feature (PMF) habitats listed in Tyler-Walters et al (2016). PMF habitats that may occur in WTR SAC include deep-sea sponge aggregations, coral gardens and cold-water coral reefs. These habitats should be identified using the relevant guidance.

- Use the Biota label tree to label:

  - The first occurrence of fish species that are listed as PMF species (Tyler-Walters et al, 2016)

  - Any non-native species (Appendix C).

- Identify evidence of anthropogenic impacts on the seabed

- Use the litter label tree to record the presence of litter using the categories listed in Annex 5.1 of the Joint Research Centres Guidance on Monitoring of Marine Litter in European Seas.

- Use the Anthropogenic label tree to annotate trawl marks or anthropogenic impacts other than litter. This will not be a complete label tree, and new labels may need to be added to the label tree.

A reference collection of representative images must be provided for each taxon label and discreet BSH identified.

Table 4. JNCC image quality categories

| Imagery quality level | Description |
| --- | --- |
| Fauna | Most fauna can be identified (e.g. including smaller taxa such as brittlestars etc.) |
| Conspicuous fauna | Large and conspicuous fauna can be identified (e.g. sponges, soft corals etc.) |
| Substrate | The substrate type can be identified, but the fauna cannot (e.g. the water column is obscured / the camera is too high off the seabed) |
| Zero | No visibility of the seabed, substrate cannot be reliably identified. |

Table 5. Summary of NMBAQC image quality categories (Turner et al 2016)

The results of the assessment for Annex I Stony Reef using the Irving criteria will then be uploaded into GIS and combined with supplied USBL data to generate a shapefile showing the extent of reef.

### Stills Processing

Stills should be analysed in BIIGLE using the label trees shown in Table 6. Annotations should be added to stills as either tier 1 or tier 2 labels depending on the label tree used. Optionally tier 1 labels may be added directly into the proforma instead of being applied to still images, where this is done it must be consistent (i.e. there should not be a mixture of BIIGLE annotations and proforma entries for JNCC image quality). More details on the still annotation types and how they should be applied are provided in Appendix A.

Table 6. Label trees for still annotation and the annotation type which should be used for each label tree

| Still analysis label tree | Still annotation type |
| --- | --- |
| JNCC image quality | Tier 1 |
| NMBAQC image quality | Tier 1 |
| Biota | Tier 2 |
| Faunal turf | Tier 2 |
| Laser points | Tier 2 |
| Litter | Tier 2 |
| Anthropogenic | Tier 2 |
| Substrate | Tier 1 |

Stills will be analysed to extract the following information:

- Each still will be assigned an Image quality using labels from two label trees. If a still image is given a score of zero (NMBAQC equivalent), no further analysis should be carried out for that segment.

  - JNCC image quality, a summary of these labels is shown in Table 4.

  - NMBAQC image quality, a summary of these scores is shown in Table 5 but described in more detail in section 2.1 of Turner et al 2016.

- Annotate each still using the Morpho-taxa label tree. For each still image, fauna should be identified and quantified using the standardised approach detailed in Appendix D. Where a previously unidentified taxon is observed, the following approaches should be used:

  - Solitary and/or erect epifaunal species present (to the lowest taxonomic level for which identification can be guaranteed) using counts (achieved by using the point annotation tool within BIIGLE).

  - Colonial and/or encrusting epifaunal species present as far as possible (to the lowest taxonomic level for which identification can be guaranteed) using percentage cover (achieved by using the polygon, magic wand, or brush tools within BIIGLE).

  - Special cases, such as where a taxon is present in high densities (i.e. brittle stars, cup corals), may be recorded directly into the tier 1 spreadsheet as an estimate of count, or percentage cover to the nearest 10%.

- Use laser points label tree to annotate lasers and calculate image area in BIIGLE. Analysts are not to use the automated laser detection tool in BIIGLE.

- Identify evidence of anthropogenic impacts on the seabed:

  - Use the litter label tree to record the presence of litter using the categories listed in Annex 5.1 of the Joint Research Centres Guidance on Monitoring of Marine Litter in European Seas.

  - Use the Anthropogenic label tree to annotate trawl marks or anthropogenic impacts other than litter. This will not be a complete label tree and new labels may need to be added to the label tree.

- Use the substrate label tree to record the substrate types present to the nearest 10 percent directly to the proforma

- Any comments from the analyst which are considered of importance can be recorded in a spreadsheet

A reference collection of representative images must be provided for each Biota label and discreet broad-scale habitat identified.

### Developing training data for artificial intelligence

AI deep-learning algorithms have the potential to be applied marine monitoring to detect animals in imagery. Pilot studies have highlighted the need for the development of a high-quality manually annotated dataset composed of images showing the diverse range of UK marine habitats in order to effectively train AI for this purpose.

In addition to providing costs for the analysis described above, please provide quotes for the following preparation of 100 stills from the drop-camera in BIIGLE to form a suitable training dataset for Artificial Intelligence models:

- Using 100 annotated stills (from this contract), convert all annotations into a bounding box. Images of image quality zero (NMBAQC equivalent) should be excluded:

  - All points and polygons must be converted into a rectangle suitable for use in an AI model

  - Example box annotations for fauna annotated with a point will be provided to the successful contractor to enable an average box size (in pixels) to be estimated

- JNCC will select 100 images randomly selected from across the dataset and from varying time points in a transect.

- Re-annotated images will be stored in a separate BIIGLE volume within the 2024 WTR survey project.

Please note that this exercise is intended to be simple and we do not anticipate that it should take a long time to complete.

### Quality Assurance

Following award of the contract, and dependent on the evaluation scores they achieve, unsuccessful bidders may be invited to undertake the independent external QA aspects of this project. Please indicate in your tender if you do not wish to be considered for this work.

Note external QA analysis may be undertaken at same time as primary analysis if preferred by successful contractor and suitable process is agreed with JNCC at start-up meeting.

Internal Quality Assurance process for image and video analysis

A minimum of 10% of still images plus 10% of video transects analysed are to be subject to an internal QA process.

Tenderers must demonstrate their internal Quality Control (QC) system, which includes routine checks of data and analysis.

QC of data and analysis is where data are re-checked and compared against the original and compared to an expected standard/limit of error/deviation from the original.  It is also where electronic records (in spreadsheets or databases) are checked against the data on the original field/laboratory datasheets.  This measures the repeatability of the method of analysis and data entry, and highlights factors such as inter-worker variability.  QC must also include details of remedial action in cases where expected standards/limits are not met.

Internal QC must be undertaken by a staff member other than the staff member who conducted the original analysis

External Quality Assurance process for image and video analysis

A separate contract will be run by JNCC for the external QA process. It will be conducted as described in this section.

10% of still images plus 10% of video transects analysed are to be subject to an independent external QA process.

The following steps will be adhered to:

- Images and video transects to be quality assured will be selected by JNCC;

- The auditing analysts receive the imagery and video data from JNCC and project level identifications (i.e. substrate and taxonomic image reference collections) from the original analyst. Abundance data are not provided to the auditing analysts, to ensure auditing analyst enumeration is undertaken blind;

- The auditing analysts complete the image and video analysis for selected images as described above;

- The results are sent to JNCC and original analysts;

- The original analysts complete the JNCC image and video analysis comparison proforma spreadsheet

- JNCC, the original and the auditing analysts meet to resolve any discrepancies in taxa identification and enumeration to the satisfaction of all parties.

Any remedial action required following the QA process must be completed by the original analysts within an agreed timeframe at no extra cost to the project.

It is the responsibility of the successful contractor to ensure this process is completed before the final delivery of each dataset. All remedial action taken, and associated rationale, are to be agreed with JNCC before being implemented, recorded and provided as outputs of this contract.  All remedial action taken, and associated rationale, are to be recorded and provided as outputs of this contract. The contract shall not be deemed complete until this external Quality Assurance step has been completed successfully.

| Party | To provide |  | Format |
| --- | --- | --- | --- |
|  | Image | Video |  |
| JNCC | Image analysis comparison proforma spreadsheet template and review of completed image analysis comparison proforma spreadsheet | Video analysis comparison proforma spreadsheet template and review of completed video analysis comparison proforma spreadsheet | MS Excel spreadsheet MS Word Document |
| Auditing analyst | Results of audit and review of completed image analysis comparison proforma spreadsheet | Results of audit and review of completed video analysis comparison proforma spreadsheet | MS Excel spreadsheet MS Word Document |
| Original analyst | Completed image analysis comparison proforma spreadsheet, review of completed image analysis comparison proforma spreadsheet and summary of all remedial action taken, and associated rationale | Completed video analysis comparison proforma spreadsheet, review of completed video analysis comparison proforma spreadsheet and summary of all remedial action taken, and associated rationale | MS Excel spreadsheet MS Word Document |

## Outputs

JNCC require the successful contractor to provide analysis results in the MEDIN compliant MS Excel proforma spreadsheet which will be provided.

Please note that the Final Report must adhere to the JNCC report template and house style. This will be provided to the successful contractor.

| Output/deliverable | Format |
| --- | --- |
| Video imagery analysis result | BIIGLE CSV reports: Video Annotation Report MEDIN compliant MS Excel spreadsheet (to be populated by contractor) |
| Stills imagery analysis results | BIIGLE CSV reports: Image Label report, “Full” Annotation report Annotation Area Report MEDIN compliant MS Excel spreadsheet (to be populated by contractor) |
| Comparison of analysis and independent analysis and reconciliation | Excel spreadsheet |
| Reference collection of images for each substrate type and taxon identified and metadata spreadsheet. Taxa to be highlighted in image (e.g. using a bounding box) | Still images files labelled with StnCode and substrate type/taxon they represent |
| Reference collection of video clips for each broad-scale habitat and biotope identified and metadata spreadsheet | Screen grab or short video files labelled with StnCode and biotope they represent |
| Polyline shapefile representing the results of the Annex I Stony Reef analysis and tier 1 annotations assigned to each video transect segment. Shapefile should be ArcGIS and QGIS compatible, embedded with MEDIN-compliant metadata and fully georeferenced in a defined coordinate system Shapefiles with drop-frame positions and the area of iceberg ploughmarks will be provided by JNCC. | ArcGIS & QGIS compatible polyline shapefile |
| Final Report | Word document |

## Product Specification

JNCC is committed to making its publicly available resources and documents accessible, in accordance with the Public Sector Bodies (Websites and Mobile Applications) (No. 2) Accessibility Regulations 2018.

Making material accessible means making sure it can be used by as many people as possible.  This includes those with:

- impaired vision

- motor difficulties

- cognitive impairments or learning disabilities

- deafness or impaired hearing

The outputs and material that JNCC publishes should be compliant with the Web Content Accessibility Guidelines version 2.1 AA standard.

To meet this standard, all reports and other documentation which are to be made publicly available must adhere to JNCC’s house-style (to be provided by JNCC) and be produced using a JNCC template (to be provided by JNCC), unless otherwise stated. All reports (draft and final) should be provided electronically via email both as a Microsoft Word document and an Adobe PDF.

Copies of documentation associated with case studies should be provided in electronic format with an associated reference catalogue.

For any other outputs or products which are to be made publicly available through JNCC, evidence regarding how the accessibility standard will be reached should be included.

(Note for author if research project/contract: see EQA Policy Appendix 4 (Communicating Evidence Quality). Ensure that data management and storage requirements are stipulated taking into account relevant policy for data access. See https://jncc.gov.uk/about-jncc/corporate-information/evidence-quality-assurance/

## Dissemination

The products/outputs produced under this contract will be a JNCC product and shall not be published or disseminated without the written permission of JNCC. Outputs may at some point be published on the JNCC website and all material supplied as part of this contract shall remain copyright of JNCC. The findings from this contract will also be made available to staff within JNCC, the UK country nature conservation bodies (name them), Defra and (list other parties)

## Timescale

Provisional dates for delivery of the contract outputs are set out below. Once the contract is awarded, a start-up meeting will be organised. Exact dates for remaining milestones are to be agreed at the start-up meeting based on Contractor and JNCC staff availability.

| Video Analysis |  |
| --- | --- |
| Output | Provisional Date |
| Start-up meeting | W/C 17 Nov 2025 |
| Interim meeting to discuss any issues or resolve questions, after the analysis of 10 camera stations has been completed. | W/C 1 Dec 2025 |
| Provision of draft deliverables to JNCC and external QA samples to external QA analyst(s) | WC 16 Feb 2026 |
| Meeting with QA analysts to discuss finalisation of video analysis | WC 16 Feb 2026 |
| Delivery of video output 5 (video shapefiles). QA of video analysis. | W/C 2 March 2026 |
| Completion external QA and provision of final deliverables to JNCC including final report | W/C 16 March 2026 |
| Wash-up meeting | W/C 16 March 2026 |

| Stills Analysis |  |
| --- | --- |
| Output | Provisional Date |
| Start-up meeting | W/C 17 Nov 2025 |
| Interim meeting to discuss any issues or resolve questions, after the analysis of 10 camera stations has been completed. | W/C 1 Dec 2025 |
| Provision of draft deliverables to JNCC and external QA samples to external QA analyst(s) | WC 23 Feb 2026 |
| Meeting with QA analysts to discuss finalisation of stills analysis | WC 23 Feb 2026 |
| Completion external QA and provision of final deliverables to JNCC including final report | W/C 16 March 2026 |
| Wash-up meeting | W/C 16 March 2026 |

In agreeing exact dates, please note that the potential for work under this contract to be funded into 2025/26 is subject to availability of funds.

## Health and Safety

The successful contractor shall comply with all relevant Health and Safety legislation and regulations, as well as JNCC’s internal Health and Safety procedures. Where applicable, the contractor must also adhere to JNCC’s Safeguarding Policy, for further information   https://jncc.gov.uk/about-jncc/corporate-information/safeguarding/ particularly where activities involve vulnerable individuals or public engagement. If the work to be carried out poses any health and safety risks, a suitable and sufficient risk assessment must be completed by the contractor. This risk assessment, along with any supporting evidence of compliance, must be submitted to the JNCC Project Manager for review and approval prior to the commencement of any work. The Project Manager will liaise with the JNCC Health & Safety Officer as required to ensure appropriate controls are in place.

Any incidents occurring within the contract period should be immediately reported to JNCC.

## Project Management

The successful Contractor shall nominate a project manager who shall be responsible for ensuring the project is completed satisfactorily and who shall be the main contact point for JNCC.

JNCC’s main contact points will be:

Name: Eilidh Boa

Email: Eilidh.Boa@jncc.gov.uk

Telephone: +44 (0)1224 083555

Name: James Albrecht

Email: James.Albrecht@jncc.gov.uk

Telephone: +44 (0) 7384836553

## Instructions for Bid Submission

The bid submission should include the following:

A brief summary of the bidder’s experience in relation to the requirements of this contract;

A proposed approach for achieving the objectives of the contract and delivering the detailed tasks identified within each objective. This should be sufficiently detailed to allow assessment against the evaluation criteria (Section 14);

A detailed project plan (including Gantt chart) with proposed work programme and an estimate of time required to achieve each objective;

A draft Table of Contents for the final report;

Details of Quality Control procedures to be followed (note for author if research project/contract: see EQA Policy Appendix 1 (Bias, Conflicting Evidence and Uncertainty) and EQU Policy Appendix 3 (Quality Assurance of Expert Knowledge and Opinion):

Details of the bidder’s own internal Quality Management System;

Please provide written responses to the following questions, with a maximum of 150 words per answer. Where possible, relate your answers to the proposed work and project team. You may include supporting evidence if helpful, but it is not required.

  - Does your business measure and take steps to reduce the greenhouse gas emissions from its operations? If so, please briefly describe what you measure (e.g. energy, transport) and what actions you take to reduce emissions.

  - What other actions does your business take to reduce your environmental impact? For example, reducing waste, improving biodiversity, or using resources more efficiently.

  - Does your business take any steps to promote fairness and inclusion at work, support staff wellbeing or help your local community?

  - In what ways does your business contribute to a positive and lasting impact on the economy? For example, do you support local jobs, use local or community business suppliers, pay fair wages, or invest in staff development?

  - What is your business’s Full-Time Equivalent (FTE) headcount?

Details of the Project Team including their roles and experience, an estimate of their time input into each task and CVs of all personnel who will be involved in the contract/project; please ensure all CVs MUST be attached as a separate PDF documentation from the proposal, so that we can meet our JNCC GDPR retention policy requirements.

Availability of the Project Team for a start-up meeting in Peterborough or Aberdeen (Project Manager to complete. Please state whether  it will be a virtual meeting)

Overall quote for the contract to include:

  - Day rates for all members of the Project Team;

  - Rates for attending start-up, interim and final meetings in Peterborough or Aberdeen (costs for travel and accommodation are attached, and should be used. These rates are analogous to the civil service rates).

  - Costs and time allocation should be clearly allocated to specific tasks within this contract/project; and

VAT

  - Bidders need to specify whether VAT at the prevailing rate would be applicable to this project and if so, provide their VAT registration number.

  - VAT Reversal. Bidders who are based outside the United Kingdom and Isle of Man should indicate in their bids whether VAT reversal should apply. Using the current HMRC (Her Majesty’s Revenue and Customs) guidance, the service is deemed to be supplied in the country where the customer (JNCC) resides and any contract arising from this procurement process, VAT reversal should be reflected at contract award.

JNCC will be required to account for VAT at the UK current rate, 20% and legally bound to pay this over to HMRC.

JNCC does not expect to receive an invoice to include the bidder home country VAT rate, however, to ensure accounting propriety please ensure that both your VAT registered number and JNCC VAT number, which is GB 854 5291 09, is shown on any future invoice(s).

The following documentation (to submit in a zip folder separate from the proposal):

  - Copies of health and safety policy statements where available or a note regarding such items as lone working, emergency procedures and accident reporting;

  - Copies of current public and employer liability insurance certificates;

  - Copies of any appropriate risk assessments;

  - Copies of your company's modern slavery and or safeguarding statement or policy and;

  - Copies of any environmental policies should you have them.

In addition, note that the bid submission should provide sufficient information to allow assessment against the evaluation criteria outlined in Section 13.

Conflict of Interest

Under PA 2023, conflict of interests will be monitored throughout the duration of the contract. Please complete and return the CoI declaration form included in the ITT pack with your bid submission. If successful, please notify the JNCC procurement team if there are conflict of interest changes throughout the duration of the contract, as these will need to be declared for any actual or potential conflicts of interest that could impact the integrity, impartiality, or fairness of the procurement process.

## Evaluation Criteria

JNCC is not bound to accept the lowest priced or any bid. Having the technical expertise and experience to complete the work to a high standard and being able to complete it within the timescale are of the essence for this contract.

The bid evaluation may be undertaken by a panel consisting of JNCC staff and staff members from Natural England, Natural Resources Wales, NatureScot, DAERA-NI and Defra.  Unless otherwise stated in your bid submission, bids will be forwarded to these agencies for evaluation purposes only. (Project Manager to state who will undertake the evaluation, whether JNCC and/or other agencies)

For information on how we handle personal data please see our Privacy Notice at https://jncc.gov.uk/about-jncc/corporate-information/privacy-statement/

Bids will be evaluated using the following criteria:

|  | EVALUATION CRITERIA | Maximum Score | Score |
| --- | --- | --- | --- |
| 1. Quality of Bid (50% of the total assessment categories) |  |  |  |
|  | Clarity of proposal (particularly work programme and deliverables) | 10 |  |
|  | Understanding of, and relevance to, the requirements in particular the adequacy of outputs and understanding of any….name any particular knowledge/skill/understanding expected) | 10 |  |
|  | Soundness and logicality of methods | 5 |  |
|  | Realism and measurability of outputs | 5 |  |
|  | Evidence provided of how accessibility standards will be met | 5 |  |
|  | Identification and proposed solutions to potential risks/issues | 5 |  |
|  | Serious weaknesses which threaten success | 5 |  |
|  | Probability of success | 5 |  |
|  | Sub Total | 50 |  |
| 2. Details of Contractor (20% of the total assessment categories) |  |  |  |
|  | Expertise, experience, and balance of team | 9 |  |
|  | Risks if important team members drop out | 5 |  |
|  | Adequacy of subcontractors if any | 6 |  |
|  | Sub Total | 20 |  |
| 3. Sustainability (10% of the total assessment categories) |  |  |  |
|  | Environmental (assessed from responses to sustainability questions 1 and 2 in section 13, scaled to business size) | 5 |  |
|  | Social (assessed from responses to sustainability questions 3 and 4 in section 13, scaled to business size) | 5 |  |
|  | Sub Total | 10 |  |
| 4. Cost (20% of the total assessment categories) |  |  |  |
|  | Total Cost (Including and whole-life cycle or Lifecycle costs) | 5 |  |
|  | Risk of cost variation (e.g. Indexed or fixed pricing) | 5 |  |
|  | Unit Rates | 5 |  |
|  | Transparency and correctness of proposal | 5 |  |
|  | Sub Total | 20 |  |
| Total Score |  | 100 |  |

## Payment

Unless a payment schedule is stated in your submission and agreed by JNCC project manager. Payment will be made on completion of the objectives following the submission of invoice(s) and based on the satisfactory undertaking of the contractual elements to the agreed standard of the JNCC Project Officer.

## Additional Requirements

All bidders are requested to carefully read the Terms and Conditions applying to this contract. Payment will only be made upon delivery of key outputs.

It is assumed that all costs associated with the production of figures, reproduction of photographs and the final report are accounted for within the rates/fees given.

The bidder is expected to supply all necessary equipment, software, licences, etc. to carry out the obligations required under the contract.

## Procurement Timetable (which may be subject to change)

| Activity | Date |
| --- | --- |
| Preliminary Market Engagement Notice |  |
| Publication of Tender Notice |  |
| Last date for receipt of clarification questions |  |
| Final submission date for bids |  |
| Evaluation of bids |  |
| Post-tender negotiation/clarification and or presentation if required |  |
| Successful/unsuccessful bidders notified Or Assessment Summaries issued to Successful & Unsuccessful Bidders |  |
| Contract award |  |
| Contract Details Notice |  |
| Start of project |  |

## Appendix A: BIIGLE still image protocol (adapted from Cefas BIIGLE protocol)

- A BIIGLE account (with editor privileges) will be created for the successful contractor, if one does not already exist, which will allow for annotations to be added to each image.

- Images will be stored on a remote volume which both JNCC and the successful contractor will have access to.

- Images should be sorted randomly for the analysis using the random filter in BIIGLE.

### Stills Annotation

The Label Tree

The BIIGLE annotation process for stills imagery is split into two parts; Tier 1 (whole image labels – used for metadata such as image quality, relief, habitat etc.)  and Tier 2 (faunal annotation).

The Annotation Process (Tier 1 - Whole Image Labelling/spreadsheet entry for Metadata)

Tier 1 still image data may be recorded in one of two ways. Regardless of the method chosen this must be done in the same way by all analysts involved in the project.

- Entered directly into the proforma provided using the same vocabulary as the label tree.

- Recorded in BIIGLE as a whole image label

Whole image labels (what we refer to a “Tier 1” labels) are annotations that apply to the whole image, not just to one specific point within the image. As such, these are very useful in annotating for the typical “metadata” that an analyst provides alongside the faunal abundance / percentage cover matrices.

The whole image label annotations should be added at the same time as the Tier 2 faunal annotations, i.e. by using the annotation tool (accessed by clicking on an individual image in the volume overview) for both sections of analysis.

To attach whole image labels using the annotation tool, select the label from the MPA Imagery Analysis Hierarchy (see user guide) and Select the “Image Labels” tab from the side menu:

Figure 4 Showing the “Image Label” tab

Once the “Image Label” tab is open, and the correct label is selected (I.e. Image Quality: Excellent in the above example) then click the “+” symbol in the top right of the “Image Label” tab to append this label to the whole image. Please ensure that a Tier 1 label is appended for every category stated in Table 6.

The Annotation Process (Tier 2 – Faunal Annotation) – must be annotated in BIIGLE

Once you have navigated to the image (and are therefore in the “Annotation tool”), select the biota label of choice (this could be a morphological label, if ID to genus or species level is impossible) , and then use the “Set Point A” button on the bottom toolbar, and click with the mouse over the first point

  - This will create the first point “Annotation” of the image.

  - Where it is possible to identify any specific taxa (to family, genus or species level), add these specific taxa to the label tree, nesting them under the most appropriate morphological class.

  - It is recommended that you annotate all individuals of the same taxa within the image at the same time, as this is more efficient.

- If the individual / colony you are annotating is a ground-cover taxon, this can be done using the “Draw Polygon” (including the brush tool) or “Magic wand” tools.  The “Magic Wand” tool is an image analysis and prediction tool for rapid drawing of highly detailed polygons Cefas again select the biota label of choice, and then hover over the Draw Polygon tool on the tool bar - you will then see a second tool appear above, this is the “Magic wand” button. Click this tool, then place the curser over the centre of the individual /colony you are annotating, press and hold the middle mouse button and slowly move the cursor out. Release the button when the polygon has best matched the individual / colony outline.

- Repeat this process until all taxa within the field of view have been classified.

- If the Magic Wand tool does not work, please use the basic Draw Polygon Tool or Brush Tool.

Any deviation from this methodology should be approved in writing by JNCC.

### Video Annotation – must be annotated in BIIGLE

The Annotation Process (video)

There are two forms of video annotation:

- Tier 1 Video Metadata (multi-frame annotations for transect / segment metadata)

  - The entire video transect should be viewed at up to 4x speed on the first review. During this review, the video will be annotated to identify segments, whereupon any time that a change in BSH (of greater than 5 m in length – see fix to point data) is noted, the appropriate segment will be changed using a whole frame annotation:

    - Using the “Start a Whole Frame Annotation H” tool, “open” the first annotation by clicking on the button or pressing H whilst viewing the desired start frame.

    - This annotation is now open until you click again to create a “closing point” (i.e. at the EOL or change of habitat). N.B.  you can switch between open annotations, so you don’t have to scroll through the video until the habitat / substrate etc. changes.

    - Make sure that the next segment starts on the same frame as the previous one ended. This avoids gaps or overlaps. Care should also be taken to ensure there are no gaps at the start and end of the video.

Once a segment has been delineated, additional whole frame labels (for other Tier 1 labels such as image quality and BSH) should be attached to the segments using the “add label tool”. using the add label tool will ensure the start and end points are the same for all labels given to a segment.

- Tier 2 - Video Faunal Annotations (single frame annotations for faunal abundance)

  - These are point annotations (even if the taxa would usually be considered “ground-cover” taxa).

  - When an animal is seen, pause the video and select the correct faunal label from the MPA Imagery analysis label tree

  - Using the “Start a Point Annotation A” tool place the annotation by clicking on a point at the centre of the individual animal.

  - No “Closing point” is needed, simply click the “Tick” mark above the point tool – this finishes the single frame annotation.

These annotations form the basis of the faunal data

Ensure that no multi-frame annotations are used for faunal annotations, as this will confuse the analysis process (such annotations are useful for tracking mobile fauna such as fish)

### Report downloading

BIIGLE allows admin users to download “Annotation Reports”. These are CSV documents which contain, line by line the: image ID, file name, annotation tag labels, exact tag position within the image (pixel x and y), BIIGLE user ID.

- It is from these reports that the final dataset will be compiled.

- The contractor can request a report to be generated as required for data management tracking purposes.

## Appendix B: Stony Reef Analysis

Stony reef will be analysed using the Irving (2009) criteria (Table 7). Any video segment that has been categorised as potential stony reef should have the Irving criteria applied. Note that where cobbles/boulders are present on top of bedrock, a segment may be considered as both bedrock and stony. Clarification on how Irving criteria should be used for this contract are provided below.

An area of iceberg ploughmark is present in WTR, which is a special case of stony reef. A shapefile of this area will be provided by JNCC, and any camera tows which occur in this area will automatically be considered stony reef, regardless of the substrate observed.

Table 7. The main Characterising features of a stony reef

Composition

Note that a cobble should have a minimum dimension of 64 mm as opposed to a maximum dimension of 64 mm. The laser scaling on the video is provided by four green dot laser pointers with the bottom two set to 67 mm and can be used as a guide to estimate 64 mm.

To help estimate the percentage cover of cobbles/boulders in a segment, when composition is near a low/medium/high threshold:

- Count the number of new areas of seabed the cameras field of view passes over during the segment;

- Divide the screen into a 3 x3 grid (either by drawing it on in BIIGLE (Figure 1) or approximating it);

- Count the number of grid squares filled by cobbles over the length of the segment;

- Use number of FOVs and number of grid squares full of cobbles to calculate percent cover using the composition calculator (an excel spreadsheet which can be provided separately).

Figure 5. 3 x 3 grid drawn in BIIGLE.

Elevation

If cobbles are visible, the seabed is not flat.

If cobbles are partially buried, then consider that they may be elevated <64 mm (low resemblance).

If cobbles are laying in the surface, then they are elevated at least 64 mm (medium resemblance)

Boulders >5 m are unlikely to be identifiable given the field of view of the camera, but if they are present, they would be considered high resemblance.

Extent

Extent is not required from the video analysis, but all segments should be at least 5 m long which is the equivalent to 1 minute.

Biota

As no information on infaunal communities is recorded, this criterion is not used in this analysis.

## Appendix C: Non-indigenous species (after Curtis et al, 2020)

Taxa listed as non-indigenous species (present and horizon) which have been selected for assessment of Good Environmental Status in GB waters under MSFD Descriptor 2 (Stebbing et al. 2014).

Additional taxa listed as non-indigenous species in the JNCC ‘Non-native marine species in British waters: a review and directory’ report by Eno et al. (1997) which have not been selected for assessment of Good Environmental Status in GB waters under MSFD.

Langenkämper et al (2017) BIIGLE 2.0 - Browsing and Annotating Large Marine Image Collections. Frontiers in Marine Science. 4: https://doi.org/10.3389/fmars.2017.00083

This will be the results of the video and imagery analysis as specified in the video and stills processing sections of this document. No additional statistical analysis is required.

Stony reef will be classed as “potential” until its presence has been confirmed using the Irving criteria. Then it should be re-classified as “Stony”. Also note that where stone/boulders are resting on top of bedrock, a segment may be labelled as both bedrock and stony reef.

https://mhc.jncc.gov.uk/

https://hub.jncc.gov.uk/assets/f23a26d7-07ad-4291-a42d-b422dad82351

https://www.nature.scot/sites/default/files/Publication%202016%20-%20SNH%20Commissioned%20Report%20406%20-%20Descriptions%20of%20Scottish%20Priority%20Marine%20Features%20%28PMFs%29.pdf

Henry, L.A., Roberts, J.M. 2014. Recommendations for best practice in deep sea habitat classification: Bullimore et al. as a case study. ICES Journal of Marine Science, 71, 895–898.

Cleland, J., Gabruk, A., Henry, L. & Roberts, M. In press. Updating the UK working definition of Coral Gardens habitat and sub-types.

https://mcc.jrc.ec.europa.eu/documents/201702074014.pdf

This label tree will be a CATAMI hierarchy with WoRMS accepted taxonomic names inserted into the hierarchy.

Please note that a mixture of point and area annotations should not be used for a single taxon. i.e. if Alcyonium digitatum is considered colonial it should be labelled as such in all cases. Any changes in annotation approach must be approved by JNCC and all annotations already made changed to match.

This survey is intended to form part of a timeseries. As such, method of analysis needs to be standardised across surveys to ensure data remains comparable over time.

https://mcc.jrc.ec.europa.eu/documents/201702074014.pdf

Random selection reduces potential bias that could be introduced into the training dataset from choosing ‘best examples’ or only choosing images at the start of a transect

http://randd.defra.gov.uk/Document.aspx?Document=13892_ME5215Objective2-Monitoring.pdf

https://hub.jncc.gov.uk/assets/1684dd5e-36e3-4969-852f-4541c82240eb