## Works In Progress 2026 27
Location | Project Manager & Service | Works undertaken | Contractor | Approx. Start Date on Site | Approx. Completion Date | Value of Works Package | Is any cover required for own plant? | Is cover required for Hired in Plant | Lead Project Officer | Service & Client Lead | Type of Contract | Date Insurance advsied | Comments
160 Friar Street | Mary Konstantopoulou, DEGNS | Strip out and refurb of commercial unit | Morris & Blunt | 2025-09-23 | 2026-01-09 | 96686 | unsure | no | MK | Danny Wo | JCT Minor Works CDP 2024 | 2025-09-08
Thameside Primary School SEND Playground | Mary Konstantopoulou, DEGNS | New external SEND playground | Playtime by FAWNs | 2025-10-27 | 2026-01-30 | 120000 | no | no | Laura Mahoney | Laura Mahoney | JCT Minor Works CDP 2024 |  | likely this will run into 2026
Civic Fire Compartmentation Works | Paul Neale, DEGNS | fire wall upgrades and making good defects | Komfort | 2025-10-15 | 2026-04-16 | 300000 | yes | unsure | PN | Charan Dhillon | JCT Design and Build
Civic Signage | Mary Konstantopoulou, DEGNS | Wayfinding and Signage design and implementation | unknown | 2025-11-06 | 2026-04-16 | 50000 | unsure | unsure | MK | Charan Dhillon | unknown
Town Hall, Museum roofs,Blagrave Street | Yvonne Mubanga, Corporate Property Services | Funding TBC: Refurbishment and Fabric improvements to all musuem roofs | TBC | 2026-06-01 | 2029-03-01 | 4500000 | No | No | Yvonne Mubanga | Charan Dhillon | JCT Intermediate | 2024-05-01 | Large scale project likely to be done in phases to accommodate operations. Procurement and phasing of works TBC. Value is based in RBC capital funds allocation
Reading Cemetery Archway | Yvonne Mubanga, Corporate Property Services | Funding TBC: Structural improvement works to Archway building | TBC | 2025-06-26 | TBC | 700000 | No | No | Yvonne Mubanga | Charan Dhillon | JCT Intermediate | 17/02/2025
35 Alexandra Road, The Mount, Reading, RG1 5PG | Yvonne Mubanga, Corporate Property Services | Residential refurbishment works to create a new Children's home | TBC | 2025-11-01 | 2026-03-26 | 350000 | No | No | Yvonne Mubanga | Charan Dhillon | JCT D&B | 17/02/2025
134, Northumberland Avenue, Reading RG2 7PU | Yvonne Mubanga, Corporate Property Services | Residential refurbishment works to create a new Children's home | TBC | 2025-11-01 | 2026-03-26 | 300000 | No | No | Yvonne Mubanga | Charan Dhillon | JCT D&B | 17/02/2025
59 Honey End Lane | Yvonne Mubanga, Corporate Property Services | Residential refurbishment works to create a new Children's home | TBC | 2025-11-01 | 2026-03-26 | 30000 | No | No | Yvonne Mubanga | Charan Dhillon | JCT D&B | 2025-08-10
Oxford Rd Community School. 146 Oxford Road, Reading RG1 7PJ | Ola Onile-Ere/Laura Mahoney- Education Asset Services | SEND - Primary School spaces-External play spaces | Playtime by Fawns | 2025-11-25 | 2026-03-26 | 45500 | No | No | Ola Onile-Ere | Charan Dhillon | JCT | 17/02/2025
Whitely Park Primary School | Ola Onile-Ere/Laura Mahoney- Education Asset Services | SEND - Primary School spaces-External play spaces | Playtime by Fawns | 2025-11-25 | 2026-03-26 | 52500 | No | No | Ola Onile-Ere | Charan Dhillon | JCT | 17/02/2025
Henley Rd Cemetery, 55 All Hallows Rd. RG4 5LP | Ola Onile-Ere/Ian Hussain Bereavement Services | Phase 1A Cremator replacement works, refurbishment and extension works - Essential works to enable the commissioning of the 2Nr newly installed Cremator | Morris & Blunt | 2023-09-23 | 2026-03-26 | 230000 | No | No | Ola Onile-Ere | Charan Dhillon | JCT | 2024-05-01
Henley Rd Cemetery, 55 All Hallows Rd. RG4 5LP | Ola Onile-Ere/Ian Hussain Bereavement Services | Phase 2A Cremator replacement works, refurbishment and extension works - Extension of the Staff Area, extension of the South Chapel, extension of the West Chapel with ramp access |  | 2025-08-01 | 2026-03-26 | 600000 | No | No | Ola Onile-Ere | Charan Dhillon | JCT | 2024-05-01
Henley Rd Cemetery, 55 All Hallows Rd. RG4 5LP | Ola Onile-Ere/Ian Hussain Bereavement Services | Additional Muslim Chambers | GEMS Precast | 2024-08-01 | 2025-06-01 | 70000 | No | No | Ola Onile-Ere | Charan Dhillon | JCT | 2024-05-01
Whitely Wood Sports Pavilion, 507 Basingstoke Rd, Reading RG2 0SH | Kim Cheun/ Emmer Kinghorn Leisure Services | Refurbishment and redecoration works | ODS | 2025-09-01 | 2026-03-01 | 300000 | No | No | Kim Cheung | Charan Dhillon | JCT | 2024-05-01
Caversham Park drainage
Caversham Park kitchen flat roof repair
Wilson Primary
Moorlands Primary water pipework distribution
Redlands Primary pipework distribution
Southcote fan convector replacement
Newbridge nursery heating distribution
Micklands boiler replacements