## Timing plan
Activity | capital costs | Senior engineer [days] | engineer [days] | junior engineer [days] | Full project | Essential to continuing as anticipated without impacting delivery | Items that could be absorbed by RT as part of unit costs | Essential to continuing as anticipated without impacting delivery | Items that could be absorbed by RT as part of unit costs | start | duration | end | Cost per week
Algorithm | Commercially sensitive information has been redacted in accordance with National Highways’ obligation under Section 94(1)(b) of the Procurement Act 2023”)”;
Investigate fixed objects
Improve detection of blocked radar
Improve time to fully active (TTO)
Investigate impact on trigger rates of low speed vehicles
Verify operation of system in tunnels (no GPS)
Invertigate improving the algorithm to see what can be done in the situation where all traffic flows are dangerous
Collate data from closed roads and investigate is detection of passing vehicles is practical
Collate data from rolling road blocks and investigate is detection of passing vehicles is practical
Stakeholder review of alarm rates and sensitivities
Main unit
Add output for vehicle mounted alarm
Add 2 inputs and 2 outputs in case road close and rolling road block switches and indicators are needed in the future
Add on CAN to allow the system to detect when emergency lights are on
Design/test combined antenna for GPS/LoRa/LTE
Work with the TOV vehicle fitters to specify cable routing, power feed, antenna fitting and cable routing and document as required
Work with Radviz supplier to understand fitting requirements
Update mount design and radar cover (assuming 2 cars, X5 and XC70)
Installation kit for each additional vehicle
E-marking (including EMC testing)
Implement unit management portal
SIM card management
Manage firmware and configuration updates
Remote fault detection
Remote service and support
arranging hosting, security certificates, URL registration, other admin (this is commong to management and hosting)
Implement basic data portal to enable technical/scientific studies in 2026
Ability to search/sort and download data from events
Plot a "heat map" of detected near misses
A data dashboard of basic statistics including the number and duration of TM events, rate of alarms, flagging and hardware issues
optional email notifications in the case of a TM with a very high rate of alarms
Ability to locate last known GPS locations of RRA600s and individual wearables
Wearable
Agree the updated v2 wearable specification in principle (see separate doc)
Development/testing of high sensitivity integrated GPS
Development/testing of integrated antenna (including on and off highway range testing)
high output sounder feasibility testing
new high output sounder integration
Development of new enclosure
Updates to electronics design (including PCB)
Updates to firmware (including new protocols that include GPS)
Updates to charging base for the new case design
Design of new wearable charing cable
built 5 test wearable v2 prototypes + docking base
End-to-end testing of firwmare, electronics, both in the office and on-site
Enviromental testing of the complete design (particular attention to water ingress at sounder)
CE testing the new wearable
Workshop to agree final settings to alarm volume and potentially other minor adjustments
Design of injection moulded tooling
Update of the current trial units
build 20 v2 wearables and 4 v2 chargoing docks)
Site visit to TOV depot to update current base units (updating radar mount, new direct CAN interface to light controller, firmware update)
Office test and development units
Build additional 8 complete production systems (including 8 v2 wearables)
Productionisation (ISO production compliance)
Development of a complete and automated test bench for the RRA600 main unit
Build and test instructions
Installation and commisioning guides
EMC testng
Project management and client liason
2.5 days average of a senior project manager for the duration of the project (Ryan)
Trial management and responding to Boris forms
2 days end to end testing for final system (off highway at test track)
Mobilisation and production
procurement process
2nd trail can begin (with updated units, but not wearable v2)
wearable v2 available for limited testing
wearable v2 available for deployment
System design complete
tooling (injection moulding)
parts procurement
production (outsourced)
production (insourced)
TOTAL |  |  |  |  | 426100 |  |  | 331300.12 | 94800
Additional PM, trail management and minor preliminaries | [7 empty] | 24000 |  | -8 | 8 | 0 | 3000
[5 empty] | Original/Full option | Essential to continuing as anticipated without impacting delivery | Items that could be absorbed by RT as part of unit costs
[5 empty] | 48400 | 35400.03 | 13000
[5 empty] | 56200 | 35600.04 | 20600
[5 empty] | 28000 | 28000 | 0
[5 empty] | 0 | 0 | 0
[5 empty] | 108800 | 99600.01 | 9200
[5 empty] | 27700 | 27700 | 0
[5 empty] | 16000 | 0.01 | 16000
[5 empty] | 50400 | 14400.03 | 36000
[5 empty] | 90600 | 90600 | 0
[5 empty] | 426100 | 331300.12 | 94800