# Annex A

| Title of Project | Ocean Country Partnership Programme: Maldives GESI and SEAH Support Phase 2 |
| --- | --- |
| Date and Time for Return of Bids | Friday 9 May 2025 @09:00 (UK) |
| Contract Reference Number | C25-0604-2044 |
| Address for Bid Submission | 1 electronic copy to be sent to TenderResponse@jncc.gov.uk PLEASE DO NOT SEND BIDS DIRECTLY TO BETH FLAVELL OR PROCUREMENT VIA THEIR WORK EMAIL ADDRESSES AS THIS WILL INVALIDATE YOUR BID. Bids must be less than 10 MB in size. On receipt of your bid, you will receive an automated e-mail to confirm receipt by the JNCC Support Co. If you do not receive this automated email, please contact the number below: (00 44 1733 866 988) |
| Contacts for Technical Information relating to this Project Specification | Procurement Team Joint Nature Conservation Committee Email: contractqueries@jncc.gov.uk Telephone: 01733 562626 |
| Contact for Queries Regarding the Procurement Procedure | Procurement Team Joint Nature Conservation Committee Email: contractqueries@jncc.gov.uk Telephone: 01733 562626 |
| Proposed Start Date | Monday 19 May 2025 |
| Proposed End Date | Friday 27 February 2026 |

Ocean Country Partnership Programme: Maldives

Maldives GESI and SEAH Support Phase 2

Contents

1.	Joint Nature Conservation Committee	3

2.	Project Background	3

3.	Project Aims and Objectives	4

4.	Project Objectives: Detailed Tasks	4

5.	Potential Follow-On Work	5

6.	Product Specification	6

7.	Dissemination	6

8.	Timescale	6

9.	Health and Safety	7

10.	Project Management	7

11.	Instructions for Bid Submission	7

12.	Evaluation Criteria	8

13.	Payment	9

14.	Additional Requirements	9

15.	Procurement Timetable (which may be subject to change)	10

## Joint Nature Conservation Committee

The Joint Nature Conservation Committee (JNCC) is the statutory adviser to the UK Government and devolved administrations on UK and international nature conservation.

Background to JNCC can be found on JNCC’s website at: https://jncc.gov.uk/about-jncc/

JNCC has a responsibility to protect the people we work with, and who work for us, and we will continuously strive to prevent bullying, harassment, exploitation and abuse and child abuse from happening.

JNCC takes a Gender Equality and Social Inclusion (GESI) approach across all elements of our work (under the Ocean Country Partnership Programme) to address unequal power relations and inequalities, reduce disparities and ensure equal rights, responsibilities, opportunities and respect for all individuals. JNCC also takes all reasonable steps to safeguard the people we come into contact with (including staff and the communities in which programmes are delivered) from sexual exploitation, abuse and harassment (SEAH).  JNCC will work with the successful bidder to meet GESI and safeguarding expectations, including the collection of data to evaluate GESI under this project.

## Project Background

JNCC is a delivery partner for the Ocean Country Partnership Programme (OCPP), a UK government-led programme funded by Official Development Assistance (ODA) under the Blue Planet Programme. More information on the OCPP can be found here: https://www.gov.uk/government/publications/blue-planet-fund/ocean-country-partnership-programme-ocpp.

OCPP aims to be GESI sensitive in its delivery and GESI transformative where possible.  Through OCPP we aim to support countries to strengthen marine science expertise, develop science-based policy and management tools and create educational resources for coastal communities. There are three main objectives for the OCPP:

- Marine Pollution:- supporting countries to be equipped with the skills and expertise needed to tackle, reduce and mitigate marine pollution through the development of science led policy and improve our understanding of the impacts of pollution, as well as identifying and supporting effective responses, we will make sure that communities are better equipped to prevent and manage marine pollution. This will improve health and livelihoods.

- Sustainable Seafood:- supporting the development of the skills and expertise needed to adopt sustainable seafood practices to reduce risks such as the spread of zoonotic diseases from unsustainable or unsafe activities and support trade in safe seafood. Assisting countries to crack down on illegal, unreported and unregulated fishing by supporting the development of better management, monitoring and enforcement capabilities.

- Marine Biodiversity:- supporting countries to develop the skills and expertise needed to establish designated, well-managed and enforced marine protected areas to support healthy ecosystems with thriving biodiversity and fisheries that communities rely on for food and livelihoods. Achieving these objectives by strengthening marine science expertise, developing evidence-based policy and management tools, and creating educational resources for coastal communities.

## Project Aims and Objectives

During 2024-25, JNCC ran a contract with a Maldives base consultancy to help improve our understanding of GESI and SEAH in Maldives. The contract included the completion of a Context Review of GESI in Maldives, review of 4 case studies of OCPPs work to provide feedback on how GESI and SEAH consideration could be improved, and the organisation of a workshop with stakeholders in Maldives to explore GESI and SEAH in the marine environment and development sector.

OCPP aim to build on the momentum of this work, by continuing to explore GESI and SEAH through the Maldives partnership. This would include actions to improve both GESI and SEAH integration into OCPPs own work, as well as providing support to stakeholders specifically working in the environmental sector in Maldives around GESI and SEAH considerations.

Please note that GESI and SEAH involve very different processes. Whilst the two are referred to together in this document, they will require separate targeted approaches through the delivery of this contract, and we would welcome discussion with the successful contractor around how to do this.

## Project Objectives: Detailed Tasks

To deliver the following tasks successfully the contractor is required to have substantial experience and expertise in GESI and SEAH specific to the Maldives to help deliver the following tasks:

- Develop a GESI Handbook and a SEAH Handbook for Maldives.

  - The 2 Handbooks would provide background information, templates, frameworks and case studies

  - The 2 Handbooks should be developed so they are Maldives specific and can easily be used by environmental sector stakeholders to progress their work on GESI

  - The 2 Handbooks should act as a training package to support wider engagement with stakeholders in Maldives.

  - The 2 Handbooks should be developed in the OCPP report template. Versions of the Handbooks should be delivered in English and Dhivehi.

  - If funds allow, the handbooks could be developed into a glossy document, please provide a quote for handbook design in your bid (please note, the handbook will be an electronic document, so printing will not be required).

- Develop the Maldives GESI and SEAH network:

  - Establish the Maldives GESI and SEAH network, based on attendees from the February 2025 GESI workshop, but open to others to join.

  - Develop Terms of Reference for the network, and guidelines on ways of working and expectations.

  - Develop a platform for the network, to allow members to share information and collaborate on developing GESI and SEAH approaches.

  - Based on the Handbooks and information provided through the Network, work with organisations to ensure that they have the information required to progress their GESI and SEAH considerations.

  - By the end of the contract, seek to ensure that at least 10 organisations have developed GESI and SEAH policies.

- Develop and facilitate a stakeholder workshop on GESI and SEAH

  - Building on the first GESI workshop, hold a follow-on workshop with the GESI and SEAH network to maintain momentum, to be held in October 2025.

  - Use the workshop to launch the Handbooks with participants.

  - Aim to provide SEAH training session during the workshop to build capacity and understanding.

  - Develop training materials for the SEAH course that can be saved as a long-term resource and shared wider in the community.

- The contractor will arrange the workshop logistics, including venue and catering. The contractor would be responsible for inviting attendees (approx. ~50 people) and arranging their travel and subsistence for their attendance (where required).  Tender responses should include sufficient funds to cover these costs.

- The contractor will be responsible for leading the delivery and facilitation of the workshop. OCPP staff will be present, and available to support delivery on the day as required.

- The contractor will be responsible for collating GESI information about attendees, and pre- and post-workshop feedback questionnaires to collect data on MEL (Monitoring Evaluation and Learning). OCPP can provide templates to support this.

- The contractor will be responsible for writing up a report of the workshop, providing information on the discussions and writing up the key recommendations.

- Provide support to OCPP in the organisation of the PCA Forum 2

  - Provide advice to OCPP team around the organisation of the workshop to maximise inclusion

  - Support OCPP in the development of GESI and SEAH materials to support the event delivery.

  - Attend event to officially launch the Maldives GESI and SEAH Handbook.

Contractors should have extensive experience of working in GESI and SEAH in Maldives. They should have experience of stakeholder engagement, workshop organisation and facilitation. We are also looking for a contractor that has practical implementation of GESI and SEAH in development projects in Maldives.

## Product Specification

The outputs for this project would include:

GESI Handbook and SEAH Handbook for Maldives

Development of GESI and SEAH Network Platform for Maldives

GESI and SEAH Workshop report

SEAH Training materials

Support to OCPP with GESI and SEAH material development for PCA Forum 2.

Please see section 3 for more information on the requirements, and section 7 for timelines.

Where necessary, the outputs and material that JNCC publishes should be compliant with the Web Content Accessibility Guidelines version 2.1 AA standard. This will be discussed with the contractor prior to production of outputs and materials and JNCC will provide a reporting template if needed.

## Dissemination

The products/outputs produced under this contract will be a JNCC product and shall not be published or disseminated without the written permission of JNCC. Outputs may at some point be published on the JNCC website and all material supplied as part of this contract shall remain copyright of JNCC. The findings from this contract will also be made available to staff within JNCC, Defra, Cefas, MMO and relevant Maldives Government departments as needed.

## Timescale

Provisional dates for delivery of the contract outputs are set out below. Exact dates are to be agreed at the start-up meeting based on Contractor and JNCC staff availability.

| Output | Provisional Date |
| --- | --- |
| Start-up meeting (via video call) | w/c 19 May 2025 |
| Delivery of draft Handbooks | 31 July 2025 |
| Delivery of final Handbooks | 26 September 2025 |
| Establishment of Maldives GESI and SEAH Network | 4 July 2025 |
| Delivery of Network Workshop | October 2025 (exact dates to be confirmed) |
| Support to OCPP on PCA Forum 2 planning | 28 November 2025 |
| Delivery of Workshop report and SEAH training materials | 28 November 2025 |
| Support for launch of Handbook at PCA Forum (date TBC) | February 2025 (exact dates to be confirmed) |
| End of contract | 27 February 2026 |

In agreeing exact dates please note that the potential for work under this contract to be funded into 2025/26 is subject to availability of funds.

## Health and Safety

The successful bidder is expected to follow appropriate Health and Safety Procedures including adhering to JNCC’ policy on safeguarding. For further information  https://jncc.gov.uk/about-jncc/corporate-information/safeguarding/ and to be able to undertake appropriate risk assessments, evidence of which should be supplied to JNCC.

(NB under no circumstances should any work or service commence prior submission of risk assessment to JNCC Project Manager, and this has been approved by JNCC).

Any incidents occurring within the contract period should be immediately reported to JNCC.

General Duty of care: The organiser shall commit to exercise reasonable care and take necessary precautions to ensure the safety and well-being of attendees during the event (s) / Workshop (s).

Emergency Procedures: Outline the steps the organiser will take in the event of an emergency, including evacuation procedures, medical assistance, and communication protocols. This may include conducting risk assessments and providing necessary safety equipment and ensuring compliance with the relevant Health and Safety regulations.

## Project Management

The successful Contractor shall nominate a project manager who shall be responsible for ensuring the project is completed satisfactorily and who shall be the main contact point for JNCC.

JNCC’s main contact points will be:

Name: Beth Flavell

Email: Beth.Flavell@jncc.gov.uk

Telephone: +441733 866952

## Instructions for Bid Submission

The bid submission should include the following:

A brief summary of the bidder’s experience in relation to the requirements of this contract;

A proposed approach for achieving the aims of the contract and delivering the detailed tasks identified within each objective. This should be sufficiently detailed to allow assessment against the evaluation criteria (Section 12);

A detailed project plan with proposed work programme and an estimate of time required to achieve each objective;

Details of the Project Team including their roles and experience

Overall quote for the contract to include:

  - Day rates for all members of the Project Team;

  - Costs and time allocation should be clearly allocated to specific tasks within this contract (as detailed in section 3);

  - JNCC adhere to UK civil service travel and subsistence rates however, rates are not listed for Maldives and the nearest city, Colombo, Sri Lanka does not adequately reflect travel and subsistence costs for Maldives. Therefore, when estimating costs for subsistence and accommodation please use the following maximum rates that have been advised by the British High Commission in Malé and based on costs experienced by JNCC when undertaking Maldives trips:

    - Malé accommodation per night $170

    - Malé daily subsistence rate $40

    - Outside of Malé accommodation per night $100

    - Outside of Malé daily subsistence rate $30

  - VAT if applicable. The contractor is to specify whether VAT at the prevailing rate would be applicable to this project and if so, provide their VAT registration number.

The following documentation (to submit in a zip folder separate from the proposal) where possible:

  - Copies of health and safety policy statements where available or a note regarding such items as lone working, emergency procedures and accident reporting;

  - Copies of current public and employer liability insurance certificates;

  - Copies of any appropriate risk assessments;

  - Copies of your company's modern slavery and or safeguarding statement or policy and;

  - Copies of any environmental policies should you have them.

## Evaluation Criteria

JNCC is not bound to accept the lowest priced or any bid. Having the technical expertise and experience to complete the work to a high standard and being able to complete it within the timescale are of the essence for this contract.

The bid evaluation may be undertaken by a panel consisting of JNCC and Cefas staff.

For information on how we handle personal data please see our Privacy Notice at https://jncc.gov.uk/about-jncc/corporate-information/privacy-statement/

Bids will be evaluated using the following criteria:

|  | EVALUATION CRITERIA | Maximum Score | Score |
| --- | --- | --- | --- |
| 1. Quality of Bid |  |  |  |
| i | Clarity of proposal outlining work programme and deliverables | 10 |  |
| ii | Understanding of, and relevance to, the requirements in particular the adequacy of outputs and understanding of cultural and engagement values in Maldives | 8 |  |
| iii | Soundness and logic of methods | 4 |  |
| iv | Identification and proposed solutions to potential risks/issues | 4 |  |
| v | Probability of success | 4 |  |
|  | Sub Total | 30 |  |
| 2. Details of Contractor |  |  |  |
| i | Expertise, experience, and balance of team, including their understanding of the GESI and SEAH position in Maldives | 13 |  |
| ii | Specific experience of working in GESI and SEAH in Maldives | 10 |  |
| Iii | Experience of implementation of GESI and SEAH in development projects |  |  |
| iv | Experience of organising events and stakeholder engagement | 10 |  |
| v | Ability to work in English and Dhivehi | 7 |  |
|  | Sub Total | 40 |  |
| 3. Cost |  |  |  |
| i | Transparency and correctness of the presentation of costs | 15 |  |
| ii | Fairness/reasonableness for the level of work and expertise required – cost effectiveness | 15 |  |
|  | Sub Total | 30 |  |
| Total Score |  | 100 |  |

## Payment

PLEASE NOTE: All quotes and all payments must be based on British Pounds (£) or US Dollars ($). If alternative currency payments are needed, please raise this at the earliest opportunity during the bid process so we can explore options.

Unless a payment schedule is stated in your submission and agreed by JNCC project manager. Payment will be made on completion of the objectives following the submission of invoice(s) and based on the satisfactory undertaking of the contractual elements to the agreed standard of the JNCC Project Officer.

## Additional Requirements

All bidders are requested to carefully read the Terms and Conditions applying to this contract. Payment will only be made upon delivery of key outputs.

It is assumed that all costs associated with the production of figures, reproduction of photographs and the final report are accounted for within the rates/fees given.

The bidder is expected to supply all necessary equipment, software, licences, etc. to carry out the obligations required under the contract.

## Procurement Timetable (which may be subject to change)

| Activity | Date |
| --- | --- |
| Publication of Tender Notice | 15 April 2025 |
| Last date for receipt of clarification questions | 2 May 2025 |
| Final submission date for bids | 9 May 2025 |
| Evaluation of bids |  |
| Post-tender negotiation/clarification and or presentation if required |  |
| Successful/unsuccessful bidders notified |  |
| Contract award | May 2025 |
| Start of project | W/C 19th May 2025 |