## Sheet1
Land at Snoxhall Fields
Knowle Lane
Cranleigh
GU6 8JN
SPECIFICATION OF WORKS
| Works: | Erection of a new machine shed and associated storage and equipment stores within a compound
| Employer: | Cranleigh Parish Council
| Architect: | Carter Davey Architects
| Dated: | 2025-09-08
| Revision: | A 12.10.25
| Status: | TENDER
CONTENTS
| A | CDM 2015 Pre-Construction Health and Safety Plan
| B | Tender Particulars
| C | Contract Particulars
| D | Completion
| E | Schedule of Works
| F | Collection
| G | Form of Tender
Part A
CDM 2015 PRE-CONSTRUCTION HEALTH AND SAFETY PLAN
Notes:
1 | INTRODUCTION:
1.1 | This Pre-Construction Health and Safety Information Report has been prepared by Carter Davey Architects LLP on behalf of our client, Craleigh Parish Council, in accordance with the Construction (Design and Management) Regulations 2015.
1.2 | The Contractor for this project will be appointed as the Principal Contractor as defined in CDM Regulations 15 and will act as Principal Designer for Work Stage 5 Construction if no others are appointed.
1.3 | The Contractor must be able to satisfy the client that they have adequate resources and are in all respects competent to execute the duties of the Principal Contractor as required by the CDM regulations 15.
1.4 | Co-operation is essential as part of the Regulations and therefore it is important that those involved with the project co-operate to enable all persons to perform their Duty or function under the CDM Regulations 15.
2 | PROJECT DETAILS:
2.1 | CLIENT: Cranleigh Parish Council, Village Way, Cranleigh, Surrey, GU6 8AF
Contact: Beverley Bell, Clerk of the Parish Council Tel: 01483 272311 Mobile: 07949073875 Email: clerk@cranleigh-pc.gov.uk
2.2 | ARCHITECT: Carter Davey Architects LLP, 9 Dale Drive, Brighton, East Sussex, BN1 8LD
Contact: Jasmine Davey Mobile: 07525 643101 Email: davey.cda@gmail.com
2.3 | STRUCTURAL ENGINEER: Hockley & Dawson Consulting Engineers Ltd, 5 Birley Courtyard, Bramley, Surrey, GU5 0LA
Contact: Chris Smaller Tel: 01483 548784 Mobile: 07969043671 Email: chris.smaller@hockleyanddawson.co.uk
2.4 | PRINCIPAL DESIGNER:
| Work Stages 0-4 | Carter Davey Architects LLP
| Work Stage 5 | Carter Davey Architects LLP
2.5 | CONTRACTOR:
To be appointed
2.6 | OTHER CONTACTS:
| Building Control: Waverley Borough Council Building Control |  |  | To be issued once Tenders have been received
Contact: Mobile: Email:
Ref:
2.7 | Description of the Works
To create secure and safe site for storage of machinery and materials, which will include; store and workshop, equipment store, field shelter, shipping containers, welfare unit and 1.8m perimeter fence panels. The project requires full new utility connections to service the site.
2.8 | Programme of Works |  |  | Contractor to complete:
Lead time:
Date of commencement:
Construction period:
3 | EXISTING SITE
3.1 | The site is located on the south-west corner of Snoxhall Fields on an existing open compound area which is already in active use. The site is located adjacent and to the east side of Knowle Lane which runs north to south, and is accessed via an existing track off of Knowle Lane which services the site and the allotment located directly to the south. To the west of Knowle Lane is Bruce MacKenzie Field.
3.2 | The existing site is bounded by a ditch and grass verge to the western side with tall tree screening seperating the site from Knowle Road, and tree and vegetation screening to the south between the site and the allotments. The site is open to Snoxhall Field, which includes a football pitch with floodlights on the eastern side.
3.3 | The site is located within the Countryside beyond the Green Belt and an Area of Strategic Visual Importance (ASVI).
3.4 | The site is located within the Dunsfold to Pollingfold Landscape Character Area, which is defined as a large character area to the south of Cranleigh and is considered to have a semi-rural character and appearance.
3.5 | Site Access
The Contractor will have shared use of the vehicular access off of Knowle Lane with the allotment site for deliveries. The vehicular access is to be kept clear at all times and will be shared use with the users of the allotment. Allow clear access to the site. There is adequate space for on site parking.
3.6 | Site Compound
The Employer will provide space for delivery and storage of materials adjacent to the Contractors parking on the site within the field area for secure storage of materials and messing facilities.
The Contractor will be granted Vacant Possession of the site to undertake the full Works package.
3.7 | Existing Fabric
The existing site comprises of hard standing, enclosed within a metal frame pallisade panels, with 2no. single vehicular access gates. Access to the site is provided via a hard standing track to both vehicular entrances, one from Snoxhall Fields to the east side, and the other to the south leading to Knowle Lane which includes a timber frame fence.
3.8 | Existing Services
There are no existing utility services known to be present on the site. Contractor should take all necessary precautions to identify services prior to undertaking the work.
4 | PROJECT INFORMATION:
4.1 | Existing Drawings
| 24866-100: | Existing Site Plan and Site Location Plan
4.2 | Planning Permission
Waverley Borough Council
Ref: WA/2025/01253
Dated: 20/08/2025
Consented drawings:
| 24866-200: | Proposed Site Plan and Site Location Plan
| 24866-201: | Proposed Site Location Plan
| 24866-210: | Proposed Plan
| 24866-211: | Proposed Plan
| 24866-212: | Proposed Floor Plan and Elevations - Store
| 24866-213: | Proposed Floor Plan and Elevations - Welfare Unit and Shipping Containers
| 24866-214: | Proposed Floor Plan and Elevations - Store and Workshop
| 24866-215: | Proposed Floor Plan and Elevations - Open Field Shelter
| 24866-216/A: | Proposed Site Sections
| 24866-217: | Proposed Site Sections
4.3 | Mechanical and Electrical Services
None
4.4 | Asbestos
N/A as the site is currently clear of structures.
4.5 | Discharge of Conditions (Planning)
| 25029-300: | Proposed Site Plan - soft landscaping
4.6 | Construction Package
| 25029-400: | Proposed Roof Plan
| 25029-401: | Proposed Site Plan
| 25029-410: | Building 1 - Store
| 25029-411: | Building 1 - Store
| 25029-412: | Building 2 - Welfare Unit
| 25029-413: | Building 2 - Welfare Unit
| 25029-414: | Building 3 - Store and Workshop
| 25029-415: | Building 3 - Store and Workshop
| 25029-416: | Building 4 - Open Field Shelter
| 25029-417 | Building 4 - Open Field Shelter
| 25029-418: | Building 5 - Shipping Containers
| 25029-600: | Construction Notes
Fixtures and Finishes Schedule
Designer Risk Assessment
4.7 | Structural Engineers Package |  |  | Sketch proposal by SE and DE only. Once final design is completed we will issue to Tenderers
| 22277 - 1 - 01 | Raft Foundation
4.8 | Drainage Engineers Package
| 252014/500/100: | Proposed Drainage Strategy
4.9 | Ecological Assessment
P10315 Snoxhall Machine Sheds Preliminary Ecological Appraisal - 19th May 2025
5 | DESIGN INFORMATION
5.1 | Hazard Identification and Risk Assessment
Risk assessments for hazards identified, where reasonably practical, in the development of the project to tender stage have been reviewed by the Architect and Structural Engineer. This review has not identified any unusual notes or hazards other than those likely to be encountered on refurbishment work of this nature.
The contractor should address any residual hazards arising from the risk assessments or identified in their development of the working procedures and method statements, together with any other identified hazards likely to be encountered in the course of executing the works and their future maintenance.
5.2 | Significant Health and Safety Hazards
The Principal Contractor should note the following particular hazards relating to the contract works which include but are not necessarily limited to:
- Existing Services: The presence of existing services close to the works should be established prior to starting work.
Care should be taken and relocation of existing overhead services which pass over the site area.
- Existing Buildings & Site: The condition and nature of the existing building should be considered in planning the works and other site operations. Particular issues identified during the design include but are not exclusive to:
• Ensuring that the site is safely secured.
• Impact on residential property in the vicinity.
- Materials: The proposed materials for use in the works are commonly used in the construction industry. However, the information on the COSHH sheets that are supplied with the products installed should be accurately followed.
- Protection of Public & Adjacent Occupiers: The proximity of the works to areas in use by the homeowner and neighbours. Particular note should be made of:
• Noise
• Vibration
• Dust
• Moving materials onto site
- Traffic Management: Ensure effective traffic management on the road to avoid putting workers at risk of being hit by vehicles turning or reversing.
5.3 | Method Statements
The Method Statements shall include, but not be exclusive to, the following details/information:-
• Protection to access routes.
• Proposed work sequence for project. This will need to be developed from the Project Drawings provided.
• Description of personnel/trades to be employed.
• Equipment to be used
• Preparation.
• Materials handling
• Control measures.
• Dust and debris removal.
• Lifting of plant and materials
• Working at height
• Site and working space security.
• Safety procedures.
• Procedures for working at heights.
• Monitoring procedures.
• Prevention of nuisance to adjacent buildings and facilities.
• Details of site access and storage.
• Fire control.
• Fire access and egress routes
• Emergency liaison procedures.
Reference should also be made to the items listed in the Project Preliminaries.
The Principal Contractor shall ensure that suitable Method Statements are produced well in advance of the commencement of any activity that presents a significant health and safety risk. These must be incorporated in and co-ordinated with the Construction Stage Health and Safety Plan.
6 | HAZARDOUS CONSTRUCTION MATERIALS
6.1 | Under no circumstances will any materials which could be harmful to the end user or hazardous to the works be allowed to be used. The Principal Contractor will not permit their use during the project. All construction materials will be used for the purpose for which they were intended and in accordance with the manufacturer’s recommendations and guidance.
6.2 | Contractors shall comply with manufacturer’s Health & Safety data sheets and the Control of Substances Hazardous to Health Regulations 1988 (COSHH) regarding the transport, storage and use of substances and materials injurious to health.
The materials to be used in the works shall be identified by the contractor and appropriate Risk Assessments for their use be undertaken in accordance with the COSHH Regulations.
A list of the materials used should be collated together with reference to COSHH assessments. This information should also be included in the Health & Safety File.
6.3 | Substances generally known to be deleterious at time of use, including substances referred to as being hazardous to health and safety in the current edition of “Hazardous Building Materials” - A Guide to the Selection of Alternatives edited by S R Curwell and S G March are included, as well as substances listed in the H.S.E. EH40 annual publication.
Asbestos: Asbestos or asbestos products as defined in the Asbestos Regulations 1969 or any statutory modification or re-enactment thereof.
Lead: Lead where metal or its corrosion products may be directly ingested, inhaled or absorbed.
Urea Formaldehyde: Urea formaldehyde foam or materials which may release formaldehyde quantities which may be hazardous or an irritant. Reference will be made to the limits set from time to time by the Health & Safety Executive.
Materials which are Generally of Mineral Fibres: Materials which are generally of mineral fibres, either man-made or naturally occurring, which have a diameter of 3 microns or less and a length of 2 microns or less which contain any fibres not sealed, encapsulated, or otherwise established to ensure that fibre migration is prevented.
6.4 | Specified Materials
The Principal Contractor is to be cognisant of the hazards associated with all materials that are used on the construction site.
7 | THE WORKING SITE
7.1 | Areas available to the Contractor
The Contractor will have full use of the vehicular access to the site. Parking is available on the site, and will be made available for clear access for deliveries to site.
The Contractor may enter the site via the main access onto the compound off of Knowle Lane to the west side of the site area.
An area adjacent to the site within the Snoxhall Field will be available to the contractor for site storage and messing facilities.
7.2 | Welfare Facilities
The contractor is required to provide appropriate sanitary facilities for site operatives and visitors. These should as a minimum comply with the Health and Safety at Work Act: Construction (Health, Safety and Welfare) Regulations 1996 and the ‘Code of Welfare for the Building Industry’.
7.3 | Water for the Works
There is no existing water suppy to the site. The Contractor will include to provide water for the Works until the supply is installaed and from that point water can be used from the site supply. From this point, use will be free of charge to the Contractor.
7.4 | Electricity for the Works
There is no existing power supply to the site. The Contractor will include for the power supply required for the Works until the supply is installed. Frm which point power for the execution of the Works may use the supply to the site. Provide all temporary wiring etc. and clear away upon completion. Use will be free of charge to the Contractor.
7.5 | Plant, tools, etc.
The Contractor is to provide and maintain all necessary tools, plant, scaffold etc. as required for the proper execution of the Works. Clear away upon completion. The Contractor shall ensure that all scaffold and other access platforms are inaccessible outside site hours and all ladders are to be placed in a locked store. Scaffold is to be made secure with 3.0m min. Heras fence.
7.6 | Drying out
The Contractor is to provide such equipment as is necessary for the drying out of the Works and pay all charges in connection.
7.7 | Clean
The site should be maintained and kept reasonably tidy at all times.
8 | OVERLAP WITH EMPLOYERS UNDERTAKING
8.1 | Working Hours
Normal working hours will be 8am to 5pm Monday to Friday.
Work outside these hours shall only be permitted with the written consent of the Employer and shall comply with local authority instructions.
8.2 | Noise Abatement
The Principal Contractor shall ensure that sufficient and adequate measures are taken to control noise levels produced by the construction operation to prevent nuisance and comply with the requirements of the Local Authority and BS5228 “Code of Practice for Noise Control on Construction and Demolition Sites”.
All compressors and pneumatic percussive tools to be used on the site shall be fitted with silencers of a type recommended by the manufacturers.
8.3 | Interruption of existing services
There are no existing services to the site, these are to be installaed as part of the Works
9 | SITE RULES
The contractor should note the following rules:
- Smoking: is not prohibited on site
- Radios: are not prohibited on site
- Noise: must comply with the Project Preliminaries
- Flammable Materials: the filling of fuel containers or transfer of flammable liquids within poorly contained or ventilated areas of the building is prohibited.
- Contractor: the principal contractor shall provide rules including; training, induction, equipment, personal protective equipment, permits to work, accident reporting, working at heights, moving equipment on and off site.
10 | PROJECT LIAISON PROVISIONS
10.1 | Contacts
Prior to the commencement of the work, the Principal Contractor shall provide the Employer with a list of names, addresses and telephone numbers of key contact personnel, including the Director who would be responsible for and capable of organising remedial action in the event of an emergency on site outside normal working hours.
10.2 | Construction Phase Health & Safety Plan
Prior to commencement of the works, the Principal Contractor shall develop a Construction Phase Health & Safety Plan, indicating his proposals for addressing the hazards. The Principal Contractor shall incorporate hazards arising during construction from unforeseen circumstances into the Health & Safety Plan. During the construction, liaison must be maintained by the Principal Contractor and the Employer.
10.3 | Site Meetings
A Health & Safety item shall be included on the Agenda for each site meeting. A copy of the minutes shall be provided to the Employer. This item shall report but not be exclusive to:
• Accidents
• Incidents
• Any hazardous materials / situations identified
• Protection of public
11 | HEALTH AND SAFETY FILE
11.1 | The Principal Contractor is responsible for the collection and collation of construction information for inclusion in the project Health & Safety File. The information to be provided shall include but is not exclusive to:
· A brief description of the work carried out;
· any hazards that have not been eliminated through the design and construction processes, and how they have been addressed (eg surveys);
· key structural principles (eg bracing, sources of substantial stored energy)
· hazardous materials used (eg lead paints and special coatings);
· health and safety information about equipment provided for cleaning or maintaining the structure;
· the nature, location and markings of significant services;
· information and as-built drawings of the building.
Further details of the requirements are described in the Project Preliminaries.
An electronic copy of the Health & Safety File, maintained and updated by the Principal Contractor, shall be provided to the Employer as soon as practical upon completion of the works.
Relevant copies of the site photographs shall also be sent to the Employer.
Part B
TENDER PARTICULARS
12 | Introduction
The following particulars apply to all Contractors submitting a Tender for this project. If the Contractor cannot comply with the following notify the Employer.
12.1 | The Employer will not be bound to accept the lowest or any Tender. The Contract will be on the basis of a fixed price.
12.2 | If a Contract Administer is appointed the Form of Contract will be the JCT Standard Form of Contract (SBC 2024) as published by the JCT.
12.3 | The Tender Package will form the Contract Documents as listed in Item 4.0.
12.4 | Tenders should be open to acceptance for a period of not less than 84 days from the date of receipt of Tenders.
12.5 | This is a performance specification. The Contractor is required to take for everything shown on the drawings or itemized in the Specification. Allow for executing the Works indicated and described and for all works not specifically mentioned but which can be reasonably inferred as being necessary for the proper execution of the Contract. Any matters which the Tenderer considers are not adequately described in the Specification or shown on the drawings must be brought to the attention of the Architect or Employer before the Tender is submitted. No extras will be considered in respect of items omitted from the drawings although itemized in the Specification or vice versa.
12.6 | The Tenderer shall visit the site and acquaint themself with all conditions appertaining to the site. They shall be deemed to have examined all of the tender documents and have acquainted themself with all aspects of the proposed works. No claim will be recognized in respect of want of knowledge.
12.7 | The Tenderer will be required to submit a priced copy of the Specification and a Schedule of Rates. The Tenderer shall allow for profit and attendance on all P.C. Sums. The prices in the Preliminaries shall be deemed to include compliance with any Enactment or Regulation appertaining and for everything necessary for the proper execution of the Contract.
12.8 | The Tenderer shall allow for all builder’s work and making good in connection with the work of all sub-contractors.
12.9 | The Contractor shall comply with all Statutory Notices appertaining and shall give all Notices required. They shall comply with all Enactments, Regulations and Working Rules relating to the Works. They shall pay all fees arising unless specified otherwise.
Part C
CONTRACT PARTICULARS
13 | Introduction
The following particulars apply to all Contractors submitting a Tender for this project. If the Contractor cannot comply with the following notify the Employer.
13.01 | Site foreman
The Contractor shall keep a competent foreman in charge of the site at all times.
13.02 | Covering up
The Contractor shall give adequate notice to the Architect/ Employer, Structural Engineer and/or Quantity Surveyor before covering up work which must be measured.
13.03 | Setting out
The Contractor will be responsible for errors in setting out and shall bring to the Architect’s attention any errors on the drawings or in the Specification.
13.04 | Programme
The Contractor shall prepare a programme before the commencement of the Works. He shall inform the Employer when the progress of the Works varies from the programme.
13.05 | Variations
The Contractor must notify the Employer of any additional costs associated with any Variations prior to related Works being undertaken for their approval and sign-off.
13.06 | Discrepancies
The Contractor shall notify the Architect of any discrepancy in the documentation and shall request instruction before proceeding with the work which is the subject of that discrepancy. The Contractor shall notify the Architect and seek instruction on any item which requires amendment as a result of findings upon opening up of the existing construction.
13.07 | Principal Designer
Will be the Architect
13.08 | Principal Contractor
Will be the main Contractor
13.09 | HSE
The project currently is not notifiable. If this changes HSE should be notified.
A construction project is considered notifiable if it is scheduled to last longer than 30 working days and involve more than 20 workers at the same time at any point on the project, OR if it is expected to exceed 500 person days in total. If this threshold is reached, Contractor to notify Architect
13.1 | Rectification Period
Will be 12 months
13.11 | Contractor Insurance
£5,000,000 (five million pounds), the Contractor is to provide the Employer with their insurance information.
13.12 | Insurance for the Works
Prior to the commencement of any Works by the Contractor the the Employer must notify their insurers of the Works intended and the date for commencement to ensure adequate insurance is in place in line with the Contract Sum and VAT and fees for the Contract Period, as set out in clause 5.4 in the JCT SBC.
Part D
COMPLETION
14 | Introduction
Upon completion of the Works all items below must be complied with.
14.01 | Drying out
The Contractor is to provide such equipment as is necessary for the drying out of the Works and pay all charges in connection.
14.02 | Clear Rubbish
Clear away from site to tip all rubbish and superfluous material. The Contractor may be required to provide evidence that such material has been correctly disposed of.
14.03 | Clean
Upon completion of the Works a full clean of all surfaces using methods suitable for the surface being cleaned and leave the Works, the site and the existing buildings clean, neat and tidy to the satisfaction of the Employer. Remove all temporary markings, coverings and protective wrappings unless otherwise instructed.
14.04 | Security
Leave the works secure with all accesses locked. Account for all keys and hand over to Employer.
14.05 | Maintenance instructions and guarantees
Forward to the Employer at Practical Completion all maintenance manuals, instructions, guarantees and certifications.
14.06 | Practical Completion
The Contractor shall request the Employer and CA to conduct an inspection and approval before striking any access, when they believe Practical Completion has been achieved.
14.07 | Final Inspection
Request Employer undertakes a final inspection and approval before striking any access. Please note that the completion of the works in accordance with the Contract Specification of Works or any subsequent instructions is the contractor's responsibility. The Employer cannot guarantee to notice all items of unfinished work, and it will be the contractor's responsibility to make all careful and final checks on this aspect before they give orders for access to be struck or labour to leave the site.
Part E
SCHEDULE OF WORKS
When completing this Schedule of Works Part A-D above applies and reference should be made to the Construction Notes, Construction Drawings, Structural Engineers Package and Fixtures and Finishing Schedule. Highlight any works missed from this schedule with associated costs in item 28.00 Other or as a note in the relevant section below.
Identify all items that include Provisional Sums within the notes column.
|  |  |  | Notes: | Quantity | Cost (£)
15 | Site Set Up
15.01 | Access
Employer will provide the Contractor with keys to the compound prior to the commencement of the Works for access during the working hours. The Contractor to be responsible for maintaining security to the site for the duration of the Works. The Contractor may enter the site from Knowle Lane and use the shared vehicular track that reaches the south side of the site. Allow for making good reasonable disturbance. The Employer will have removed all machinery and storage from the site area. The Employer will have cleared the surrounding vegetation where required prior to commencemnt of the Works.
15.02 | Welfare facilities
The contractor may use a portion of the land adjacent to the site for Welfare facilities. Location to be agreed with the Employer. This area must be contained at all times.
15.03 | Fire extingushers
Contractor to keep at least four suitable fire extinguishers on site in suitable locations at all times.
15.04 | Existing Site Assessment/Survey
Prior to commencing the works undertake a pre-site survey.
15.05 | Temporary facilities
The contractor may use a portion of the land adjacent to the site for storage and messing facilities. Location to be agreed with the Employer. This area must be contained at all times. The contractor will ensure the site is left tidied and clear of rubbish with materials neatly stored at the end of each working week. Provide facilities for waste materials. The Contractor shall note the risk of leaving a skip on site. He shall ensure that when it is required it is placed at least 6.0m away from any building, fence or tree as is possible. Any flammable materials shall be removed from the site at the end of each day.
15.06 | Temporary Protection
The contractor shall contain the working area to the minimum extent required to execute the Works safely. Provide all necessary temporary protection for the security of the site, maintain and clear away upon completion. No materials or equipment should be left in any place that is not secure.
15.07 | Access Platforms
Provide all necessary temporary platforms and structures to facilitate the execution of the Works in accordance with the safe working practices and regulations, maintain and clear away, including all materials upon completion. All poles shall have plastic caps fitted where these will abut the masonry. Except for the reason of Health & Safety no fixings shall be made into the masonry for securing the scaffold and when they are required the positions at which the scaffold wishes to fix shall be referred to the Contract Administrator for comment. The scaffold shall be designed by the scaffolder in accordance with current Regulations – the contractor shall allow for all costs in connection.
15.08 | Services
There are no existing electrical or water service connections to the site. Contractor to include for the supply of these services until they are available for use within the site. Once services are connected. the Contractor will have use of water and electrics from the site. The Contractor shall be responsible for maintaining all services for the duration of the Works unless otherwise agreed.
Total for Site Set Up
16 | Dismantlement
Refer to the construction drawings for the demolition layout. Ensure existing ground mot base to be retained is supported at all times. Seek advice from the Structural Engineer if the existing construction is not in line with their package.
Provide all necessary temporary protection for the security of the site, maintain and clear away upon completion. All materials to be disposed of appropriately.
16.01 | Externally
At the appropriate stage dismantle the existing boundary fencing in line with the construction drawings and Structural Engineer's package, and clear away. The existing 2no. Access gates are to be retained for reuse.
Total for Dismantlement
17 | Foundations
17.01 | Trial holes
Refer to the bore hole survey report which has been used in the preparation of the Strcutrual Design Package to establish the required depth of the foundations prior to the commencement of the works.
17.02 | Excavation
Excavate trenches to the required depths, dimensions and in the locations indicated in accordance with the Construction Drawings, Construction Notes and Structural Engineers package. Should the Building Control Officer require a depth greater than that shown on the drawings, seek an instruction to confirm. Provide all temporary support required either by the depth of the excavation or the nature of the ground strata. Allow to clear away excavated waste materials.
17.03 | Foundations
Form foundations in accordance with the Construction Drawings, Construction Notes (item 1.00) and Structural Engineers package and to the approval of the Building Control Officer.
Allow for the foundations for:
| Building 1 - Store | 12 x 7m
| Building 2 - Welfare Unit | 5.87 x 2.74m
| Building 3 - Store and Workshop | 9.6 x 6m
| Building 4 - Field Shelter | 12 x 4m
| Building 5 - 2no. Shipping Containers | 2.4 x 6.96m
Total for Foundations
18 | Drainage & Water Supply
18.01 | New Water Supply
Thames Water, or Self-Lay provider (SLP) to lay new water mains connection to the site and connect up operable in accordance with the Construction Drawings and Construction notes and to the approval of Thames Water and Building Control.
18.02 | Foul Drainage - Water Treatment Plant
Construct new in accodance with the Drainage Design and Construction Notes and to the approval of Building Control.
18.03 | Surface water drainage
Construct new in accodance with the Drainage design, Construction Drawings and Construction Notes and to the approval of Building Control.
18.04 | Rainwater goods
Supply and fix new gutters, downpipes and all required fittings in accodance with the Construction Drawings and Construction Notes and to the approval of Building Control.
18.05 | French drains/ Aco drains
Construct new in accodance with the Drainage Design, Construction Drawings and Construction Notes and to the approval of Building Control.
Total for Drainage
19 | Floors
19.01 | Floor Slab
Construct in accodance with the Construction Drawings, Construction Notes (item 5.00) and Structural Engineers Package and to the approval of Building Control.
Allow for Floor Slab for:
| Building 1 - Store | 12x7m
| Building 2 - Welfare Unit | 5.87x2.74m
| Building 3 - Store and Workshop | 9.6x6m
| Building 4 - Field Shelter | 12x4m
19.02 | Finishes
Supply and install in accordance with the F&F Schedule.
Total for Floors
20 | Superstructure
20.01 | Walls
Supply and install steel frame structures and all associated fixings in accordance with the Construction drawings and Construction notes.
20.02 | Roof
Supply and install steel frame structures and all associated fixings in accordance with the Construction drawings and Construction notes.
Allow for the supply and installation of:
| Building 1 - Store | 12x7m
| Building 2 - Welfare Unit | 5.87x2.74m
| Building 3 - Store and Workshop | 9.6x6m
| Building 4 - Field Shelter | 12x4m
20.03 | Wall Cladding
Supply and install vertical timber batten cladding including all associated fixings to all external walls in accordance with the Construction drawings and Construction notes.
20.04 | Roof Cladding
Supply and install sheet metal roof finish in accordance with the Construction drawings and Construction notes.
Allow for the supply and installation of:
| Building 1 - Store | 12x7m
| Building 2 - Welfare Unit | 5.87x2.74m
| Building 3 - Store and Workshop | 9.6x6m
| Building 4 - Field Shelter | 12x4m
20.05 | Insulation
Supply and install insulation to walls and ceilings within the Welfare unit and store and workshop in accordance with the Construction drawings and Construction notes
Allow for the supply and installation of:
| Building 2 - Welfare Unit | 5.87x2.74m
| Building 3 - Store and Workshop | 9.6x6m
20.06 | Internal Walls
Construct in accodance with the Construction Drawings, Construction Notes (items 7.00) and Structural Engineers Package and to the approval of Building Control.
Allow for the supply and installation of:
| Building 2 - Welfare Unit | 5.87x2.74m
20.07 | Finishes
Supply and install in accordance with the F&F Schedule.
| Building 2 - Welfare Unit | Shower panels
Total for Super Structure
21 | Shipping Containers
21.01 | Shipping Container 1
Supply and install 1no. Shipping containers in accordance with the Construction drawings and Construction notes.
21.02 | Shipping Container 2
Allow for the relocation of 1no. Shipping container already owned by Cranleigh Parish Council, this is located on the other side of the field.
21.02 | Cladding
Containers to be clad in vertical timber batten cladding to 3no. sides.
Total for Shipping Containers
22 | Windows and Doors
22.01 | Windows
Supply and install all windows in accordance with the Construction Drawings, Construction Notes, Structural Engineer's package and F&F Schedule. All dimensions must be checked and confirmed on site once opening has been formed.
| Building 1 - Store | 6no. Rooflights | RL01-06
| Building 2 - Welfare Unit | Window | W01
|  | 3no. Rooflights | RL11-13
| Building 3 - Store and Workshop | 4no. Rooflights | RL07-10
| Building 4 - Field Shelter | 3no. Rooflights | RL14-16
22.02 | Doors
Supply and install all doors in accordance with the Construction Drawings, Construction Notes, Structural Engineer's package and F&F Schedule. All dimensions must be checked and confirmed on site once opening has been formed.
| Building 1 - Store | Roller Shutter 3x3m | ED01
|  | Personelle Door | ED02
| Building 2 - Welfare Unit | Personelle Door | ED05
|  | Door between Welfare & Worshop | ID01
|  | Internal Door | ID02
|  | Internal Door | ID03
| Building 3 - Store and Workshop | Roller Shutter 3x3m | ED03
|  | Personelle Door | ED04
| Building 4 - Open Field Shelter | Roller Shutter 3x2.5m | ED06
Total for Windows and Doors
23 | Piped Services
23.01 | Sanitaryware
Connect cold and hot water supplies to the fittings indicated and connect up operable. Refer to Construction Drawings, Construction Notes (item 15.00) and F&F Schedule.
Supply and install sanitaryware in line with Construction Drawings, Construction Notes and F&F Schedule.
| Building 2 - Welfare Unit | WC
Shower Room
Allow for supply and drainage within Welfare Unit for a future sink within the office space
| External Water Supplies | Taps
23.02 | Test
Test all installations and leave in full working order and certify accordingly.
Total for Piped Services
24 | Electrical/ Wired Services
24.01 | New Power Supply
A new power supply is required to the site, to be connected by the local Distribution Network Operator (DNO) or an Idependant Connection Provider (ICP). Their current provider is UK Power.
Allow for the supply and installation of a new power supply
24.02 | Power
Refer to the Construction Notes (item 16.00) and the F&F Schedule. Install new terminals as may be required to provide power to the points indicated on the drawings
24.03 | Lighting
Refer to the Construction Notes (item 16.00) and the F&F Schedule. Install new terminals as may be required to provide power to the points indicated on the drawings
24.04 | Mechanical Ventilation
Refer to the Construction Notes (item 11.00) and the F&F Schedule. Install new terminals as may be required to provide mechanical ventilation to the points indicated on the drawings
24.05 | Water Heater
Supply and install electric shower and water heater for sink as per the Construction Drawings and Construction Notes.
24.06 | Radiators
Supply and install new radiators in accordance with the Construction Drawings, Construction Notes (item 18.00) and F&F Schedule. All radiators shall be provided with thermostatic radiator valves TRVs.
24.07 | Towel rails
Supply and install new towel rails in accordance with the Construction Drawings, Construction Notes (item 18.00) and F&F Schedule. All radiators shall be provided with thermostatic radiator valves TRVs.
24.08 | Telephone and Internet Connection
Allow for the supply of data to the site
24.09 | Security
Supply and install new CCTV and security alarm system
24.1 | Fire Alarm
Supply and install new fire alarm system CIA (Securitas Technology) or others
24.11 | Test
Test all installations and leave in full working order and certify accordingly.
Total for Wired Services
25 | External Works
25.01 | Entrance Gates
Retain the existing security entrance gates.
25.02 | Fencing
Supply and install new 1.8m high galvanised metal fencing between buildings and gates to form secure perimeter to the site, in accordance with the Construction drawings and Construction notes and clad in vertical timber boarding.
25.03 | Yard Area Floor Finish
Retain the existing finish wherever possible. Make good to match existing.
Shore up existing base to SE design (removing existing timber)
25.04 | Armco Barriers
Supply and install Armco impact barriers to the frontage of Buildings 1 and 3, to either side of the roller doors to protect the front corners of the building from accidental damage.
25.05 | Landscaping
Supply and install planting in accordance with the Landscaping Proposal and Discharge of Condition no.4 drawing 25029/300.
Total for External Works
26 | Other (required but not included above)
26.01 | Ecology
The development shall be completed at all times in accordance with the Ecological Assessment (Ecology Co-op dated 19th May 2025 in line with Planning Condition no. 3.
Total for Other
27 | Completion
Clear away all rubbish and leave the site neat and tidy to the satisfaction of the Contract Administrator.
Total for Completion
28 | Overheads and Profit
Contractor to include for all on and off site management including working site foreman, project management, office support, surveying, and setting out. OH&P and any other requirements in order to execute the Works.
Total for OHP
Part F
COLLECTION
| 15 | Site Set Up
| 16 | Dismantlement
| 17 | Foundations
| 18 | Drainage & Water Supply
| 19 | Floors
| 20 | Superstructure
| 21 | Shipping Containers
| 22 | Windows and Doors
| 23 | Piped Services
| 24 | Electrical/ Wired Services
| 25 | External Works
| 26 | Other not included above
| 27 | Completion
| 28 | Overheads and Profit
|  |  | Total to Form of Tender | £
Part G
FORM OF TENDER
To: | Cranleigh Parish Council
Village Way
Cranleigh
Surrey
GU6 8AF
Works: | Erection of a new machine shed and associated storage and equipment within a compound
Sirs/Madam -
I/We having read the Specification of Works delivered to us and having examined the drawings and documents referred to therein do hereby offer to execute and complete in accordance with the Conditions to the Contract the whole of the Works described for the Sum of
£
( in words__________________________________________________________________________________________)
and within __________________________________Weeks from the date for possession.
I/We will be able to commence the Works within __________________________________ Weeks from the date of acceptance of this Tender.
I/We agree that should obvious errors in pricing or errors in arithmetic be discovered before acceptance of this offer these errors will be dealt with in accordance with Alternative 2 contained in Section 6 of the ‘Code of Procedure for Single Stage Selective Tendering’ 1994 edition:
‘The Tenderer should be given an opportunity of confirming his offer or of amending it to correct genuine errors. Should he elect to amend his offer and the revise Tender is no longer the lowest, the offer of the firm now lowest in the competition should be examined.’
This Tender will remain open for consideration for 84 days from the date fixed for the submission of Tenders.
| Dated: | _________________________________
| Name: | _________________________________
| Address: | ____________________________________________________________________________
____________________________________________________________________________
| Signature: | _________________________________