# Annex A

| Title of Project | Towards development of a UK peatland indicator framework |
| --- | --- |
| Date and Time for Return of Bids | Tuesday 25th November 2025 @09:00 Hours (UK) |
| Contract Reference Number | C25-0607-2122 |
| Address for Bid Submission | 1 electronic copy to be sent to TenderResponse@jncc.gov.uk PLEASE DO NOT SEND BIDS DIRECTLY TO (name of project officers) OR A MEMBER OF THE JNCC PROCUREMENT TEAM VIA THEIR WORK EMAIL ADDRESSES AS THIS WILL INVALIDATE YOUR BID. Bids must be less than 10 MB in size. On receipt of your bid, you will receive an automated e-mail to confirm receipt by the JNCC Support Co. If you do not receive this automated email, please contact the number below; (00 44 1733 866 988) |
| Contacts for Technical Information relating to this Project Specification | Procurement Team Joint Nature Conservation Committee Email: contractqueries@jncc.gov.uk Telephone: 01733 562626 |
| Contact for Queries Regarding the Procurement Procedure | Procurement Team Joint Nature Conservation Committee Email: contractqueries@jncc.gov.uk Telephone: 01733 562626 |
| Proposed Start Date | Monday 12th January 2026 |
| Proposed End Date | Friday 20th March 2026 |

Towards development of a UK peatland indicator framework

Contents

1.	Joint Nature Conservation Committee	3

2.	Project Aims	3

3.	Project Background	3

4.	Project Objectives	3

5.	Project Objectives: Detailed Tasks	3

6.	Potential Follow-On Work (delete if non-applicable)	3

7.	Outputs	4

8.	Product Specification	4

9.	Dissemination (delete if non-applicable)	4

10.	Timescale	5

11.	Health and Safety	5

12.	Project Management	5

13.	Instructions for Bid Submission	6

14.	Evaluation Criteria	7

15.	Payment	9

16.	Additional Requirements	9

17.	References	9

18.  Procurement Timetable (which may be subject to change)	9

## Joint Nature Conservation Committee

The Joint Nature Conservation Committee (JNCC) is the statutory adviser to the UK Government and devolved administrations on UK and international nature conservation

Our role is to provide scientific evidence, information, and advice to inform decisions to  protect the natural environment. Our specific role is to work on nature conservation issues that affect the UK as a whole and internationally, by:

advising Government on the development and implementation of policies for, or affecting, nature conservation in the UK and internationally;

providing advice and disseminating knowledge on nature conservation issues affecting the UK and internationally;

establishing common standards throughout the UK for nature conservation, including monitoring, research, and the analysis of results; and

commissioning or supporting research which it deems relevant to these functions.

Background to JNCC can be found on JNCC’s website at: https://jncc.gov.uk/about-jncc/

## Project Aims

To develop conceptual models describing the variables affecting wildfire risk, flood risk, water quality and/or water provisioning in and downstream from peatland.

## Project Background

When in good condition, peatlands are important for delivering a wide range of benefits to society, such as carbon storage and reduced emissions, wildfire regulation, flood regulation, water quality regulation, and water provision - as well as many cultural and supporting services, such as preservation of archaeology, outdoor recreation, and habitat provision. Whilst a national indicator of peatland carbon balance already exists, within the UK Greenhouse Gas Inventory, similar national scale data are not currently available for the other benefits that peatlands provide.

In order to ultimately reach the stage of developing additional indicators focused on societal outcomes, the first step is to gain a thorough understanding from the literature of the known variables affecting that benefit and develop a conceptual model – as specified within this invitation to tender.

The eventual existence of such indicators would allow for:

- more effective business cases to be made by those seeking funding for peatland conservation and restoration activities

- more informed decisions to be made by funders, and stronger justification for decisions they make around public spending

- a clear and relatable way to communicate the importance of peat to non-specialists, such as ministers and the general public

- tracking of progress through time, for example against each of the four UK countries’ Peatland Strategies

- policymakers to design more effective policies through an improved understanding of the pressures and drivers that are affecting the indicator results

- depending on the format of the final model, potentially spatial prioritisation, prediction of the output of any given policy, and an understanding of any trade-offs and potential for perverse incentives from a given policy.

Stakeholder engagement across the four UK countries has identified a need for a UK peatland indicator framework, and several potential indicators were selected as priorities –  four of which (wildfire risk, flood risk, water quality, and water provisioning) JNCC wish to let an initial research phase on. JNCC have already undertaken a short scoping exercise on the feasibility of a range of potential peatland indicators, the outputs of which will be shared with the successful contractor as a starting point.

For the purposes of this project, we use the term ‘indicator’ in its broadest sense; anything that gives an indicative metric of change through time, whether that is measured or modelled, and whether that is related to a driver, a pressure, a state, an impact or a response; with modelled impact indicators being the specific direction within this that we wish to take forward. We are however focusing on indicators relevant to a national scale - whether producing a national total or a national map - rather than indicators that are designed to be used in an individual project on a very small scale, for example to determine whether restoration actions of an individual project have been successful.

## Project Objectives

To meet the overall aims of this project (Section 2), the objectives are:

- To undertake an evidence review identifying the factors affecting peatland’s delivery of the following societal outcomes. We welcome bids to develop a minimum of one and a maximum of all four outcomes, depending on the expertise of the bidder. Please note JNCC reserves the right to accept all or part of your bid:

  - Wildfire risk

  - Flood risk

  - Water quality

  - Water provision

- To develop a conceptual model (a graphical representation of a system, identifying components of the system and the relationships between them) based on the literature review findings

- To note any relevant available data that the contractor comes across whilst undertaking the other two objectives

## Project Objectives: Detailed Tasks

  - Evidence review

- Each review should answer one of the following key questions:

  - Which variables (pressures, management actions, condition metrics, geographic or climatic features, etc) affect wildfire risk in UK peatland environments? What is their relationship (e.g. positive/negative, strong/weak, linear/complex) with wildfire risk in UK peatland environments?

  - Which variables (pressures, management actions, condition metrics, geographic or climatic features, etc) affect flood risk downstream from UK peatland environments? What is their relationship (e.g. positive/negative, strong/weak, linear/complex) with downstream flood risk?

  - Which variables (pressures, management actions, condition metrics, geographic or climatic features, etc) affect water quality downstream from UK peatland environments? What is their relationship (e.g. positive/negative, strong/weak, linear/complex) with downstream water quality? Water quality includes the presence of discolouration, the presence of a range of specific chemical pollutants (e.g. nitrates and sulphates) and/or water treatment costs to remove those of relevance to human health.

  - Which variables (pressures, management actions, condition metrics, geographic or climatic features, etc) affect water provisioning capabilities downstream from UK peatland environments? What is their relationship (e.g. positive/negative, strong/weak, linear/complex) with water provision capabilities?

- The search strategy and information to be recorded from each paper should be proposed to JNCC at the start-up meeting, for input and agreement, before work commences

Where possible, the review methodology should align with the ‘quick scoping review’ and/or ‘rapid evidence review’ guidance provided at https://www.gov.uk/government/publications/the-production-of-quick-scoping-reviews-and-rapid-evidence-assessments

- Where any quantitative evidence about relationships between variables, interactions between variables, and the relative weighting of variables are found, this information should be recorded (e.g. the benefit increases linearly with variable x; or variable a only effects the benefit when variable b is in a particular state)

- The list of papers screened, included/excluded, and raw notes from each paper reviewed should be shared as an output

- In addition, findings should be written up into a short summary that could be included within a technical report at a later date, if an indicator based on this information is subsequently developed

- Where evidence gaps are noted (e.g. ‘it was not possible to conclude on x from the studies available’), these should be noted within the summary

Recent JNCC work assessing the impacts of peatland restoration actions on ecosystem service delivery will be shared with the successful contractor for them to build on . If undertaking the wildfire review, the contractor may also wish to build on this previous JNCC project predicting wildfire risk in the Brecon Beacons: https://hub.jncc.gov.uk/assets/7691fb4a-b77a-4f8e-8660-a06b567ba345

- Conceptual model

  - By conceptual model, we mean a flowchart depicting key factors of relevance to the societal benefit in question, including peatland-relevant pressures, management actions, condition metrics, geographic or climatic features, and intermediate steps in the system

  - This task will synthesise the findings from the literature review into a similar diagram

  - The aim is not for an entirely complete systems map, but to identify the variables likely to be most significant. The successful contractor will involve the JNCC steering group in the decision-making process behind inclusion/exclusion of each variable

  - The purpose of this is to act as a framework for potential subsequent quantitative model development in future financial years

- Data availability

Whilst we do not expect the contractor to undertake a full data review of sources that could be used as input data for each variable within the conceptual model in any potential subsequent modelling, we do ask the contractor to make a note of any data that may be relevant for this purpose which they come across anyway as part of their evidence review.

  - Ideally, these will be open access data sources. Where open access data are not available, licensed datasets can be noted alongside their relevant licensing information

  - Ideally, these will be spatial data, with the geographic resolution noted. Where spatial data are not available, non-spatial data can be noted

  - Ideally, these will be UK in scale. Where only smaller geographic scales are available, these can be included instead, with the area that they do cover noted

  - Data on previous wildfires, floods, water quality and availability of water for provision in a subset of relevant locations will also be considered within scope, for potential use to train an empirical model in future that captures the variables identified within the literature review. If data on these factors cannot be found, this should be noted so alternative modelling approaches can be taken (e.g. as will be used in JNCC’s soil health indicator).

## Potential Follow-On Work

Bidders should be aware that there is the potential for the successful bidder to be requested by JNCC to undertake additional work on this contract into the financial year 2026/27 as follows:

- Involvement in an expert engagement process to review and integrate expert knowledge into the conceptual models

- A data review to identify sources that could be used as input data for each variable within the conceptual model in subsequent modelling work

- Development of the conceptual models into quantitative models

Please note however that the potential for additional work to be undertaken is subject to a continuing need, availability of funds, whether contractor skillset matches this additional task, and satisfactory contractor performance. For the avoidance of doubt, no guarantee can be given that you will be asked to undertake the potential additional work outlined within this Annex A document. Bidders are not asked to provide detailed project plans for these follow-on aspects at this stage.

## Outputs

Any products or outputs submitted to JNCC should adhere to JNCC’s house-style and should be produced in an accessible format (see product specification for more information).

Outputs should include:

- The list of papers screened, included/excluded, and raw notes from each paper reviewed as part of the literature review

- A short summary of literature review findings that could be included within a technical report at a later date, if an indicator based on this information is subsequently developed

- A conceptual model diagram for each societal benefit reviewed

- A list of any relevant data sources identified that could be used for each variable within the model

## Product Specification

JNCC is committed to making its publicly available resources and documents accessible, in accordance with the Public Sector Bodies (Websites and Mobile Applications) (No. 2) Accessibility Regulations 2018.

Making material accessible means making sure it can be used by as many people as possible.  This includes those with:

- impaired vision

- motor difficulties

- cognitive impairments or learning disabilities

- deafness or impaired hearing

The outputs and material that JNCC publishes should be compliant with the Web Content Accessibility Guidelines version 2.1 AA standard.

To meet this standard, all reports and other documentation which are to be made publicly available must adhere to JNCC’s house-style (to be provided) and be produced using a JNCC template (to be provided), unless otherwise stated. All reports (draft and final) should be provided electronically via email both as a Microsoft Word document and an Adobe PDF.

Copies of documentation associated with case studies should be provided in electronic format with an associated reference catalogue.

For any other outputs or products which are to be made publicly available through JNCC, evidence regarding how the accessibility standard will be reached should be included.

(Note for author of research project/contract: see EQA Policy Appendix 4 (Communicating Evidence Quality). Ensure that data management and storage requirements are stipulated taking into account relevant policy for data access. See https://jncc.gov.uk/about-jncc/corporate-information/evidence-quality-assurance/

## Dissemination

The products/outputs produced under this contract will be a JNCC product and shall not be published or disseminated without the written permission of JNCC. Outputs may at some point be published on the JNCC website and all material supplied as part of this contract shall remain copyright of JNCC. The findings from this contract will also be made available to staff within JNCC, the UK country nature conservation bodies (Natural England, Natural Resources Wales, NatureScot, Northern Ireland Environment Agency), Defra, DAERA, Scottish Government and Welsh Government.

## Timescale

Provisional dates for delivery of the contract outputs are set out below. Exact dates are to be agreed at the start-up meeting based on Contractor and JNCC staff availability.

| Output | Provisional Date |
| --- | --- |
| Start-up meeting (UK) | 12th Jan 2026 |
| Delivery of draft literature review report | 16th Feb 2026 |
| Delivery of draft conceptual model(s) | 23rd Feb 2026 |
| Delivery of draft data review | 9th March 2026 |
| Delivery of final outputs | 20th March 2026 |

In agreeing exact dates please note that the potential for work under this contract to be funded into 2026/27 is subject to availability of funds.

## Health and Safety

The successful contractor shall comply with all relevant Health and Safety legislation and regulations, as well as JNCC’s internal Health and Safety procedures. Where applicable, the contractor must also adhere to JNCC’s Safeguarding Policy, for further information   https://jncc.gov.uk/about-jncc/corporate-information/safeguarding/ particularly where activities involve vulnerable individuals or public engagement. If the work to be carried out poses any health and safety risks, a suitable and sufficient risk assessment must be completed by the contractor. This risk assessment, along with any supporting evidence of compliance, must be submitted to the JNCC Project Manager for review and approval prior to the commencement of any work. The Project Manager will liaise with the JNCC Health & Safety Officer as required to ensure appropriate controls are in place.

Any incidents occurring within the contract period should be immediately reported to JNCC.

## Project Management

The successful Contractor shall nominate a project manager who shall be responsible for ensuring the project is completed satisfactorily and who shall be the main contact point for JNCC.

JNCC’s main contact points will be:

Name: Maddie Harris

Email: Maddie.Harris@jncc.gov.uk

Telephone: +44 (0)1733 866969

Name: Betty Roberts

Email: Betty.Roberts@jncc.gov.uk

Telephone: +44 (0)1733 866947

## Instructions for Bid Submission

The bid submission should include the following:

A brief summary of the bidder’s experience in relation to the requirements of this contract;

A proposed approach for achieving the objectives of the contract and delivering the detailed tasks identified within each objective. This should be sufficiently detailed to allow assessment against the evaluation criteria (Section 14);

A detailed project plan (including Gantt chart) with proposed work programme and an estimate of time required to achieve each objective;

A draft Table of Contents for the final report;

Details of Quality Control procedures to be followed (note for author if research project/contract: see EQA Policy Appendix 1 (Bias, Conflicting Evidence and Uncertainty) and EQU Policy Appendix 3 (Quality Assurance of Expert Knowledge and Opinion);

Details of the bidder’s own internal Quality Management System;

(For procurement £30,001 to threshold only; Project Manager to delete if 10% sustainability evaluation criteria will not be used) 
Please provide written responses to the following questions, with a maximum of 150 words per answer. Where possible, relate your answers to the proposed work and project team. You may include supporting evidence if helpful, but it is not required.

  - Does your business measure and take steps to reduce the greenhouse gas emissions from its operations? If so, please briefly describe what you measure (e.g. energy, transport) and what actions you take to reduce emissions.

  - What other actions does your business take to reduce your environmental impact? For example, reducing waste, improving biodiversity, or using resources more efficiently.

  - Does your business take any steps to promote fairness and inclusion at work, support staff wellbeing or help your local community?

  - In what ways does your business contribute to a positive and lasting impact on the economy? For example, do you support local jobs, use local or community business suppliers, pay fair wages, or invest in staff development?

  - What is your business’s Full-Time Equivalent (FTE) headcount?

Details of the Project Team including their roles and experience, an estimate of their time input into each task and CVs of all personnel who will be involved in the contract/project; please ensure all CVs MUST be attached as a separate PDF documentation from the proposal, so that we can meet our JNCC GDPR retention policy requirements.

Availability of the Project Team for an online start-up meeting during the week beginning 12th January.

Overall quote for the contract to include:

  - Day rates for all members of the Project Team;

  - Costs and time allocation should be clearly allocated to specific tasks within this contract/project; and

VAT

  - Bidders need to specify whether VAT at the prevailing rate would be applicable to this project and if so, provide their VAT registration number.

  - VAT Reversal. Bidders who are based outside the United Kingdom and Isle of Man should indicate in their bids whether VAT reversal should apply. Using the current HMRC (Her Majesty’s Revenue and Customs) guidance, the service is deemed to be supplied in the country where the customer (JNCC) resides and any contract arising from this procurement process, VAT reversal  should be reflected at contract award.

JNCC will be required to account for VAT at the UK current rate, 20% and legally bound to pay this over to HMRC.

JNCC does not expect to receive an invoice to include the bidder home country  VAT rate, however, to ensure accounting propriety please ensure that both your VAT registered number and JNCC VAT number, which is GB 854 5291 09, is shown on any future invoice(s).

The following documentation (to submit in a zip folder separate from the proposal):

  - Copies of health and safety policy statements where available or a note regarding such items as lone working, emergency procedures and accident reporting;

  - Copies of current public and employer liability insurance certificates;

  - Copies of any appropriate risk assessments;

  - Copies of your company's modern slavery and or safeguarding statement or policy and;

  - Copies of any environmental policies should you have them.

In addition, note that the bid submission should provide sufficient information to allow assessment against the evaluation criteria outlined in Section 14.

Conflict of Interest

Under PA 2023, conflict of interests will be monitored throughout the duration of the contract. Please complete and return the CoI declaration form included in the ITT pack with your bid submission. If successful, please notify the JNCC procurement team if there are conflict of interest changes throughout the duration of the contract, as these will need to be declared for any actual or potential conflicts of interest that could impact the integrity, impartiality, or fairness of the procurement process.

## Evaluation Criteria

JNCC is not bound to accept the lowest priced or any bid. Having the technical expertise and experience to complete the work to a high standard and being able to complete it within the timescale are of the essence for this contract.

The bid evaluation may be undertaken by a panel consisting of JNCC staff.  Unless otherwise stated in your bid submission, bids will be forwarded to these agencies for evaluation purposes only

For information on how we handle personal data please see our Privacy Notice at https://jncc.gov.uk/about-jncc/corporate-information/privacy-statement/

Bids will be evaluated using the following criteria:

|  | EVALUATION CRITERIA |  | Maximum Score | Score |
| --- | --- | --- | --- | --- |
| 1. Quality of Bid (50% of the total assessment categories) |  |  |  |  |
|  |  | Clarity of proposal particularly work programme and deliverables | 10 |  |
|  |  | Understanding of, and relevance to, the requirements in particular the adequacy of outputs and understanding of evidence synthesis processes, peatland ecosystems, and ecosystem services | 10 |  |
|  |  | Soundness and logicality of methods | 5 |  |
|  |  | Realism and measurability of outputs | 5 |  |
|  |  | Evidence provided of how accessibility standards will be met | 5 |  |
|  |  | Identification and proposed solutions to potential risks/issues | 5 |  |
|  |  | Serious weaknesses which threaten success | 5 |  |
|  |  | Probability of success | 5 |  |
|  |  | Sub Total | 50 |  |
| 2. Details of Contractor (20% of the total assessment categories) |  |  |  |  |
|  |  | Expertise, experience, and balance of team | 15 |  |
|  |  | Risks if important team members drop out | 5 |  |
|  |  | Sub Total | 20 |  |
| 3. Sustainability (10% of the total assessment categories) |  |  |  |  |
|  |  | Environmental (assessed from responses to sustainability questions 1 and 2 in section 13, scaled to business size) | 10 |  |
|  |  | Sub Total | 10 |  |
| 4. Cost (20% of the total assessment categories) |  |  |  |  |
|  |  | Total Cost (Including and whole-life cycle or Lifecycle costs) | 5 |  |
|  |  | Risk of cost variation (e.g. Indexed or fixed pricing) | 5 |  |
|  |  | Unit Rates | 5 |  |
|  |  | Transparency and correctness of proposal | 5 |  |
|  |  | Sub Total | 20 |  |
| Total Score |  |  | 100 |  |

## Payment

PLEASE NOTE: All quotes and all payments must be based on British Pounds (£), US Dollars ($) or Euros (€). If alternative currency payments are needed, please raise this at the earliest opportunity during the bid process so we can explore options.

Unless a payment schedule is stated in your submission and agreed by JNCC project manager. Payment will be made on completion of the objectives following the submission of invoice(s) and based on the satisfactory undertaking of the contractual elements to the agreed standard of the JNCC Project Officer.

## Additional Requirements

All bidders are requested to carefully read the Terms and Conditions applying to this contract. Payment will only be made upon delivery of key outputs.

It is assumed that all costs associated with the production of figures, reproduction of photographs and the final report are accounted for within the rates/fees given.

The bidder is expected to supply all necessary equipment, software, licences, etc. to carry out the obligations required under the contract.

## References

## 18.  Procurement Timetable (which may be subject to change)

| Activity | Date |
| --- | --- |
| Preliminary Market Engagement Notice | NA |
| Publication of Tender Notice | 30th October 2025 |
| Last date for receipt of clarification questions | 18th November 2025 |
| Final submission date for bids | 25th November 2025 |
| Evaluation of bids | 28th November 2025 |
| Post-tender negotiation/clarification and or presentation if required | NA |
| Successful/unsuccessful bidders notified Or Assessment Summaries issued to Successful & Unsuccessful Bidders | 4th December 2025 |
| Contract award | 15th December 2025 |
| Contract Details Notice | 05th January 2026 |
| Start of project | 12th January 2026 |