## Sheet1
CLARIFICATION LOG
Tender: | Design, supply and installation of playground equipment, landscaping and surfacing at Mount Wise Gardens, Newquay
Tender Reference: | Design, supply and installation of playground equipment, landscaping and surfacing at Mount Wise Gardens, Newquay
Published Date: | 2025-10-20
Version number: | V1.3
Number | Clarification | Response | Reply date
CL001 | Please can you confirm would it be possible to have an extension for Mount Wise? | The deadline has been extended to 15 December 2025 | 2025-10-27
CL002 | Can you please also confirm the timetable as clarification deadline is 24/12/2025 and submission is 01/12/2025? | The new deadlines for clarifications are; Deadline for Supplier clarification questions to be submitted 01/12/2025, Clarification responses to be issued by 08/12/2025 | 2025-10-27
CL003 | Internal Clarification | The new deadlines for clarifications are; Deadline for Supplier clarification questions to be submitted 05/01/2026, Clarification responses to be issued by 12/01/2026 | 2025-10-29
CL004 | Is the proposed area highlighted Red on the Proposed Play Area Plan the only area which can be utilised for the play equipment? | The Council is open to the Northern section of the Gardens being used as part of the design however though the primary focus would be the Southern section. The Specification, Location Plan and CDM Documents have been updated to reflect this. | 2025-10-30
Clarifications will be published against the Contract Notice on Find a Tender.
If interested in tendering for this project please ensure you add a "watch this notice" for alerts as from time to time additional information or clarifications may be published related to this tender.
It will be the responsibility of Bidders to ensure they are aware of all published clarifications and ensure that their bid has taken these into account.
In the event of any queries please contact: