## Option 1
Item | Description | Unit | Number | £/unit | Cost (£)
1 | Mobilisation and setting out | Item | 1
2 | Site clearance and preparation
2.1 | Marking pipe runs, sockets and services | Item | 1
2.1 | Dig out and expose existing outfall pipes, clear and make ready for installation of new inspection chambers | No | 2
2.2 | Mow as short as possible, collect clippings and dispose offsite | m2 | 27100
2.3 | Strip vegetation with Koro or similar to dispose on site to break down | m2 | 27100
3 | Installation of drains
3.1 | Supply and install 160 mm collector drain at depths between 0.8m and 1.4m | Lin. m | 175
3.2 | Supply and install 80 mm lateral drains at 5m centres including backfill at 500 mm nominal depth (grade at 0.5%) | Lin. m | 5372
3.3 | Supply and install 100 mm lateral drains including backfill at 500 mm nominal depth (grade at 0.5%) | Lin. m | 110
3.5 | Install rootzone slits at 0.8m centres and 250 mm depth over drained area | Lin. m | 27100
3.1-3.3 | Drain junctions | No | 47
3.6 | Supply and install inspection chambers with flood flaps | No | 4
4 | Agronomic works
4.1 | Stone pick | m2 | 27100
4.2 | Spike and roughen the surface | m2 | 27100
4.3 | Supply and spread 50 mm layer specified rootzone material | t | 2439
4.4 | Supply and apply specified fertiliser | m2 | 27100
4.5 | Supply and drill specified seed | m2 | 27100
4.6 | Vertidraining | m2 | 27100
5 | Disposal of arisings
5 | Dispose of arisings off-site at suitably licensed facility (assume Hazardous classification) | t | 72
5 | Dispose of arisings off-site at suitably licensed facility (assume Inert classification) | t | 1128
6 | Maintenance to handover
6 | Maintain to handover (6 months) | Item | 1
7 | As built survey and provision of O and M manual
7 | Provide an as-built survey in DWG and PDF format | Item | 1
7 | Provide an O and M manual for the ongoing maintenance of the drained pitches | Item | 1
| Sub total |  |  |  | 0
| 10% contingency |  |  |  | 0
| Total cost of contract |  |  |  | 0
PI | Provisional items
P1 | Replace existing water pipe with black HDPE 50 mm pipe and connect to hydrant by square and existing water supply point | Item | 1

## Option 2
Item | Description | Unit | Number | £/unit | Cost (£)
1 | Mobilisation and setting out | Item | 1
2 | Site clearance and preparation
2.1 | Marking pipe runs, sockets and services | Item | 1
2.1 | Dig out and expose existing outfall pipes, clear and make ready for installation of new inspection chambers | No | 2
2.2 | Mow as short as possible, collect clippings and dispose offsite | m2 | 18400
2.3 | Strip vegetation with Koro or similar to dispose on site to break down | m2 | 18400
3 | Installation of drains
3.1 | Supply and install 160 mm collector drain at depths between 0.8m and 1.4m | Lin. m | 105
3.2 | Supply and install 80 mm lateral drains at 5m centres including backfill at 500 mm nominal depth (grade at 0.5%) | Lin. m | 3936
3.4 | Supply and install 100 mm collector drains including backfill at minimum 600 mm nominal depth (grade at around 0.5%) | Lin. m | 344
3.5 | Install rootzone slits at 1.0m centres and 250 mm depth over drained area | Lin. m | 18400
3.1-3.4 | Drain junctions | No | 65
3.6 | Supply and install inspection chambers with flood flaps | No | 7
4 | Agronomic works
4.1 | Stone pick | m2 | 18400
4.2 | Spike and roughen the surface | m2 | 18400
4.3 | Supply and spread 50 mm layer specified rootzone material | t | 1656
4.4 | Supply and apply specified fertiliser | m2 | 18400
4.5 | Supply and drill specified seed | m2 | 18400
4.6 | Vertidraining | m2 | 18400
5 | Disposal of arisings
5 | Dispose of arisings off-site at suitably licensed facility (assume Hazardous classification) | t | 100
5 | Dispose of arisings off-site at suitably licensed facility (assume Inert classification) | t | 798
6 | Maintenance to handover
6 | Maintain to handover (6 months) | Item | 1
7 | As built survey and provision of O and M manual
7 | Provide an as-built survey in DWG and PDF format | Item | 1
7 | Provide an O and M manual for the ongoing maintenance of the drained pitches | Item | 1
Sub total
Total cost of contract
PI | Provisional items
P1 | Replace existing water pipe with black HDPE 50 mm pipe and connect to hydrant by square and existing water supply point | Item | 1