www.gov.uk/naturalengland

Request for Quotation

Training Modules for Engagement Training

October 2025

Request for Quotation

Engagement Training

You are invited to submit a quotation for the requirement described in the specification, Section 2.

Please confirm by email, receipt of these documents and whether you intend to submit a quote or not.

Your response should be returned to the following email address by:

Email: Cordelia.spalding@naturalengland.org.uk

Date: 26/11/2025

Time: 12pm - midday

Ensure you include the name of the quotation and ‘Final Submission’ in the subject field to make it clear that it is your response.

Contact Details and Timetable

Barbara Silva will be your contact for any questions linked to the content of the quote or the process. Please submit any clarification questions via email and note that, unless commercially sensitive, both the question and the response will be circulated to all tenderers.

| Action | Date |
| --- | --- |
| Date of issue of RFQ | 18/11/2025 |
| Deadline for clarifications questions | 23/11/2025 |
| Deadline for receipt of Quotation | 26/11/2025 @ 12:00 midday |
| Intended date of Contract Award | 03/12/2025 |
| Intended Contract Start Date | 05/12/2025 |
| Intended Delivery Date / Contract Duration | 28/3/2026 |

Section 1: General Information

Glossary

Unless the context otherwise requires, the following words and expressions used within this Request for Quotation shall have the following meanings (to be interpreted in the singular or plural as the context requires):

| “Authority” | Means Natural England who is the Contracting Authority. |
| --- | --- |
| “Contract” | means the contract to be entered into by the Authority and the successful supplier. |
| “Response” | means the information submitted by a supplier in response to the RFQ. |
| “RFQ” | means this Request for Quotation and all related documents published by the Authority and made available to suppliers. |

Conditions applying to the RFQ

You should examine your Response and related documents ensuring it is complete and in accordance with the stated instructions prior to submission.

Your Response must contain sufficient information to enable the Authority to evaluate it fairly and effectively. You should ensure that you have prepared your Response fully and accurately and that prices quoted are arithmetically correct for the units stated.

By submitting a Response, you, the supplier, are deemed to accept the terms and conditions provided in the RFQ. Confirmation of this is required in Annex 2.

Failure to comply with the instructions set out in the RFQ may result in the supplier’s exclusion from this quotation process.

Acceptance of Quotations

By issuing this RFQ the Authority does not bind itself to accept any quotation and reserves the right not to award a contract to any supplier who submits a quotation.

Costs

The Authority will not reimburse you for any costs and expenses which you incur preparing and submitting your quotation, even if the Authority amends or terminates the procurement process.

Self-Declaration and Mandatory Requirements

The RFQ includes a self-declaration response (Annex 1) which covers basic information about the supplier, as well as any grounds for exclusion. If you do not comply with them, your quotation will not be evaluated.

Any mandatory requirements will be set out in Section 2, Specification of Requirements and, if you do not comply with them, your quotation will not be evaluated.

Clarifications

Any request for clarification regarding the RFQ and supporting documentation must be submitted via email no later than the deadline for clarifications set out in the Timetable. The Authority shall be under no obligation to respond to queries raised after the clarification deadline.

The Authority will respond to all reasonable clarifications as soon as possible but cannot guarantee a minimum response time. The Authority will publish all clarifications and its responses to all suppliers via email unless deemed commercially sensitive.

If a supplier believes that a request for clarification is commercially sensitive, it should clearly state this when submitting the clarification request. However, if the Authority considers either that:

the clarification and response are not commercially sensitive; and

all suppliers may benefit from its disclosure,

then the Authority will notify the supplier (via email), and the supplier will have an opportunity to withdraw the request for clarification by sending a further message requesting the withdrawal of the clarification request. If not withdrawn by the supplier within 2 working days of the Authority’s notification, the Authority may publish the clarification request and its response to all suppliers and the Authority shall not be liable to the supplier for any consequences of such publication.

The Authority reserves the right to seek clarification of any aspect of a quotation and/or provide additional information during the evaluation phase to carry out a fair evaluation. Where the Authority seeks clarification on any aspect of the quotation, the supplier must respond within the timeframe requested by the Authority.

Amendments

The Authority may amend the RFQ at any time prior to the deadline for receipt. If it amends the RFQ the Authority will notify you via email.

Suppliers may modify their quotation prior to the deadline for Responses. No Responses may be modified after the deadline for Responses.

Suppliers may withdraw their quotations at any time by submitting a notice via the email to the named contact.

Conditions of Contract

The Authority’s Standard Goods and Services Terms & Conditions (used for purchases under £50k) can be located on the Natural England Website and will be applicable to any contract awarded as a result of this quotation process. The Authority will not accept any changes to these terms and conditions proposed by a supplier.

Suppliers should note that the quotation provided by the successful bidder will form part of the Contract.

Prices

Prices must be submitted in £ sterling, inclusive of VAT.

Disclosure

All Central Government Departments, their Executive Agencies and Non Departmental Public Bodies are subject to control and reporting within Government. In particular, they report to the Cabinet Office and HM Treasury for all expenditure. Further the Cabinet Office has a cross-Government role delivering overall Government policy on public procurement, including ensuring value for money and related aspects of good procurement practice. For these purposes, the Authority may disclose within Government any details contained in your quotation. The information will not be disclosed outside Government during the procurement.

In addition, the Authority is subject to the Freedom of Information Act 2000 and the Environmental Information Regulations 2004, which provide a public right of access to information held by public bodies. In accordance with these two statutes, the Authority may be required to disclose information contained in your quotation to any person who submits a request for information pursuant to those statutes.

Further to the Government’s transparency agenda, all UK Government organisations must advertise on Contract Finder in accordance with the following publication thresholds:

Central Contracting Authority’s: £12,000

Sub Central Contracting Authority’s and NHS Trusts: £30,000

For the purpose of this RFQ the Authority is classified as a Central Contracting Authority with a publication threshold of £12,000 inclusive of VAT.

If this opportunity is advertised via Contracts Finder, we are obliged to publish details of the awarded contract including who has won the contract, the contract value, and indicate whether the winning supplier is a small and medium-sized enterprise (“SMEs”) or voluntary organisation or charity. A copy of the contract must also be published with confidential information redacted.

By submitting a Response, you consent to these terms as part of the procurement.

Disclaimers

Whilst the information in this RFQ and any supporting information referred to herein or provided to you by the Authority have been prepared in good faith the Authority does not warrant that this information is comprehensive or that it has been independently verified.

The Authority does not:

make any representation or warranty (express or implied) as to the accuracy, reasonableness or completeness of the RFQ;

accept any liability for the information contained in the RFQ or for the fairness, accuracy or completeness of that information; or

accept any liability for any loss or damage (other than in respect of fraudulent misrepresentation or any other liability which cannot lawfully be excluded) arising as a result of reliance on such information or any subsequent communication.

Any supplier considering entering into contractual relationships with the Authority following receipt of the RFQ should make its own investigations and independent assessment of the Authority and its requirements for the goods and/or services and should seek its own professional financial and legal advice.

Protection of Personal Data

In order to comply with the General Data Protection Regulations 2018 the supplier must agree to the following:

You must only process any personal data in strict accordance with instructions from the Authority.

You must ensure that all the personal data that we disclose to you or you collect on our behalf under this agreement are kept confidential.

You must take reasonable steps to ensure the reliability of employees who have access to personal data.

Only employees who may be required to assist in meeting the obligations under this agreement may have access to the personal data.

Any disclosure of personal data must be made in confidence and extend only so far as that which is specifically necessary for the purposes of this agreement.

You must ensure that there are appropriate security measures in place to safeguard against any unauthorised access or unlawful processing or accidental loss, destruction or damage or disclosure of the personal data.

On termination of this agreement, for whatever reason, the personal data must be returned to us promptly and safely, together with all copies in your possession or control.

General Data Protection Regulations 2018

For the purposes of the Regulations the Authority is the data processor.

The personal information that we have asked you provide on individuals (data subjects) that will be working for you on this contract will be used in compiling the tender list and in assessing your offer. If you are unsuccessful the information will be held and destroyed within two years of the award of contracts. If you are awarded a contract it will be retained for the duration of the contract and destroyed within seven years of the contract’s expiry.

We may monitor the performance of the individuals during the execution of the contract, and the results of our monitoring, together with the information that you have provided, will be used in determining what work is allocated under the contract, and in any renewal of the contract or in the award of future contracts of a similar nature. The information will not be disclosed to anyone outside the Authority without the consent of the data subject, unless the Authority is required by law to make such disclosures.

Equality, Diversity & Inclusion (EDI)

The Client is striving to create a diverse and inclusive working environment where every individual has equality of opportunity to progress and to apply their unique insights to making the UK a great place for living. The Service Provider is expected to respect this commitment in all dealings with Natural England staff and service users.

Suppliers are expected to;

support Defra group to achieve its Public Sector Equality Duty as defined by the Equality Act 2010, and to support delivery of Defra group’s Equality & Diversity Strategy.

meet the standards set out in the Government’s Supplier Code of Conduct

work with Defra group to ensure equality, diversity and inclusion impacts are addressed (positive and negative) in the goods, services and works we procure, barriers are removed and opportunities realised.

Sustainability

Natural England protects and improves the environment and is committed to reducing the sustainability impacts of its activities directly and through its supply chains.  We expect the Contractor to share this commitment and adopt a sound, proactive sustainable approach in keeping with the 25 yr environmental plan/our commitments compliant with all applicable legislation. This includes understanding and reducing direct and indirect sustainability impacts and realising opportunities, including but not restricted to; resilience to climate change, reducing greenhouse gas emissions, water use and quality, biosecurity, resource efficiency and waste, reducing the risk of pollution, biodiversity, modern slavery and equality, diversity & inclusion, negative community impacts.

As a delivery partner, the successful contractor is expected to pursue sustainability in their operations, thereby ensuring the Contracting Authority is not contracting with a supplier whose operational outputs run contrary to the Contracting Authority’s objectives. The successful contractor will need to approach the project with a focus on the entire life cycle of the project

Sustainable Procurement

Addressing global sustainability impacts and realising additional community benefits within commercial activity is core to Defra group’s approach, working with its supply chain is key to achieving sustainable outcomes. In addition to supporting Defra group to meet its outcomes we look to understand and reduce negative sustainability impacts associated with our commercial activity and realise benefits.

The Client encourages its suppliers to share these values, work to address negative impacts and realise opportunities, measure performance and success.

Suppliers are expected to have an understanding of the Sustainable Development Goals, the interconnections between them and the relevance to the Goods, Services and works procured on the Client’s behalf

Conflicts of Interest

The concept of a conflict of interest includes but is not limited to any situation where an Involved Person or Relevant Body has directly or indirectly, a financial, economic or other personal interest which might be perceived to compromise their impartiality and independence in the context of the procurement procedure and/or affect the integrity of the contract award.

We expect suppliers to mitigate appropriately against any real or perceived conflict of interest through their work with government. A supplier with a position of influence gained through a contract should not use that position to unfairly disadvantage any other supplier or reduce the potential for future competition

Where the supplier is aware of any circumstances giving rise to a conflict of interest or has any indication that a conflict of interest exists or may arise you should inform the Authority of this as soon as possible (whether before or after they have submitted a quotation). Tenderers should remain alert to the possibility of conflicts of interest arising at all stages of the procurement and should update the Authority if any new circumstances or information arises, or there are any changes to information already provided to the Authority. Failure to do so, and/or to properly manage any conflicts of interest may result in a quotation being rejected.

Provided that it has been carried out in an open, fair and transparent manner, routine pre-market engagement carried out by the Authority should not represent a conflict of interest for the supplier.

Section 2: The Invitation

Specification of Requirements

Background to Natural England

Natural England is the government’s advisor for the natural environment in England, helping to protect England’s nature and landscapes for people to enjoy and for the services they provide. Nature Recovery is at the centre of the Government’s Environmental Improvement Plan (publishing.service.gov.uk) - but this can only be achieved through working with partners and stakeholders and engaging with participants. Building and deepening engagement skills and knowledge is key to the success of Protected Site Strategies and the Stakeholders and Partners it collaborates with.

Natural England's new strategy illustrates the key priorities going forward

"Recovering Nature for Growth, Health and Security"

https://www.gov.uk/government/publications/natural-englands-strategy-recovering-nature-for-growth-health-and-security/natural-englands-strategy-recovering-nature-for-growth-health-and-security

We work with a wide range of partners, stakeholders and customers on a huge range of projects, from influencing construction, advising farmers and landowners how they can manage their land in a sustainable way for the benefit of the environment, gathering and analysing environmental data, and carrying out vital statutory duties. Across the country, we’re helping nature to support people and our planet.

Further information about Natural England can be found at: Natural England

Background to the specific work area relevant to this purchase

The Environment Act 2021 sets out the Government’s aim to put nature on the road to recovery for future generations. It has given us some of the tools needed to deliver for our environment, from cleaning up the country’s air, restoring natural habitats, increasing biodiversity, reducing waste, and making better use of our resources.

Protected Site Strategies will play an important part in this.  These aim to bring together key stakeholders to address on and offsite pressures on protected sites (such as Sites of Special Scientific Interest) to help restore our most precious habitats, species and geodiversity. "Engagement" expertise, skills and understanding are key to the success of Protected Site Strategies.

https://naturalengland.blog.gov.uk/2022/06/16/springing-into-action-with-protected-site-strategies-for-natures-recovery/

Project Title:

Stakeholder Engagement Training

Protected Site Strategies enables the bringing together of a wide variety of Stakeholders.  Understanding a variety of approaches, methodologies, tools and possible topics to support engagement is key to the ongoing successful delivery and creation of novel and dynamic approaches to environmental recovery, growth and Stakeholder engagement

Protected Sites Strategies

The main purpose and rationale for Protected Site Strategies (PSS) (enshrined in the Environment Act legislation that provides us with new power to work collaboratively) is to find solutions to environmental issues that cannot be resolved well at the site level. Often, their root causes are part of a wider picture, whether it be from diffuse pollution of air or water, overgrazing from overpopulations of herbivores, or a result of disconnection of people from the many benefits nature brings. This legislative power enables PSS's to convene partners and stakeholders from a wide range of disciplines and interests and opens up opportunities for cross discipline research and innovation.

Project Brief

This new project builds on the success and learnings from the creation of a Guidance resource for Protected Sites Strategies, that aims to enable and empower PSS's teams to consider novel, creative, systematic and reproducible approaches to all areas of their work, and also the resources housed in Natural England's SharePoint Engagement Hub.

The aim of all PSS's is to tackle the most pressing problems that affect protected sites, and subsequently affect local communities, industry and opportunities for growth and sustainability. By working across disciplines, often new opportunities for research and collaboration are discovered that may be of interest to a wide number of players both within and beyond the sector. These may include areas such as Health, Education, Sustainability, New Materials, new Tech, the Arts and Culture. Engaging across disciplines therefore is key to reaching new strategy ambitions.

The aim of this contract is to create a digital resource that can be included in the PSS's guidance and in the Engagement hub, that will guide and equipe PSS Managers and teams and other Natural England teams, with a modular training opportunity, that will support engagement with a wide range of stakeholders - and signpost to further resources already created.

Project Aims

This project will develop a modular training pathway - using a variety of approaches that can provide the starting point for a number of engagement processes and development points and provide signposting to existing resources, as well as higher level/more in-depth guidance for more advanced learners and teams to ensure that Natural England teams have the skills to support Stakeholder Engagement at a variety of levels, and in a number of settings.

The project will deliver a series of training and development modules that cover a wide range of Engagement topics and approaches.  Some may be video based, animation based, some may involve exercises such as "engagement mapping" to try out and learn from, some may include "homework & research", some may include short inserts from experts in the field. The modules will provide a methodological, and "engaging/curiosity raising" approach that takes participants through the milestones and areas of development that will lead to a systematic and robust building of skills that will support the creation and implementation of a robust Stakeholder Engagement Plan, and its subsequent iterative development and delivery, and signpost to existing resources on the Engagement Hub.

Modules may be accessed and presented individually or worked through systematically over a series of months.  The modules will form part of the overall approach to engagement and will be embedded in a programme of engagement training that will be delivered internally at a later date.  The contract should include a set of resources for the Delivery officer to refer to as part of the module. When delivered by an NE Engagement Officer they will be delivering to small groups of NE Officers. The modules will be hosted on the Protected Site Strategies SharePoint site and Natural England's internal "Engagement Hub"- also hosted on SharePoint. (Technical information on formats will be supplied)

The look and feel of the resources developed for the contract should be upbeat, raise curiosity, and invite debate.  They should encourage staff to consider engagement as an integral part of their plans for sites and partnership aims, as well as communities, and associated anchor organisations (i.e. Growth Partners, Health Providers, Employment services, Culture/Faith Organisations), and enable and empower them to weave engagement practices and approaches throughout their environmental plans.

To ensure that the content and approach fulfil needs a small Focus Group of NE PSS's officers will be regularly engaged with throughout the development process.  Their thoughts, comments and evaluations will ensure through iterative development and discussions that needs are met.

Project Logistics:

It is anticipated that this project will start on December 2nd 2025 and would need to be completed by 31st March 2026. NE staff can facilitate and provide further information and guidance. Regular project meetings with a small steering group should also be scheduled to support delivery and report on progress.

Project Outputs:

Content for this training has been identified and broken down into a series of modules.  The Contractor may consider other options, or additions but this gives a framework of what may be included.

Module 1: Introduction to Engagement and Stakeholders

- Lays the foundation by defining community and partner engagement in practice, identifying key stakeholders, and setting personal learning goals.

- Outcomes:  Clear understanding of engagement scope completed stakeholder mapping, and shared purpose.

Module 2: Place-Based Working

- Explores how culture, heritage, landscape, and local power structures shape engagement, with attention to equity, accessibility, and safeguarding.

- Outcomes: Refined understanding of local context and its influence on engagement strategies.

Module 3: Recognising Opportunities for Engagement: Scoping & Mapping

- Helps identify where engagement fits into wider agendas, cross-sector work, and windows of opportunity. 	How to formulate a methodology for a R&D Engagement based project. Stakeholder mapping: the do's and don'ts. How to scope your engagement: where you start, where it may "ripple" out to, and where to stop

- Outcomes: Mapped opportunities, allies, and relevant touchpoints across agencies and partners.

Module 4: Boundary Spanning and External Partnerships

- Develops skills to collaborate across departments and sectors, aligning with organisations such as the NHS or Arts Council.

- Outcomes: Practical plan to initiate cross-sector conversations and mapped strategic partnerships.

Module 5: Communications and Engagement Strategy + Peer Feedback

- Covers communication fundamentals, planning, and integration with engagement, followed by peer and specialist feedback sessions. How to best articulate aims and ambitions for Engagement with a wide variety of Stakeholders

- Outcomes: Drafted, refined communications plan and improved confidence in presenting internally.

Module 6: Planning for Engagement Activities + Peer Feedback

- Guides ambassadors to design, deliver, and assess place-based engagement activities, with feedback on research presentations. Ethics and Governance and the role they play in an engagement context

- Outcomes: Stronger storytelling, analysis of local context, and strategies for building support. Robust structures for engagement.

Module 7: Building Empathy and Perspective-Taking

- Encourages ambassadors to understand the perspectives of communities, partners, and colleagues, using dialogue tools and guest insights. The role of Focus groups and their selection.

- Outcomes: Greater capacity for empathy and awareness of personal and structural biases.

Module 8: Writing Your Engagement Plan and aligning aims in a Theory of Change

- Supports ambassadors in consolidating learning into a structured, actionable engagement plan. Understanding the role of a Theory of change, when it appears in an engagement timeline, how it is iteratively developed.

- Outcomes: Completed engagement plan with clear success measures, roles, and timelines.

Module 9: Evaluating Your Engagement Work

- Introduces qualitative and quantitative evaluation methods to measure engagement impact and learning. Creative approaches to evaluation- both Qualitative and Quantitative

- Outcomes: Evaluation strategy and toolkit for assessing engagement outcomes and impact. How to feed insights into broader strategy refresh and KPI tracking. How to establish an ongoing model of reflective practice, storytelling, and peer learning

- Useful Accessibility Resources:

https://design.homeoffice.gov.uk/accessibility/audio-and-video

https://design-system.service.gov.uk/styles/colour/

https://www.gov.uk/service-manual/helping-people-to-use-your-service/making-your-service-accessible-an-introduction#meeting-government-accessibility-requirements

Please note the following:

Outputs and Contract Management

During the w/c 1st December 2025, a start-up meeting will be held between the project officer and supplier - whether in-person or via teams to be agreed after the contract has been awarded. Fortnightly (or weekly if required) teleconferences can be booked in thereafter. Approximate meeting dates are suggested below, and these can be negotiated if required:

| - Date | - Reason |
| --- | --- |
| - 5th Dec 25 | - Project Start up Meeting including presentation of ideas, discussion of approaches and formats. Sharing of NE and PSS's aims and ambitions. |
| - 9th Dec25 | - Project meeting to present initial modular approach/module titles and content- introduce Focus Group to contractor and gauge initial thoughts and requirements |
| - 19th DEC 25 | - - Presentation of completed modular titles and selection of additional (videos/links etc) contents |
| - 7th January 2026 | - First viewings and discussion of look, feel, content, tone and any additional inputs. |
| - 14th Jan 26 | - Milestone 1 - Second stage contents and inserts, Expert input and discussion of "Engagement Training Schedule". Focus group involvement. |
| - 21st Jan 26 | - First "storyboard" of modules. Detailing any additional material, input, references - "Hints & Tips" |
| - 4th Feb 26 | - Run through of modules. Clarification of any queries, |
| - 18th Feb 26 | - Module Clarifications #2 |
| - 4th March 26 | - - Final viewing of edited and completed modules - Focus group extended session. |
| - 11th March 26 | - Editorial meeting for Delivery Officer Information and guidance. |
| - 25th March 26 | - Milestone 2 - Completed project end and handover of final modules in compatible platform format. |
| - 30th March 24 | - Wash up meeting if required |

Payment

The Authority will raise purchase orders to cover the cost of the services and will issue to the awarded supplier following contract award.

The Authority’s preference is for all invoices to be sent electronically, quoting a valid Purchase Order number. Part payment will be made after each Milestone has been met with the balance payable on project completion and report submission.

It is anticipated that this contract will be awarded for a period of 16 weeks to end no later than 28/03/26. Prices will remain fixed for the duration of the contract award period. We may at our sole discretion extend this contract to include related or further work. Any extension shall be agreed in writing in advance of any work commencing and may be subject to further competition.

Evaluation Methodology

Your response evaluation will be broken down into 2 elements, technical (quality) and commercial (price). A weighting is applied to each element to indicate its level of importance. We will award this contract in line with the most economically advantageous tender (MEAT) as set out in the following award criteria:

Technical – 70%

Commercial – 30%

Evaluation criteria

Evaluation weightings are 60% technical and 40% commercial, the winning tenderer will be the highest scoring combined score.

| Award Criteria | Weighting (%) | Evaluation Topic & Weighting | Sub-Criteria | Weighted Question |
| --- | --- | --- | --- | --- |
| Technical | 70 | Knowledge / Experience / Methodology | Experience (20%) | Experience of creating modular training packages and "wrap around material" for Delivery teams |
|  |  |  | Knowledge (20%) | Understanding audience and how to connect to them - How to best share knowledge of engagement approaches to others. Demonstrate a number of approaches and mediums that have been used in the past. |
|  |  |  | Engagement (20%) | An understanding of engagement processes and approaches and the ability to guide learners through the process to culminate in the creation of a robust and deliverable Stakeholder Engagement plan. |
|  |  |  | Methodology (10%) | Outline and detail a proposed methodology to fulfil this contract |
| Commercial | 30% | Whole life cost of the proposed Contract | Commercial Model | 1 Question (40% of commercial score available) |

Technical (70%)

Technical evaluations will be based on responses to specific questions covering key criteria which are outlined below.  Scores for questions will be based on the following:

| Description | Score | Definition |
| --- | --- | --- |
| Very good | 100 | Addresses all the Authority’s requirements with all the relevant supporting information set out in the RFQ. There are no weaknesses and therefore the tender response gives the Authority complete confidence that all the requirements will be met to a high standard. |
| Good | 70 | Addresses all the Authority’s requirements with all the relevant supporting information set out in the RFQ. The response contains minor weaknesses and therefore the tender response gives the Authority confidence that all the requirements will be met to a good standard. |
| Moderate | 50 | Addresses most of the requirements with most of the relevant supporting information set out in the RFQ. The response contains moderate weaknesses and therefore the tender response gives the Authority confidence that most of the requirements will be met to a suitable standard. |
| Weak | 20 | Substantially addresses the requirements but not all and provides supporting information that is of limited or no relevance or a methodology containing significant weaknesses and therefore raises concerns for the Authority that the requirements may not all be met. |
| Unacceptable | 0 | No response or provides a response that gives the Authority no confidence that the requirement will be met. |

Technical evaluation is assessed using the evaluation topics and sub-criteria stated in the Evaluation Criteria section above.

Separate submissions for each technical question should be provided and will be evaluated in isolation. Tenderers should provide answers that meet the criteria of each technical question.

| Technical | Detailed Evaluation Criteria |
| --- | --- |
| Q1.1 Experience of creating modular training packages and "wrap around material" for Delivery teams | Your response should: 1) clearly demonstrate your experience of designing and producing training packages 2) clearly demonstrate you experience of producing training that encourages curiosity and creative approaches to stakeholder engagement |
| Q1.2 Understanding audience and how to connect to them - How to best share knowledge of engagement approaches to others | Your response should: 1) clearly demonstrate evidence of successful previous work on similar projects supporting connection/engagement with diverse audiences. 2) explain how you considered accessibility issues 3) demonstrate a wide range of mediums and approaches used on similar projects |
| Q1.3 An understanding of engagement processes and approaches and the ability to guide learners through the process to culminate in the creation of a robust and deliverable Stakeholder Engagement plan. | Your response should: 1) clearly demonstrate your experience and knowledge of Stakeholder Engagement and the processes, tasks and activities that will lead to the creation of robust Stakeholder Engagement Plans |
| Q1.4 Provide details of the methodology and approaches proposed to deliver the requirements of this project | Your response should: 1) Demonstrate a clear understanding of the project requirements 2) Provide an outline proposal of how you will deliver the project, which is clear, practical, achievable, cost-effective and considers accessibility issues. 3) A summary of what you believe to be the main risks and areas of uncertainty, their potential impact on the project and how significant they are, and how you would act to minimise and manage them. This should include contingency plans to cover the unexpected availability of staff. |

Commercial (30%)

The Contract is to be awarded as a fixed rate which will be paid according to the completion of the deliverables stated in the Specification of Requirements.

Suppliers are required to submit a total cost to provide the deliverables stated in the Specification of Requirements. In addition to this the Commercial Response template must be completed to provide a breakdown of the whole life costs against each deliverable used in the delivery of this requirement.

Calculation Method

The method for calculating the weighted scores is as follows:

Commercial

Score =  (Lowest Quotation Price / Supplier’s Quotation Price ) x 30%
(Maximum available marks)

Technical

Score = (Bidder’s Total Technical Score / Highest Technical Score) x 70%  (Maximum available marks)

The total score (weighted) (TWS) is then calculated by adding the total weighted commercial score (WC) to the total weighted technical score (WT): WC + WT = TWS.

Information to be returned

Please note, the following information requested must be provided. Incomplete tender submissions may be discounted.

Please complete and return the following information:

completed Commercial Response template

separate response submission for each technical question (in accordance with the response instructions)

completed Mandatory Requirements (Annex 1)

completed Acceptance of Terms and Conditions (Annex 2)

Award

Once the evaluation of the Response(s) is complete all suppliers will be notified of the outcome via email. The successful supplier will be issued the contract via a Purchase Order.

Annex 1 Mandatory Requirements

Part 1 Potential Supplier Information

Please answer the following self-declaration questions in full and include this Annex in your quotation response.

Part 1.1 Potential Supplier Information:

| Question no. | Question | Response |
| --- | --- | --- |
| 1.1(a) | Full name of the potential supplier submitting the information |  |
| 1.1(b) | Registered office address (if applicable) |  |
| 1.1(c) | Company registration number (if applicable) |  |
| 1.1(d) | Charity registration number (if applicable) |  |
| 1.1(e) | Head office DUNS number (if applicable) |  |
| 1.1(f) | Registered VAT number |  |
| 1.1(g) | Are you a Small, Medium or Micro Enterprise (SME)? | (Yes / No) |

Note: See EU definition of SME https://ec.europa.eu/growth/smes/business-friendly-environment/sme-definition_en

Part 1.2 Contact details and declaration

By submitting a quotation to this RFQ I declare that to the best of my knowledge the answers submitted and information contained in this document are correct and accurate.

I declare that, upon request and without delay you will provide the certificates or documentary evidence referred to in this document.

I understand that the information will be used in the selection process to assess my organisation’s suitability to be invited to participate further in this procurement.

I understand that the authority may reject this submission in its entirety if there is a failure to answer all the relevant questions fully, or if false/misleading information or content is provided in any section.

I am aware of the consequences of serious misrepresentation.

| Question no. | Question | Response |
| --- | --- | --- |
| 1.2(a) | Contact name |  |
| 1.2(b) | Name of organisation |  |
| 1.2(c) | Role in organisation |  |
| 1.2(d) | Phone number |  |
| 1.2(e) | E-mail address |  |
| 1.2(f) | Postal address |  |
| 1.2(g) | Signature (electronic is acceptable) |  |
| 1.2(h) | Date |  |

Part 2 Exclusion Grounds

Part 2.1 Grounds for mandatory exclusion

| Question no. | Question | Response |
| --- | --- | --- |
| 2.1(a) | Please indicate if, within the past five years you, your organisation or any other person who has powers of representation, decision or control in the organisation been convicted anywhere in the world of any of the offences within the summary below. |  |
|  | Participation in a criminal organisation. | (Yes / No) If yes please provide details at 2.1 (b) |
|  | Corruption. | ((Yes / No) If yes please provide details at 2.1 (b) |
|  | Fraud. | (Yes / No) If yes please provide details at 2.1 (b) |
|  | Terrorist offences or offences linked to terrorist activities | (Yes / No) If yes please provide details at 2.1 (b) |
|  | Money laundering or terrorist financing | (Yes / No) If yes please provide details at 2.1 (b) |
|  | Child labour and other forms of trafficking in human beings | (Yes / No) If yes please provide details at 2.1 (b) |
| 2.1(b) | If you have answered yes to question 2.1(a), please provide further details. Date of conviction, specify which of the grounds listed the conviction was for, and the reasons for conviction. Identity of who has been convicted If the relevant documentation is available electronically please provide the web address, issuing authority, precise reference of the documents. |  |
| 2.1 (c) | If you have answered Yes to any of the points above have measures been taken to demonstrate the reliability of the organisation despite the existence of a relevant ground for exclusion? (i.e. Self-Cleaning) | (Yes / No) |
| 2.1(d) | Has it been established, for your organisation by a judicial or administrative decision having final and binding effect in accordance with the legal provisions of any part of the United Kingdom or the legal provisions of the country in which the organisation is established (if outside the UK), that the organisation is in breach of obligations related to the payment of tax or social security contributions? | (Yes / No) |
| 2.1(e) | If you have answered yes to question 2.3(a), please provide further details. Please also confirm you have paid or have entered into a binding arrangement with a view to paying, the outstanding sum including where applicable any accrued interest and/or fines. |  |

Part 2.2 Grounds for discretionary exclusion

| Question no. | Question | Response |
| --- | --- | --- |
| 2.2(a) | The detailed grounds for discretionary exclusion of an organisation are set out on this webpage, which should be referred to before completing these questions. Please indicate if, within the past three years, anywhere in the world any of the following situations have applied to you, your organisation or any other person who has powers of representation, decision or control in the organisation |  |
| 2.2(b) | Breach of environmental obligations? | (Yes / No) If yes please provide details at 2.2 (f) |
| 2.2(c) | Breach of social obligations? | (Yes / No) If yes please provide details at 2.2 (f) |
| 2.2(d) | Breach of labour law obligations? | (Yes / No) If yes please provide details at 2.2 (f) |
| 2.2(e) | Shown significant or persistent deficiencies in the performance of a substantive requirement under a prior public contract, a prior contract with a contracting entity, or a prior concession contract, which led to early termination of that prior contract, damages or other comparable sanctions? | (Yes / No) If yes please provide details at 2.2 (f) |
| 2.2 (f) | If you have answered Yes to any of the above, explain what measures been taken to demonstrate the reliability of the organisation despite the existence of a relevant ground for exclusion? (Self Cleaning) |  |

Annex 2 Acceptance of Terms and Conditions

I/We accept in full the terms and conditions appended to this Request for Quote document.

Company ____________________________________________________

Signature ____________________________________________________

Print Name ____________________________________________________

Position ____________________________________________________

Date ____________________________________________________