JCT 2024 Design and Build Contract

# A10 PROJECT PARTICULARS

Clauses

110	The Project

- Name: Neeld Hall & Town Hall Decarbonisation

- Nature: Decarbonisation of existing Neeld Hall and Town Hall complex, comprising M&E works, firestopping, asbestos removal and all consequential works.

- Location:  Neeld Community & Arts Centre, Town Hall, High Street and Borough Parade Car Park

- Timescale for construction work:  12 calendar weeks

120	Employer (client)

- Name:  Chippenham Town Council

- Address:  High Street, Chippenham, SN15 3ER

- Contact:  Beth O’Brien, Head of Venues

- Telephone:  01249 446699

- Email:  bobrien@chippenham.gov.uk

130	Principal Contractor (CDM/ Building Regulations)

- Name:  TBA

- Address:

- Contact:

- Telephone:

- Email:

140	Employer’s Agent

- Name:  Michael Edwards Consultants Limited t/a MEA.

- Address:  The New Workshops, Beehive Yard, Bath, BA1 5BT

- Contact:  William Kennett

- Telephone:  07947 932159

- Email:  william@meaconsult.co.uk

150	Principal Designer (CDM / Building Regulations)

- Duties: Appointed to plan, manage and monitor the pre-construction phase, identify non-conformances with both the Building Safety Act 2022 and Construction (Design & Management) Regulations 2015 and work with the design team to reduce or eliminate these. We will assist the client with the discharge of the duties under both pieces of legislation.

- Name:  Core-Compliance

- Address:  Office 35, Genesis Building, 235 Union Street, Plymouth, PL1 3HN

- Contact:  David Owen

- Telephone:  07921 134938

- Email:  davidowen@core-compliance.co.uk

- Competence

  - Standard:  Available on request

  - Evidence of competence

    - Submittals:

    - Timing:

160	Quantity Surveyor

- Name:  Michael Edwards Consultants Limited t/a MEA.

- Address:  The New Workshops, Beehive Yard, Bath, BA1 5BT

- Contact:  William Kennett

- Telephone:  07947 932159

- Email:  william@meaconsult.co.uk

- Evidence of competence:   Available on request

  - Submittals:

  - Timing:

170	Structural Engineer

- Name:  Giraffee Engineering Ltd

- Address:  5 Union Road, Chippenham, Wiltshire, SN15 1HW

- Contact:  Ralph Pelly

- Telephone:  01249 704524

- Email:  ralph@giraffeengineering.com

- Competence

  - Standard:  Available on request

  - Evidence of competence

    - Submittals:

    - Timing:

175	Mechanical Engineer

- Name:  E3 Consulting Engineers Ltd

- Address:  Queen Square House, 18-21 Queen Square, Bristol, BS1 4NH

- Contact:  Isabelle Ballinger

- Telephone:  0117 238 0909

- Email:  Isabelle.ballinger@e3ce.com

- Competence

  - Standard:  Available on request

  - Evidence of competence

    - Submittals:

    - Timing:

178	Electrical Engineer

- Name:  As A10/175

- Address:

- Contact:

- Telephone:

- Email:

- Competence

  - Standard:

  - Evidence of compliance

    - Submittals:

    - Timing:

198	Fire Engineer

- Name:  TBA

- Address:

- Contact:

- Telephone:

- Email:

- Competence

  - Standard:

  - Evidence of competence

    - Submittals:

    - Timing:

A11
Tender and contract documents

Clauses

110	Tender Drawings

- The tender drawings are:  listed in the Appendices

120	Contract drawings

- The contract drawings: The same as the tender drawings.

160	Pre-construction information

- Format: The pre-construction information is described in these Preliminaries in section A34. It refers to information given elsewhere in the Preliminaries, specifications, drawings and associated documents.

180	Other documents

- Inspection: Drawings and other documents relating to the Contract but not included in the tender documents may be seen by appointment during normal office hours at the office of Employer

A12
The site/ existing buildings

Clauses

110	The site

- Description:  Grade II Listed historic municipal building, now a multiple use complex, serving as the councils offices and Neeld Hall community and arts center.

120	Existing buildings on/ adjacent to the site

- Description:

  - Town Hall

  - Neeld Hall

  - Cheese Hall

  - Town Center Retail Units

  - Town Center Residential Units

  - Car Park

140	Existing utilities and services

- Drawings: (Information shown is indicative only): Refer E3 drawings.

170	Site investigation

- Report: Included in the tender documents.

180	Health and safety file

- Availability for inspection: The health and safety file for the site/ building may be seen by appointment during normal office hours at: Michael Edwards Consultants Limited

200	Access to the site

- Description:  Via Neeld Hall entrance

- Limitations:  Public car park

- Access for inspections: Provide access at reasonable times for both on-site and off-site work.

210	Parking

- Restrictions on parking of the Contractor’s and employees' vehicles:  Parking available in chargeable public car park only

220	Use of the site

- General: Do not use the site for any purpose other than carrying out the Works.

- Note; refer introduction and programme for client requirements for access to site.

230	Surrounding land/ building uses

- General: Adjacent or nearby uses or activities are as follows:

  - Council offices will remain in operation in existing wider site location. Generally Commercial, retail, food retail, residential units and public car park.

240	Health and safety hazards

- General: The nature and condition of the site/ building cannot be fully and certainly ascertained before it is opened up. However, the following hazards are or may be present: Asbestos, refer reports.

- Information: The accuracy and sufficiency of this information is not guaranteed. Ascertain if any additional information is required to ensure the safety of all persons and the works.

- Site staff: Draw to the attention of all personnel working on the site the nature of any possible contamination and the need to take appropriate precautionary measures.

250	Site visit

- Assessment: Ascertain the nature of the site, access thereto and all local conditions and restrictions likely to affect the execution of the Works.

- Arrangements for visit:  via Chippenham Town Council, Beth O’Brien.

A13
Description of the work

Clauses

110	Preparatory work by others

- Details:  No Works

- Timescale:

120	The works

- Description:  Decarbonisation works, associated M&E, consequential ACM removal and firestopping.

130	Work by others concurrent with the Contract

- Description:  Refer programme, refurbishment of Town Hall FF.

140	Completion work by others

- Description:  No Works.

A20
JCT Design and Build Contract (DB)

Clauses

JCT Design and Build Contract (DB)

- The Contract: JCT Design and Build Contract (DB) DB Design and build contract 2024.

- Requirement: Allow for the obligations, liabilities and services described.

The Recitals

First - The Works

- Comprise:  Decarbonisation and consequential works

- Location:  Neeld Community & Arts Centre, Borough Parade, Chippenham, SN15 3WL

Fifth - Division of the Works into Sections

- See contract particulars fifth recital.

Sixth – Framework Agreement

- The Sixth Recital will be deleted.

Articles

4 – Employer’s Agent

- Employer’s Agent: See clause A10/140.

6 - CDM Regulations - Principal Designer and Principal Contractor

- Principal Designer: See clause A10/150.

- Principal Contractor: See clause A10/130.

7 - Building Regulations - Principal Designer and Principal Contractor

- Principal Designer: See clause A10/150.

- Principal Contractor: See clause A10/130.

10 - Legal proceedings

- Amendments:  None

Contract Particulars

Fourth Recital and Clause 4.5 - Construction Industry Scheme

- Employer at Base Date is not a contractor for the purposes of the CIS.

Fifth Recital - Description of Sections

- Description of Sections:

  - Section 1 – Neeld Hall Back of House Works

  - Section 2 – Neeld Hall Front of House Works

  - Section 3 – Town Hall Back of House Works

- Section 4 – Town Hall Front of House Works

Sixth Recital - Framework Agreement

- Framework agreement:  N/A

Seventh Recital and Part 1 of Schedule 2 - Supplemental Provisions - Part 1

- Named subcontractors: Supplemental Provision 1 does not apply

- Valuation of changes - Contractor's estimates: Supplemental Provision 2 applies

- Loss and expense - Contractor's estimates: Supplemental Provision 3 applies

Seventh Recital and Part 2 of Schedule 2 - Supplemental Provisions - Part 2

- Acceleration quotation: Supplemental Provision 4 applies.

- Collaborative working: Supplemental Provision 5 applies

- Health and safety: Supplemental Provision 6 applies

- Cost savings and value improvements: Supplemental Provision 7 applies

- Sustainable developments and environmental considerations: Supplemental Provision 8 applies

- Performance indicators and monitoring: Supplemental Provision 9 applies

- Notification and negotiation of disputes: Supplemental Provision 10 applies

- Where Supplemental Provision 10 applies, the respective nominees of the parties are:

  - Employer's nominee: Beth O’Brien

  - Contractor's nominee: TBA

  - Or such replacement as each party may notify to the other from time to time.

Article 5 - Employer's Requirements, Contractor’s Proposals, Contract Sum Analysis

- Employer's Requirements: All documents listed in appendices and the works identified in the work schedules.

- Contractor's Proposals: TBA

- Contract Sum Analysis: Contained within ER’s

- Specific Requirements: None

Article 9 - Arbitration

- Article 9 and clauses 9.4 to 9.9 (Arbitration) do not apply

Clause 1.1 - Base Date

- Base Date:  1st December 2025

Clause 1.1 - BIM Protocol

- BIM Protocol (where applicable):  Does not apply

Clause 1.1 - Date for Completion of the Works

- Date for Completion of the Works (where completion by Sections does not apply):  16th October 2026

  - Refer to programme for indicative sectional completion dates.

Clause 1.7.3 - Addresses for service of notices

- Employer

  - Address:  The Town Hall, High Street, Chippenham, Wiltshire, SN15 3ER

  - Email:  msmith@chippenham.gov.uk

- Contractor

  - Address: TO BE COMPLETED BY CONTRACTOR.

  - Email: TO BE COMPLETED BY CONTRACTOR.

Clause 1.7.4.2 - Service of notices by email

- Clause 1.7.4.2:

- Employer's email:  msmith@chippenham.gov.uk

- Contractor's email: TO BE COMPLETED BY CONTRACTOR.

Clause 2.3 - Date of Possession of the site

- Date of Possession of the site:  27th July 2026

Clause 2.4 - Deferment of possession of the site

- Clause 2.5 applies

- Where clause 2.5 applies, maximum period of deferment (if less than six weeks) is 6 weeks.

Clause 2.17.3 – Limit of Contractor’s Liability for Loss of Use, etc

- Limit of Contractor's liability for loss of use:  £5,000,000

Clause 2.29.2 - Liquidated Damages

- Damages: At the rate of £1,000 per week per section.

Clause 2.34 - Section Sums

- Section Sums

  - Section 1 – Need Hall Back of House Works: Sum: TBC

  - Section 2 - Neeld Hall Front of House Works: Sum: TBC

  - Section 3 – Town Hall Back of House Works: Sum: TBC

  - Section 4 – Town Hall Front of House Works: Sum: TBC

Clause 2.35 - Rectification Period

- Period: 12 months from the date of practical completion of the Works.

Clause 4.2, 4.12 and 4.13 - Fluctuations Provision

- Fluctuations Provision:  N/A

Clause 4.6 - Advance payment and Advance Payment Bond

- Advance payment: Clause 4.7 does not apply.

Clause 4.7 – Method of payment – Alternative B

- Payment: periodically, in accordance with Alternative B.

Clause 4.7.2 - Interim payments - Interim Valuation Dates

- The first Interim Valuation Date is: TBA, and thereafter the same date in each month or the nearest Business Day in that month.

Clause 4.15.4 - Listed Items - uniquely identified

- The Contract Particulars item for clause 4.10.4 will be deleted.

4.15.5 - Listed Items - not uniquely identified

- Listed Items: The Contract Particulars entry for Clause 4.10.5 will be deleted.

4.17 – Contractors Retention Bond

- Clause 4.17 does not apply.

4.18.1 – Retention Percentage

- Retention: 5 per cent.

Clause 4.21.6 and 4.21.7 - Relevant Matters

- Clause 4.17.5 (the effects of an epidemic on the execution of the Works etc.):  does not apply

- Clause 4.17.6 (exercise of a statutory power etc.):  does not apply

Clause 5.5 - Daywork

- Percentage additions to each section of the prime cost or, if they apply in respect of labour, the All-Inclusive Rates, are set out in the following document:  Dayworks and Overheads Statement

Clause 6.4.1 - Contractor's Public Liability Insurance: Injury to persons or property

- Insurance cover for any one occurrence or series of occurrences arising out of one event:  £5m

Clause 6.5.1 - Insurance - liability of Employer

- Insurance is not required.

Clause 6.7 and Schedule 1 - Works insurance - Insurance Options

- Schedule 1: Insurance Option C applies.

- Percentage to cover professional fees: 20 per cent.

- If Option A applies, annual renewal date (as supplied by the Contractor): TO BE COMPLETED BY CONTRACTOR.

- Where Insurance Option C applies, Paragraph C1:  applies

Clause 6.10 and Schedule 1 - Terrorism Cover

- Details of the required cover:  Not required

Clause 6.17 - Joint Fire Code

- The Joint Fire Code: Does not apply.

Clause 6.20 - Joint Fire Code – Amendments and Revisions

- N/A

Clause 7.2 – Assignment / Grant by Employers of Rights Under Clause 7.2

- Clause 7.2 applies.

Clause 7.3.1 - Performance bond or guarantee

- Bond or guarantee from bank or other approved surety: is required

- Details:

  - Required form:  ABI.

  - Initial value (percentage of the Contract Sum):  10%

  - Period of validity:  until PC

  - Reduction in value:  N/A

Clause 7.3.2 - Guarantee from the Contractor's parent company

- Guarantee:   TBC

  - Parent company's name and registration number: TO BE COMPLETED BY CONTRACTOR.

  - The required form of guarantee is set out in:

Clause 7.4 - Collateral Warranties

- Details: As set out in the following documents: Refer to Appendices Section 1 Introduction

Clause 8.9.2 - Period of suspension (termination by Contractor)

- Period of suspension:

Clauses 8.11.1.1 to 8.11.1.7 - Period of suspension (termination by either Party)

- Period of suspension:

Clause 9.1 - Notification and negotiation of disputes

- The respective nominees of the Parties are

  - Employer's nominee:  TBA

  - Contractor's nominee: TO BE COMPLETED BY CONTRACTOR.

- Or such replacement as each Party may notify to the other from time to time.

Clause 9.3.1 - Adjudication

- The Adjudicator is:  TBA

- Nominating body - where no Adjudicator is named or where the named Adjudicator is unwilling or unable to act (whenever that is established):  Royal Institution of Chartered Surveyors

Clause 9.5.1 - Arbitration

- Appointor of Arbitrator (and of any replacement): N/A

Conditions - No Amendments

Section 1: Definitions and Interpretation

1.5 - Reckoning periods of days

- Amendments:  None

1.12 - Applicable law

- Amendments:  None

Section 2: Carrying out the Works

2.1 - General obligations

- Amendments:  None

Section 3: Control of the Works – No Amendments

Section 4: Payment - No Amendments

Section 5: Variations - No Amendments

Section 6: Injury, Damage and Insurance - No Amendments

Section 7: Assignment, Performance Bonds and Guarantees and Collateral Warranties - No Amendments

Section 8: Termination - No Amendments

Section 9: Settlement of Disputes - No Amendments

Project Bank Account – Does not apply

Execution

Execution

- The Contract: Will be executed as a Deed

A30
Tendering/ subletting/ supply

Main contract tendering

110	Scope

- General: These conditions are supplementary to those stated in the invitation to tender and on the form of tender.

145	Tendering procedure

- General: In accordance with the principles of: JCT Practice Note 6 (Main Contract Tendering) Alternative 1

160	Exclusions

- Inability to tender: Immediately inform if any parts of the work as defined in the tender documents cannot be tendered.

- Relevant parts of the work: Define those parts, stating reasons for the inability to tender.

170	Acceptance of tender

- Acceptance: No guarantee is offered that any tender will be recommended for acceptance or be accepted, or that reasons for non acceptance will be given.

- Costs: No liability is accepted for any cost incurred in the preparation of any tender.

190	Period of validity

- Period: After submission or lodgement, keep tender open for consideration (unless previously withdrawn) for not less than 3 months.

- Date for possession/ commencement: See section A20.

Pricing/ submission of documents

210	Preliminaries in the specification

- Measurement rules: Preliminaries/ General Conditions have not been prepared in accordance with SMM& / NRM2

220	Pricing of preliminaries

- Abbreviations - the following have been used:

  - F = Fixed charge item.

  - TR = Time related charge item.

250	Priced documents

- Alterations: Do not alter or qualify the priced documents without written consent. Tenders containing unauthorised alterations or qualifications may be rejected.

- Measurements: Where not stated, ascertain from the drawings.

- Deemed included: Costs relating to items, which are not priced, will be deemed to have been included elsewhere in the tender.

- Submit:  with tender

300	Quantities in the priced document

- Quantities: Where included in the priced document, these have not been prepared in accordance with SMM7 / NRM 2

310	Tender

- General: Tenders must include for all work shown or described in the tender documents as a whole or clearly apparent as being necessary for the complete and proper execution of the Works.

480	Programme

- Programme of work: Prepare a summary showing the sequence and timing of the principal parts of the Works and periods for planning and design. Itemize any work which is excluded.

- Submit:  with tender

500	Tender stage method statements

- Method statements: Prepare, describing how and when the following is to be carried out:

- Statements: Submit upon request

510	Alternative method tenders

- General: In addition to and at the same time as tendering based upon the date or period specified in section A20, an alternative tender based upon a different date for completion or period may be submitted.

- Date for Completion: If any such tender is accepted the Date for Completion inserted in the Contract will be the date stated in the alternative tender or determined from the period stated in the alternative tender.

515	Alternative time tenders

- General: In addition to and at the same time as tendering based upon the date or period specified in section A20, an alternative tender based upon a different date for completion or period may be submitted.

- Date for Completion: If any such tender is accepted the Date for Completion inserted in the Contract will be the date stated in the alternative tender or determined from the period stated in the alternative tender.

520	Design documents

- General

  - Scope: Include the following in the Contractor’s Proposals.

  - Design drawings:

  - Technical information:

- Submit: With tender.

530	Substitute products

- Details: If products of different manufacture to those specified are proposed, submit details with the tender giving, reasons for each proposed substitution. Unless notification is given at tender stage, proposals for substitutions may not be considered.

- Compliance: Substitutions accepted will be subject to the verification requirements of clause A31/200.

540	Quality control resources

- Statement: Describe the organization and resources to control the quality of the Works, including the work of subcontractors.

- QA staff: Identify in the statement the number and type of staff responsible for quality control, with details of their qualifications and duties.

- Submit:  upon request

550	Health and safety information

- Content: Describe the proposed organization and resources to safeguard the health and safety of operatives, including those of subcontractors, and of any person whom the Works may affect.

- Include

  - Policy document: A copy of the Contractor's health and safety policy documents, including risk assessment procedures.

  - Records: Accident and sickness records for the past five years and of any previous Health and Safety Executive enforcement action.

  - Training: Records of training and training policy.

  - Personnel: The proposed number and type of staff responsible for health and safety on this project with details of their qualifications and duties.

- Submit:  upon request

570	Outline construction phase health and safety plan

- Content

  - Risk assessment: Method statements on how risk from hazards identified in the pre-construction information and other hazards identified by the contractor will be addressed. Procedures for carrying out risk assessment and for managing and controlling the risk.

  - Management system: Details of the proposed management structure, responsibilities and arrangements for issuing health and safety directions. Include procedures for informing other contractors and employees of health and safety hazards.

  - Selection: Proposed procedure for ensuring competency of other contractors, the self-employed and designers.

  - Communication: Procedures for communications between the project team, other contractors and site operatives. Include arrangements for cooperation and coordination between contractors.

  - Emergency: Procedures including those for fire prevention and escape.

  - Records: Arrangements for ensuring that accidents, illness and dangerous occurrences are recorded.

  - Personnel: Procedures for ensuring that persons on site have received relevant health and safety information and training. Include arrangements for consulting with and taking the views of people on site, for preparing site rules and drawing them to the attention of those affected and ensuring compliance.

  - Monitoring: Monitoring procedures to ensure compliance with site rules, selection and management procedures, health and safety standards and statutory requirements. Review procedures to obtain feedback.

  - Welfare facilities: Include appropriate arrangements.

- Submittal date:  prior to commencement

Subletting/ supply

630	Domestic subcontracts

- Details: Provide details of all subcontractors and the work for which they will be responsible.

- Submit:  upon request

A31
Provision, content and use of documents

Definitions and interpretations

110	Definitions

- Meaning: Terms, derived terms and synonyms used in the Preliminaries/ general conditions and specification are as stated here or in the appropriate referenced document.

120	Communication

- Definition: Includes advise, inform, submit, give notice, instruct, agree, confirm, seek, provide or obtain information, consent or instructions, or make arrangements.

- Format: In writing to the person named in clause A10/140 unless specified otherwise.

- Response: Do not proceed until response has been received.

130	Products

- Definition: Materials, both manufactured and naturally occurring, and goods, including components, equipment and accessories, intended for the permanent incorporation in the Works.

- Includes: Goods, plant, materials, site materials and things for incorporation into the Works.

135	Site equipment

- Definition: Apparatus, appliances, machinery, vehicles or things of whatsoever nature required in or about the construction for the execution and completion of the Works but not materials or other things intended to form or forming part of the Permanent Works.

- Includes: Construction appliances, vehicles, consumables, tools, temporary works, scaffolding, cabins and other site facilities.

- Excludes: Products and equipment or anything intended to form or forming part of the permanent works.

150	Contractor's Design

- Meaning: Design to be carried out or completed by the Contractor and supported by appropriate contractual arrangements, to correspond with specified requirements.

155	Submit proposals

- Meaning: Submit information in response to specified requirements.

160	Terms used in specification

- Remove: Disconnect, dismantle as necessary and take out the designated products or work and associated accessories, fixings, supports, linings and bedding materials. Dispose of unwanted materials. Excludes removal and disposal of associated pipework, wiring, ductwork or other services.

- Remediate: Action or measures taken to lessen, clean up, remove or mitigate the existence of hazardous materials; in accordance with standards, or requirements as may be set out by statutes, rules, regulations or specification.

- Fix: Receive, unload, handle, store, protect, place and fasten in position; dispose of waste and surplus packaging. To include all labour, materials and site equipment for that purpose.

- Supply and fix: As above, but including supply of products, components or systems to be fixed, together with everything necessary for their fixing. All products, components or systems are to be supplied and fixed unless stated otherwise.

- Keep for reuse: Do not damage designated products or work. Clean off bedding and jointing materials. Stack neatly, protect adequately and store until required by the employer/ purchaser, or until required for use in the works as instructed.

- Keep for recycling: As 'keep for reuse', but relates to a naturally occurring material rather than a manufactured product.

- Make good: Execute local remedial work to designated work. Make secure, sound and neat. Excludes redecoration and/ or replacement.

- Replace: Supply and fix new products matching those removed. Execute work to match original new state of that removed.

- Repair: Execute remedial work to restore something to its original working state. Make secure, sound and neat. Excludes redecoration and/ or replacement.

- Refix: Fix removed products.

- Ease: Adjust moving parts of designated products, or work to achieve free movement and good fit in open and closed positions.

- Match existing: Provide products and work of the same appearance and features as the original, excluding ageing and weathering. Make joints between existing and new work as inconspicuous as possible.

- System: Equipment, accessories, controls, supports and ancillary items (including installation) necessary for that section of the work to function.

- Building Manual: A document containing information of use to subsequent building owners, occupiers and users about the requirements and procedures for effective operation, maintenance, decommissioning and demolition of the building.

170	Manufacturer and product reference

- Definition: When used in this combination:

  - Manufacturer: The person or legal entity under whose name or trademark the particular product, component or system is marketed

  - Product reference: The proprietary brand name and/ or identifier by which the particular product, component or system is described.

- Currency: References are to the particular product as specified in the manufacturer’s technical literature current on the date of the invitation to tender.

200	Substitution of products

- Products: If an alternative product to that specified is proposed, obtain approval before ordering the product.

- Reasons: Submit reasons for the proposed substitution.

- Information to be submitted:

- Manufacturer and product reference.

- Cost.

- Availability.

- Relevant standards.

- Performance.

- Function.

- Compatibility of accessories.

- Proposed revisions to drawings and specification.

- Compatibility with adjacent work.

- Appearance.

- Copy of warranty or guarantee.

- Alterations to adjacent work: If needed, advise scope, nature and cost.

- Manufacturers’ guarantees: If substitution is accepted, submit before ordering products.

210	Cross references

- Accuracy: Check remainder of the annotation or item description against the terminology used in the section or clause referred to.

- Related terminology: Where a numerical cross reference is not given, the relevant sections and clauses of the specification will apply.

- Relevant clauses: Clauses in the referred to specification section dealing with general matters, ancillary products and execution also apply.

- Discrepancy or ambiguity: Before proceeding, obtain clarification or instructions.

220	Referenced documents

- Conflicts: Specification prevails over referenced documents.

230	Equivalent products

- Inadvertent omission: Wherever products are specified by proprietary name the phrase 'or equivalent' is to be deemed included.

240	Substitution of standards

- Specification: To British Standard or European Standard.

- Substitution: May be proposed complying with a grade or category within a national standard of another Member State of the European Community or an International Standard recognized in the UK.

- Before ordering: Submit notification of all such substitutions.

- Documentary evidence: Submit for verification when requested as detailed in clause A31/200. Any submitted foreign language documents must be accompanied by certified translations into English.

250	Currency of documents and information

- Currency: References to published documents are to the editions, including amendments and revisions, current on the date of the invitation to tender.

260	Sizes

- General dimensions: Products are specified by their co-ordinating sizes.

- Timber: Cross section dimensions shown on drawings are:
Target sizes as defined in BS EN 336 for structural softwood and hardwood sections.
Finished sizes for non-structural softwood or hardwood sawn and further processed sections.

Documents provided on behalf of employer

410	Additional copies of drawings/ documents

- Additional copies: Issued free of charge.

440	Dimensions

- Scaled dimensions: Do not rely on.

450	Measured quantities

- Ordering products and constructing the Works: The accuracy and sufficiency of the measured quantities are not guaranteed.

- Precedence: The specification and drawings shall override the measured quantities.

460	The specification

- Coordination: All sections must be read in conjunction with Main Contract Preliminaries/ General conditions.

Documents provided by contractor/ subcontractors/ suppliers

510	Design and production information

- Master programme: Make reasonable allowance for completing design/ production information, submission (including information relevant to the CDM Regulations), comment, inspection, amendment, resubmission and reinspection.

- Design/ production information: Submit two copies, one could be returned with comments and this will be deemed to be a direction, notice or instruction under the Contract. Ensure that any necessary amendments are made without delay and resubmit unless it is confirmed that it is not required.

- Contractor’s changes to Employer's Requirements: Support request for substitution or variation with all relevant information.

- Employer’s amendments to Employer’s Requirements: If considered to involve a variation, which has not already been acknowledged as a variation, notify without delay (maximum period 7 days), and do not proceed until instructed. Claims for extra cost, if made after it has been carried out, may not be allowed.

- Final version of design/ production information: Submit ……….

600	Contractor's Design information

- General: Complete the design and detailing of parts of the Works as specified.

- Provide: Production information based on the drawings, specification and other information.
Liaison to ensure coordination of the work with related building elements and services.

- Master programme: Make reasonable allowance for completing design/ production information, submission (including information relevant to the CDM Regulations), comment, inspection, amendment, resubmission and reinspection.

- Information required:

  - Format:

  - Number of copies:

- Submit: Within one week of request.

610	Production information

- Contractor/ Domestic subcontractor provide:

- Submit: For comment and make necessary amendments, sufficient copies of final version for distribution to all affected parties.

620	As-built drawings and information

- Contractor designed work

  - Provide the following drawings/ information:

- Submit: At least two weeks before Date for Completion.

630	Technical literature

- Availability: Retain on site for reference by supervisory personnel.

- Information: Manufacturers' current information and relevant British Standards, relating to products to be used in the Works.

640	Maintenance instructions and guarantees

- Components and equipment: Obtain or retain copies, register with manufacturer and hand over on or before completion of the Works.

- Information location: In Building Manual.

- Emergency call out services: Provide telephone numbers for use after completion. Extent of cover: ……….

650	Energy rating calculation

- Calculation documentation

  - Number of copies:  TBC

  - Deliver to: Energy Performance Certificate Assessor and also lodge in the Building Manual.

A32
Management of the works

Generally

110	Supervision

- General: Accept responsibility for coordination, supervision and administration of the Works, including subcontracts.

- Coordination: Arrange and monitor a programme with each subcontractor, supplier, local authority and statutory undertaker, and obtain and supply information as necessary for coordination of the work.

115	Considerate Constructors Scheme

- Registration: Before starting work, register the site and pay the appropriate fee.

- Contact

  - Address: Considerate Constructors Scheme Office, The Maltings, Hoe Lane, Ware, SG12 9LR.

  - Tel: 01920 485959.

  - Free phone: 0800 7831423.

  - Web: www.ccscheme.org.uk.

  - E mail: enquiries@ccscheme.org.uk.

- Standard: Comply with the scheme's Code of Considerate Practice.

  - Minimum compliance level:  TBA

120	Insurance

- Documentary evidence: Before starting work on site submit details, and/ or policies and receipts for the insurances required by the Conditions of Contract.

130	Insurance claims

- Notice: If an event occurs that may give rise to any claim or proceeding in respect of loss or damage to the Works or injury or damage to persons or property arising out of the Works, immediately give notice to the Employer, the person administering the Contract on their behalf and the insurers.

- Failure to notify: Indemnify the Employer against any loss, which may be caused by failure to give such notice.

140	Climatic conditions

- Climatic conditions: Record accurately and retain.

- Information

  - Air temperatures: Daily maximum and minimum, including overnight.

  - Delay records: Due to adverse weather, include a description of the weather, the types of work affected and the number of hours lost.

150	Ownership

- Alteration/ clearance work: Materials arising become the property of the Contractor except where otherwise stated. Remove from site as work proceeds.

Programme/ progress

210	Programme

- Master programme: When requested and before starting work on site, submit in an approved form a master programme for the works, which must include details of:

  - Design, production information and proposals provided by the contractor/ subcontractors/ suppliers, including inspection and checking (see section A31).

  - Planning and mobilization by the contractor.

  - Earliest and latest start and finish dates for each activity and identification of all critical activities.

  - Running in, adjustment, commissioning and testing of all engineering services and installations

  - Work resulting from instructions issued in regard to the expenditure of provisional sums (see section A54)

  - Work by or on behalf of the employer and concurrent with the contract (see section A50). The nature and scope of which, the relationship with preceding and following work and any relevant limitations are suitably defined in the contract documents.

- Exclusions: Where and to the extent that the programme implications for work which is not so defined are impossible to assess, exclude it and confirm this when submitting the programme.

- Submit:  upon request

230	Submission of programme

- Further information: Submission of the programme will not relieve the Contractor of the responsibility to give notice of the need for further drawings or details or instructions in accordance with the Contract.

250	Monitoring

- Progress

  - Records: Record on a copy of the programme kept on site.

  - Delays: Minimize. Take appropriate action to recover lost time.

  - Corrective action: Where progress falls below target, submit proposals.

  - Submittal date: As soon as possible.

  - Completion forecast: Submit on the last working day of each week.

260	Site meetings

- General: Site meetings will be held to review progress and other matters arising from administration of the Contract.

- Frequency:  Monthly

- Location:  On Site

- Accommodation: Ensure availability at the time of such meetings.

- Attendees: Attend meetings and inform subcontractors and suppliers when their presence is required.

- Chairperson (who will also take and distribute minutes):  Michael Edwards Consultants Limited

265	Contractor's progress report

- General: Submit a progress report at least two days before the site meeting.

- Content: Notwithstanding the Contractor's obligations under the Contract the report must include:

  - A progress statement by reference to the master programme for the Works.

  - Details of any matters materially affecting the regular progress of the Works.

  - Subcontractors' and suppliers' progress reports.

  - Any requirements for further drawings or details or instructions to fulfil any obligations under the Conditions of Contract.

270	Contractor’s site meetings

- General: Hold meetings with appropriate subcontractors and suppliers shortly before main site meetings to facilitate accurate reporting of progress.

280	Photographs

- Number of locations:  TBA

- Number of images from each location:  TBA

- Frequency of intervals:  TBA

- Image format:  TBA

- Other requirements: TBA

285	Partial possession by Employer

- Clause 2.25 of Conditions of Contract: Ensure all necessary access, services and other associated facilities are also complete.

290	Notice of completion

- Requirement: Give notice of the anticipated Date for Completion of the whole or parts of the Works.

- Associated works: Ensure that necessary access, services and facilities are complete.

- Period of notice (minimum):  1 week

310	Extensions of time

- Notice: When a notice of the cause of any delay or likely delay in the progress of the Works is given under the Contract, written notice must also be given of all other causes which apply concurrently.

- Details: As soon as possible, submit:

- Relevant particulars of the expected effects, if appropriate, related to the concurrent causes.

- An estimate of the extent, if any, of the expected delay in the completion of the Works beyond the Date for Completion.

- All other relevant information required.

Control of cost

410	Cash flow forecast

- Submission: Before starting work on site, submit a forecast showing the gross valuation of the Works at the date of each Interim Certificate throughout the Contract period. Base on the programme for the Works.

420	Removal/ replacement of existing work

- Extent and location: Agree before commencement.

- Execution: Carry out in ways that minimize the extent of work.

430	Proposed instructions

- Estimates: If a proposed instruction requests an estimate of cost, submit without delay, and in any case within seven days.

- Include:

- A detailed breakdown of the cost, including any allowance for direct loss and expense.

- Details of any additional resources required.

- Details of any adjustments to be made to the programme for the Works.

- Any other information as is reasonably necessary to fully assess the implications of issuing such an instruction.

- Inability to comply: Inform immediately if it is not possible to comply with any of the above requirements.

440	Measurement

- Covered work: Give notice before covering work required to be measured.

450	Daywork vouchers

- Before commencing work: Give reasonable notice to person countersigning daywork vouchers.

- Content: Before delivery, each voucher must:

- Be referenced to the instruction under which the work is authorized.

- Include a full description of the work undertaken and time spent on individual tasks.

- Be signed by the Contractor's person in charge as evidence that the operatives' names, the time spent by each, and the plant and materials shown are correct.

- Submit: By the end of the week in which the work has been executed.

470	Products not incorporated into the Works

- Ownership: At the time of each valuation, supply details of those products not incorporated into the Works which are subject to reservation of title inconsistent with passing of property as required by the Conditions of Contract, together with their respective values.

- Evidence: When requested, provide evidence of freedom of reservation of title.

475	Listed products stored off site

- Evidence of Title: Submit reasonable proof that the property in 'listed items' is vested in the Contractor.

- Include for products purchased from a supplier: A copy of the contract of sale and a written statement from the supplier that any conditions of the sale relating to the passing of property have been fulfilled and the products are not subject to any encumbrance or charge.

- Include for products purchased from a supplier by a subcontractor or manufactured or assembled by any subcontractor: Copies of the subcontract with the subcontractor and a written statement from the subcontractor that any conditions relating to the passing of property have been fulfilled.

480	Labour and equipment returns

- Records: Provide for verification at the beginning of each week in respect of each of the previous seven days.

- Records must show

  - The number and description of craftsmen, labourers and other persons directly or indirectly employed on or in connection with the Works or Services, including those employed by subcontractors.

  - The number, type and capacity of all mechanical, electrical and power-operated equipment employed in connection with the Works or Services

A33
Quality standards/ control

Standards of products and executions

110	Incomplete documentation

- General: Where and to the extent that products or work are not fully documented, they are to be:

  - Standard: ﻿Of a kind and standard appropriate to the nature and character of that part of the Works where they will be used.

  - Suitability: Suitable for the purposes stated or reasonably to be inferred from the project documents.

- Contract documents: Omissions or errors in description and/ or quantity shall not vitiate the Contract nor release the Contractor from any obligations or liabilities under the Contract.

120	Workmanship skills

- Operatives: Appropriately skilled and experienced for the type and quality of work.

- Registration: With Construction Skills Certification Scheme.

- Verification: When requested, operatives must produce evidence of skills/ qualifications.

130	Quality of products

- Generally: New. (Proposals for recycled products may be considered.)

- Supply of each product: From the same source or manufacturer.

- Whole quantity of each product required to complete the Works: Consistent kind, size, quality and overall appearance.

- Tolerances: Where critical, measure a sufficient quantity to determine compliance.

- Deterioration: Prevent. Order in suitable quantities to a programme and use in appropriate sequence.

135	Quality of execution

- Generally: Fix, apply, install or lay products securely, accurately, plumb, neatly and in alignment.

- Colour batching: Do not use different colour batches where they can be seen together.

- Dimensions: Check on-site dimensions.

- Finished work: Not defective, e.g. not damaged, disfigured, dirty, faulty, or out of tolerance.

- Location and fixing of products: Adjust joints open to view so they are even and regular.

140	Evidence of Compliance

- Proprietary products: Retain on site evidence that the proprietary product specified has been supplied.

- Performance specification: Submit upon request evidence of compliance with performance specifications, including:

- Test reports indicating properties tested.

- Pass or fail criteria.

- Test methods and procedures.

- Test results.

- Identity of testing agency.

- Test dates and times.

- Identities of witnesses.

- Analysis of results.

150	Inspections

- Products and executions: Inspection, or other action, of products or executions must not be taken as approval, unless confirmed in writing and including:

- Date of inspection.

- Part of the work inspected.

- Respects or characteristics which are approved.

- Extent and purpose of the approval.

- Any associated conditions.

160	Related work

- Details: Provide all trades with necessary details of related types of work. Before starting each new type or section of work ensure previous related work is:

- Appropriately complete.

- In accordance with the project documents.

- To a suitable standard.

- In a suitable condition to receive the new work.

- Preparatory work: Ensure that all necessary preparatory work has been carried out.

170	Manufacturer’s recommendations/ instructions

- General: Comply with manufacturer's printed recommendations and instructions current on the date of the Invitation to tender.

- Exceptions: Submit details of changes to recommendations or instructions.

- Execution: Use ancillary products and accessories supplied or recommended by main product manufacturer.

- Products: Comply with limitations, recommendations and requirements of relevant valid certificates.

180	Water for the works

- Mains supply: Clean and uncontaminated.

- Other: Do not use until:

- Evidence of suitability is provided.

- Tested to BS EN 1008 if instructed.

Samples/ approvals

210	Samples

- Products or executions: Comply with all other specification requirements and in respect of the stated or implied characteristics either:

- To an express approval.

- To match a sample expressly approved as a standard for the purpose.

220	Approval of products

- Submissions, samples, inspections and tests: Undertake or arrange to suit the Works programme.

- Approval: Relates to a sample of the product and not to the product as used in the Works. Do not confirm orders or use the product until approval of the sample has been obtained.

- Complying sample: Retain in good, clean condition on site. Remove when no longer required.

230	Approval of execution

- Submissions, samples, inspections and tests: Undertake or arrange to suit the Works programme.

- Approval: Relates to the stated characteristics of the sample. (If approval of the finished work as a whole is required this is specified separately). Do not conceal, or proceed with affected work until compliance with requirements is confirmed.

- Complying sample: Retain in good, clean condition on site. Remove when no longer required.

Accuracy/ setting out generally

320	Setting out

- General: Submit details of methods and equipment to be used in setting out the Works.

- Levels and dimensions: Check and record the results on a copy of drawings. Notify discrepancies and obtain instructions before proceeding.

- Inform: When complete and before commencing construction.

330	Appearance and fit

- Tolerances and dimensions: If likely to be critical to execution or difficult to achieve, as early as possible either:

- submit proposals; or

- arrange for inspection of appearance of relevant aspects of partially finished work.

- General tolerances (maximum): To BS 5606, Tables 1 and 2.

340	Critical dimensions

- Critical dimensions: Set out and construct the Works to ensure compliance with the tolerances stated.

350	Levels of structural floors

- Maximum tolerances for designed levels to be

  - Floors to be self-finished, and floors to receive sheet or tile finishes directly bedded in adhesive: +/- 10 mm.

  - Floors to receive dry board/ panel construction with little or no tolerance on thickness: +/- 10 mm.

  - Floors to receive mastic asphalt flooring/ underlays directly: +/- 10 mm.

  - Floors to receive mastic asphalt flooring/ underlays laid on mastic asphalt levelling coat(s): +/- 15 mm.

  - Floors to receive fully bonded screeds/ toppings/ beds: +/- 15 mm.

  - Floors to receive unbonded or floating screeds/ beds: +/- 20 mm.

360	Record drawings

- Site setting out drawing: Record details of all grid lines, setting-out stations, benchmarks and profiles. Retain on site throughout the Contract and hand over on completion.

Services generally

410	Services regulations

- New or existing services: Comply with the bye-laws or regulations of the relevant statutory authority.

420	Water regulations/ bye-laws notification

- Requirements: Notify water Statutory Provider of any work carried out to, or which affects, new or existing services. Submit required plans, diagrams and details.

- Consent: Allow adequate time to receive Statutory Provider's consent before starting work. Inform the Employer immediately if consent is withheld or is granted subject to significant conditions.

430	Water regulations/ bye-laws contractor’s certificate

- On completion of the work: Submit a certificate (copy where also required to the water Statutory Provider), including:

  - Installation: Description of the new installation and/ or the work carried out to an existing installation, including the address.

  - Statement: Confirmation that the installation complies with the relevant water regulations or bye-laws.

  - Inspection: Provide the Contractor's name and address, the name and signature of the individual responsible for checking compliance and the date on which the installation was checked.

435	Electrical installation certificate

- Submit: When relevant electrical work is completed.

- Original certificate: To be lodged in the Building Manual.

445	Service runs

- General: Provide adequate space and support for services, including unobstructed routes and fixings.

- Ducts, chases and holes: Form during construction rather than cut in situ.

- Coordination with other works: Submit details of locations, types and methods of fixing of services to fabric and identification of runs and fittings.

450	Mechanical and electrical services

- Final tests and commissioning: Carry out so that services are in full working order at completion of the Works.

- Building Regulations notice: Copy to be lodged in the Building Manual.

Supervision/ inspection/ defective work

510	Supervision

- General: The whole of the contract work and any significant parts must be under the close control of competent trade supervisors to ensure maintenance of satisfactory quality, progress and coordination.

- Evidence: Submit, including details of:

- the person proposed;

- their relevant skills training and knowledge;

- practical experience;

- qualifications;

- membership or registration with professional bodies;

- employment history;

- work related assessments; and

- management structure.

- Submittal date:  upon request

- Replacement: Give maximum possible notice before changing supervisory personnel.

520	Coordination of engineering services

- Suitability: Site organization staff must include one or more persons with appropriate knowledge and experience of mechanical and electrical engineering services to ensure compatibility between engineering and the Works generally.

- Evidence: Submit on request, including:

- details of the person proposed;

- their relevant skills, training and knowledge;

- practical experience;

- qualifications; membership or registration with professional bodies;

- employment history;

- work-related assessments; and

- management structure.

530	Overtime working

- Notice: Prior to overtime being worked, submit details of times, types and locations of work to be done.

  - Minimum period of notice:

- Concealed work: If executed during overtime for which notice has not been given, it may be required to be opened up for inspection and reinstated at the Contractor's expense.

540	Defects in existing work

- Undocumented defects: When discovered, immediately give notice. Do not proceed with affected related work until response has been received.

- Documented remedial work: Do not execute work which may hinder access to defective products or work, or be rendered abortive by the remedial work.

550	Access for inspection

- Removal: Before removing scaffolding or other facilities for access, give notice of not less than 1 week

560	Tests and inspections

- Timing: Agree and record dates and times of tests and inspections to enable all affected parties to be represented.

- Confirmation: One working day prior to each such test or inspection. If sample or test is not ready, agree a new date and time.

- Records: Submit a copy of test certificates and retain copies on site.

595	Energy performance certificate

- Assessment: Undertaken by a member of an approved accreditation scheme. Submit details of scheme name and evidence of qualifications when requested.

  - Building Type:  TBC

  - Method:  TBC

- Format

  - Certificate: To be incorporated in the Building Manual.

  - Report:  TBC

- Submit:  TBC

610	Proposals for rectification of defective products/ executions

- Proposals: Where any execution or product is, or appears to be, not in accordance with the Contract, immediately submit proposals for opening up, inspection, testing, making good, adjustment of the Contract Sum, or removal and re-execution.

- Acceptability: Such proposals may be unacceptable and contrary instructions may be issued.

620	Measures to establish acceptability

- General: Wherever inspection or testing shows that the work, materials or goods are not in accordance with the Contract and measures (e.g. testing, opening up, experimental making good) are taken to help in establishing whether or not the work is acceptable, such measures will be at the expense of the Contractor, and will not be considered as grounds for revision of the Completion Date.

630	Quality control

- Procedures: Establish and maintain to ensure that the Works, including the work of subcontractors, comply with specified requirements.

- Records: Maintain full records, keep copies on site for inspection, and submit copies on request.

- Content of records

  - Identification: Describe each element, item, batch or lot including location in the Works.

  - Inspections, tests and approvals: Describe purpose and dates.

  - Nonconforming work: Describe nature and extent of work found.

  - Corrective action: Details of work carried out.

Work at or after completion

710	Work before completion

- General: Make good all damage consequent upon the Works.

- Temporary markings, coverings and protective wrappings: Remove unless otherwise instructed.

- Cleaning: Clean the Works thoroughly inside and out, including all accessible ducts and voids. Remove all splashes, deposits, efflorescence, rubbish and surplus materials.

- Cleaning materials and methods: As recommended by manufacturers of products being cleaned, and must not damage or disfigure other materials or construction.

- COSHH dated data sheets: Obtain for all materials used for cleaning and ensure they are used only as recommended by their manufacturers.

- Minor faults: Touch up in newly painted work, carefully matching colour and brushing out edges. Repaint badly marked areas back to suitable breaks or junctions.

- Moving parts of new work: Adjust, ease and lubricate as necessary to ensure easy and efficient operation, including doors, windows, drawers, ironmongery, appliances, valves and controls.

720	Security at completion

- General: Leave the Works secure with, where appropriate, all accesses closed and locked.

- Keys: Account for and adequately label all keys, and hand over together with an itemized schedule, retaining duplicate schedule signed as a receipt.

730	Making good defects

- Remedial work: Arrange access with Michael Edwards Consultants Limited

- Rectification: Give reasonable notice for access to the various parts of the Works.

- Completion: Notify when remedial works have been completed.

A34
Security/ safety/ protection

Security, health and safety

110	Pre-construction information

- Location: Integral with the project Preliminaries, including but not restricted to the following sections:

  - Description of project: Sections A10 and A11.

  - Client’s consideration and management requirements: Sections A12, A13 and A36.

  - Environmental restrictions and on-site risks: Section A12, A35 and A34.

  - Significant design and construction hazards: Section A34.

  - The health and safety file: Section A37.

120	Execution hazards

- Common hazards: Not listed. Control by good management and site practice.

- Significant hazards: The design of the project includes the following:

  - Hazard:

  - Precautions assumed:

  - Specification reference:

  - Drawing reference:

130	Product hazards

- Hazardous substances: Site personnel levels must not exceed occupational exposure standards and maximum exposure limits stated in the current version of HSE document EH40: Workplace exposure limits.

- Common hazards: Not listed. Control by good management and site practice.

- Significant hazards: Specified construction materials include the following:

  - Hazard:

  - Material:

  - Specification reference:

140	Construction phase health and safety plan

- Submission: Present to the employer/ client no later than 2 weeks prior to commencement.

- Confirmation: Do not start construction work until written confirmation is received that the construction phase health and safety plan includes the procedures and arrangements required by the CDM Regulations.

- Content: Develop the plan from and draw on the outline construction phase health and safety plan, clause A30/570, and the pre-tender health and safety plan/ pre-construction information.

150	Security

- Protection: Safeguard the site, the Works, products, materials, and any existing buildings affected by the Works from damage and theft.

- Access: Take all reasonable precautions to prevent unauthorized access to the site, the Works and adjoining property.

- Special requirements:  None noted

160	Stability

- Responsibility: Maintain the stability and structural integrity of the Works and adjacent structures during the Contract.

- Design loads: Obtain details, support as necessary and prevent overloading.

170	Occupied premises

- Extent: Existing buildings will be occupied and/ or used during the Contract as follows: existing council offices and Neeld Hall, refer to section 1.

- Works: Carry out without undue inconvenience and nuisance and without danger to occupants and users.

- Overtime: If compliance with this clause requires certain operations to be carried out during overtime, and such overtime is not required for any other reason, the extra cost will be allowed, provided that such overtime is authorized in advance.

210	Safety provisions for site visits

- Access: Provide at reasonable times.

- Inspections: Agree dates and times several days in advance, to enable affected parties to be present.

- Safety: Submit details in advance of safety provisions and procedures (including those relating to materials, which may be deleterious), which will require their compliance when visiting the site.

- Protective clothing and/ or equipment: Provide and maintain on site for visitors to the-site.

Protect against the following

310	Explosives

- Use: Not permitted.

330	Noise and vibration

- Standard: In accordance with BS 5228-1.

- Equipment: Fit compressors, percussion tools and vehicles with effective silencers of a type recommended by manufacturers of the compressors, tools or vehicles.

- Restrictions: Obtain consent before using percussion tools and other noisy appliances. Do not use radios or other audio equipment, or permit employees to use them in ways or at times that may cause nuisance.

340	Pollution

- Prevention: Protect the site, the works and the general environment (including the atmosphere, land, streams and waterways) against pollution.

- Contamination: If pollution occurs, report immediately, including to the appropriate authorities, and provide relevant information.

350	Pesticides

- Use: Not permitted.

360	Nuisance

- Duty: Prevent nuisance from smoke, dust, rubbish, vermin and other causes.

- Surface water: Prevent hazardous build-up on site, in excavations and to surrounding areas and roads.

370	Asbestos containing materials

- Duty: Report immediately any suspected materials discovered during execution of the works. Do not disturb, and agree methods for safe removal or encapsulation.

371	Dangerous or hazardous substances

- Duty: Report immediately suspected materials discovered during execution of the works. Do not disturb and agree methods for safe removal or remediation.

375	Antiquities

- Duty: Report immediately any fossils, antiquities and other objects of interest or value discovered during execution of the works.

- Preservation: Keep objects in the exact position and condition in which they were found.

- Special requirements:  No requirements.

380	Fire prevention

- Duty: Prevent personal injury or death, and damage to the Works or other property from fire.

- Standard: Comply with Fire prevention on construction sites. The joint code of practice on the protection from fire of construction sites and buildings undergoing renovation, published by the Fire Protection Association (the 'Joint Fire Code').

390	Smoking on-site

- Smoking on-site: Not permitted.

400	Burning on-site

- Burning on-site: Not permitted.

410	Moisture

- Wetness or dampness: Prevent, where this may cause damage to the Works.

- Drying out: Control humidity and the application of heat to prevent:

- Blistering and failure of adhesion.

- Damage due to trapped moisture.

- Excessive movement.

420	Infected timber/ Contaminated materials

- Removal: Where instructed to remove material affected by fungal/ insect attack from the building, minimize the risk of infecting other parts of the building.

- Testing: Carry out and keep records of appropriate tests to demonstrate that hazards presented by concentrations of airborne particles, toxins and other microorganisms are within acceptable levels.

430	Waste

- Waste: Includes rubbish, debris, spoil, containers and packaging, and surplus material requiring disposal.

- Requirement: Minimize production and prevent accumulation of waste. Keep the site and works clean and tidy. Clean out voids and cavities in the construction before closing.

- Disposal: Collect and store in suitable containers. Remove from site and dispose of in a safe and competent manner, as approved and directed by the waste regulation authority.

- Recyclable material: Sort and dispose of at a materials recycling facility approved by the waste regulation authority.

- Documentation: Retain on-site.

440	Electromagnetic interference

- Duty: Prevent excessive electromagnetic disturbance to apparatus outside the site.

450	Laser equipment

- Construction laser equipment: Install, use and store in accordance with BS EN 60825-1 and the manufacturer's instructions.

- Class 1 or Class 2 laser equipment: Ensure that the laser beam is not set at eye level and is terminated at the end of its useful path.

- Class 3R and Class 3B laser equipment: Do not use without approval and subject to submission of a method statement on its safe use.

460	Powder actuated fixing systems

- Use: Not permitted.

470	Invasive species

- General: Prevent the introduction or spread of species (e.g. plants or animals) that may adversely affect the site and/ or the Works economically, environmentally or ecologically.

- Special precautions:

- Duty: Report immediately any suspected invasive species discovered during execution of the Works. Do not disturb and agree methods for safe eradication or removal.

Protect the following

510	Existing services

- Confirmation: Notify service authorities, statutory undertakers and/ or adjacent owners of proposed works not less than one week before commencing site operations.

- Identification: Before starting work, check and mark positions of utilities/ services. Where positions are not shown on drawings obtain relevant details from service authorities, statutory undertakers or other owners.

- Work adjacent to services: Comply with service authority's or statutory undertaker's recommendations. Adequately protect, and prevent damage to services. Do not interfere with their operation without consent of service authorities, statutory undertakers or other owners.

- Identifying services

  - Below ground: Use signboards, giving type and depth.

  - Overhead: Use headroom markers.

- Damage to services

  - Action: Immediately give notice and notify appropriate service authority/ statutory undertaker.

  - Repair: Make arrangements for making good without delay to the satisfaction of service authority, statutory undertaker or other owner as appropriate.

- Liability: Measures taken to deal with an emergency will not affect the extent of the Contractor's liability.

- Marker tapes or protective covers: Replace, if disturbed during site operations, to service authority's/ statutory undertakers recommendations.

520	Roads and footpaths

- Duty: Maintain roads and footpaths within and adjacent to the site and keep clear of mud and debris.

- Damage caused by site traffic or otherwise consequent upon the Works: Make good to the satisfaction of the Employer, local authority or other owner.

555	Wildlife species and habitats

- Protected habitats and species: Upon discovery immediately advise. Do not proceed until instruction is received.

- Education: Ensure that employees and visitors to the site receive suitable instruction and awareness training.

560	Existing features

- Protection: Prevent damage to existing buildings, fences, gates, walls, roads, paved areas and other site features, which are to remain in position during execution of the Works.

570	Existing work

- Protection: Prevent damage to existing work, structures or other property during the course of the work.

- Removal: Minimum amount necessary.

- Replacement work: To match existing.

580	Building interiors

- Protection: Prevent damage from exposure to the environment, including weather, flora, fauna, and other causes of material degradation during the course of the work.

600	Existing furniture, fittings and equipment

- Protection: Prevent damage or move as necessary to enable the Works to be executed. Reinstate in original positions.

610	Especially valuable/ vulnerable items

- Protection: Ensure provision and maintenance of special protective measures to prevent damage.

- Items:  TBA

- Method statement: Submit within one week of request describing special protection to be provided.

625	Adjoining property restrictions

- Precautions: Prevent trespass of workpeople and take precautions to prevent damage to adjoining property. Pay charges. Remove temporary protection and make good on completion or when directed.

- Damage: Bear cost of repairing damage arising from execution of the Works.

630	Existing structures

- Duty: Check proposed methods of work for effects on adjacent structures inside and outside the site boundary.

- Supports

  - Standards: In accordance with BS 5975 and BS EN 12812.

  - Requirements:

- Provide and maintain all incidental shoring, strutting, needling and other supports as may be necessary to preserve stability of existing structures on the site or adjoining, which may be endangered or affected by the Works.

- Do not remove until new work is strong enough to support existing structure.

- Prevent overstressing of completed work when removing supports.

- Adjacent structures: Monitor and immediately report excessive movement.

640	Materials for recycling/ reuse

- Duty: Sort and prevent damage to stated products or materials, clean off bedding and jointing materials and other contaminants.

- Storage: Stack neatly and protect until required by the Employer or for use in the Works as instructed.

A35
Specific limitations on method/ sequence/ timing

Clauses

110	Scope

- General: The limitations described in this section are supplementary to limitations described or implicit in information given in other sections or on the drawings.

120	Design constraints

- Details:

130	Method/ sequence of work

- Specific Limitations: Include the following in the programme:

  - ……….

140	Scaffolding

- Scaffolding: Make available to subcontractors and others at all times.

160	Use or disposal of materials

- Specific limitations:

170	Working Hours

- Specific limitations:

180	Completion in sections or in parts

- General: Where the Employer is to take possession of any Section or part of the Works and such Section or part will, after its practical completion, depend for its adequate functioning on work located elsewhere on the site: Complete such other work in time to permit such possession to take place.

- Remainder of the Works: During execution, ensure that completed Sections or parts of the Works have continuous and adequate provision of services, fire precautions, means of escape and safe access.

A36
Facilities/ temporary work/ services

Generally

110	Spoil heaps, temporary works and services

- Location: Give notice and details of intended siting.

- Maintenance: Alter, adapt and move as necessary. Remove when no longer required and make good.

Accommodation

210	Room for meetings

- Facilities: Provided by the client.

- Furniture and Equipment: Provided by the client.

230	Temporary accommodation

- Accommodation made available by the Employer: The following may be used for the duration of the Contract without charge provided that:

- It is used solely for the purposes of carrying out the Works.

- The use to which it is put does not involve undue risk of damage.

- Temporary adaptations are approved by or on behalf of the Employer before being carried out.

- It is vacated on completion of the Works or determination of the Contract.

- When vacated, its condition is at least equivalent to its condition at the start of the Contract.

- Description:  TBC

- Available services and facilities:

260	Sanitary accommodation

- Requirement: Provide sanitary accommodation for the Employer/ Purchaser, and other members of the consultant team, either separate or shared with the Contractor's supervisory staff. Maintain in clean condition and provide all consumables.

Temporary works

310	Roads

- Permanent roads, hard standings and footpaths on the site: The following may be used, subject to clause A34/520:

340	Name boards/ advertisements

- Name boards/ advertisements: Not permitted.

Services and facilities

410	Lighting

- Finishing work and inspection: Provide temporary lighting, the intensity and direction of which closely resembles that delivered by the permanent installation.

420	Lighting and power

- Supply: Electricity from the existing mains may be used for the Works

- Continuity: No responsibility will be accepted for the consequences of failure or restriction in supply.

430	Water

- Supply: The existing mains may be used for the Works

- Continuity: No responsibility will be accepted for the consequences of failure or restriction in supply.

440	Telephones

- Temporary on site telephone: Provide as soon as practicable after the start on site for joint use by the Contractor and subcontractors and pay all charges.

- Responses: Make arrangements (e.g. call diverts) to ensure that incoming calls are answered promptly.

470	E-mail and internet facility

- General: As soon as practicable after the start on site provide a suitable email facility on site, with a separate dedicated connection, for the use of the Contractor, subcontractors and other members of the project team.

- Use on behalf of Employer: Allow for the cost of a reasonable number of transmissions made by other members of the project team.

520	Use of permanent heating system

- Permanent heating installation: May be used for drying out the Works/ services and controlling temperature and humidity levels.

- Requirements: Take responsibility for operation, maintenance and remedial work. Arrange supervision by and indemnification of the appropriate subcontractors. Pay fuel and associated costs.

540	Meter readings

- Charges for service supplies: Where to be apportioned ensure that:

- Meter readings are taken by relevant authority at possession and/ or completion as appropriate.

- Copies of readings are supplied to interested parties.

550	Thermometers

- General: Provide on site and maintain in accurate condition a maximum and minimum thermometer. Measure atmospheric shade temperature in an approved location.

560	Surveying Equipment

- General: Provide on site and maintain in accurate condition

570	Personal protective equipment

- General: Provide the equipment described below for the sole use of other members of the project team, in sizes to be specified.

- Safety helmets

  - Standard: To BS EN 397, neither damaged nor time expired.

  - Number required:  2

- High-visibility waistcoats

  - Standard: To BS EN ISO 20471.

  - Class:  2

  - Number required:  2

- Safety boots

  - Standard: To BS EN ISO 20345, with steel insole and toecap.

  - Number of pairs required:  2

- Disposable respirators

  - Standard: To BS EN 149, FFP1S.

  - Number required: 2

- Eye protection

  - Standard: To BS EN ISO 16321-1 and BS EN ISO 16321-3, as appropriate.

  - Number required:  2

- Ear protection

  - Standard: Muffs to BS EN 352-1, plugs to BS EN 352-2.

  - Number required:  2

- Hand protection

  - Standard: To BS EN 388, BS EN 407, BS EN ISO 21420 or BS EN 511 as appropriate.

  - Number required:  2

A37
Operation/ maintenance of the finished works

Generally

110	The Building Manual

- Purpose: The Building Manual is to be a comprehensive information source and guide for owners and users of the completed Works. It should provide an overview of the main design principles and describe key components and systems to enable proper understanding, efficient and safe operation and maintenance.

- Scope

  - Part 1: General: content as clause 120.

  - Part 2: Fabric: content as clause 130.

  - Part 3: Services: content as clause 140.

  - Part 4: The Health and Safety File: content as clause 150.

  - Part 5: Building User Guide: content as clause 151.

- Responsibility for production:  The Building Manual is to be produced by the Contractor

- Date required:  No later than completion

- Information provided by others:  on request

- Compilation: Prepare all information for Contractor designed or performance specified work including as-built drawings. Obtain or prepare all other information to be included in the Building Manual.

- Reviewing the Building Manual: Prepare and circulate a complete draft. Amend in the light of any comments and recirculate. Do not proceed with production of the final copies until authorized.

- Final copies of the Building Manual

  - Number of copies:  2

  - Format:  Paper and PDF

  - Latest date for submission:  0 weeks before the date for completion stated in the contract

- As-built drawings and schedules

  - Number of copies:  2

  - Format:  A3 paper & PDF

115	The Health and Safety File

- Responsibility:  Principal Contractor

- Content:  TBA

- Format:  TBA

- Delivery to: ……PD By (date): PC

120	Content of the Building Manual part 1: General

- Content: Obtain and provide the following, including all relevant details not included in other parts of the Building Manual:

- Index: List the constituent parts of the Building Manual, together with their location in the document.

- The Works:

- Description of the buildings and facilities.

- Ownership and tenancy, where relevant.

- Health and safety information – other than that specifically required by the Construction (Design and Management) Regulations.

- The Contract:

- Names, addresses and contact details of all significant consultants, contractors, subcontractors, suppliers and manufacturers.

- Overall design criteria.

- Environmental performance requirements.

- Relevant authorities, consents and approvals.

- Third-party certification, such as those made by 'competent' persons in accordance with the Building Regulations.

- Operational requirements and constraints of a general nature:

- Maintenance contracts and contractors.

- Fire safety strategy for the buildings and the site. Include drawings showing emergency escape and fire appliance routes, fire-resisting doors, location of emergency alarm and firefighting systems, services, shut off valves switches, etc.

- Emergency procedures and contact details in case of emergency.

- Other specific requirements:

- Other key documents:

- Timescale for completion:

130	Content of the Building Manual part 2: Building fabric

- Content: Obtain and provide the following, including all relevant details not included in other parts of the Building Manual:

- Detailed design criteria: Including:

- Floor and roof loadings.

- Durability of individual components and elements.

- Loading restrictions.

- Insulation values.

- Fire ratings.

- Other relevant performance requirements.

- Construction of the building:

- A detailed description of methods and materials used.

- As-built drawings recording the construction, together with an index.

- Information and guidance concerning repair, renovation or demolition/ deconstruction.

- Periodic building maintenance guide chart: Provide for all significant items of work.

- Inspection reports:

- Manufacturer’s instructions index: Include relevant COSHH data sheets and recommendations for cleaning, repair and maintenance of components.

- Fixtures, fittings and components schedule and index:

- Guarantees, warranties and maintenance agreements: Obtain from manufacturers, suppliers and subcontractors.

- Test certificates and reports required in the specification: Obtain, including:

- Air permeability.

- Resistance to passage of sound.

- Continuity of insulation.

- Electricity and gas safety.

- Other specific requirements:

- Timescale for completion:

140	Content of the Building Manual part 3: Building services

- Content: Obtain and provide the following, including all relevant details not included in other parts of the Building Manual:

- Detailed design criteria and description of the systems, including:

- Services capacity, loadings and restrictions.

- Services instructions.

- Services log sheets.

- Manufacturers’ instruction manuals and leaflets index.

- Fixtures, fittings and component schedule index.

- Detailed description of methods and materials used:

- As-built/ record drawings: For each system recording the construction, together with an index, including:

- Diagrammatic drawings indicating principal items of plant, equipment and fittings.

- Record drawings showing overall installation.

- Schedules of plant, equipment, valves, etc. describing location, design performance and unique identification cross-referenced to the record drawings.

- Identification of services – a legend for colour-coded services.

- Product details: Including for each item of plant and equipment:

- Name, address and contact details of the manufacturer.

- Catalogue number or reference.

- Manufacturer’s technical literature, including detailed operating and maintenance instructions.

- Information and guidance concerning dismantling, repair, renovation or decommissioning.

- Operation: A description of the operation of each system, including:

- Starting up, operation and shutting down.

- Control sequences.

- Procedures for seasonal changeover.

- Procedures for diagnostics, troubleshooting and fault-finding.

- Guarantees, warranties and maintenance agreements: Obtain from manufacturers, suppliers and subcontractors.

- Commissioning records and test certificates: List for each item of plant, equipment, valves, etc. used in the installations, including:

- Electrical circuit tests.

- Corrosion tests.

- Type tests.

- Work tests.

- Start and commissioning tests.

- Equipment settings: Schedules of fixed and variable equipment settings established during commissioning.

- Preventative maintenance: Recommendations for frequency and procedures to be adopted to ensure efficient operation of the systems

- Lubrication: Schedules of all lubricated items

- Consumables: A list of all consumable items and their source.

- Spares: A list of recommended spares to be kept in stock, being those items subject to wear and tear or deterioration and which may involve an extended delivery time when replacements are required.

- Emergency procedures: For all systems, significant items of plant and equipment.

- Annual maintenance summary chart:

- Other specific requirements:

- Timescale for completion:

150	Content of the Building Manual part 4: the Health and Safety File

- Content: Obtain and provide the following, including all relevant details not included in other parts of the Building Manual:

- Residual hazards and how they have been dealt with.

- Hazardous materials used.

- Information regarding the removal or dismantling of installed plant and equipment.

- Health and safety information about equipment provided for cleaning or maintaining the structure.

- The nature, location and markings of significant services.

- Information and as-built drawings of the structure, its plant and equipment.

- Information provided by others:

- Timescale for completion:

151	Content of the Building Manual part 5: the building user guide

- Content: Obtain and provide the following:

- Building services information.

- Emergency information.

- Energy and environmental strategy.

- Water use.

- Transport facilities.

- Materials and waste policy.

- Refit/ rearrangement considerations.

- Reporting provision.

- Training.

- Links and references.

- Other specific requirements:

- Timescale for completion:

160	Presentation of Building Manual

- Format:

- Hard copy documents

  - Presentation: A4-size, plastics-covered, loose-leaf, four-ring binders with hard covers, each indexed, divided and appropriately cover-titled.

  - Selected drawings needed to illustrate or locate items mentioned in the Manual: Where larger than A4, to be folded and accommodated in the binders so that they may be unfolded without being detached from the rings.

  - Number required:

- As-built drawings: The main sets may form annexes to the Building Manual.

190	Maintenance service

- Scope: Provide a comprehensive maintenance service. Include all planned preventative maintenance, as set out within the maintenance schedule, and replacement of all consumable items.

- Plant and equipment to be maintained:

- Terms:

- Commencement:

- Duration:

220	Training

- Objective: Before completion, explain and demonstrate to designated maintenance staff the purpose, function and operation of the installations including items and procedures listed in the Building Manual.

- Level of training:

- Time allowance (minimum):

230	Spare parts

- General: Prepare a priced schedule of recommended spare parts that should be obtained and kept in stock for maintenance of the services installations.

- Content: Include in the priced schedule for:

- Manufacturers' current prices, including packaging and delivery to site.

- Checking receipts, marking and numbering in accordance with the schedule of spare parts.

- Referencing to the plant and equipment list in part 3 of the Building Manual.

- Painting, greasing, etc. and packing to prevent deterioration during storage.

- Latest date for submission:

250	Tools

- General: Provide tools and portable indicating instruments for the operation and maintenance of all services plant and equipment (except any installed under Named Sub-contracts) together with suitable means of identifying, storing and securing.

- Quantity: Two complete sets.

- Consumables: Supply a complete list of all consumables necessary for the operation.

- Time of submission: At completion.

A40
Contractor’s general cost items: management and staff

Clauses

110	Management and staff

- Cost-significant items:

A41
Contractor’s general cost items: site accommodation

Clauses

110	Site accommodation

- Details: Site accommodation required or made/ not made available by the Employer: See section A36.

- Cost significant items:

A42
Contractor’s general cost items: services and facilities

Clauses

110	Services and facilities

- Details: Services or facilities required or made/ not made available by the Employer: See section A36.

- Cost significant items:

A43
Contractor’s general cost items: mechanical plant

Clauses

110	Mechanical plant

- Cost significant items:

A44
Contractor’s general cost items: temporary works

Clauses

110	Temporary works

- Details: Temporary works required or made/ not made available by the Employer: See section A36.

- Cost significant items:

A50
Work/ products by/ on behalf of the employer

Clauses

110	Work by/ on behalf of employer

- None

120	Products provided by/ on behalf of employer

- None

A53
Work by statutory authorities/ undertakers

Clauses

110	Work by Local Authority

- None

120	Work by statutory undertakers

- None

A54
Provisional work/ items

Clauses

See Section 3/7 Provisional Sums

A55
Dayworks

Clauses

See Section 5 – Dayworks & Overheads

A56
Advance procurement

Clauses

Not Used