## Cover Sheet
Schedule of Works for Replacement External Lighting to The Adult Care Day Centre, 38 Oxford Street Wellingborough NN8 4JG
North Northants Count Counc Robinson Way, Telford Way Industrial Estate, Kettering, Northants NN16 8PP Tel: 0300126 3000 ¦ DD: 01536 534463

## SoW
Schedule of Work Patch repairing cycle path H&S Nearest Postcode NN8 2HZ
Item | Description | Unit | Quant | Rate | £ / p
1 | General Items
1.1 | The path is a current health and safety issue that needs attention, the path will need to be patched repaired. Marked and numbered sections 1-23 Install safety barriers and signs. Saw cut existing surface back to good tarmac. Excavate and dispose of existing surface. Weed kill area of excavation. Install a tack coat emulsion and cold joint to sides. Areas Total of 794.88 sq metres. Provide and lay 20mm base course macadam. Provide and lay 6mm wearing course macadam. Total costing for the patch repairs numbered 1-23 refer to document description of works for sizes Set up compound and welfare facility for security of plant ( out of hours ), material storage area and welfare for staff. Install safety barriers and signs. Saw cut existing surface back to good tarmac. Excavate and dispose of existing surface. Weed kill area of excavation. Install a tack coat emulsion and cold joint to sides. Areas Total of 794.88 sq metres. Provide and lay 20mm base course macadam. Provide and lay 6mm wearing course macadam.
1.2 | This schedule of works is to be read in conjunction with the Pre Construction Information (PCI) included within the tender documentation .
1.4 | The [Principal] Contractor MUST submit a programme of works as part of their tender, the level of detail to be commensurate with the complexity and duration of the works.
1.5 | The work items detailed in the Tender Documents are not to be taken as a complete list of the works to be carried out. The [Principal] Contractor will be deemed to have included in their submission for all other items of work, either actual or implied, in the Contract Preliminariesand Schedule of Works.
1.6 | The location of the compound is to be formally agreed, however, an indicative location may be shown and/or described within the RFQ / ITT that the contractor must use for pricing purposes.
1.7 | This Schedule of Work is provided as an excel document and your costs must be inserted in the cash column for each work item. An electronic copy of this schedule MUST be returned with your submission. All items must be priced separately and NOT grouped. Where an item is not priced it is deemed to be included elsewhere in the Tender or to have no financial significance. Failure to conform to this instruction may invalidate your submission and lead to exclusion from the competition.
Total of Page Carried Forward To Collection £ |  |  |  |  | 0
1.8 | The [Principal] Contractor must visit site and survey the relevant area/building to establish exact sizes and measurements for the repair as specified and in accordance with the specification.
1.9 | This Schedule of Work will be used as a basis for assessing and/or preparing valuations. | Item
1.1 | Skips must be covered and lockable. | Item
Plant and Equipment
1.11 | Allow for all plant necessary to deliver the works. | Item
1.12 | Allow for all equipment necessary to deliver the works. | Item
1.13 | Allow to undertake a detailed photographic record and schedule of condition of all areas affected by the work including the access areas to the site / proposed compound areas and all working areas and provide this to the Client prior to commencing works on site and as necessary as works progress through each area of works. | Item
1.14 | The [Principal] Contractor is to maintain the condition of the existing access areas for the duration of the contract and allow for any necessary repairs to re-instate any damage caused ensuring the access surface / substrate is left in a similar or better condition than existing. The [Principal] Contractor is to confirm with Tender return any concerns raised regarding this item. | Item
Total of Page Carried Forward To Collection £
Statutory Appointments / Requirements
1.15 | Irrespective as to whether the works are notifiable under the (Construction Design and Management) Regulations 2015, the appointed [Principal] Contractor will be required to undertake the works in a safe manner and will implement the works in the spirit of the Regulations. The Contractor will fulfil the role of [Principal] Contractor and will be required to provide the following for the CA to review and approve: • Construction Phase Plan inclusive of all Method Statements and Risk Assessments for the works • Compile the Operation and Maintenance / Health & Safety File (OMHS) ongoing for submission to the Client at completion. | Item
1.16 | NOTE: Until the OMHS has been submitted, reviewed and amended as necessary by the [Principal] Contractor, then the project will not be deemed to be complete. The Client reserves the right to withhold 5% of monies owed until completion has been acheieved.
1.17 | A full copy of the Construction Phase Plan should be forwarded to the [Principal] Designer prior to commencement of the works. A full copy of these documents should be included in the on-site Health and Safety file, with periodic review, during the Construction Phase. Work must not commence on site the Construction Phase Plan has been approved by the [Principal] Designer. | Item
1.18 | At least one week prior to handover, provide 2 full sets of the Operation & Maintenance / Health & Safety File (OMHS) as per Appendix 1 in the Pre-Construction Information. This document will be reviewed by the [Principal] Designer, and subject to amendment as necessary by the [Principal] Contractor. | Item
Site Access and Restrictions
1.19 | Access to the pathway is on charles street NN8 2HZ. Refer to the PCI for further information on the site constraints and hazards.. | Item
1.2 | Set up compound and welfare facility for security of plant ( out of hours ), material storage area and welfare for staff. | Item
Total of Page Carried Forward To Collection £
3 | Provisional / Prime Cost / Contingency Sums
3.1 | Allow for a Contingency Sum of £1500.00 (One Thousand Five Hundred Pounds ). This amount will be deducted if not required and agreed with the CA. | Item
Total of Page Carried Forward To Collection £
Collection Page
1 | From page 1
2 | From page 2
3 | From page 3
4 | From page 4
Total of Collection Page Carried Forward to Summary page £
Summary Page
From Preliminaries (Pages 1-22)
From Collection Page (Pages 1 -5)
The Contractor is to include here for any items not specifically covered /mentioned in this schedule but that the Contractor deems necessary for proper and thorough execution of the work :
List Items:
1
2
3
4
Total of Summary Page Carried to Form of Tender £