| Invitation to Tender Gig Boat Exhibit Hanging |  |  |
| --- | --- | --- |
| Project: | Cultural Centre and Museum, St Mary’s, IoS |  |
| Date of issue: | 25th November 2025 |  |
| Revision: | 0 |  |
| Purpose of Issue: | Comment |  |

# Description of the works

This package of works comprises the hanging of the historic Gig, “The Klondike”, into the completed café extension to the new Cultural Centre and Museum (CCaM), St Mary’s, Isles of Scilly, including:

- The supply and fix of all fixings back to the structure, brackets, suspension wires, struts, strapping and rods.

- Supply of all lifting tackle, lifting appliances and temporary works

- Rigging the Klondike including erection of mast and sails

- Lifting the Klondike into it’s permanent position at first floor floor level. “Fine tuning” to equalize the “trim” of the gig, and position the gig centrally within the void left in the first floor floor area

The gig has not been weighed; our best guess as to the mass of the gig is circa 300kg. However, as this has not been accurately weighed, we would ask you to assume a mass of 500kg for the purposes of sizing lifting equipment.

This package excludes:

- Design of the permanent works (which is by Fenton Holloway)

- Moving the Klondike from its current location to the cafe

- Moving the Klondike into the building to rest on the ground below its final intended position (which will be undertaken by the IoS Fire Service, on behalf of the client)

The Klondike is a historic artefact, so should be handled accordingly

# List of documents

### FH Drawings Contractor Works: fixings, bracketry, slings, cradle, rods, etc.

### Surveys

Klondike Survey dated 14.3.25

### Other drawings- surrounding works and architectural intent

### Contractor-suggested design amendments

Should the contractor wish to make any amendments to the existing design, e.g., amending the under-gig rods’ design to allow for the works to be undertaken in a single visit, this should be stated in their return.

# Overall project description CCaM

The overall CCaM project comprises the refurbishment and extension of the existing Town Hall to create an Art Gallery, performance space and café area.

The Klondike will form the central exhibit of the new café area.

# Attendances/responsibilities schedule

| Item | Contractor | Client-CIoS | Notes |
| --- | --- | --- | --- |
| Design of all permanent works: fixings, bracketry, slings, cradle, rods, etc. |  |  |  |
| Supply and fix of all permanent works- fixings, bracketry, slings, cradle etc. |  |  |  |
| Movement of the historic boat into the café area |  |  |  |
| Site Inductions & Health/Safety Briefings |  |  |  |
| Provision of Risk Assessments and Method Statement RAMS |  |  |  |
| Vetting/commenting on RAMS |  |  |  |
| Explanation of RAMS to workforce |  |  |  |
| Safe Access to site Areas |  |  |  |
| Mobile Elevating Works Platform |  |  | The client will make their AWP-30S AC MEWP available (see data sheet attached in this cell). Should fixed scaffolding be required, tendering contractors to detail in their tender return. |
| Driver for any MEWP used on site, including the client-provided MEWP |  |  | Only personnel with a recognised, valid and in-date IPAF (or similar approved) training certificate will be permitted to use powered access. |
| Space for storage |  |  | The client will make a small external area available for storage. The contractor should allow for any lockable tool boxes/stores required. |
| Power Supply transformers- temporary power 110v on site |  |  | 240v power will be available in the building; the contractor should provide step down transformers if required |
| Safety lighting |  |  |  |
| Task Lighting and all power leads etc. |  |  |  |
| Welfare Facilities during main contract construction period |  |  | The completed museum WCs will be made available to the contractor |
| Waste disposal |  |  |  |
| All lifting, hoisting etc. |  |  |  |
| Provision of accommodation for workforce or visitors |  |  | Contractor to confirm their requirements in their tender return |
| Transport of plant and materials to Penzance Docks |  |  |  |
| Shipping of plant and materials to St Mary's |  |  | Provisional sum at this stage for discussion |
| Transport of plant and materials from St Mary's docks to site |  |  | Provisional sum at this stage for discussion |
| Movement of all plant and materials around site |  |  |  |
| Spreading any point loads from lifting equipment |  |  | Provisional sum at this stage: After appointment, the contractor should provide a proposed lifting plan, which will be checked by the Structural Engineer to ensure this does not overload the floor in the position of the underfloor service duct. Some matting/bridging may be required. |

# Programme

Programme is to be confirmed, but we envisage these works being undertaken following completion of the building works, circa October 2026.

We would ask tendering contractors to advise on overall fixing duration.

# Test lift

Should the contractor wish to undertake a test lift of the gig in its current storage site, they should allow for this in their price; the client will make this available to the contractor.