C.20733

West Yorkshire Fire & Rescue Service

Bradford Fire Station

V1

PRELIMINARIES NEC3 ECSC

Tender

18-03-2025

Contents

A10 Project particulars	1

A11 Tender and contract documents	3

A12 The site/ existing buildings	4

A13 Description of the work	6

A20 NEC3 engineering and construction short contract	7

A30 Tendering/ subletting/ supply	11

A31 Provision, content and use of documents	14

A32 Management of the works	19

A33 Quality standards/ control	22

A34 Security/ safety/ protection	28

A35 Specific limitations on method/ sequence/ timing	34

A36 Facilities/ temporary work/ services	35

A37 Operation/ maintenance of the finished works	37

A40 Contractor's general cost items: management and staff	39

A41 Contractor's general cost items: site accommodation	40

A42 Contractor's general cost items: services and facilities	41

A43 Contractor's general cost items: mechanical plant	42

A44 Contractor's general cost items: temporary works	43

A50 Work/ products by/ on behalf of the employer	44

A53 Work by statutory authorities/ undertakers	45

A10
Project particulars

Clauses

110 	The Project

- Name: Bradford Fire Station Shower & Dormitory Refurbishment

- Nature: Refurbishment works including renewal of washroom and sanitary facilities across each floor (GF-2F) and alterations to existing dormitories to form new individual rest rooms.

- Location: Bradford Fire Station, 540 Leeds Road, Bradford BD3 9SB

- Timescale for construction work: 16 Weeks

120 	Employer (client)

- Name: West Yorkshire Fire & Rescue Service

- Address: Oakroyd Hall, Birkenshaw, BD11 2DY

- Contact: Josef Turner

- Telephone: 07760 992135

- Email: Josef.Turner@westyorksfire.gov.uk

130 	Principal contractor (CDM)

- Name: TBC

- Address: TBC

- Contact: TBC

- Telephone: TBC

- Email: TBC

150 	Principal designer

- Name: West Yorkshire Fire & Rescue Service

- Address: Oakroyd Hall, Birkenshaw, BD11 2DY

- Contact: Josef Turner

- Telephone: 07760 992135

- Email: Josef.Turner@westyorksfire.gov.uk

200 	Mechanical & Electrical Design Consultants

- Name: Robert Whetham Associates

- Address: Castle Hill House, 31 Mill Brow, Chadderton, Oldham, Greater Manchester OL1 2RT

- Contact: Robert Whetham

- Telephone: 0161 624 5544

- Email: rob@robertwhetham.co.uk

201 	Structural Design Consultants

- Name: JNP Group

- Address: Woodvale House, Woodvale Road, Brighouse, HD6 4AB

- Contact: Ksenija Bicko

- Telephone: 01484 400691

- Email: Ksenija.Bicko@jnpgroup.co.uk

Ω End of Section

A11
Tender and contract documents

Clauses

110 	Tender documents

- The tender documents are

  - The Specification comprising Schedules of Work, Preliminaries and Reference Specification.

  - The following drawings:

- ……….

120 	Contract drawings

- The contract drawings: The same as the tender drawings.

160 	Pre-construction information

- Format: The pre-construction information is described in these Preliminaries in section A34. It refers to information given elsewhere in the Preliminaries, specification, drawings and associated documents.

Ω End of Section

A12
The site/ existing buildings

Clauses

110 	The site

- Description: The site is a wholetime fire station situated close to the centre of Bradford city, near several shops and residential streets. The station is accessed directly off Leeds Road with a rear gated car park (including a LGF undercroft with additional staff parking) accessed off of Maud Street.

120 	Existing buildings on/ adjacent to the site

- Description: There are several commercial shops and other residential properties in close proximity to the station which accounts for the areas high traffic. The roads behind the station on approach to the rear car park predominantly serve industrial and commercial buildings but are less trafficked than the main road.

140 	Existing utilities and services

- Drawings: (Information shown is indicative only): The existing services and utilities are indicated on the Robert Whetham Associates Tender Drawings.

- Other information: None

180 	Health and safety file

- Availability for inspection: The health and safety file for the site/ building may be seen by appointment during normal office hours at: ……….

- Other documents:

- Arrangements for inspection: Josef Turner, WYFRS

200 	Access to the site

- Description: Access to the rear car park of the site is off Maud Street which can be accessed via Mulgrave Street off Leeds Road.

- Limitations: The access road is shared with a number of other industrial/commercial properties. The entrance to the rear car park is blocked via a physical barrier and PAC access controls.

- Access for inspections: Provide access at reasonable times for both on-site and off-site work.

210 	Parking

- Restrictions on parking of the Contractor’s and employees' vehicles: There is a car park to the rear of the station but contractor allocated parking spaces will be limited to cater to crew member parking and for placing welfare facilities and to not obstruct the ingress/egress of appliances.

220 	Use of the site

- General: Do not use the site for any purpose other than carrying out the Works.

- Limitations: The Contractor must liaise with the Project Manager and/or Watch Commander daily to keep them informed of what activities are to take place to ensure the works do not affect the daily running of the fire station.

230 	Surrounding land/ building uses

- General: Adjacent or nearby uses or activities are as follows:

  - There is a main road (A647) immediately outside the station..

  - There are various commercial, industrial and residential properties in the surrounding area.

240 	Health and safety hazards

- General: The nature and condition of the site/ building cannot be fully and certainly ascertained before it is opened up. However, the following hazards are or may be present:

  - Refer to Pre-construction Information document contained within the tender documents.

- Information: The accuracy and sufficiency of this information is not guaranteed. Ascertain if any additional information is required to ensure the safety of all persons and the works.

- Site staff: Draw to the attention of all personnel working on the site the nature of any possible contamination and the need to take appropriate precautionary measures.

250 	Site visit

- Assessment: Ascertain the nature of the site, access thereto and all local conditions and restrictions likely to affect the execution of the Works.

- Arrangements for visit: Josef Turner, WYFRS

Ω End of Section

A13
Description of the work

Clauses

110 	Preparatory work by others

- Details: None

- Timescale: N/A

120 	The works

- Description: The works to Bradford Fire Station comprise the refurbishment of existing WC areas (GF-2F) to provide new unisex shower room units, specifically on the GF for operational staff to use when returning from an incident, facilitated by the formation of a new structural opening between the appliance bay and new shower/WC facilities.1F dormitory layouts will be altered via the removal and subsequent erection of internal partition walls to provide 12No. individual rest rooms. 1F/2F shower and WC facilities will be refreshed and made unisex. Renewal of small power, lighting, ventilation, turnout provisions and heating.

130 	Work by others concurrent with the Contract

- Description: None

140 	Completion work by others

- Description:

- None

Ω End of Section

A20
NEC3 engineering and construction short contract

Clauses

NEC3 engineering and construction short contract

- The conditions of contract: The core clauses, conditions and secondary options indicated, for the NEC3 Engineering and Construction Short Contract (April 2013).

- Housing Grants Construction and Regeneration Act 1996, as amended by the Local Democracy, Economic Development and Construction Act 2009: applies

- Requirement: Allow for the obligations, liabilities and services described.

Contract data

The Employer

- See clause A10/120.

The Works

- The Works: Summarised in clause A13/120 and defined in the description, drawings and specifications..

The Site

- The site: Described in clause A12/110 and detailed in Site Information.

Starting date

- The starting date is: TBC

Completion date

- The completion date is: 20 Weeks from the commencement date.

Period for reply

- The period for reply is: 4 Weeks

Defects date

- The defects date is: 52 weeks after completion.

Defects correction period

- The defects correction period is: 4 Weeks

Delay damages

- The delay damages are: 50.00 per day.

Assessment day

- The assessment day is the: 1st (or closest working calendar day after) of each month.

Retention

- The retention is: 5%.

Adjudicator

- The Adjudicator is

  - Name: To be nominated by the Royal Institute of Chartered Surveyors

  - Address: TBD

  - Tel: TBD

  - E mail: TBD

Interest on late payment

- The interest on late payment is 0.5% per complete week of delay.

Limitation of liability

- The Contractor is not liable to the Employer for loss of or damage to the Employer’s property in excess of: £10,000,000.00 for any one event.

Insurance

- The Employer provides this insurance

  - The employer will retain responsibility for insuring Bradford Fire Station.

Insurance cover

- The minimum amount of cover for the third insurance stated in the Insurance Table is: £10,000,000.00

- The minimum amount of cover for the fourth insurance stated in the Insurance Table is: £10,000,000.00

Adjudicator nominating body

- The body is: The Royal Institute of Chartered Surveyors

Tribunal

- The tribunal is: Arbitration

Arbitration

- If the tribunal is arbitration, the arbitration procedure is: Construction Industry Model Arbitration Rules (CIMAR)

Additional conditions

- Contractor’s design: Undertake and accept full responsibility for the design of the following parts of the works: None.

  - Design liability: Warrant that the parts of the works are designed with reasonable skill and care of an appropriate professional designer competent to take on this type of work.

  - Drawings and supporting documentation: Submit with tender.

- Additional conditions are: None

Client

- The Client: The Employer defined in clause A10/120.

Price list

Price list

- Pricing the Works: By Schedules of Work.

- Basis for valuation of variations: Prices within the Schedules of Work.

Works information

1 - Description of the works

- The Works comprise: See clause A13/120.

- Contractor designed work

  - Employer’s requirements: Head restraint design for 1F blockwork walls as recommended by Structural Engineer.

  - Contractor’s proposals: TO BE COMPLETED BY CONTRACTOR

2 - Drawings

- Drawings applicable to this contract

  - Listed in clause A11/110.

  - ……….

3 - Specifications

- The specification documents

  - Schedules of Work and reference documents including Preliminaries.

  - Pre-construction information: See clause A11/160.

  - ……….

4 - Constraints on how the Contractor provides the Works

- Construction hazards: As clause A34/120.

- Material hazard: As clause A34/130.

- Choice of subcontractor for specific categories of work: None

- Considerate Constructors Scheme: As clause A32/115.

- Occupier's rules and regulations: As clause A34/190.

- Other constraints: None

5 - Requirements for the programme

- Programme

  - Submission: As clause A32/210.

  - Updating: As clause A32/250.

6 - Services and other things provided by the Employer

- Employer to provide

  - Services Electricity supply - see clause A36/420, Water - see clause A36/430, Permanent heating system - see clause A36/520.

  - Facilities None.

  - Plant, materials and equipment None.

- Date to be supplied: Commencement Date

- Retain the following for use by the Employer

  - Description: N/A

  - Storage: N/A

Site information

Site information

- Information: Listed in section A12 of the Preliminaries.

- Publicly available information:

- Other:

Ω End of Section

A30
Tendering/ subletting/ supply

Main contract tendering

110 	Scope

- General: These conditions are supplementary to those stated in the Invitation to Tender and on the form of tender.

145 	Tendering procedure

- General: In accordance with NBS Guide to Tendering for Construction Projects.

- Errors: Alternative 2 is to apply.

160 	Exclusions

- Inability to tender: Immediately inform if any parts of the work as defined in the tender documents cannot be tendered.

- Relevant parts of the work: Define those parts, stating reasons for the inability to tender.

170 	Acceptance of tender

- Acceptance: No guarantee is offered that any tender will be recommended for acceptance or be accepted, or that reasons for non acceptance will be given.

- Costs: No liability is accepted for any cost incurred in the preparation of any tender.

190 	Period of validity

- Period: After submission or lodgement, keep tender open for consideration (unless previously withdrawn) for not less than 2 Months.

- Date for possession/ commencement: See section A20.

Pricing/ submission of documents

210 	Preliminaries in the specification

- The Preliminaries/ General conditions sections (A10-A56 inclusive) must not be relied on as complying with SMM7/ NRM2.

220 	Pricing of preliminaries

- Charges: When pricing Preliminaries, identify separately for each item where, for the purpose of valuing the work, the charge for that item is considered to be:

  - Fixed: (i.e. where the charge for the item does not depend on duration).

  - Time related: (i.e. where the charge for the item is dependent on duration).

250 	Priced documents

- Alterations: Do not alter or qualify the priced documents without written consent. Tenders containing unauthorised alterations or qualifications may be rejected.

- Measurements: Where not stated, ascertain from the drawings.

- Deemed included: Costs relating to items, which are not priced, will be deemed to have been included elsewhere in the tender.

- Submit: With tender

310 	Tender

- General: Tenders must include for all work shown or described in the tender documents as a whole or clearly apparent as being necessary for the complete and proper execution of the Works.

440 	Schedule of rates

- Schedule of rates (unpriced): Included with the tender documents. The contractor may insert additional items. All items must be fully priced.

- Fully priced copy

  - Submittal date: with the tender

480 	Programme

- Programme of work: Prepare a summary showing the sequence and timing of the principal parts of the Works and periods for planning and design. Itemize any work which is excluded.

- Submit: With tender

500 	Tender stage method statements

- Method statements: Prepare, describing how and when the following is to be carried out:

  - Formation of structural opening to partition wall between G.03 and G.04.

- Statements: Submit with the tender.

510 	Alternative method tenders

- General: In addition to and at the same time as tendering for the Works as defined in the tender documents, alternative methods of construction/ installation may be submitted for consideration. Alternatives, which would involve significant changes to other work, may not be considered.

- Alternative tenders: Such alternatives will be deemed to be alternative tenders and each must include a complete and precise statement of the effects on cost and programme.

- Safety method statement: Carry out a health and safety risk assessment for each alternative and where appropriate provide a safety method statement suitable for incorporation in the Health and Safety Plan.

- Full technical data: Submit for each alternative together with details of any consequential amendments to the design and/ or construction of other parts of the Works.

- Submit: With tender

530 	Substitute products

- Details: If products of different manufacture to those specified are proposed, submit details with the tender giving reasons for each proposed substitution. Substitutions, which have not been notified at tender stage, may not be considered.

- Compliance: Substitutions accepted will be subject to the verification requirements of clause A31/200.

550 	Health and safety information

- Content: Describe the organization and resources to safeguard the health and safety of operatives, including those of subcontractors, and of any person whom the Works may affect.

- Include

  - A copy of the health and safety policy document, including risk assessment procedures.

  - Accident and sickness records for the past five years.

  - Records of previous Health and Safety Executive enforcement action.

  - Records of training and training policy.

  - The number and type of staff responsible for health and safety on this project with details of their qualifications and duties.

- Submit: With the Tender

570 	Outline construction phase health and safety plan

- Content: Submit the following information within one week of request:

  - Method statements on how risks from hazards identified in the pre-construction information and other hazards identified by the contractor will be addressed.

  - Details of the management structure and responsibilities.

  - Arrangements for issuing health and safety directions.

  - Procedures for informing other contractors and employees of health and safety hazards.

  - Selection procedures for ensuring competency of other contractors, the self-employed and designers.

  - Procedures for communications between the project team, other contractors and site operatives.

  - Arrangements for cooperation and coordination between contractors.

  - Procedures for carrying out risk assessment and for managing and controlling the risk.

  - Emergency procedures including those for fire prevention and escape.

  - Arrangements for ensuring that all accidents, illness and dangerous occurrences are recorded.

  - Arrangements for welfare facilities.

  - Procedures for ensuring that all persons on site have received relevant health and safety information and training.

  - Arrangements for consulting with and taking the views of people on site.

  - Arrangements for preparing site rules and drawing them to the attention of those affected and ensuring their compliance.

  - Monitoring procedures to ensure compliance with site rules, selection and management procedures, health and safety standards and statutory requirements.

  - Review procedures to obtain feedback.

599 	Freedom of Information Act

- Records: Retain, make available for inspection and supply on request information reasonably required to allow response to requests made under the provisions of the Freedom of Information Act.

- Determination: Submit requests received. Do not supply information to anyone other than the project participants without express written permission.

- Confidentiality: Maintain at all times.

Subletting/ supply - No Amendments

Ω End of Section

A31
Provision, content and use of documents

Definitions and interpretations

110 	Definitions

- Meaning: Terms, derived terms and synonyms used in the preliminaries/ general conditions and specification are as stated here or in the appropriate referenced document.

120 	Communication

- Definition: Includes advise, inform, submit, give notice, instruct, agree, confirm, seek, provide or obtain information, consent or instructions, or make arrangements.

- Format: In writing to the person named in clause A10/140 unless specified otherwise.

- Response: Do not proceed until response has been received.

130 	Products

- Definition: Materials, both manufactured and naturally occurring, and goods, including components, equipment and accessories, intended for the permanent incorporation in the Works.

- Includes: Goods, plant, materials, site materials and things for incorporation into the Works.

135 	Site equipment

- Definition: Apparatus, appliances, machinery, vehicles or things of whatsoever nature required in or about the construction for the execution and completion of the Works but not materials or other things intended to form or forming part of the Permanent Works.

- Includes: Construction appliances, vehicles, consumables, tools, temporary works, scaffolding, cabins and other site facilities.

- Excludes: Products and equipment or anything intended to form or forming part of the permanent works.

140 	Drawings

- Definitions: To BSRIA BG 6, 'A design framework for building services: Design activities and drawing definitions'.

- CAD data: In accordance with ISO 19650.

145 	Contractor's choice

- Meaning: Selection delegated to the Contractor, but liability to remain with the specifier.

150 	Contractor's Design

- Meaning: Design to be carried out or completed by the Contractor and supported by appropriate contractual arrangements, to correspond with specified requirements.

155 	Submit proposals

- Meaning: Submit information in response to specified requirements.

160 	Terms used in specification

- Remove: Disconnect, dismantle as necessary and take out the designated products or work and associated accessories, fixings, supports, linings and bedding materials. Dispose of unwanted materials. Excludes removal and disposal of associated pipework, wiring, ductwork or other services.

- Remediate: Action or measures taken to lessen, clean up, remove or mitigate the existence of hazardous materials; in accordance with standards, or requirements as may be set out by statutes, rules, regulations or specification.

- Fix: Receive, unload, handle, store, protect, place and fasten in position; dispose of waste and surplus packaging. To include all labour, materials and site equipment for that purpose.

- Supply and fix: As above, but including supply of products, components or systems to be fixed, together with everything necessary for their fixing. All products, components or systems are to be supplied and fixed unless stated otherwise.

- Keep for reuse: Do not damage designated products or work. Clean off bedding and jointing materials. Stack neatly, protect adequately and store until required by the employer/ purchaser, or until required for use in the works as instructed.

- Keep for recycling: As 'keep for reuse', but relates to a naturally occurring material rather than a manufactured product.

- Make good: Execute local remedial work to designated work. Make secure, sound and neat. Excludes redecoration and/ or replacement.

- Replace: Supply and fix new products matching those removed. Execute work to match original new state of that removed.

- Repair: Execute remedial work to restore something to its original working state. Make secure, sound and neat. Excludes redecoration and/ or replacement.

- Refix: Fix removed products.

- Ease: Adjust moving parts of designated products, or work to achieve free movement and good fit in open and closed positions.

- Match existing: Provide products and work of the same appearance and features as the original, excluding ageing and weathering. Make joints between existing and new work as inconspicuous as possible.

- System: Equipment, accessories, controls, supports and ancillary items (including installation) necessary for that section of the work to function.

170 	Manufacturer and product reference

- Definition: When used in this combination:

  - Manufacturer: the person or legal entity under whose name or trademark the particular product, component or system is marketed

  - Product reference: the proprietary brand name and/ or identifier by which the particular product, component or system is described.

- Currency: References are to the particular product as specified in the manufacturer’s technical literature current on the date of the invitation to tender.

200 	Substitution of products

- Products: If an alternative product to that specified is proposed, obtain approval before ordering the product.

- Reasons: Submit reasons for the proposed substitution.

- Documentation: Submit relevant information, including:

  - manufacturer and product reference;

  - cost;

  - availability;

  - relevant standards;

  - performance;

  - function;

  - compatibility of accessories;

  - proposed revisions to drawings and specification;

  - compatibility with adjacent work;

  - appearance;

  - copy of warranty/ guarantee.

- Alterations to adjacent work: If needed, advise scope, nature and cost.

- Manufacturers’ guarantees: If substitution is accepted, submit before ordering products.

210 	Cross references

- Accuracy: Check remainder of the annotation or item description against the terminology used in the section or clause referred to.

- Related terminology: Where a numerical cross reference is not given, the relevant sections and clauses of the specification will apply.

- Relevant clauses: Clauses in the referred to specification section dealing with general matters, ancillary products and execution also apply.

- Discrepancy or ambiguity: Before proceeding, obtain clarification or instructions.

220 	Referenced documents

- Conflicts: Specification prevails over referenced documents.

230 	Equivalent products

- Inadvertent omission: Wherever products are specified by proprietary name the phrase 'or equivalent' is to be deemed included.

240 	Substitution of standards

- Specification to British Standard or European Standard: Substitution may be proposed complying with a grade or category within a national standard of another Member State of the European Community or an international standard recognised in the UK.

- Before ordering: Submit notification of all such substitutions.

- Documentary evidence: Submit for verification when requested as detailed in clause A31/200. Any submitted foreign language documents must be accompanied by certified translations into English.

250 	Currency of documents and information

- Currency: References to published documents are to the editions, including amendments and revisions, current on the date of the Invitation to Tender.

260 	Sizes

- General dimensions: Products are specified by their co-ordinating sizes.

- Timber: Cross section dimensions shown on drawings are:

  - Target sizes as defined in BS EN 336 for structural softwood and hardwood sections.

  - Finished sizes for non-structural softwood or hardwood sawn and further processed sections.

Documents provided on behalf of employer

410 	Additional copies of drawings/ documents

- Copies: Two of each contract drawing and contract document will be issued free of charge (not counting any certified copies).

- Additional copies: Issued on request and charged to the Contractor.

440 	Dimensions

- Scaled dimensions: Do not rely on.

460 	The specification

- Coordination: All sections must be read in conjunction with Main Contract Preliminaries/ General conditions.

Documents provided by contractor/ subcontractors/ suppliers

510 	Design and production information

- General: Complete the design and detailing of parts of the Works as specified.

- Provide

  - Production information based on the drawings, specification and other information.

  - Liaison to ensure coordination of the work with related building elements and services.

- Master programme: Make reasonable allowance for completing design/ production information, submission (including information relevant to the CDM Regulations), comment, inspection, amendment, resubmission and reinspection.

- Design/ production information: Submit two copies, one can be returned with comments. Ensure that any necessary amendments are made without delay.

- Contractor’s changes to Employer's Requirements: Support request for substitution or change with all relevant information.

- Employer’s amendments to Employer’s Requirements: If considered to involve a change, which has not already been acknowledged as a change, notify without delay (maximum period 7 days), and do not proceed until instructed. Claims for extra cost, if made after it has been carried out, may not be allowed.

- Final version of design/ production information: Submit one copy.

600 	Contractor's Design information

- General: Complete the design and detailing of parts of the Works as specified.

- Provide

  - Production information based on the drawings, specification and other information.

  - Liaison to ensure coordination of the work with related building elements and services.

- Master programme: Make reasonable allowance for completing design/ production information, submission (including information relevant to the CDM Regulations), comment, inspection, amendment, resubmission and reinspection.

- Information required: Head restraints for 1F blockwork wall (see Structural Engineers specification).

  - Format: Provide scale proposed drawing or typical installation detail.

  - Number of copies: 1

- Submit: Within one week of request.

620 	As-built drawings and information

- Contractor designed work: Provide drawings/ information:

  - Head restraints for 1F blockwork wall.

- Submit: At least two weeks before date for completion.

630 	Technical literature

- Information: Keep on site for reference by all supervisory personnel:

  - Manufacturers' current literature relating to all products to be used in the Works.

  - Relevant British, EN or ISO Standards.

Document/ data interchange - No Amendments

Ω End of Section

A32
Management of the works

Generally

110 	Supervision

- General: Accept responsibility for coordination, supervision and administration of the Works, including subcontracts.

- Coordination: Arrange and monitor a programme with each subcontractor, supplier, local authority and statutory undertaker, and obtain and supply information as necessary for coordination of the work.

118 	Vehicle safety requirements

- Vehicle equipment: Ensure that all vehicles have the following:

  - Audible alert to other road users to the planned movement of the vehicle when the vehicle’s indicators are in operation.

  - Prominent signage at the rear of the vehicle to warn cyclists of the dangers of passing the vehicle on the inside.

  - Properly adjusted class VI mirror/s or Fresnel lens to eliminate the near side blind spot.

  - Side under run guards.

- Driver training

  - Drivers must be trained on vulnerable road user safety through an approved course and hold a current valid Certificate of Competence.

  - Drivers must have a valid driving licence and be legally able to drive the vehicle.

- Scheme membership: Submit evidence of registration with and accreditation to the Fleet Operator Recognition Scheme (FORS)

- Level of accreditation: Bronze

- Submittal date: Before commencement of operations on site

120 	Insurance

- Documentary evidence: Before starting work on site submit details, and/ or policies and receipts for the insurances required by the Conditions of Contract.

130 	Insurance claims

- Notice: If any event occurs which may give rise to any claim or proceeding in respect of loss or damage to the Works or injury or damage to persons or property arising out of the Works, immediately give notice to the employer/ client, the person administering the Contract on their behalf and the Insurers.

- Failure to notify: Indemnify the employer/ client against any loss, which may be caused by failure to give such notice.

140 	Climatic conditions

- Information: Record accurately and retain:

  - Daily maximum and minimum air temperatures (including overnight).

  - Delays due to adverse weather, including description of the weather, types of work affected and number of hours lost.

Programme/ progress

210 	Programme

- Master programme: Immediately when requested and before starting work on site, submit in an approved form a master programme for the works, which must include details of:

  - Work stages or elements of the construction as appropriate for the works.

  - Design and production information provided by the contractor/ subcontractors/ suppliers, including inspection and checking (see sectionA31).

  - Planning and mobilization by the contractor.

  - Earliest and latest start and finish dates for each activity and identify all critical activities.

  - Running in, adjustment, commissioning and testing of all engineering services and installations.

  - Work by or on behalf of the employer (see section A50) the nature and scope of which, the relationship with preceding and following work and any relevant limitations, are suitably defined in the contract documents.

- Exclusions: Where and to the extent that the programme implications for work which is not so defined are impossible to assess, exclude it and confirm this when submitting the programme.

- Submit: one copy (Electronic)

250 	Monitoring

- Progress: Record on a copy of the programme kept on site.

- Avoiding delays: If any circumstances arise which may affect the progress of the Works submit proposals or take other action as appropriate to minimize any delay and to recover any lost time.

- Weekly completion forecast: Submit on the last working day.

- Key Performance Indicators

  - Record progress against each of the KPIs. If performance against KPI falls short of target, submit proposals for remediation.

255 	Notification of compensation event

- Content: Notwithstanding the Contractor's obligations under the Contract written notice must also be given of all other causes which apply concurrently.

260 	Site meetings

- General: Site meetings will be held to review progress and other matters arising from administration of the Contract (progress visits to be made weekly).

- Frequency: Every month

- Location: Bradford Fire Station

- Accommodation: Ensure availability at the time of such meetings.

- Attendees: Attend meetings and inform subcontractors and suppliers when their presence is required.

- Chairperson (who will also take and distribute minutes): Contract Administrator (Josef Turner, WYFRS)

Control of cost

420 	Removal/ replacement of existing work

- Extent and location: Agree before commencement.

- Execution: Carry out in ways that minimize the extent of work.

430 	Quotations for proposed instructions or compensation events

- Include

  - A detailed breakdown of the cost including any allowance for direct loss and expense.

  - Details of any additional resources required.

  - Details of any adjustments to be made to the programme for the Works.

  - Any other information as is reasonably necessary to fully assess the implications of issuing such an instruction.

- Inability to comply: Inform immediately if it is not possible to comply with any of the above requirements.

440 	Measurement

- Covered work: Give notice before covering work required to be measured.

Ω End of Section

A33
Quality standards/ control

Standards of products and executions

110 	Incomplete documentation

- General: Where and to the extent that products or work are not fully documented, they are to be:

  - Of a kind and standard appropriate to the nature and character of that part of the Works where they will be used.

  - Suitable for the purposes stated or reasonably to be inferred from the project documents.

- Contract documents: Omissions or errors in description and/ or quantity shall not vitiate the Contract nor release the Contractor from any obligations or liabilities under the Contract.

120 	Workmanship skills

- Operatives: Appropriately skilled and experienced for the type and quality of work.

- Registration: With Construction Skills Certification Scheme.

- Verification: When requested, operatives must produce evidence of skills/ qualifications.

130 	Quality of products

- Generally: New. (Proposals for recycled products may be considered).

- Supply of each product: From the same source or manufacturer.

- Whole quantity of each product required to complete the Works: Consistent kind, size, quality and overall appearance.

- Tolerances: Where critical, measure a sufficient quantity to determine compliance.

- Deterioration: Prevent. Order in suitable quantities to a programme and use in appropriate sequence.

135 	Quality of execution

- Generally: Fix, apply, install or lay products securely, accurately, plumb, neatly and in alignment.

- Colour batching: Do not use different colour batches where they can be seen together.

- Dimensions: Check on-site dimensions.

- Finished work: Not defective, e.g. not damaged, disfigured, dirty, faulty, or out of tolerance.

- Location and fixing of products: Adjust joints open to view so they are even and regular.

140 	Evidence of Compliance

- Proprietary products: Retain on site evidence that the proprietary product specified has been supplied.

- Performance specification: Submit evidence of compliance, including test reports indicating:

  - Properties tested.

  - Pass/ fail criteria.

  - Test methods and procedures.

  - Test results.

  - Identity of testing agency.

  - Test dates and times.

  - Identities of witnesses.

  - Analysis of results.

150 	Inspections

- Products and executions: Inspection or any other action must not be taken as approval unless confirmed in writing referring to:

  - Date of inspection.

  - Part of the work inspected.

  - Respects or characteristics which are approved.

  - Extent and purpose of the approval.

  - Any associated conditions.

160 	Related work

- Details: Provide all trades with necessary details of related types of work. Before starting each new type or section of work ensure previous related work is:

  - Appropriately complete.

  - In accordance with the project documents.

  - To a suitable standard.

  - In a suitable condition to receive the new work.

- Preparatory work: Ensure all necessary preparatory work has been carried out.

170 	Manufacturer’s recommendations/ instructions

- General: Comply with manufacturer's printed recommendations and instructions current on the date of the Invitation to tender.

- Exceptions: Submit details of changes to recommendations or instructions.

- Execution: Use ancillary products and accessories supplied or recommended by main product manufacturer.

- Products: Comply with limitations, recommendations and requirements of relevant valid certificates.

180 	Water for the works

- Mains supply: Clean and uncontaminated.

- Other: Do not use until:

  - Evidence of suitability is provided.

  - Tested to BS EN 1008 if instructed.

Samples/ approvals

210 	Samples

- Products or executions: Comply with all other specification requirements and in respect of the stated or implied characteristics either:

  - To an express approval.

  - To match a sample expressly approved as a standard for the purpose.

220 	Approval of products

- Submissions, samples, inspections and tests: Undertake or arrange to suit the Works programme.

- Approval: Relates to a sample of the product and not to the product as used in the Works. Do not confirm orders or use the product until approval of the sample has been obtained.

- Complying sample: Retain in good, clean condition on site. Remove when no longer required.

230 	Approval of execution

- Submissions, samples, inspections and tests: Undertake or arrange to suit the Works programme.

- Approval: Relates to the stated characteristics of the sample. (If approval of the finished work as a whole is required this is specified separately). Do not conceal, or proceed with affected work until compliance with requirements is confirmed.

- Complying sample: Retain in good, clean condition on site. Remove when no longer required.

320 	Setting out

- General: Submit details of methods and equipment to be used in setting out the Works.

- Levels and dimensions: Check and record the results on a copy of drawings. Notify discrepancies and obtain instructions before proceeding.

- Inform: When complete and before commencing construction.

330 	Appearance and fit

- Tolerances and dimensions: If likely to be critical to execution or difficult to achieve, as early as possible either:

  - Submit proposals; or

  - Arrange for inspection of appearance of relevant aspects of partially finished work.

- General tolerances (maximum): To BS 5606, tables 1 and 2.

340 	Critical dimensions

- Critical dimensions: Set out and construct the Works to ensure compliance with the tolerances stated.

- Location: Detailed on drawings ……….

360 	Record drawings

- Site setting out drawing: Record details of all grid lines, setting-out stations, benchmarks and profiles. Retain on site throughout the Contract and hand over on completion.

410 	Services regulations

- New or existing services: Comply with the Byelaws or Regulations of the relevant Statutory Authority.

420 	Water regulations/ byelaws notification

- Requirements: Notify Water Undertaker of any work carried out to (or which affects) new or existing services and submit any required plans, diagrams and details.

- Consent: Allow adequate time to receive Undertaker's consent before starting work. Inform immediately if consent is withheld or is granted subject to significant conditions.

430 	Water regulations/ byelaws contractor’s certificate

- On completion of the work: Submit (copy where also required to the Water Undertaker) a certificate including:

  - The address of the premises.

  - A brief description of the new installation and/ or work carried out to an existing installation.

  - The Contractor's name and address.

  - A statement that the installation complies with the relevant Water Regulations or Byelaws.

  - The name and signature of the individual responsible for checking compliance.

  - The date on which the installation was checked.

435 	Electrical installation certificate

- Submit: When relevant electrical work is completed.

- Original certificate: To be lodged in the Building Manual.

440 	Gas, oil and solid fuel appliance installation certificate

- Before the completion date stated in the Contract: Submit a certificate stating:

  - The address of the premises.

  - A brief description of the new installation and/ or work carried out to an existing installation.

  - Any special recommendations or instructions for the safe use and operation of appliances and flues.

  - The Contractor's name and address.

  - A statement that the installation complies with the appropriate safety, installation and use regulations.

  - The name, qualification and signature of the competent person responsible for checking compliance.

  - The date on which the installation was checked.

- Certificate location: Building Manual / Health and Safety File

445 	Service runs

- General: Provide adequate space and support for services, including unobstructed routes and fixings.

- Ducts, chases and holes: Form during construction rather than cut.

- Coordination with other works: Submit details of locations, types/ methods of fixing of services to fabric and identification of runs and fittings.

450 	Mechanical and electrical services

- Final tests and commissioning: Carry out so that services are in full working order at completion of the Works.

- Building Regulations notice: Copy to be lodged in the Building Manual.

510 	Supervision

- General: In addition to the constant management and supervision of the Works provided by the Contractor's person in charge, all significant types of work must be under the close control of competent trade supervisors to ensure maintenance of satisfactory quality and progress.

- Evidence: Submit, including details of the person proposed, their relevant skills training and knowledge; practical experience; qualifications; membership or registration with professional bodies; employment history, work related assessments and management structure.

- Submittal date: One week before start on site

- Replacement: Give maximum possible notice before changing person in charge or site agent.

525 	Access

- Extent: Provide at all reasonable times access to the Works and to other places of the Contractor or subcontractors where work is being prepared for the Contract.

- Designate: Site Manager

530 	Overtime working

- Notice: Prior to overtime being worked, submit details of times, types and locations of work to be done.

  - Minimum period of notice: One week

- Concealed work: If executed during overtime for which notice has not been given, it may be required to be opened up for inspection and reinstated at the Contractor's expense.

540 	Defects in existing work

- Undocumented defects: When discovered, immediately give notice. Do not proceed with affected related work until response has been received.

- Documented remedial work: Do not execute work which may:

  - Hinder access to defective products or work; or

  - Be rendered abortive by remedial work.

550 	Access for inspection

- Removal: Before removing scaffolding or other facilities for access, give notice of not less than one week to allow inspections by the CA/WYFRS.

560 	Tests and inspections

- Timing: Agree and record dates and times of tests and inspections to enable all affected parties to be represented.

- Confirmation: One working day prior to each such test or inspection. If sample or test is not ready, agree a new date and time.

- Records: Submit a copy of test certificates and retain copies on site.

610 	Proposals for rectification of defective products/ executions

- Proposals: Immediately any execution or product is known, or appears, to be not in accordance with the Contract, submit proposals for opening up, inspection, testing, making good, adjustment of the Contract Sum, or removal and re-execution.

- Acceptability: Such proposals may be unacceptable and contrary instructions may be issued.

710 	Work before completion

- General: Make good all damage consequent upon the Works.

- Temporary markings, coverings and protective wrappings: Remove unless otherwise instructed.

- Cleaning: Clean the Works thoroughly inside and out, including all accessible ducts and voids. Remove all splashes, deposits, efflorescence, rubbish and surplus materials.

- Cleaning materials and methods: As recommended by manufacturers of products being cleaned, and must not damage or disfigure other materials or construction.

- COSHH dated data sheets: Obtain for all materials used for cleaning and ensure they are used only as recommended by their manufacturers.

- Minor faults: Touch up in newly painted work, carefully matching colour and brushing out edges. Repaint badly marked areas back to suitable breaks or junctions.

- Moving parts of new work: Adjust, ease and lubricate as necessary to ensure easy and efficient operation, including doors, windows, drawers, ironmongery, appliances, valves and controls.

720 	Security at completion

- General: Leave the Works secure with, where appropriate, all accesses closed and locked.

- Keys: Account for and adequately label all keys, and hand over together with an itemized schedule, retaining duplicate schedule signed as a receipt.

730 	Making good defects

- Remedial work: Arrange access with WYFRS.

- Rectification: Give reasonable notice for access to the various parts of the Works.

- Completion: Notify when remedial works have been completed.

Ω End of Section

A34
Security/ safety/ protection

Security, health and safety

110 	Pre-construction information

- Location: Integral with the project Preliminaries, including but not restricted to the following sections:

  - Description of project: Sections A10 and A11.

  - Client’s consideration and management requirements: Sections A12, A13 and A36.

  - Environmental restrictions and on-site risks: Section A12, A35 and A34.

  - Significant design and construction hazards: Section A34.

  - The health and safety file: Section A37.

120 	Execution hazards

- Common hazards: Not listed. Control by good management and site practice.

130 	Product hazards

- Hazardous substances: Site personnel levels must not exceed occupational exposure standards and maximum exposure limits stated in the current version of HSE document EH40: 'Workplace Exposure Limits'.

- Common hazards: Not listed. Control by good management and site practice.

140 	Construction phase health and safety plan

- Submission: Present to the employer/ client no later than 2 weeks prior to the commencement of works on site.

- Confirmation: Do not start construction work until the employer has confirmed in writing that the construction phase health and safety plan includes the procedures and arrangements required by the CDM Regulations.

- Content: Develop the plan from, and draw on, the outline construction phase health and safety plan, clause A30/570, and the pre-tender health and safety plan/ pre-construction information.

150 	Security

- Protection: Safeguard the site, the Works, products, materials, and any existing buildings affected by the Works from damage and theft.

- Access: Take all reasonable precautions to prevent unauthorized access to the site, the Works and adjoining property.

- Special requirements: Ensure tools are stored in lockable containers overnight and ensure temporary units are lockable as the public is not blocked off from entering the rear car park via perimeter fencing/gating.

160 	Stability

- Responsibility: Maintain the stability and structural integrity of the works and adjacent structures during the contract.

- Design loads: Obtain details, support as necessary and prevent overloading.

170 	Occupied premises

- Extent: Existing buildings will be occupied and/ or used during the contract as follows: The fire station will continue to be used as a wholetime station, meaning crew members will be on-site 24/7 (unless called out to attend an incident)..

- Works: Carry out without undue inconvenience and nuisance and without danger to occupants and users.

- Overtime: If compliance with this clause requires certain operations to be carried out during overtime, and such overtime is not required for any other reason, the extra cost will be allowed, provided that such overtime is authorized in advance.

180 	Access control

- Controlled areas: The whole building

- Control type: PAC type security access, contractors will be provided with spare PAC cards for the project duration.

- Authorised persons: Submit a list of the names of all persons requiring access together with any other related information reasonably required.

- Return of credentials: When requested or on completion of the work to which the controlled area relates.

190 	Occupier’s rules and regulations

- Compliance: Conform to the occupier's rules and regulations affecting the site.

- Copies

  - Location: WYFRS - copies will be provided as part of the tender documents.

  - Arrangements for inspection: WYFRS

200 	Mobile telephones and portable electronic equipment

- Restrictions on use

  - None.

210 	Safety provisions for site visits

- Safety: Submit details in advance of safety provisions and procedures (including those relating to materials, which may be deleterious), which will require their compliance when visiting the site.

- Protective clothing and/ or equipment: Provide and maintain on site for visitors to the-site.

Protect against the following

330 	Noise and vibration

- Standard: Comply with the recommendations of BS 5228-1, in particular clause 7.3, to minimize noise levels during the execution of the Works.

- Equipment: Fit compressors, percussion tools and vehicles with effective silencers of a type recommended by manufacturers of the compressors, tools or vehicles.

- Restrictions: Do not use:

  - Percussion tools and other noisy appliances without consent during the hours of 6pm-9am.

  - Radios or other audio equipment or permit employees to use in ways or at times that may cause nuisance.

340 	Pollution

- Prevention: Protect the site, the works and the general environment (including the atmosphere, land, streams and waterways) against pollution.

- Contamination: If pollution occurs, report immediately, including to the appropriate authorities, and provide relevant information.

350 	Pesticides

- Use: Not permitted.

360 	Nuisance

- Duty: Prevent nuisance from smoke, dust, rubbish, vermin and other causes.

- Surface water: Prevent hazardous build-up on-site, in excavations and to surrounding areas and roads.

370 	Asbestos containing materials

- Duty: Report immediately any suspected materials discovered during execution of the works.

  - Do not disturb.

  - Agree methods for safe removal or encapsulation.

371 	Dangerous or hazardous substances

- Duty: Report immediately suspected materials discovered during execution of the works.

  - Do not disturb.

  - Agree methods for safe removal or remediation.

375 	Antiquities

- Duty: Report immediately any fossils, antiquities and other objects of interest or value discovered during execution of the works.

- Preservation: Keep objects in the exact position and condition in which they were found.

380 	Fire prevention

- Duty: Prevent personal injury or death, and damage to the Works or other property from fire.

- Standard: Comply with Joint Code of Practice 'Fire Prevention on Construction Sites', published by Construction Industry Publications and The Fire Protection Association (The 'Joint Fire Code').

390 	Smoking on-site

- Smoking on-site: Not permitted.

400 	Burning on-site

- Burning on-site: Not permitted.

410 	Moisture

- Wetness or dampness: Prevent, where this may cause damage to the Works.

- Drying out: Control humidity and the application of heat to prevent:

  - Blistering and failure of adhesion.

  - Damage due to trapped moisture.

  - Excessive movement.

420 	Infected timber/ Contaminated materials

- Removal: Where instructed to remove material affected by fungal/ insect attack from the building, minimize the risk of infecting other parts of the building.

- Testing: carry out and keep records of appropriate tests to demonstrate that hazards presented by concentrations of airborne particles, toxins and other microorganisms are within acceptable levels.

430 	Waste

- Waste: Includes rubbish, debris, spoil, containers and packaging, and surplus material requiring disposal.

- Requirement: Minimize production and prevent accumulation of waste. Keep the site and works clean and tidy. Clean out voids and cavities in the construction before closing.

- Disposal: Collect and store in suitable containers. Remove from site and dispose of in a safe and competent manner, as approved and directed by the waste regulation authority.

- Recyclable material: Sort and dispose of at a materials recycling facility approved by the waste regulation authority.

- Documentation: Retain on-site.

440 	Electromagnetic interference

- Duty: Prevent excessive electromagnetic disturbance to apparatus outside the site.

450 	Laser equipment

- Construction laser equipment: Install, use and store in accordance with BS EN 60825-1 and the manufacturer's instructions.

- Class 1 or Class 2 laser equipment: Ensure laser beam is not set at eye level and is terminated at the end of its useful path.

- Class 3R and Class 3B laser equipment: Do not use without approval and subject to submission of a method statement on its safe use.

460 	Powder actuated fixing systems

- Use: Not permitted.

470 	Invasive species

- General: Prevent the spread of species (e.g. plants or animals) that may adversely affect the site or works economically, environmentally or ecologically.

- Duty: Report immediately any suspected invasive species discovered during execution of the works.

  - Do not disturb.

  - Agree methods for safe eradication or removal.

Protect the following

510 	Existing services

- Confirmation: Notify all service authorities, statutory undertakers and/ or adjacent owners of proposed works not less than one week before commencing site operations.

- Identification: Before starting work, check and mark positions of utilities/ services. Where positions are not shown on drawings obtain relevant details from service authorities, statutory undertakers or other owners.

- Work adjacent to services

  - Comply with service authority's/ statutory undertaker's recommendations.

  - Adequately protect, and prevent damage to services: Do not interfere with their operation without consent of service authorities/ statutory undertakers or other owners.

- Identifying services

  - Below ground: Use signboards, giving type and depth;

  - Overhead: Use headroom markers.

- Damage to services: If any results from execution of the Works:

  - Immediately give notice and notify appropriate service authority/ statutory undertaker.

  - Make arrangements for the work to be made good without delay to the satisfaction of service authority/ statutory undertaker or other owner as appropriate.

  - Any measures taken to deal with an emergency will not affect the extent of the Contractor's liability.

- Marker tapes or protective covers: Replace, if disturbed during site operations, to service authority's/ statutory undertakers recommendations.

520 	Roads and footpaths

- Duty: Maintain roads and footpaths within and adjacent to the site and keep clear of mud and debris.

- Damage caused by site traffic or otherwise consequent upon the Works: Make good to the satisfaction of the Employer, Local Authority or other owner.

530 	Existing topsoil/ subsoil

- Duty: Prevent over compaction of existing topsoil and subsoil in those areas which may be damaged by construction traffic, parking of vehicles, temporary site accommodation or storage of materials and which will require reinstatement prior to completion of the Works.

- Protection: Before starting work submit proposals for protective measures.

560 	Existing features

- Protection: Prevent damage to existing buildings, fences, gates, walls, roads, paved areas and other site features, which are to remain in position during execution of the Works.

570 	Existing work

- Protection: Prevent damage to existing work, structures or other property during the course of the work.

- Removal: Minimum amount necessary.

- Replacement work: To match existing.

580 	Building interiors

- Protection: Prevent damage from exposure to the environment, including weather, flora, fauna, and other causes of material degradation during the course of the work.

600 	Existing furniture, fittings and equipment

- Protection: Prevent damage or move as necessary to enable the Works to be executed. Reinstate in original positions.

- Extent: Before work in each room starts, the following will be removed:

  - Existing desks, IT equipment and furniture. Existing lockers will also need to be removed and/or personal belongings decanted until new lockers are made available. Firefighting kit in the muster bay will need to be relocated elsewhere in the premises in storage boxes or otherwise as arranged by the Client.

625 	Adjoining property restrictions

- Precautions

  - Prevent trespass of workpeople and take precautions to prevent damage to adjoining property.

  - Pay all charges.

  - Remove and make good on completion or when directed.

- Damage: Bear cost of repairing damage arising from execution of the Works.

630 	Existing structures

- Duty: Check proposed methods of work for effects on adjacent structures inside and outside the site boundary.

- Supports: During execution of the Works:

  - Provide and maintain all incidental shoring, strutting, needling and other supports as may be necessary to preserve stability of existing structures on the site or adjoining that may be endangered or affected by the Works.

  - Do not remove until new work is strong enough to support existing structure.

  - Prevent overstressing of completed work when removing supports.

- Adjacent structures: Monitor and immediately report excessive movement.

- Standard: Comply with BS 5975 and BS EN 12812.

640 	Materials for recycling/ reuse

- Duty: Sort and prevent damage to stated products or materials, clean off bedding and jointing materials and other contaminants.

- Storage: Stack neatly and protect until required by the Employer or for use in the Works as instructed.

Ω End of Section

A35
Specific limitations on method/ sequence/ timing

Clauses

130 	Method/ sequence of work

- Specific Limitations: Include the following in the programme:

  - Works to be phased on each floor (GF-2F) as per Phasing Plan. Contractor to determine preferred method of sequencing 1F works in order to effectively separate active works areas and contractor access routes from building users as the station will continue to be operational during the contract period.

160 	Use or disposal of materials

- Specific limitations: Materials and waste must be removed from site regularly and should not be allowed to accumulate or affect the running of the fire station.

170 	Working Hours

- Specific limitations: TBC

Ω End of Section

A36
Facilities/ temporary work/ services

Clauses

110 	Spoil heaps, temporary works and services

- Location: Give notice and details of intended siting.

- Maintenance: Alter, adapt and move as necessary. Remove when no longer required and make good.

220 	Contractor Site Accommodation Type A

- Purpose: Essential Contractor welfare facilities.

- Facilities: Provide and obtain approval of suitable lockable temporary accommodation and facilities as follows:

- WC's as required.

- Site Office and/or Welfare Unit as required.

  - Status: May be part of the contractor's own accommodation

  - Location: Rear car park area (exact location TBC)

  - Floor area: Contractor to provide illustrated site plan proposal

  - Furniture and equipment: As required

  - Temperature control: As required

  - Lighting: As required

  - Services: Temporary electrical and water supplies required

  - Sanitary facilities: WC's

  - Consumables: As required

  - Attendance: As required

230 	Temporary accommodation

- Proposals for temporary accommodation and storage for the Works: Submit two weeks prior to starting on site.

- Details to be included: Type of accommodation and storage, its siting and the programme for site installation and removal.

260 	Sanitary accommodation

- Requirement: Provide sanitary accommodation for the Employer/ Purchaser, and other members of the consultant team, either separate or shared with the Contractor's supervisory staff. Maintain in clean condition and provide all consumables.

340 	Name boards/ advertisements

- Name boards/ advertisements: Will be permitted.

410 	Lighting

- Finishing work and inspection: Provide temporary lighting, the intensity and direction of which closely resembles that delivered by the permanent installation.

420 	Lighting and power

- Supply: Electricity from the existing mains may be used for the Works as follows:

  - Metering: Free of charge

  - Point of supply: As per Robert Whetham Associates Drawings.

  - Available capacity: TBC

  - Frequency: 50 Hz.

  - Phase: Single

  - Current: Alternating.

- Continuity: No responsibility will be accepted for the consequences of failure or restriction in supply.

430 	Water

- Supply: The existing mains may be used for the Works as follows:

  - Metering: Free of charge

  - Source: As per Robert Whetham Associates Drawings.

  - Location of supply point: As per Robert Whetham Associates Drawings.

  - Conditions/ Restrictions: None

- Continuity: No responsibility will be accepted for the consequences of failure or restriction in supply.

440 	Telephones

- Direct communication: As soon as practicable after the Date of Possession provide the Contractor's person in charge with a mobile telephone.

520 	Use of permanent heating system

- Permanent heating installation: May be used for drying out the Works/ services and controlling temperature and humidity levels.

- Installation: If used:

  - Take responsibility for operation, maintenance and remedial work.

  - Arrange supervision by and indemnification of the appropriate Subcontractors.

  - Pay costs arising.

570 	Personal protective equipment

- General: Provide for the sole use of other members of the project team, in sizes to be specified:

  - Safety helmets to BS EN 397, neither damaged nor time-expired. Number required: 2

  - High-visibility waistcoats to BS EN ISO 20471 Class 1. Number required: 2.

  - Safety boots with steel insole and toecap to BS EN ISO 20345. Pairs required: 0

  - Disposable respirators to BS EN 149.FFP1S.

  - Eye protection to BS EN ISO 16321-1 and BS EN ISO 16321-3.

  - Ear protection - muffs to BS EN 352-1, plugs to BS EN 352-2

  - Hand protection - to BS EN 388, 407, 420 or 511, as appropriate.

Ω End of Section

A37
Operation/ maintenance of the finished works

Clauses

110 	The building manual

- Responsibility: Principal Contractor

- Content: Obtain and provide comprehensive information for owners and users of the completed Works. Include an overview of the main design principles and describe key components and systems within the finished Works, so affording a complete understanding of the Works, including all buildings and their systems to enable efficient and safe operation and maintenance.

- Specific requirements: Refer to Pre-construction Information document.

- Format: Electronic

- Number of copies: 1

- Delivery to: WYFRS by (date) 2 weeks prior to Practical Completion.

115 	The Health and Safety File

- Responsibility: the Principal Contractor

- Content: Obtain and provide the following information: Refer to Pre-construction Information document.

- Format: Electronic

- Delivery to: WYFRS By (date): 2 weeks prior to Practical Completion.

155 	Content of the building manual

- General: Details of the property, the parties, fire safety strategy, operational requirements and constraints of a general nature.

- Building fabric: Design criteria, maintenance details, product details, and environmental and trafficking conditions.

- Building services: Description and operation of systems, diagrammatic drawings, record drawings, identification of services, product details, equipment settings, maintenance schedules, consumable items, spares and emergency procedures.

- Documentation: Guarantees, warranties, maintenance agreements, test certificates and reports.

160 	Presentation of building manual

- Format: A4 size, plastics covered, loose leaf, four ring binders with hard covers, each indexed, divided and appropriately cover titled.

- Selected drawings needed to illustrate or locate items mentioned in the Manual: Where larger than A4, to be folded and accommodated in the binders so that they may be unfolded without being detached from the rings.

- As-built drawings: The main sets may form annexes to the Manual.

190 	Maintenance service

- Scope: Provide a comprehensive maintenance service for the following items of plant and equipment. Include all planned preventative maintenance, as set out within the maintenance schedule, and replacement of all consumable items.

  - ……….

- Terms:

- Commencement:

- Duration:

220 	Training

- Objective: Before Completion, explain and demonstrate to designated maintenance staff the purpose, function and operation of the installations including items and procedures listed in the Building Manual.

- Level of training Comprehensive.

- Time allowance: Include a minimum of One days.

Ω End of Section

A40
Contractor's general cost items: management and staff

Clauses

110 	Management and staff

- Cost-significant items: Full-time site manager to be in attendance on site to liaise with fire station staff as and when required to ensure works do not disrupt station operations on a daily basis.

Ω End of Section

A41
Contractor's general cost items: site accommodation

Clauses

110 	Site accommodation

- Details: Site accommodation required or made/ not made available by the Employer: See section A36.

- Cost significant items: Contractors site office and welfare.

The provision and connections for temporary electricity and water supplies must be allowed for within the costs for the above accommodation.

Ω End of Section

A42
Contractor's general cost items: services and facilities

Clauses

110 	Services and facilities

- Details: Services or facilities required or made/ not made available by the Employer: See section A36.

- Cost significant items: None

Ω End of Section

A43
Contractor's general cost items: mechanical plant

Clauses

110 	Mechanical plant

- Cost significant items: None

Ω End of Section

A44
Contractor's general cost items: temporary works

Clauses

110 	Temporary works

- Details: Temporary works required or made/ not made available by the Employer: See section A36.

- Cost significant items: None

Ω End of Section

A50
Work/ products by/ on behalf of the employer

Clauses - No Amendments

Ω End of Section

A53
Work by statutory authorities/ undertakers

Clauses - No Amendments

Ω End of Section

Specification created using NBS Chorus