## Instructions
Tender Response - Part C - Pricing Schedule - East Cliff Stabilisation Works
NEC Option A: Priced contract with activity schedule
Option A
Bidder Name:
Instructions Please add your Company Name into the cell highlighted in yellow above. The tendered prices must include all associated costs applicable to this Contract and must be the full inclusive value for the works including all costs and expenses which may be required to fulfil the contract together with all general risks, liabilities and obligations set forth in or implied as necessary to comply with the contract documents. Please complete the yellow cells in each green activity schedule worksheet in this workbook filling in your pricing for each item. The headings are for guidance and the bidder can add or amend activities to suit. The sub-total for each worksheet will automatically calculate into the orange cell at the bottom of each worksheet. The sub-total from each worksheet will pull through to the summary in the 'Summary' worksheet. This price in the Summary will form your pricing submission for the tender evaluation. In addition please complete the yellow cells in the People rates and Tender Assessment Sheet . The Tender Assessment Sheet is used solely to assist the Employer in assessing tenders for purposes of awarding the Contract and will not form part of the Contract Sum. Amounts stated are for assessment purposes only and do not reflect anticipated values. Please note that all pricing to be submitted should be submitted exclusive of VAT. Please do not amend any formula's within this document. If you think there is an error with a formula, please contact the Client through the Messaging feature on ProContract. The tenderer is responsible for checking this worksheet for any arithmetical errors

## Summary
East Cliff Stabilisation Works
Option A
Tender summary
ACTIVITY SCHEDULE
1 | Preliminaries | 0
2 | Demolition and Site Clearance | 0
3 | Ground Reinforcement | 0
4 | In - situ Concrete | 0
4 | Concrete Ancillaries | 0
5 | Brickwork, Blockwork and Masonry | 0
6 | Miscellaneous Work | 0
| TOTAL TENDER SUM | 0

## Preliminaries
East Cliff Stabilisation Works
Option A
Preliminaries
ACTIVITY SCHEDULE
This is an indicative schedule of the minimum price breakdown that is required. Complete the yellow cells only. The tenderer may break the price down further and add any additional items required.
Ref | Item Description | Amount
NOTE: To be read in conjunction and priced in compliance with the Works Information and Specifications
General items
Contractual requirements
1 | Performance bond
2 | Insurances
Specified requirements
Accomodation
3 | Offices for contract administrators; establishment and removal
4 | Offices for contract administrators; maintenance
Testing of materials
5 | In accordance with Specification Appendix 1/5
Surveys and reports
6 | Preparation of Health and Safety documentation including risk assessments
7 | Undertake PAS 128 Survey to verify location of services and undertake clash detection
8 | Pre works dilapidation survey
9 | Post works dilapidation survey
10 | Undertake intrusive asbestos survey in cafeteria building
11 | Undertake intrusive asbestos survey in Substation & Top Station buildings
Approvals and Briefings
12 | Carry out Principal Contractor’s role under CDM Regulations
13 | Obtain statutory utility plans in advance of fieldwork
14 | Attendance at pre-start meetings
15 | Undertake UXO Site briefing before commencing intrusive works on site
Method-Related charges (To be edited/inserted by the tenderer as required)
Accomodation
16 | Fixed charges
17 | Time related charges
Services
18 | Fixed charges
19 | Time related charges
Plant
20 | Fixed charges
21 | Time related charges
Temporary Works
22 | Traffic Management (Fixed charges)
23 | Traffic Management (Time related charges)
24 | Access Track (Fixed charges)
25 | Access Track (Time related charges)
26 | Propping of substation wall during substation roof slab removal
27 | Propping of café building to allow internal asbestos survey
Supervision and labour
28 | Site Agent (minimum 5 years experience)
29 | Site Health and Safety Coordinator
30 | Data Coordinator
31 | Technical Drilling Supervisor (specify grade required)
32 | Drilling Supervisor (L3 Vocational Qualification)
33 | Other specialists (e.g. unexploded ordnance/contaminated waste/environmental specialist, traffic safety control officer or geophysicist)
34 | Project Manager
35 | Site Planner/Programmer
36 | Technical Lead (specify grade required)
| TOTAL CARRIED TO SUMMARY | 0

## Demo & site Clearance
East Cliff Stabilisation Works
Option A
Demolition and Site Clearance
ACTIVITY SCHEDULE
This is an indicative schedule of the minimum price breakdown that is required. Complete the yellow cells only. The tenderer may break the price down further and add any additional items required.
Ref | Item Description | Amount
NOTE: To be read in conjunction and priced in compliance with the Works Information and Specifications
Item 1 - Demolition and removal of natural and artiﬁcial articles, objects and obstructions which are above the Original Surface complete in accordance to drawings and specification
Note: Items for demolition and site clearance shall be deemed to include disposal of the materials arising
An initial phase of site clearance may be carried out by others prior to the Contractor’s appointment to align with the timing of environmental constraints. Notwithstanding this, the Contractor is to include for all vegetation clearance required to undertake the works in accordance with the Scope. The price will be adjusted accordingly, if required, to align with the outcome.
1.1 | Site Clearance
1.1.1 | Vegetation clearance
1.1.2 | Removal & disposal of overhanging cliff extents
1.1.3 | Removal & disposal of loose material (scaling) across works area; includes removal of loose blockwork on terracing
1.1.4 | Removal & disposal of existing footpath material
1.1.5 | Trimming of redundant brick work chamber & disposal
1.1.6 | Removal & disposal of existing coir roll matting
1.1.7 | Removal & disposal of biohazard waste including drug paraphernalia within the site area
1.1.8 | Removal & disposal of inorganic waste from the crest and slopes of the cliff
| TOTAL | 0
1.2 | Cliff top building and substation
1.2.1 | Removal of brickwork and blockwork, and non-bearing internal walls in pit; cliff top building & substation
1.2.2 | Removal of concrete roof slab, paving slabs and associated hand rails; cliff top building & substation
1.2.3 | Removal of concrete seaward face wall & piers; cliff top building & substation
1.2.4 | Removal of concrete roof slab (to be undertaken in 2 stages) to include green roof and parapets; cliff top building & substation
1.2.5 | Removal of concrete retaining wall above ground level; cliff top building & substation
1.2.6 | Removal of concrete internal walls and balance of external walls; cliff top building & substation
1.2.7 | Removal of concrete substation floor slab, lower ground level to suit new slab; cliff top building & substation
1.2.8 | Removal of existing substation steps; cliff top building & substation (no predominant material)
1.2.9 | Part-demolish existing substructure at bottom station (lower cliff lift pit): cut down and cap existing pipe and grout voids, and collect, test, and dispose of any displaced water
1.2.10 | Removal of topstation service pit covers and associated steel support beams; cliff top building & substation
1.2.11 | Removal and salvage of pit equipment (winch motor, gear box, pulley along with switchgear); cliff top building & substation
1.2.12 | Removal and salvage of substation equipment (transformers and switchgear); cliff top building & substation
1.2.13 | Removal of funicular pulleys; cliff top building & substation (no predominant material)
| TOTAL | 0
1.3 | Cafeteria
1.3.1 | Removal of concrete high level retaining wall; cafeteria
1.3.2 | Removal of concrete roof slab; cafeteria
1.3.3 | Partial removal and disposal of westward concrete floor slab, stairs, front wall and associated hand rails (bay 1); cafeteria
1.3.4 | Removal of concrete eastward floor slab, external staircase, front wall, balcony and associated hand rails (bay 6); cafeteria
1.3.5 | Removal of concrete floor slab bays 3 & 5 and partial removal of front wall and back wall dry lining; cafeteria
1.3.6 | Removal of concrete floor slab bays 2 & 4 and partial removal of front wall and back wall dry lining; cafeteria
1.3.7 | Removal of masonry first floor walls, conventional masonry cavity walls; cafeteria
1.3.8 | Removal of masonry front and internal walls; cafeteria
1.3.9 | Removal of soil wedge from behind first floor; cafeteria
1.3.10 | Removal of soil wedge from behind retaining wall
| TOTAL | 0
1.4 | Funicular Railway
1.4.1 | Removal of redundant services containment; funicular railway
1.4.2 | Removal of Metal (Steel) rails and other ancillary items; funicular railway
1.4.3 | Partial removal of eastern funicular railway reinforced concrete wing wall to just above ground level; funicular railway
1.4.4 | Removal of shipping containers
| TOTAL | 0
| TOTAL CARRIED TO SUMMARY | 0

## Ground reinforcement
East Cliff Stabilisation Works
Option A
Ground Reinforcement
ACTIVITY SCHEDULE
This is an indicative schedule of the minimum price breakdown that is required. Complete the yellow cells only. The tenderer may break the price down further and add any additional items required.
Ref | Item Description | Amount
NOTE: To be read in conjunction and priced in compliance with the Works Information and Specifications
Item 1 - Ground reinforcement with soil nailing comprising 38mm dia. galvanised tendons cement grouted into 90mm dia. Holes, with enhanced corrosion protection at proximal end (stainless steel)
Note: soil nail lengths are taken from the front face of the cliff / terracing / walls, the contractor shall allow for any additional lengths required to form head plate arrangements
1.1 | Permanent soil nailing
ln material other than rock or artificial hard material
1.1.1 | Permanent soil nailing at Cliff
ln material which includes rock or artificial hard material
1.1.2 | Permanent soil nailing at former Canopy
1.1.3 | Permanent soil nailing at Terrace
1.1.4 | Permanent soil nailing at Toilet Block
1.1.5 | Permanent soil nailing at Café Building
1.1.6 | Permanent soil nailing at Top Station
1.1.7 | Permanent soil nailing at Sub Station
1.2 | Total length of tendons in material which includes rock or artificial hard material
1.2.1 | Soil nail 8m length at Canopy
1.2.2 | Soil nail 8m length at Terrace
1.2.3 | Soil nail 16m length at Terrace
1.2.4 | Soil nail 8m length at Toilet Block
1.2.5 | Soil nail 8m length Café Building
1.2.6 | Soil nail 8m length Top Station
1.2.7 | Soil nail 8m length Sub Station
1.3 | Total length of tendons in material other than rock or artificial hard material
1.3.1 | Soil nail 5m length at Cliff
1.3.2 | Soil nail 8m length at Cliff
1.3.3 | Soil nail 18m length at Cliff
| TOTAL | 0
Item 2 - Miscellaneous Geotechnical Works
2.1
2.1.1 | Stainless high tensile steel mesh
2.1.2 | Erosion matting
2.1.3 | Raking drain - 76mm dia slotted or perforated pipe typical of length 12m
2.1.4 | Spike plate to suit cliff soil nails
2.1.5 | Square plate to suit terracing / wall soil nails and associated mortar
2.1.6 | Wire rope anchor to suit tensile mesh
2.1.7 | Coring of walls and terracing to enable soil nail installation
2.1.8 | Sand drain decommissioning
2.1.9 | Weepholes to canopy wall - 50mm dia uPVC pipe @ 2.5m centres
| TOTAL | 0
| TOTAL CARRIED TO SUMMARY | 0

## In-situ conc
East Cliff Stabilisation Works
Option A
In-situ Concrete
ACTIVITY SCHEDULE
This is an indicative schedule of the minimum price breakdown that is required. Complete the yellow cells only. The tenderer may break the price down further and add any additional items required.
Ref | Item Description | Amount
NOTE: To be read in conjunction and priced in compliance with the Works Information and Specifications
Item 1 - In - situ Concrete in accordance to drawings and specification
1.1 | Top Building, Substation works
Provision of concrete
1.1.1 | Designated concrete; strength RC35
1.1.2 | Designated concrete; strength C40/50
1.1.3 | Standardised prescribed concrete
Placing of concrete
1.1.4 | Mass filling in service trench
1.1.5 | Mass filling in service pit
1.1.6 | Mass filling in void fill (near brick inspection chamber)
1.1.7 | Reinforced slab; thickness 150-300mm
1.1.8 | Reinforced wall; thickness 150-300mm
1.1.9 | Reinforced wall; thickness 300-500mm
1.1.10 | Reinforced wall; thickness 300-500mm
1.1.11 | Concrete Copes above RC wall
| TOTAL | 0
1.2 | Cafeteria Works
Provision of concrete
1.2.1 | Designated concrete; strength C40/50
Placing of concrete
1.2.2 | Reinforced wall; varying thickness
1.2.3 | Concrete Copes above RC wall
1.2.4 | Mass lean mix concrete; facing at Cafeteria and Toilet Block
| TOTAL | 0
1.3 | Funicular Railway Works
1.3.1 | Capping of railway wing wall (RC50, 300mm high, with 2no. B20 reinforcement bars)
1.3.2 | Track bed concrete repair near toe, at 2 locations, each approx. 500mm long
| TOTAL | 0
| TOTAL CARRIED TO SUMMARY | 0

## Conc Acillarires
East Cliff Stabilisation Works
Option A
Concrete Ancillaries
ACTIVITY SCHEDULE
This is an indicative schedule of the minimum price breakdown that is required. Complete the yellow cells only. The tenderer may break the price down further and add any additional items required.
Ref | Item Description | Amount
NOTE: To be read in conjunction and priced in compliance with the Works Information and Specifications
Formwork, Reinforcement, Joints, Post-tensioned Prestressing, and Accessories for In Situ Concrete complete in accordance to drawings and specification
1 | Formwork
Rough Finish. Plane vertical (for formed face)
1.1 | Width: exceeding 1.22m; for lean mix concrete cast; at café and toilet block
Fair Finish. Plane vertical (for copes)
1.2 | Width: not exceeding 0.2 - 0.4m; at top building and substation
1.3 | Width: not exceeding 0.2 - 0.4m; at café and toilet block
1.4 | For lean mix concrete cast; at café and toilet block
| TOTAL | 0
2 | Formwork: Stated surface features
Plane vertical - textured faux stone finish with fairface perimiter.
2.1 | Walls; at top building and substation
2.2 | Walls; at café and toilet block
| TOTAL | 0
3 | Reinforcement
Deformed high yield steel bars & mesh
3.1 | Reinforcement; at Top Building and substation works
3.2 | Reinforcement; Café and toilet block
3.3 | Reinforcement; capping of railway wing wall
Steel mesh
3.4 | A192 Stainless Steel Mesh; at Top Building and substation works
3.5 | A192 Stainless Steel Mesh; at café and toilet block
| TOTAL | 0
4 | Joints
Dowels
4.1 | 16mm dia stainless steel dowels, resin fixed with hit-re 500 V4 at maximum 750mm centres horizontally and vertically; at top building and substation
4.2 | 16mm dia stainless steel dowels, resin fixed with hit-re 500 V4 at maximum 750mm centres horizontally and vertically; at café and toilet block
Formed surface plain
4.3 | Average width: not exceeding 0.5m; at Top building and substation
4.4 | Average width: not exceeding 0.5m; at café and toilet block
| TOTAL | 0
5 | Concrete accessories
Weepholes
5.1 | 50mm dia uPVC pipe to form weepholes through the wall @ 2.5m centres; at top building and substation
5.2 | 50mm dia uPVC pipe to form weepholes through the wall @ 2.5m centres; at café and toilet block
Finishing of top surfaces
5.3 | Steel trowel top surface finish; at top building and substation copes
5.4 | Steel trowel top surface finish; at café and toilet block copes
| TOTAL | 0
| TOTAL CARRIED TO SUMMARY | 0

## Masonry
East Cliff Stabilisation Works
Option A
Brickwork, Blockwork and Masonry
ACTIVITY SCHEDULE
This is an indicative schedule of the minimum price breakdown that is required. Complete the yellow cells only. The tenderer may break the price down further and add any additional items required.
Ref | Item Description | Amount
NOTE: To be read in conjunction and priced in compliance with the Works Information and Specifications
Brickwork, Blockwork and Masonry
1 | Brickwork, Blockwork and Masonry complete in accordance to drawings and specification
1.1 | Blockwork; ancillaries; cliff repair work - replace missing blocks
1.2 | Blockwork; ancillaries; crack repair for cliff - repointing
1.3 | Blockwork; ancillaries; bond works for cliff - crack stitching
| TOTAL | 0
| TOTAL CARRIED TO SUMMARY | 0

## Misc. Works
East Cliff Stabilisation Works
Option A
Miscellaneous Work
ACTIVITY SCHEDULE
This is an indicative schedule of the minimum price breakdown that is required. Complete the yellow cells only. The tenderer may break the price down further and add any additional items required.
Ref | Item Description | Amount
NOTE: To be read in conjunction and priced in compliance with the Works Information and Specifications
Fencing, Drainage & Gabion Structures complete in accordance to drawings and specification
1
1.1 | Steel handrails, height 1-1.25m and infill with galvanised finish Tube Stanchion 60.3 dia, x 4.0 CHS, as detailed on Drawing no: 70119008-WSP-ZZ-DG-S-141
1,2 | Galvanised steel palisade fencing comprising to toe, R20 galvanised bars with 100x55 UB posts 1850 high, inc. foundations & connections
| TOTAL | 0
| TOTAL CARRIED TO SUMMARY | 0

## People rates
Data for the Short Schedule of Cost Components - People Rates
ITEM | UNIT | TENDER ASSESSMENT QUANTITY | RATE | TOTAL
The tenderer shall enter the hourly rates for each category of person as inserted in the Contract Data Part 2 into the yellow cells. The tenderer may add any additional persons as required.
Category of person
Project Manager | HOUR | 60 |  | 0
Site Planner/Programmer | HOUR | 6 |  | 0
Quantity Surveyor | HOUR | 6 |  | 0
Site Agent (minimum 5 years experience) | HOUR | 60 |  | 0
Site Health and Safety Coordinator | HOUR | 15 |  | 0
Technical Lead (specify grade required) | HOUR | 6 |  | 0
Data Coordinator | HOUR | 6 |  | 0
Logging and/or Sampling Supervisor (specify grade required) | HOUR | 6 |  | 0
Technical Drilling Supervisor (specify grade required) | HOUR | 6 |  | 0
Drilling Supervisor (L3 Vocational Qualification) | HOUR | 6 |  | 0
Unskilled Operative | HOUR | 15 |  | 0
Add additional persons if required
|  |  | CARRIED FORWARD TO TENDER ASSESSMENT SHEET | 0

## Tender Assessment Sheet
Tender Assessment Sheet
This sheet is used solely to assist the Employer in assessing tenders for purposes of awarding the Contract and will not form part of the Contract Documents. Amounts stated are for assessment purposes only and do not reflect anticipated values.
The tenderer shall enter the % as inserted in the Contract Data Part 2 into the yellow cells.
Data for the Short Schedule of Cost Components
People (Total from the Price List for People) |  |  | 0
Materials (Allowance of 1% of the total tender sum for this tender assessment) |  |  | 0
Plant (Allowance of 1% of the total tender sum for this tender assessment)
Published List of Equipment (​​​The Civil Engineering Contractors Association Schedules of Contractor Equipment Rates For Use On Construction Contracts Including Rail Equipment Items – 2nd Edition – April 2022 – Volumes 1 & 2)​​
The percentage for adjustment for Equipment in the published list is (state plus or minus) | of | 0 | 0
|  | Sub Total | 0
The fee percentage is | of | 0 | 0
Total for assessment purposes only |  |  | 0
Tendered Total of the Prices from Summary |  |  | 0
TOTAL FOR TENDER ASSESSMENT PURPOSES ONLY |  |  | 0