Dated                                   2026

- [DEVELOPER]

- [LANDOWNER]

- ALPHA HOUSING (NORTHERN IRELAND) LIMITED

__________________________________________

SALE & DEVELOPMENT AGREEMENT

[insert site address]

__________________________________________

THIS AGREEMENT is made the              day of                                           2026

BETWEEN:

(1)	[            ] (“Developer”); and

(2)	[            ] (“Landowner”); and

(3)	ALPHA HOUSING (NORTHERN IRELAND) LIMITED (company no. NP000394) (IP Number 394IP) whose registered office of which is situate Alpha House, Edgewater Road, Belfast, BT3 9JQ (“Alpha”).

WHEREAS:-

The Developer intends to undertake a residential housing development at [            ] on land currently in the ownership of the Landowner.

The Landowner has agreed to sell and Alpha has agreed to purchase the land on which the Developer shall construct for Alpha dwellings upon the following terms of this Agreement.

NOW IT IS HEREBY AGREED as follows:

1.	DEFINITIONS

In this Agreement unless the context otherwise requires the following expressions shall have the following meanings:

  - “Agreed Fixed Price” means the sum detailed in the Contract Sum Analysis but which for the avoidance of doubt is £[            ] which excludes the Site Value.

  - “Agreed Form” means a form populated by the Parties.

  - “Agreed Rate” means three (3) per centum per annum above the base rate for the time being of Bank of England.

  - “Architect” means [            ] or such other reputable and professionally qualified person firm or company experienced in the provision of social housing as the Developer may appoint with the approval of Alpha (such approval not to be unreasonably withheld or delayed) to act as the architect in connection with the Developer’s Works and whose identity shall be notified to Alpha in writing.

  - “Alpha’s Approval” means the approval by Alpha’s Board of Management that the Scheme is reasonably acceptable to Alpha.

  - “Alpha’s Board of Management” means the individuals from time to time appointed to the management board of Alpha.

  - “Alpha’s Building Inspector” means such person, firm or company from time to time appointed by Alpha for the purposes of this Agreement to inspect the Developer’s Works from time to time, of whose appointment the Developer shall be notified in writing by Alpha.

  - “Alpha’s Final Statement” means the statement to which clause 24.10 refers.

  - “Alpha’s Procedures” means the handover and defects procedures set out at Schedule 8.

  - “Alpha’s Requirements”  means the design and other requirements of Alpha and the DfC Guide as set out in the documentation annexed to Schedule 1.

  - “Alpha’s Solicitors” means Edwards & Co Solicitors of 28 Hill Street, Belfast, BT1 2LA or other firm or firms of solicitors from time to time appointed by Alpha in connection with this Agreement of whose appointment the Developer shall be notified in writing by Alpha.

  - "Alpha's Unacceptable Condition(s)"  means a condition, obligation or restriction which has not been waived in writing by Alpha imposed in a planning permission applied for under this Agreement or required in an agreement under section 76 of the Planning Act regulating the Scheme or use of the Site, of one or more of the following kinds:-

(a)	it requires the payment or expenditure of money or other consideration by Alpha by way of planning gain or on works outside the Site;

(b)	it prevents development without the agreement or co-operation of an independent third party which cannot be obtained on terms, at a cost or within a time frame that is reasonable in the circumstances in the opinion of Alpha (acting reasonably);

(c)	it requires the provision of facilities or amenities within the Site which have not been specified for in the Planning Application; and/or

(d)	it is in the reasonable opinion of Alpha unreasonable or unduly restrictive in the circumstances

  - “Building Contract” means the building contract(s) with any Contractor for the carrying out of the Developer’s Works or any part of them in the Agreed Form.

  - “Certificates” means the Certificates of Completion, Stage Payment Certificates and/or the Defects Certificates as the case may be.

  - “Certificate of Completion” means the written statement issued by the Employer’s Agent acting reasonably certifying completion of the Developer’s Works in respect of each of the Dwellings confirming that each relevant Dwelling is fit for reasonable use and occupation by a potential purchaser and/or a tenant and setting out the full cost of the works for that Dwelling.

  - “Charge” means any fixed and/or floating security affecting the Site as of the date of this Agreement.

  - “CIS” means the Construction Industry Scheme under the Finance Act 2004.

  - “Civil Engineer” means  or such other reputable and professionally qualified person firm or company as the Developer may appoint with the approval of Alpha (such approval not to be withheld or delayed) to act as the civil engineer in connection with the Developer’s Works and whose identity shall be notified in writing to Alpha.

  - “Collateral Warranty” means the collateral warranties provided or to be provided by the Developer pursuant to this Agreement.

  - “Completion Certificate Date” means the date of a Certificate of Completion in respect of each of the Dwellings on the Site.

  - “Completion Date” means the date stated in the last Certificate of Completion.

  - “Conditions Precedent” means (i) the Developer obtaining Design Approval in accordance with Clause 4 of this Agreement; (ii) Alpha obtaining NIHE Approval in accordance with Clause 12 of this Agreement; (iii) the granting of Satisfactory Planning Permission; (iv) the Landowner provide vacant possession and clear, unencumbered title to the Site in accordance with Clause 13 of this Agreement; (v) the Developer completing any environmental remedial works (including inter alia contamination) to the Site (if applicable) so as to ensure that same is compliant with environmental legislation and which said works are independently verified to the satisfaction of Alpha; (vi) Agreement of the final form Building Contract(s); (vii) the Developer providing documentary evidence from a third party (e.g. bank or accountant or such other third party as Alpha shall deem as equivalent) to demonstrate proof of funding of the Development Costs; and (viii) the Developer providing evidence that the insurances set out in Clauses 23 and 25 [together with the Performance Bond] have all been effected.

  - “Conditions Precedent Longstop Date” means the date falling twenty four (24) months after the date of this Agreement.

  - Contract Addendum” means the provisions and requirements set out at Schedule 9 hereto.

  - “Contract Sum Analysis” means a breakdown and analysis of all proposed Interim Payments appended hereto at Schedule 5.

  - “Contractor” means any person engaged by the Developer to carry out any building and/or construction works forming all or any part of the Developer’s Works.

  - “Cover Note”  means a cover note issued by the NHBC pursuant to the Buildmark scheme or such other scheme approved by Alpha (acting reasonably) in respect of the dwellings which provides for 10 years plus 2 years cover plus cover for Contactor insolvency and fees.

  - “Defects” means any defect in the Developer’s Works due to it not being constructed in accordance with the terms of this Agreement.

  - “Defects Certificate” means the Certificate issued by the relevant member of the Professional Team in relation to a Dwelling or Dwellings confirming the correction of all Defects identified during the twelve (12) month period following the Completion Certificate Date.

  - “Defects Date” means the date which is twelve (12) months after the Completion Date.

  - “Deleterious Materials” means any products, substances or materials not in conformity with relevant British or an equivalent international standard or Codes of Practice or which at the time of use are widely known to builders or designers of the relevant discipline to be either unacceptable in general building practice for Developer’s Works or deleterious to health and safety or to the durability of buildings and/or other structures and/or finishes and/or plant and machinery or any parts thereof in the particular circumstances in which they are used or any other product, substance or material specified as deleterious by Alpha.

  - "Design Approval" means Alpha’s Approval of the Developer’s proposals for carrying out the Scheme in accordance with the Employer’s Requirements.

  - “Design Team” means the Architect, the Services Engineer, the Civil Engineer, the Structural Engineer, the Principal Designer and the Quantity Surveyor.

  - “Developer’s Solicitors” means   or other firm or firms of solicitors from time to time appointed by the Developer in connection with this Agreement of whose appointment Alpha shall be notified in writing by the Developer.

  - “Developer’s Unacceptable Condition” means a condition, obligation or restriction which has not been waived in writing by the Developer imposed in a planning permission applied for under this Agreement or required in an agreement under section 76 of the Planning Act regulating the Scheme or use of the Site, of one or more of the following kinds:

(a)	it will or is likely to (in the Developer’s reasonable opinion) increase the cost of carrying out the Developer’s Works by £25,000 or more;

(b)	it reduces the total number of Dwellings permitted to be constructed at the Site to less than five (5); and/or

(c)	it requires the payment of a capital sum under an agreement under section 76 of the Planning Act.

  - “Developer’s Works” means the works to be carried out by the Developer pursuant to clause 16 and in accordance with the Employer’s Requirements, the Specification, the Project Execution Plan, and the Requisite Consents and which comprise the construction of the Dwellings (and any associated infrastructure/common areas) to facilitate the Scheme.

  - “DfC” means the Department for Communities in Northern Ireland.

  - “DfC Guide” means Housing Association Guide as varied by the DfC from time to time which sets out standards for work effected by Housing Associations) operative at the time of DfC Approval.

  - “Dispute Resolution Procedure” means the procedure set out in clause 28.

  - "DPG Development Programme" means the programme of grant assistance administered by NIHE to enable housing associations to develop social housing.

  - “Dwelling” means each of the residential units to be constructed by the Developer on the Site and “Dwellings” shall be construed accordingly.

  - “Employer’s Agent” means such surveyor or other suitably qualified person firm or company from time to time appointed by Alpha for the purposes of this Agreement of whose appointment the Developer shall be notified in writing by Alpha.

  - “Employer’s Requirements” means the design and other requirements of Alpha as set out in the documentation annexed at Schedule 1.

  - “Expert” means a person with at least ten (10) years' post-qualification experience including significant relevant experience in the subject matter of the dispute.

  - "Extended Planning Longstop Date" means the date six (6) months after the date of the Planning Longstop Date.

  - “Final Statement” means the statement to which clause 24.8 refers.

  - “Force Majeure” means any of the following:- a) war, hostilities, rebellion, revolution, insurrection, military or usurped power or civil war; b) labour lock outs, strikes or without limitation other labour disputes; c) riot, civil commotion or disorder; d) decree of government; e) delay by a local authority or statutory undertaker in carrying out work in pursuance of its statutory obligations or failure by such authority or statutory undertaker to carry out such works or to sign any statutory agreements as long as such failure is not attributable to the Developer; f) non availability of materials or equipment; and g) any other cause or circumstance beyond the reasonable control of the Developer including any delays caused as a result of the Covid-19 outbreak or any other epidemic or pandemic.

  - “Funder” means any bank, financial institution or other person providing finance (whether or not to be secured upon the Site) to Alpha.

  - “General Conditions” mean the Law Society of Northern Ireland General Conditions of Sale (4th Edition) and “General Condition” shall be construed accordingly.

  - “Gross Valuation” has the meaning set out in clause 24.15.

  - “Independent Surveyor” means a surveyor appointed pursuant to clause 7.

  - “Insurance Policy” means an insurance policy maintained or to be maintained by the Developer at its own cost on terms satisfactory to Alpha and from an insurer to be approved by Alpha (acting reasonably).

  - “Intellectual Property” means all drawings, designs, specifications, surveys, reports, and all other work necessarily required by this Agreement for the Development in electronic form.

  - IP licences means licences granted to Alpha by each member of the Professional Team in respect of Alpha’s use of the Intellectual Property.

  - “Interim Application” means the application made by the Developer to Alpha for Interim Payments pursuant to clause 24.3.

  - “Interim Payment” means any of the payments to which clause 24.3 refers.

  - “Interim Payment Retention” means 5% of each and every Interim Payment.

  - “Landowner’s Solicitors” means [          ] or other firm or firms of solicitors from time to time appointed by the Landowner in connection with this Agreement of whose appointment Alpha shall be notified in writing by the Developer.

1.57a  “Liquidated Damages” means a capped sum of £[    ] per unit per week.

  - “Local Planning Authority” means the local council, the Department for Infrastructure or such other body at any time charged with planning functions under the Planning Act or such other legislative instrument from time to time in force regulating the development or use of the land.

  - “Longstop Date” means the date three months after the Target Date for completion of the Developer’s Works as may be extended in accordance with clauses 16.8 and 16.9.

  - “NIHE" means the Northern Ireland Housing Executive.

  - “NIHE Approval" means approval by NIHE that the Scheme is eligible for housing association grant assistance funding as part of the DPG Development Programme.

  - “Party” the Developer and/or Alpha (and the “Parties” shall be construed accordingly).

  - “Plan” means the plan annexed in Schedule 2 to this Agreement.

  - “Planning Act” means the Planning Act (Northern Ireland) 2011.

  - "Planning Appeal Decision" means the written decision of the Planning Appeals Commission pursuant to an appeal under Clause 6.

  - "Planning Appeals Commission" means the Planning Appeals Commission in Northern Ireland or any other official body appointed to determine planning appeals.

  - "Planning Application" means the application for Planning Permission.

  - "Planning Longstop Date" means the date eighteen (18) months after the date of this Agreement as may be extended in accordance with clause 9.1, or such longer period as is otherwise agreed in writing by the Parties.

  - “Planning Permission” means the planning permission relating to the Site [   ], ascribed planning reference  [            ].

  - “Principal Designer” means [            ] or such other reputable and professionally qualified person firm or company experienced in the provision of social housing as the Developer may appoint with the approval of Alpha (such approval not to be unreasonably withheld or delayed) to act as the Principal Designer in connection with the Developer’s Works and whose identity shall be notified to Alpha in writing.

  - “the Professional Team” means such of the Architect, the Quantity Surveyor and the Services Engineer, Principal Designer, Structural Engineer, Civil Engineer, Project Manager and any other professionals appointed by the Developer in connection with the Developer’s Works.

  - “Project Manager” means [            ] or such other reputable and professionally qualified person firm or company as the Developer may appoint with the approval of Alpha (such approval not to be unreasonably withheld or delayed) to act as the project manager in connection with the Developer’s Works and whose identity shall be notified to Alpha in writing.

  - “Project Execution Plan” means a draft written plan (to be finalised thereafter with the prior written agreement of Alpha acting reasonably) satisfying the requirements of clause 15 and which is appended hereto at Schedule 7.

  - “Quantity Surveyor” means  [            ] or such other reputable and professionally qualified person firm or company as the Developer may appoint with the approval of Alpha (such approval not to be withheld or delayed) to act as the Quantity Surveyor in connection with the Developer’s Works and whose identity shall be notified in writing to Alpha.

  - “the Regulations” means the Construction (Design and Management) Regulations (Northern Ireland) 2016 and any replacement regulations of them.

  - “Requisite Consents” means the Planning Permission, building control approval and such other  consents,  approvals,  licences,  certificates and permits as may be necessary to lawfully commence,  carry out,  maintain and complete the Developer’s Works or so as to be able to sell or lease the Dwellings to a well advised purchaser and/or tenant.

  - “Retention” means a sum representing 10% of the Agreed Fixed Price and which shall be deductible from any payment on account in respect of the Agreed Fixed Price made by Alpha to the Developer which for the avoidance of doubt excludes any Interim Payment Retention.

  - “Satisfactory Planning Permission” means the Planning Permission or Planning Appeal Decision granted by the Local Planning Authority or Planning Appeals Commission for the Scheme not being subject to an Alpha’s Unacceptable Condition (except those waived in writing by Alpha in accordance with Clause 8.4) nor subject to a Developer’s Unacceptable Condition (except those waived in writing by the Developer in accordance with Clause 8.5).

  - “the Scheme” means the development of the Site in accordance with the Requisite Consents.

  - “Services Engineer” means [            ] or such other reputable and professionally qualified person firm or company as the Developer may appoint with the approval of Alpha (such approval not to be unreasonably withheld or delayed) to act as the Services Engineer in connection with the Developer’s Works and whose identity shall be notified to Alpha in writing.

  - “Site” means all the property known as the [            ]   more particularly delineated in the Plan.

  - “Site Completion Date” means the date of completion of the sale of the Site by the Landowner to Alpha calculated in accordance with clause 8.1.

  - “Site Transfer” means the transfer of the Site to be granted by the Landowner to Alpha in the form of Land Registry Form 9 as annexed in Schedule 3 to this Agreement.

  - “Site Value” means the sum equal to 15% of the Gross Valuation or market value (whichever is lower) which the Parties agree represents the value of the Site at the date of this Agreement.

  - “Specification” means the specification of the Developer’s Works and a design guide as attached at Schedule 4 hereto and/or any specifications and/or drawings which the Developer is entitled to introduce under the terms hereof and which the Parties may subsequently agree shall be substituted therefor, or used in conjunction therewith whether such new specifications and/or drawings vary the specification and drawings annexed hereto or otherwise.

  - “Stage Payment Certificate” means a certificate furnished by the Developer in relation to each Interim Payment an stating the sum that the Developer considers to be due to it and the basis on which that sum has been calculated.

  - “Structural Engineer” means or such other reputable and professionally qualified person firm or company as the Developer may appoint with the approval of Alpha (such approval not to be withheld or delayed) to act as the structural engineer in connection with the Developer’s Works and whose identity shall be notified in writing to Alpha.

  - “Target Date” means the target date specified in the Project Execution Plan for completion of the Developer’s Works, as may be extended in accordance with clauses 16.8 and16.9.

  - “Unconditional Date” means the date of satisfaction of the last of the Conditions Precedent when this Agreement shall become unconditional (to the extent that any such Conditions Precedent have not been waived by Alpha in accordance with this Agreement).

  - “VAT” means Value Added Tax.

  - “Working Day” means any day other than Saturday or Sunday upon which clearing banks in the United Kingdom are open to the public for the transaction of business.

Words importing the singular number only shall include the plural number and vice versa.  Where there are two (2) or more persons included in the expression “the Developer” or “Alpha” obligations herein contained which are expressed to be made by the Developer or Alpha shall be binding jointly and severally on them and their respective successors and representatives whomsoever. Words importing persons include corporations and vice versa.

2.	THE CONDITIONS PRECEDENT

2.1	Subject to clause 2.5, this Agreement is conditional upon the Conditions Precedent being fulfilled by the Conditions Precedent Longstop Date.

2.2	The Developer shall:-

(i)	use its reasonable endeavours and proceed diligently at its own expense at all times to satisfy the Conditions Precedent prior to the Conditions Precedent Longstop Date and shall keep Alpha fully informed of progress from time to time in this respect; and

(ii)	provide Alpha with monthly updates in relation to the progress of the Project Execution Plan, a payment schedule in relation to those Interim Payments which are anticipated for the following month, and where the Scheme is within three (3) months of completion, a proposed completion plan (including inter alia a handover schedule).

2.3	Without prejudice to the rights of Alpha outlined in Clauses 9 and 12.5 of this Agreement, if by the Conditions Precedent Longstop Date the Conditions Precedent have not been fulfilled (subject to clause 2.5) then Alpha shall be entitled to determine this Agreement by notice in writing to the Developer and upon service of such notice this Agreement shall determine and neither party shall be under any further obligation to the other whether for compensation, damages, costs, expenses or otherwise save in respect of any antecedent breach of this Agreement.

2.4	For the avoidance of doubt (and notwithstanding anything contained in this Agreement) the Developer is not entitled to be paid any sum under this Agreement and Alpha will not be liable to make any payment to the Developer whatsoever until the Conditions Precedent have been satisfied (subject to clause 2.5) and in the event that the Developer carries out any works relating to the Scheme prior to the satisfaction of the Conditions Precedent it does so entirely at its own risk.

2.5	Notwithstanding any other provision herein, Alpha may waive any of the Conditions Precedent by giving written notice of waiver to the Developer.

3.	SALE AND PURCHASE

3.1	Subject to satisfaction of the Conditions Precedent, the Landowner as beneficial owner shall sell and Alpha shall purchase the Site for the Site Value on the terms of this Agreement.

3.2	The General Conditions are deemed to be incorporated in this Agreement in so far as they are applicable and are not inconsistent with the other conditions (including this condition) of this Agreement and are hereby varied as follows:-

3.2.1	The words ‘and will if the Vendor so requires be conveyed’ shall be deleted from General Condition 4.2 (b).

3.2.2	General Condition 5 shall not apply.

3.2.3	General Condition 6.1 shall be deleted and the following substituted therefor: “The Vendor shall retain the risk until completion of the Site Transfer”

3.2.4	General Condition 12.3 shall not apply.

3.3	The Developer hereby irrevocably appoints Alpha as its attorney under the Powers of Attorney (Northern Ireland) Act 1971 and all other powers vested in the Developer for the purposes of enabling Alpha to interact with, instruct and direct the Professional Team or any other professionals Alpha wishes to instruct and implement and complete the Development utilising the Intellectual Property Licences or such other professional support as Alpha sees fit in the event that the Developer fails to do so for any reason at any time.

4.	DESIGN APPROVAL

4.1	Within twenty (20) Working Days after the date of this Agreement, the Developer will submit to Alpha for approval the Developer’s proposals for the carrying out of the Scheme in accordance with the Employer’s Requirements.

4.2	Subject to Clause 4.1, the Developer will co-operate with Alpha and use all reasonable endeavours to assist Alpha throughout the Design Approval process.

4.3	Within twenty (20) Working Days after Alpha has received the Developer’s proposals pursuant to Clause 4.1, Alpha’s internal review team will provide to the Developer in writing its provisional comments on the Developer’s proposals, and thereafter (and in any event within 12 weeks of receipt of the Developer’s proposals) Alpha will notify the Developer in writing that Alpha either approves or disapproves the proposals.

4.4	If Alpha does not approve the proposals, Alpha may at the same time or within two (2) Working Days after the date of that notice, rescind this Agreement by notifying the Developer in writing.

4.5	If Alpha does not:-

4.5.1	approve the proposals; and

4.5.2	rescind this Agreement in accordance with Clause 4.4;

the Developer will submit revised proposals to Alpha for approval.  The procedures set out in Clauses 4.2 and 4.3 will apply to the revised proposals as if they were the first proposals.  The Developer will continue to submit revised proposals to Alpha for approval until proposals are approved by Alpha unless this Agreement is rescinded in accordance with Clause 4.4.

5.	Planning Application

  - 5.1 	Subject to the Developer obtaining Design Approval, within five (5) Working Days after the grant of Design Approval the Developer will, to the extent not already done prior to the date hereof, submit to Alpha for approval the Developer's proposed application for planning permission for the Scheme.

  - 5.2	Within ten (10) Working Days after Alpha has received the Developer’s proposed application, Alpha will notify the Developer in writing that Alpha either approves or disapproves the proposed application.

  - 5.3	If Alpha does not approve the proposed application, the Developer will submit a revised proposed application to Alpha for approval.  The procedure set out in Clause 5.2 will apply to the revised proposed application as if it were the first proposed application.  The Developer will continue to submit revised proposed applications to Alpha for approval until a proposed application is approved by Alpha.

  - 5.4	Within five (5) Working Days after Alpha has approved the Developer's proposed application, the Developer will submit the Planning Application to the Local Planning Authority and will use all reasonable endeavours to obtain Satisfactory Planning Permission as soon as reasonably possible.

  - 5.5	Before the submission of the Planning Application the Developer will, if requisite or desirable in order to obtain it, enter into discussions or negotiations with the Local Planning Authority and where necessary to comply with the Planning Act any pre-application community consultation.

  - 5.6	The Developer may in consequence of discussions or negotiations with the Local Planning Authority (if it appears requisite or desirable in order to obtain Satisfactory Planning Permission), amend or withdraw and immediately thereafter submit a fresh application for planning permission, or in the alternative lodge a non-determination appeal with the Planning Appeals Commission (such non-determination appeal being subject to approval by Alpha (acting reasonably)).

  - 5.7	The Developer may in its reasonable discretion agree with the Local Planning Authority an extension of the statutory period for the giving of notice of its decision under section 60 of the Planning Act, but not beyond an additional period of three (3) months without the consent of Alpha (consent not to be unreasonably withheld or delayed).

  - 5.8	In conducting discussion or negotiation with the Local Planning Authority the Developer will keep Alpha fully informed and will:-

    - 5.8.1	supply Alpha with copies of all correspondence to or from the Developer and/or the Local Planning Authority or to or from the Developer's Solicitors in connection with the Planning Application (including accompanying plans and other documents, but excluding correspondence exclusively between the Developer and the Developer's Solicitors or other legal representative) within five (5) Working Days after either:-

      - 5.8.1.1	the date of any correspondence sent by the Developer or the Developer's Solicitors; or

      - 5.8.1.2		the date of receipt of any correspondence by the Developer or the Developer's Solicitors;

    - 5.8.2		give Alpha at least five (5) Working Days' notice of any meetings to be held in connection with the Local Planning Authority, highway authority, service undertakers, local residents in connection with the Planning Application and will give Alpha and Alpha's representatives, agents, counsel and Alpha's Solicitors the opportunity to attend and a copy of any minutes.

  - 5.9	Alpha will co-operate with the Developer and use reasonable endeavours to assist the Developer in seeking to obtain Satisfactory Planning Permission, but in so doing Alpha may not act independently of the Developer.

  - 5.10	If reasonably required by the Developer (where the Developer is able to demonstrate that it is required as a condition of the issue of Satisfactory Planning Permission) Alpha will enter into any agreement with the Local Planning Authority pursuant to the provisions of section 76 of the Planning Act that the Local Planning Authority may require (subject to the Developer indemnifying Alpha in full against any cost and/or liabilities which it may have to undertake in connection therewith) PROVIDED ALWAYS that any such section 76 agreement shall be conditional upon the grant of Satisfactory Planning Permission for the Scheme.

  - 5.11	Alpha will not be required to enter into any agreement that:-

    - 5.11.1	obliges Alpha to pay money or to carry out works;

    - 5.11.2	requires Alpha to dedicate, make available or otherwise provide, transfer or dispose of any land not forming part of the Site; or

    - 5.11.3	requires Alpha to grant any right or to enter into any covenant over any land that does not form part of the Site.

  - 5.12	The Developer will keep Alpha indemnified against all liability, proceedings, costs, claims, demands and expenses incurred or arising under each agreement that Alpha enters into under clause 5.10 this Agreement, including any irrecoverable VAT thereon.

  - 5.13	Alpha will keep the Developer fully informed of all action it may take in accordance with Clause 5.10.

  - 5.14	The Developer will, within five (5) Working Days after receiving it, give a copy of the Planning Permission to Alpha.

  - 5.15	At the same time as the Developer gives Alpha a copy of the Planning Permission pursuant to clause 5.14, the Developer shall notify Alpha in writing whether or not a condition to which the Planning Permission is subject is a Developer’s Unacceptable Condition.

  - 5.16	The Landowner hereby agrees to permit the Developer to submit an application for Planning Permission to the Local Planning Authority in respect of the Site and agrees to provide such assistance as is necessary in relation to same to enable the Developer to achieve a Satisfactory Planning Permission.

# 6.	Planning Appeal

  - 6.1	If the Local Planning Authority grants planning permission, it will be deemed to have granted Satisfactory Planning Permission unless:-

    - 6.1.1		before the expiry of fifteen (15) Working Days from the date of such grant Alpha gives written notice to the Developer specifying which of the conditions to which the Planning Permission is subject Alpha regards as being Alpha's Unacceptable Conditions and against which Alpha requires the Developer to appeal; and/or

    - 6.1.2		the Developer gives written notice to Alpha that one or more of the conditions to which the Planning Permission is subject is a Developer’s Unacceptable Condition in accordance with clause 5.15.

    - 6.2	In the event that the Local Planning Authority refuses the grant of Planning Permission pursuant to the Planning Application or fails to make a decision (non-determination), Alpha may at its discretion serve written notice requiring the Developer to appeal.

  - 6.3	If any written notice is given pursuant to Clause 6.1.1 or 6.1.2 or 6.2 the Developer will within twenty (20) Working Days of the aforementioned notice or four (4) months from the date of the decision (whichever is shorter) lodge an appeal to the Planning Appeals Commission.

  - 6.4	Once the Developer has lodged an appeal:-

    - 6.4.1	it will provide Alpha with a copy of the notice of appeal;

    - 6.4.2	it is obliged to continue unless Alpha agrees otherwise.

  - 6.5	The Developer will use all reasonable endeavours to pursue the appeal to secure that the Satisfactory Planning Permission is granted as soon as possible.

  - 6.6	In pursuing the appeal the Developer will keep Alpha fully informed of all relevant information with respect to the appeal, including all correspondence, notifications, instructions to and advice of counsel, evidence of expert and other witnesses, and the dates of any enquiry hearing or for the submission of written representations.

  - 6.7	The Developer will, within five (5) Working Days after receiving it, give a copy of the Planning Appeal Decision to Alpha.

  - 6.8	At the same time as the Developer gives Alpha a copy of the Planning Appeal Decision to Alpha pursuant to clause 6.7, the Developer shall notify Alpha in writing whether or not a condition to which the Planning Appeal Decision is subject is a Developer’s Unacceptable Condition.

  - 6.9	In the event that the Developer lodges a non-determination appeal pursuant to section 58 and 60 of the Planning Act the provisions 6.4 to 6.7 will apply equally to the non-determination appeal.

# 7.	Planning Appeal Decision with Conditions Attached

  - 7.1	If the Planning Appeal Decision is to grant planning permission, it will be deemed to be a Satisfactory Planning Permission unless:-

    - 7.1.1	before the expiry of ten (10) Working Days after the date that Alpha has received a copy of the Planning Appeal Decision from the Developer pursuant to Clause 6.7 Alpha gives written notice to the Developer specifying which of the conditions to which the Planning Appeal Decision is subject Alpha considers to be Alpha's Unacceptable Conditions and requiring the Planning Appeal Decision to be referred to an Independent Surveyor; and/or

    - 7.1.2	the Developer gives written notice to Alpha that one or more of the conditions to which the Planning Appeal Decision is subject is a Developer’s Unacceptable Condition in accordance with clause 6.8.

  - 7.2	If Alpha gives notice to the Developer under Clause 7.1.1, Alpha may at the same time or within two (2) Working Days after the date of that notice rescind this Agreement by notifying the Developer in writing.

  - 7.3	If the Developer gives notice to Alpha under clause 7.1.2, the Developer may at the same time or within five (5) Working Days of the date of that notice rescind this Agreement by notifying Alpha in writing.

  - 7.4	The Parties may agree to extend any time limit for giving any notice under this Clause.

  - 7.5	The Planning Appeal Decision will be referred to an Independent Surveyor to determine whether each planning condition is an Alpha's Unacceptable Condition, if:-

    - 7.5.1	a notice has been given by Alpha under Clause 7.1.1 requiring the Planning Appeal Decision to be referred to the Independent Surveyor; and

    - 7.5.2	Alpha has not rescinded this Agreement under Clause 7.2; and

    - 7.5.3	the Developer has not rescinded this Agreement under Clause 7.3.

  - 7.6	An Independent Surveyor will be appointed by agreement between the Developer and Alpha or, if the Parties are unable to agree an appointment, either of them may request the appointment to be made by the chairman of the Royal Institution of Chartered Surveyors in Northern Ireland (“Chairman”).

  - 7.7	An Independent Surveyor must be a Fellow of the Royal Institution of Chartered Surveyors, with at least ten years’ experience including experience in development of the same type as the Scheme.

  - 7.8	If an Independent Surveyor appointed dies or becomes unwilling or incapable of acting or does not deliver the decision within the time required by this Clause, then:-

    - 7.8.1	either the Developer or Alpha may apply to the Chairman to discharge the appointed Independent Surveyor and to appoint a replacement Independent Surveyor; and

    - 7.8.2	this Clause will apply in relation to the replacement Independent Surveyor as if it were the first appointed Independent Surveyor.

  - 7.9	The Independent Surveyor will act as an expert and will be required in respect of each condition within the Planning Appeal Decision to:-

    - 7.9.1	decide whether it is an Alpha's Unacceptable Condition; and

    - 7.9.2	prepare a written note of the decision and give a copy of the decision to both the Developer and Alpha within a maximum of 20 Working Days of the date of Independent Surveyor's appointment.

# 8. 	Grant of Satisfactory Planning Permission

  - 8.1	If the Planning Application or an appeal pursuant to Clause 7 results in the grant of Satisfactory Planning Permission for the Scheme or if the Independent Surveyor determines that no conditions to the Planning Appeal Decision are Alpha's Unacceptable Conditions then subject also to satisfaction of the other Conditions Precedent and to the provisions of Clause 8 hereof Alpha shall complete the purchase of the Site on the later of:

  - 8.1.1	(subject always to clause 8.3) the date that is three (3) months and one (1) week from the grant of such Satisfactory Planning Permission or the date of the Independent Surveyor's determination, whichever is the later (the "Satisfaction Date") unless within that three (3) months and one (1) week period there should be an application for leave to apply for judicial review of the Satisfactory Planning Permission lodged with the High Court in Belfast or any such other court of competent jurisdiction (collectively "Proceedings") which shall have formally been commenced or applied for in which case the Satisfaction Date shall be the date which is twelve (12) weeks after the date upon which the Satisfactory Planning Permission has been confirmed as valid and remains free from Alpha's Unacceptable Conditions and Developer’s Unacceptable Conditions consequent upon the determination of such Proceedings including no such appeals being lodged against any decision of the High Court or any such higher court relating to the application for leave to apply for judicial review or substantive hearing thereafter; and

  - 8.1.2	The date five (5) Working Days from the Unconditional Date.

  - 8.2	If there should be any application for leave to apply for judicial review of the Satisfactory Planning Permission then this Agreement may be rescinded by Alpha at its discretion by giving written notice to that effect to the Developer.

  - 8.3	Alpha may waive the three (3) month and one (1) week or twelve (12) calendar week delay in Clause 8.1 by giving written notice of waiver to the Developer, whereupon the Satisfaction Date shall occur on an earlier date as agreed by the Parties.

  - 8.4	If a Planning Permission is granted subject to one or more Alpha's Unacceptable Conditions, Alpha may waive its right to treat any of the conditions as Alpha’s Unacceptable Conditions by giving written notice to that effect to the Developer within ten (10) Working Days of the grant of Planning Permission.

  - 8.5	If a Planning Permission is granted subject to one or more Developer’s Unacceptable Conditions, the Developer may waive its right to treat any of the conditions as Developer’s Unacceptable Conditions by giving written notice to that effect to Alpha within ten (10) Working Days of the grant of Planning Permission.

  - 8.6	It is an essential condition of this Agreement that all Intellectual Property Licences be furnished to the prior to Planning Longstop Date.

# 9. 	Time Limits

  - 9.1	If Satisfactory Planning Permission has not issued by the Planning Longstop Date, Alpha shall have the right to rescind this Agreement by giving written notice to that effect to the Developer. Without prejudice to the right to rescind this Agreement, if at the Planning Longstop Date:-

    - 9.1.1	the Developer has appealed but the Planning Appeals Commission has not yet issued its recommendation, determination or decision or if such has been issued, the Local Planning Authority has not yet acted upon it; or

    - 9.1.2	the Planning Appeals Commission has issued its decision however it has been referred to an Independent Surveyor pursuant to Clause 7.1.1; or

    - 9.1.3	Alpha have served notice on the Developer pursuant to Clause 6.1.1 or 6.2 seeking that the Developer lodge an appeal; or

    - 9.1.4	In Alpha’s absolute discretion it is of the opinion that the Local Planning Authority will grant the Planning Permission; or

    - 9.1.5	Satisfactory Planning Permission has been granted, but the three (3) month and one (1) week period referred to in Clause 8.1 has not then expired, or Proceedings are then in progress.

Alpha may at its discretion and by confirmation in writing, postpone its right to rescind this Agreement until the Extended Planning Longstop Date. The Conditions Precedent Longstop Date will be extended by the same period as a result of the postponement of the Planning Longstop Date to the Extended Planning Longstop Date.

# 10. 	Costs of Planning Application

  - 10.1	All costs in connection with any Planning Application (or any appeal in relation to it or any referral to an Independent Surveyor) shall be borne by the Developer.

  - 10.2	The Developer will indemnify Alpha against all reasonable legal costs and disbursements properly incurred by Alpha in connection with the Planning Application (or any appeal in relation to it or any referral to an Independent Surveyor).

# 11. 	Notification of Planning Decisions

  - 11.1	The Developer will notify Alpha within five (5) Working Days of the receipt of any planning decision resulting from the Planning Application (whether original, amended or resubmitted), or the making of an appeal, whether issued by the Local Planning Authority, the Planning Appeals Commission or the Court.

  - 11.2	The Developer will promptly notify Alpha of any decision it may take as to the making, amending or resubmission of the Planning Application or the making of an appeal against a refusal of planning permission.

## 12.  	NIHE APPROVAL

  - 12.1	Subject to the Developer obtaining Design Approval, Alpha will make an application to NIHE for NIHE Approval at any time prior to the grant of Satisfactory Planning Condition and the Developer will provide all documentation / information required by NIHE as soon as reasonably possible after the submission of the Planning Application.

  - 12.2	The Developer will co-operate with Alpha and use all reasonable endeavours to assist Alpha in obtaining NIHE Approval.

  - 12.3	Alpha will within 5 Working Days after receiving it advise the Developer that it has obtained NIHE Approval.

  - 12.4	If NIHE Approval has not been granted by the Conditions Precedent Longstop Date or six (6) months after the date of Satisfactory Planning Permission, whichever is later, Alpha may rescind this Agreement by notifying the Developer in writing.

- Vacant Possession & Title

The Site is sold by the Landowner with vacant possession. The Landowner’s title to the Site has been deduced to Alpha’s Solicitors before the date of this Agreement. Alpha is deemed to have full knowledge of the Landowner’s title and is not entitled to raise any objection enquiry or requisition in relation to it save in relation to matters arising between the date of this Agreement and the Site Completion Date.

- THE SITE VALUE AND Delivery of the SITE TRANSFER

14.1	On the Site Completion Date, Alpha shall pay the Site Value by way of telegraphic transfer or other direct transfer to the client account of the Landowner’s Solicitors or such other account or accounts in the United Kingdom as the Landowner shall require in writing.

14.2	Immediately following the payment of Site Value due in accordance with clause 14.1 the Landowner shall deliver to Alpha:

14.2.1	the duly executed Site Transfer; and

14.2.2	duly executed releases of any Charges in so far as they relate to the Site.

14.3	On the Site Completion Date the Landowner and/or the Developer shall convey, transfer and assign to Alpha all interest, rights and title to the plans and drawings submitted in connection with the Planning Permission and any property rights whatsoever it has in same.

14A Contract Addendum

14A.1	The Developer shall at all times comply at their own cost with the Contract Addendum and indemnify Alpha against any failure to do so;

15.	PROJECT EXECUTION PLAN

15.1	Within fifteen (15) Working Days of the later of the date on which Satisfactory Planning Permission is granted or of the date of this Agreement, the Developer shall prepare and submit to Alpha a draft Project Execution Plan.

15.2	In preparing the draft Project Execution Plan, the Developer shall:

15.2.1	ensure the draft Project Execution Plan complies with the Employer’s Requirements

15.2.2	address (without limitation):

the phasing and location of the Dwellings to be built;

the timetable for carrying out the Developer’s Works;

the Developer’s team structure and how it fits in the Developer’s organisation structure;

communications including, but not limited to, a communications plan for the Scheme;

a proposed mechanism for the preparation and issue of progress reports;

financial methodology including projected cash flows;

project plan for Site operations;

project controls;

technical, financial and quality assurance information (including inter alia health and safety files in accordance with the Regulations);

completion plan including handover procedures (in accordance with Alpha’s Policies) and defects management plan including response times;

the Target Date; and

the Longstop Date.

15.3	Within fifteen (15) Working Days after Alpha receives the draft Project Execution Plan, Alpha shall notify the Developer in writing whether Alpha approves the draft Project Execution Plan. Alpha shall give reasons if it does not approve the draft Project Execution Plan.

15.4	If Alpha does not approve the draft Project Execution Plan, the Developer shall within ten (10) Working Days of receipt of such notification by Alpha submit a revised draft Project Execution Plan to Alpha for approval (such approval not to be unreasonably withheld or delayed). The procedure set out in clause 15.3 shall apply to any revised draft Project Execution Plan as if it were the first draft Project Execution Plan. The Developer shall continue to submit revised drafts of the Project Execution Plan to Alpha for approval until a Project Execution Plan is approved in writing by Alpha.

15.5	From time to time, if reasonably required by Alpha, the Developer shall prepare variations to the Project Execution Plan in writing for approval by Alpha (such approval not to be unreasonably withheld or delayed).

16.	THE DEVELOPER’S WORKS

16.1	Commencement and Completion of the Developer’s Works

Within fifteen (15) Working Days following the completion of the Site Transfer, the Developer shall, subject to the provisions of this Agreement and in accordance with the Employer’s Requirements, the Specification, the Project Execution Plan, and the Developer’s tender submitted in connection with this Agreement (and in the event of conflict, in the order of priority listed), at its own cost and as quickly as reasonably practicable carry out and complete or procure to be carried out and completed by no later than the Longstop Date the Developer’s Works, in a good and workmanlike manner, regularly and diligently, with good new sound and suitable materials (without using or specifying for use any Deleterious Materials) of their every kind in accordance with the Requisite Consents, good building and design practice, relevant international and British Standards Institution Standards or Codes of Practice and the Regulations, so as to ensure that Alpha is not subject to material liabilities in respect of the condition of the Scheme pursuant to laws relating to the environment (including, without limitation, common law, domestic legislation and any order or regulation made pursuant to such legislation, bylaws and judgments or orders of any court or administrative tribunal) applicable at the date of this Agreement also ensuring that there is a proper physical connection to mains services of all drains, pipes, cables, wires and other conducting media to be constructed or placed in or upon the Site, subject only to an application of the user of such services for the commencement of supply.

- 16.1.A	To the exclusion of all other terms of this Development Agreement, the Developer acknowledges and accepts all risk associated with the ground conditions and/or physical conditions of the Site including but not limited to any contamination, manmade or otherwise, found within the Site.  The Agreed Fixed Price shall not be adjusted for any reason in relation to the ground conditions and/or physical conditions of the Site.  The Developer shall ensure that good industry practice is used with respect to the disposal of any soils and/or other materials from the site and the Developer shall bear any and all costs with respect to same.  Similarly, if any dewatering is required for any sub-surface construction (including but not limited to basement construction), the Developer shall use, and be responsible for the costs of, appropriate groundwater testing and monitoring prior to disposal.

- 16.1.B	If the Completion Date has not occurred by the Target Date, the Developer shall pay to Alpha Liquidated Damages, which shall be paid weekly in arrears, on written demand, as a fair and reasonable estimate of Alpha’s loss relating to delay in the occurrence of the Completion Date, from the Target until the Completion Certificate Date.

16.2	Prior to Commencement of the Developer’s Works

16.2.1	The Developer will before the Commencement of the Developer’s Works:-

16.2.1.1	produce evidence that the Developer and any Contractor is registered with NHBC and has been offered and obtained the offer of cover for the Cover Note and shall hand over all documentation in relation to same to Alpha upon request and for the avoidance of doubt it is agreed that the Developer and/or Contractor will through the period when it is carrying out the Developer’s Works remain registered with NHBC or such other provider of the Cover Note.

16.2.1.2	take all reasonable steps to be reasonably satisfied that each member of the Professional Team is suitable and competent having regards to its responsibilities in relation to the Developer, the Building Contract and the Construction (Design and Management) Regulations (Northern Ireland) 2016.

16.2.1.3	submit details of the proposed terms of any professional appointment of each member of the Professional Team to Alpha and supply certified copies of the actual terms of each such professional appointment to Alpha.

16.2.1.4	to as soon as practicably possible appoint the members of the Professional Team.

16.3	Licence to carry out Developer’s Works

From and including the date of the delivery of the Site Transfer in accordance with clause 16.2 until the earlier of (i) the Completion Date; and (ii) termination of this Agreement, Alpha shall afford the Developer its servants agents and licencees (including without limitation the Professional Team and any Contractor) full and unfettered licence to the extent necessary to enter and remain on the Site for the purpose of fulfilling its obligations under this Agreement.

16.3	Alpha to be informed

The Developer shall keep Alpha or procure that Alpha and the Employer’s Agent is kept fully informed at all times of the progress of the Developer’s Works and of any material delay or potential material delay to or proposed acceleration of completion of the Developer’s Works and shall supply to Alpha:-

16.3.1	prior to commencement of the Developer’s Works a copy of the initial programme and any proposed variations as may from time to time occur; and

16.3.2	on request such information as Alpha may reasonably require to satisfy itself that the Developer is complying with its obligations under this Agreement.

16.3.3	all IP Licences

16.4	Inspection of the Developer’s Works

16.4.1	The Employer’s Agent and Alpha’s Building Inspector may:

- (a)	at any reasonable time on prior appointment with the Developer enter upon the Site in order to view the state and progress of the Developer’s Works and to carry out any reasonable tests of materials and/or workmanship;

- (b)	within five (5) Working Days after any such entry serve on the Project Manager a notice (“Defects Notice”) specifying any respects in which the Employer’s Agent considers that any part of the Developer’s Works are not being or have not been carried out in accordance with this Agreement; and

- (c)	attend any site meetings in connection with the Developer’s Works and the Employer’s Agent shall be furnished with the notice and agenda for such meeting at the same time as this is issued to those others entitled to attend and shall be furnished with the minutes of any site meeting.

16.4.2	The Developer shall have due regard for and shall procure that the Project Manager shall have due regard to the contents of any Defects Notice and if any inspection or tests reveal that any materials and/or workmanship are not in accordance with the Employer’s Requirements and/or the Specification and/or this Agreement, the Developer shall cause the defective materials to be replaced and/or the defective work to be made good in which event the Developer shall then be liable to pay to Alpha on demand all proper and reasonable fees incurred by Alpha in connection with such inspection and tests and in connection with the approval and supervision of all remedial work, provided if such fees and expenditure are not paid within ten (10) Working Days of written demand they shall be treated as a debt payable by the Developer to Alpha.

16.5	Warranties and Other Documents

On or before the Completion Date the Developer will deliver or procure the delivery to Alpha of:

16.5.1	two complete sets of “as-built” plans and two service manuals of the Developer’s Works as completed in paper format and in digital format;

16.5.2	all documents reasonably required to facilitate a sale or lease including (but not limited to) the originals of the following for each relevant Dwelling:

- (a)	a building control final completion certificate;

- (b)	(if applicable) the Road Bond and Private Streets Agreements from the publicly adopted road to each respective Dwelling;

- (c)	(if applicable) either Article 161 or 163 Water and Sewerage Agreement;

- (d)	an Energy Performance Certificate;

- (e)	a certificate under the National House Building Council Buildmark scheme (or other similar scheme approved by Alpha);

- (f)	all testing/compliance certificates for any oil, gas, electrical and solid fuel heating installations (including without limitation fire/smoke alarms test certificates); and

- (g)	any manuals/guarantees for white goods and/or such other fittings or appliances fixed to or installed in each Dwelling; and

16.5.3	all other relevant documentation and approvals in respect of the Developer’s Works then in the possession or control of the Developer including Collateral Warranties referred to in clause 16.6 for the benefit of Alpha.

To the extent that any of the documentation and/or the approvals referred to in clause 16.6 are not in the possession or control of the Developer at the Completion Date the Developer shall use all reasonable endeavours to obtain them as same as reasonably practicable thereafter and shall deliver them to Alpha immediately upon receipt.

16.6	Collateral Warranties

16.6.1	The Developer shall ensure, within ten (10) Working Days of the date of this Agreement (or, if later, within ten (10) Working Days of the appointment of the relevant member of the Design Team or of a Contractor), that each member of the Design Team and each Contractor has executed and delivered a deed of Collateral Warranty in favour of Alpha in the form set out in Schedule 6 Part I, Part II and Part III hereto.

16.6.2	As soon as practicable following written request from Alpha, the Developer shall procure a deed of Collateral Warranty from any member of the Design Team and any Contractor then appointed in favour of any Funder in the form set out in Schedule 6 hereto.

16.6.3	If any deed of Collateral Warranty provided by a member of the Design Team or a Contractor requires execution by the Developer, the Developer shall execute and deliver the Collateral Warranty to Alpha within the time limits set out in this clause. If the Developer does not execute and deliver a deed of Collateral Warranty in accordance with this Agreement, Alpha may execute that deed on the Developer’s behalf, and the Developer hereby appoints Alpha as the Developer’s attorney for the purpose of executing that deed and the Developer agrees to ratify and confirm any act done by Alpha pursuant to this power of attorney and agrees that this power is irrevocable pursuant to section 3, Powers of Attorney Act (Northern Ireland) 1971.

16.7	If there is any delay in completing the Developer’s Works arising from the act or default of Alpha or the Employer’s Agent, the Target Date and the Longstop Date shall be extended by such period as the Architect acting reasonably shall certify as being reasonable and proper in light of the reasons for the delay.

16.8	Where completion of the Developer’s Works is delayed or likely to be delayed due to any event or cause that is beyond the Developer’s reasonable control and which have not occurred by reason of the act or default of the Developer, including but not limited to Force Majeure, the Target Date and Longstop Date shall both be extended by such period certified by the Architect (acting reasonably) as being fair and reasonable having regard to the delay in question.

17.	HEALTH & SAFETY

The Developer will in respect of the Developer’s Works so far as is possible under the Regulations assume the obligations on behalf of Alpha as the client for the purposes of the Regulations and will ensure that the Principal Designer carries out his duties in accordance with the Regulations and the Developer will discharge its obligations in accordance with the Regulations, and in the course of carrying out those obligations the Developer shall procure and deliver to Alpha as soon as practicable after each Completion Date (but not later than one (1) week after that date) in a format approved by Alpha (acting reasonably) a copy of the health and safety file prepared, maintained and completed as required by the Regulations.

18.	DEVELOPER’S VARIATIONS TO THE SPECIFICATION

The Developer may not without obtaining the prior written approval of Alpha (approval not to be unreasonably withheld or delayed) make variations or alterations to the materials specified in the Specification and/or Employer’s Requirements, save where any substitute materials used are of an equal quality and suitability to those originally specified.

19.	Alpha’S CHANGES

19.1	For the purposes of this Agreement “Alpha’s Changes” means any works requested in writing by Alpha additional to or in modification of the Developer’s Works.

19.2	Alpha may, no later than eight (8) weeks prior to the Completion Date, request the Developer’s consent to incorporate Alpha’s Changes and such consent shall not be unreasonably withheld or delayed (save in respect of any changes which in the Developer’s reasonable opinion are likely to materially and adversely impact on the remainder of the Scheme in which case the Developer shall have discretion whether to consent or not and subject always to clause 19.3).

19.3	The Developer shall be entitled to withhold consent to a request for Alpha’s Changes unless Alpha agrees to meet any reasonable and proper increase in the Agreed Fixed Price resulting therefrom in full (as certified by the Developer).

19.4	If Alpha is required to pay for such increase in the Agreed Fixed Price resulting from Alpha’s Changes under clause 19.3 Alpha will pay the reasonable and proper costs of Alpha’s Changes as they are incurred.

19.5	Save as a result of the incorporation of any Alpha’s Changes or as a result of the provisions of clause 16, the Developer will not be entitled to payment of any increase in the Agreed Fixed Price arising as a result of any other event, cause or matter whatsoever (including without limitation any event, cause or matter arising from any act or omission of Alpha).

19.6	If the Developer incorporates Alpha’s Changes pursuant to this clause which, in the reasonable opinion of the Developer and/or Architect, will cause delay in the completion of the Developer’s Works, the Target Date and the Longstop Date shall be extended by such reasonable period equal to the length of anticipated delay, as notified by the Developer to Alpha.

19.7	Any dispute in connection with this clause 19 shall be referred to determination under the Dispute Resolution Procedure.

20.	ENFORCEMENT

20.1	The Developer shall take all steps necessary with due diligence to procure the performance and observance of the obligations and duties of each member of the Professional Team and of any Contractor.

20.2	The Developer shall not at any time waive, release, vary nor estop itself from enforcing or seeking redress for any such obligation or duty without the consent of Alpha (such consent not to be unreasonably withheld or delayed). The Developer shall immediately notify Alpha if the Developer believes that the member of the Professional Team may be intending to rescind its contract or professional appointment.

20.3	The Developer shall not do anything nor omit to do anything which (apart from the provisions of any Collateral Warranty) would entitle a member of the Professional Team to treat its contract for services or any Contractor to treat its contract for works in connection with the Developer’s Works as terminated by breach.

20.4	If the Developer, with the consent of Alpha, terminates the engagement of any member of the Professional Team or of any Contractor, the Developer shall engage a replacement person or firm as a substitute member of the Professional Team or Contractor (in accordance with the requirements stipulated in the pre-qualification questionnaire tender documentation issued by Alpha in connection with the appointment of the Developer), subject to obtaining the approval of Alpha and shall secure a Collateral Warranty from that substitute promptly.

21.	CERTIFICATES

21.1	Inspections, Representations etc

The Developer shall procure that:

21.1.1	Alpha shall be given not less than ten (10) Working Days’ notice of the intention of the Project Manager and/or other member of the Professional Team to inspect the Developer’s Works with a view to the issue of any of the Certificates;

21.1.2	each such notice shall state the proposed date and time of such inspection;

21.2.3	the Employer’s Agent and Alpha’s Building Inspector shall be permitted to accompany the Project Manager or other member of the Professional Team as the case may be on the inspections prior to the issue of any of the Certificates (and in the case of the Certificate of Completion, the Employer’s Agent shall accompany the Project Manager or other member of the Professional Team as the case may be);

21.1.4	the Project Manager or other member of the Professional Team as the case may be shall take proper account of any representations made by the Employer’s Agent and Alpha’s Building Inspector during such inspections or made no later than three (3) Working Days after such inspection in relation to the intended issue of a Certificate as to either (i) the state and condition of the Developer’s Works or (ii) whether the Developer’s Works or any part of them have not been properly completed; and

21.1.5	a Certificate (together with any schedule listing all minor omissions, imperfections, defects and other faults discovered in the course of such inspections) shall be issued if (and only if) as appropriate the Project Manager and/or Architect as the case may be or, in the case of the Certificate of Completion, the Employer’s Agent is satisfied (acting reasonably at all times) that completion of the relevant part of the Developer’s Works has been achieved or the relevant Defects have been corrected as the case may be.

21.2	Objection Notices

Alpha may at any time before the expiry of five (5) Working Days after the issue of a Certificate serve on the Developer an objection notice specifying all material outstanding works, defects or omissions from the Developer’s Works which Alpha properly and reasonably considers should be completed or remedied (“the Objection Notice”).

21.3	Endeavour to Resolve

The Developer and Alpha shall endeavour to agree what (if any) action should be taken to resolve the objections set out in any Objection Notice, but if they cannot or do not do so the provisions of clause 21.4 below shall apply.

21.4	Disputes

If Alpha shall serve an Objection Notice and the Developer shall consider that the works specified in the Objection Notice have been properly completed in accordance with the Developer’s obligations herein contained the dispute shall be referred to the Expert in accordance with the following provisions:

21.4.1	The Expert shall determine whether the works specified in the Objection Notice have been properly completed in accordance with the Developer’s obligations herein contained and if not so completed shall determine what works remains outstanding or as the case may be what remedial steps are required to be undertaken by the Developer in order to comply with the Developer’s obligations herein contained PROVIDED THAT in the event of the Expert determining the works specified in the Objection Notice have been properly completed in accordance with the Developer’s obligations herein contained Alpha shall pay interest at the Agreed Rate on any monies due by Alpha the payment of which has been delayed by the Objection Notice.

21.4.2	The Parties shall be obliged to submit their respective views in connection with the dispute in writing within five (5) Working Days of the Expert being appointed and the Expert shall be obliged to produce his decision within five (5) Working Days thereafter.

21.4.3	The decision of the Expert shall be made as an expert and not as an arbitrator and such decision shall be final and binding upon the Parties hereto (save in the case of manifest error or fraud).

21.4.4	The cost of any reference to the Expert in connection with any dispute shall be within the award of the Expert.

21.5	Remedial measures

The Developer shall take whatever action may be required in consequence of the resolution of the Objection Notice.

22.	DEFECTS

22.1	Inspection and Delivery of Schedule

Alpha may:-

22.1.1	periodically inspect the Developer’s Works and prepare a schedule, or where appropriate, schedules of Defects itemising Defects, shrinkages and other faults due to materials or workmanship not in accordance with the Employer’s Requirements, the Specification or due to frost occurring before each relevant Completion Certificate Date; and

22.1.2	deliver a copy of each schedule referred to in 22.1.1. above to the Developer as soon as reasonably practicable (but in any event not less than twenty (20) Working Days before the Defects Date) in order for the Developer to consider all schedules.

22.2	Correcting Defects notified after Completion but before the Defects Date

22.2.1	The Developer shall comply with the obligations under this Agreement in relation to Defects in the period from each Completion Certificate Date (as certified by the Architect) until such time as the relevant Defects Certificate is issued.

22.2.2	The Developer shall give the following priorities to the making good of Defects prior to the Defects Date in accordance with any schedule of Defects issued by Alpha to the Developer:

22.2.2.1	Emergency (to be completed within 4 hours of the Developer being notified): Repairs and defects which immediately endanger the health, safety and welfare of tenants or the general public, or could cause serious damage to the fabric of the building;

22.2.2.2	Urgent (to be completed within 4 Working Days of the Developer being notified): Repairs affecting the comfort and convenience of the tenants; and

22.2.2.3	Routine (to be completed within 20 Working Days of the Developer being notified): Repairs or faults which do not cause major inconvenience to tenants or damage the fabric of the building

PROVIDED ALWAYS that Alpha reserves the right in the event of any of the above time periods being exceeded by the Developer to execute the works required, without prior notice needing to be given by Alpha to the Developer, in which case the cost of such work shall be charged to the Developer and paid by the Developer by Alpha within ten (10) Working Days of written demand.

22.3	Access by Developer to correct Defects

Alpha shall permit the Developer and all persons reasonably authorised by it at all reasonable times and by prior appointment to have access to the Site in order to correct any Defects and the Developer shall procure that such person so entering shall:

22.3.1	cause as little interference and disruption as is reasonably possible to Alpha and anyone in occupation of any part of the Site and any of the Dwellings;

22.3.2	make good as soon as reasonably practicable any damage thereby caused; and

22.3.3	at all times comply with the reasonable requirements of Alpha as to safety and security whilst at the Site.

Provided that if the Developer fails to comply with the obligation to correct any Defects, then Alpha may, after giving five (5) Working Days’ notice to the Developer, execute such remedial work as may be necessary in which event the cost of such work shall be paid by the Developer to Alpha within ten (10) Working Days of written demand.

22.4	Access by Developer to correct non-Defect rectifications

Alpha shall permit the Developer and all persons reasonably authorised by it at all reasonable times and by prior appointment to have access to the Site in order to carry out any rectifications, repairs, alterations, faults etc. which are not Defects but which require action by the Developer to facilitate completion of the Scheme in accordance with the Employer’s Requirements or the Specification before each relevant Completion Certificate Date, and each call-out in relation to same shall be charged by the Developer at an amount not exceeding £100 per call-out. For the avoidance of doubt, the rectification of any non-Defects which may be notified by Alpha to the Developer which are not required to facilitate completion of the Scheme in accordance with the Employer’s Requirements or the Specification shall be at Alpha’s cost and the Developer shall not be required to carry out any such rectification until the cost has been notified to and agreed by Alpha. The cost of any such rectification shall be in addition to the call-out fee payable to the Developer under this clause.

23. 	PERFORMANCE BOND OR INSURANCE POLICY

23.1 	Notwithstanding any other provision of this Agreement, it shall be a condition precedent to completion of this agreement he Developer’s entitlement to be paid any sum under this Agreement ] [that the Performance Bond or an Insurance Policy providing cover to a maximum level of [£       ] in the event of the insolvency of the Developer, as Alpha in its absolute discretion may choose shall have been completed and delivered to Alpha.

23.2 In the event that the Developer does not have in place the Performance Bond in accordance with clause 23 then Alpha may deduct the Retention which become due under this agreement and for the avoidance of doubt this is in addition to the Interim Payment Retention until the earlier of (i) the date the Developer provides the Performance Bond and (ii) the Completion Date.

24.	PAYMENT

24.1	Save as provided for in clause 19 or this clause 24, the Agreed Fixed Price shall not be increased in any way.

24.2	If Alpha is or at any time up to the final payment to be made by Alpha for the Developer’s Works becomes a “contractor” for the purposes of the CIS, its obligation to make any payment for the Developer’s Works is subject to the provisions of the CIS.

24.3	Interim Payments as more particularly detailed in the Contract Sum Analysis shall be made by Alpha to the Developer in respect of the Developer’s Works, as follows:

24.3.1	in relation to each Interim Payment, the Developer shall make an application (“Interim Application”) to the Employer’s Agent providing a Stage Payment Certificate with each application and stating the sum that the Developer considers to be due to it and the basis upon which that sum has been calculated;

24.3.2	for the period up to the Completion Date, Interim Applications shall be made at monthly intervals, with the first Interim Application being one (1) month after the commencement by the Developer of the Developer’s Works, and thereafter on the same date in each month or on the nearest Working Day in that month;

24.3.3	after the Completion Date, the last Interim Application shall be made upon the issue of the last Defects Certificate;

24.3.4	the due date for each Interim Payment shall be the date of receipt by the Employer’s Agent of the relevant Interim Application;

24.3.5	the final date for payment of an Interim Payment shall be fourteen (14) days from receipt by Alpha of the Developer’s invoice referred to in clause 24.3.6 or clause 24.3.7;

24.3.6	not later than 5 days after the due date Alpha shall give a notice (“Payment Notice”) to the Developer in accordance with clause 24.4 and, subject to any Pay Less Notice given by or on behalf of Alpha under clause 24.3.8, the amount of the Interim Payment shall be the sum stated as due in the Payment Notice and the Developer shall send to Alpha an invoice for that amount as soon as possible thereafter;

24.3.7	if the Payment Notice is not given in accordance with clause 24.3.6, the amount of the Interim Payment to be made by Alpha shall, subject to any Pay Less Notice under clause 24.3.8, be the sum stated as due in the Interim Application and the Developer shall send to Alpha an invoice for that amount;

24.3.8	if Alpha intends to pay less than the sum stated as due from it in the Payment Notice or Interim Application, as the case may be, it shall not later than one (1) day before the final date for payment give the Developer notice of that intention in accordance with clause 24.5 (“Pay Less Notice”) and where a Pay Less Notice is given, the payment to be made on or before the final date for payment shall not be less than the amount stated as due in the notice;

24.3.9	if Alpha fails to pay a sum, or any part of it, due to the Developer under this Agreement for the Developer’s Works by the final date for payment, Alpha shall, in addition to any unpaid amount that should properly have been paid, pay the Developer simple interest on that amount at the Agreed Rate for the period from the final date for payment until payment is made.

24.4.	Each Payment Notice under this Agreement shall specify the sum that the Party giving the notice considers to be or have been due at the due date in respect of the relevant payment and the basis on which that sum has been calculated.

24.5.	A Pay Less Notice:

24.5.1	(where it is to be given by Alpha) shall specify both the sum that Alpha considers to be due to the Developer at the date the notice is given and the basis on which that sum has been calculated;

24.5.2	(where it is to be given by the Developer) shall specify both the sum that the Developer considers to be due to Alpha at the date the notice is given and the basis on which that sum has been calculated.

24.6	A Payment Notice or a Pay Less Notice to be given by Alpha may be given on its behalf by the Employer’s Agent or by any other person who Alpha notifies the Developer as being authorised to do so.

24.7	In relation to the requirements for the giving of notices under this clause 24 and the submission of a Final Statement, it is immaterial that the amount then considered to be due may be zero.

24.8	Following the Completion Date the Developer shall submit the Final Statement to the Employer’s Agent and supply him such supporting documents he may reasonably require including inter alia adoption certificates in relation to roads and water and sewerage services if same have not already been provided.

24.9	The Final Statement shall set out any adjustments to the Agreed Fixed Price as are permitted under this Agreement, the Agreed Fixed Price as so adjusted and the sum of the amounts already paid by Alpha to the Developer for the Developer’s Works.   The final payment shall be the difference (if any) between the Agreed Fixed Price as so adjusted and the sum of the amounts already paid by Alpha to the Developer for the Developer’s Works, which shall be shown as a balance due to the Developer from Alpha or to Alpha from the Developer, as the case may be.  The Final Statement shall state the basis on which that amount has been calculated, including details of all such adjustments.

24.10	If the Developer does not submit the Final Statement within three (3) months of the Completion Date, Alpha may on or after the expiry of that period give the Developer notice that unless that statement is submitted within two (2) months from the date of the notice Alpha may itself issue a final statement in lieu of that from the Developer.  Unless the Developer submits the Final Statement prior to Alpha exercising that right, Alpha may at any time after the two (2) month notice period issue a final statement to the Developer (“Alpha’s Final Statement”) in the form and with the details required by clause 24.9, so far as Alpha, on the information in its possession, is reasonably able to do so.

24.11	The due date for the final payment shall be the date one (1) month after whichever of the following occurs:

24.11.1	the date of the issue of the last Defects Certificate; or

24.11.2	the date of submission to the other Party of the Final Statement or, if issued first, Alpha’s Final Statement (“the relevant statement”).

24.12	The final date for payment of the final payment shall be fourteen (14) days from the due date.  Not later than five (5) days after the due date, the Party by whom the relevant statement shows the final payment as payable (“payer”) shall give a Payment Notice to the other Party with the details specified in clause 24.4.  Subject to any Pay Less Notice under clause 24.13, the payment to be made on or before the final date for payment shall be the sum stated in the Payment Notice or, if such notice is not given, the balance stated in the relevant statement.

24.13	If the payer intends to pay less than the sum stated in the Payment Notice for the final payment or, in default of such notice, less than the amount stated in the relevant statement, the payer shall not later than one (1) day before the final date for payment give the other Party a Pay Less Notice in accordance with clause 24.5.  Where such a Pay Less Notice is given, the payment to be made on or before the final date for payment shall not be less than the amount stated as due in the notice.

24.14	If the payer fails to pay the final payment, or any part of it, by the final date for payment, the payer shall, in addition to any unpaid amount that should properly have been paid, pay the other Party simple interest on that amount at the Agreed Rate for the period from the final date for payment until payment is made.

24.15	The Gross Valuation shall be [£       ] (which for the avoidance of doubt includes the Agreed Fixed Price and the Site Value).

24.16	Notwithstanding any other provision, Alpha may deduct and retain from each Interim Payment the Interim Payment Retention.

24.17	Forty percent (40%) of the total sum of the Interim Payment Retention held by Alpha shall be paid to the Developer on the Completion Date together with One hundred percent (100%) of the Retention.

24.18	The remaining sixty percent (60%) of the total sum of the Interim Payment Retentions held by Alpha shall be paid to the Developer on the Defects Date.

25.	DEVELOPER’S INSURANCE

25.1	Insurance of the Developer’s Works

From the date of commencement of the Developer’s Works until the Completion Date the Developer shall maintain an Insurance Policy covering the Developer’s Works and the Site against all risks usually covered by a “Contractor’s All Risks” policy in an amount equal to the full cost of reinstating the Developer’s Works (or such part of the Developer’s Works as shall from time to time have been carried out plus at least 15% to cover professional fees) at a level to be approved by Alpha (such approval not be unreasonably withheld or delayed) and shall use reasonable endeavours to procure that the Insurance Policy is in the joint names of the Developer and Alpha (and such other persons or parties as Alpha may reasonably notify to the Developer).

25.2	Destruction of Developer’s Works

The Developer shall notify Alpha promptly upon the occurrence of any material damage to or material destruction of the Developer’s Works (whether or not caused by any of the risks insured against) and in any such case shall use all insurance monies received to rebuild repair and otherwise reinstate the Developer’s Works without delay in accordance with the provisions of this Agreement.  If the proceeds of the insurance are insufficient to cover the cost of reinstatement then the Developer will make good any deficiency out of its own monies.

25.3	Public Liability Insurance

From the date of commencement of the Developer’s Works until the Completion Date the Developer shall maintain an Insurance Policy providing cover of at least ten million pounds (£10,000,000) for any one occurrence, or series of occurrences to cover liability for loss of or damage to property (other than the Developer’s Works) and liability for bodily injury to or death of a person (not an employee of the Developer) caused by activity in connection with this Agreement and shall use reasonable endeavours to procure that the Insurance Policy is in the joint names of the Developer and Alpha (and such other persons or parties as Alpha may reasonably notify to the Developer).

25.4	Liability Insurance

From the date of commencement of the Developer’s Works until the Completion Date the Developer shall maintain an Insurance Policy providing cover of at least ten million pounds (£10,000,000) for any one occurrence, or series of occurrences to cover liability for bodily injury to or death of employees of the Developer arising out of and in the course of their employment in connection with this Agreement and shall use reasonable endeavours to procure that the Insurance Policy is in the joint names of the Developer and Alpha (and such other persons or parties as Alpha may reasonably notify to the Developer).

25.5	Professional Indemnity Insurance

25.5.1	The Developer shall maintain an Insurance Policy providing professional indemnity cover for an amount of at least £5,000,000 for any one occurrence, or series of occurrences, arising out of any one event for a period beginning on the date of this Agreement and ending twelve (12) years after the Completion Date, provided that such insurance is available at commercially reasonable rates.  The Developer shall maintain that Insurance Policy on terms that do not require the Developer to discharge any liability before being entitled to recover from the insurers and that would not adversely affect the rights of any person to recover from the insurers under the Third Parties (Rights Against Insurers) Act 2010.

25.5.2	Any increased or additional premium required by insurers for the insurance referred to in this clause 25.5 because of the Developer’s claims record or other acts, omissions, matters or things particular to the Developer shall be deemed to be within commercially reasonable rates.

25.5.3	The Developer shall at Alpha’s request send Alpha evidence that the Developer’s insurance referred to in this clause 25.5 is in force, including, if required by Alpha, an original letter from the Developer’s insurers or brokers confirming the Developer’s then current professional indemnity insurance and that the premiums for that insurance have been paid in full at the date of that letter.

25.6	Neighbouring Property Insurance

25.6.1	If deemed applicable by the Developer it shall take out and maintain an Insurance Policy for an amount at the required level pre-approved by Alpha in respect of any expense, liability, loss. claim or proceedings which Alpha may incur or sustain by reason of injury or damage to any property caused by collapse, subsidence, heave, vibration, weakening or removal of support or lowering of ground water arising out of or in the course of or by reason of the Developer’s Works, excluding injury or damage:

(a)	which is covered by any Insurance Policy maintained under clause 25.3 and/or clause 25.5;

(b)	to the Developer’s Works except in so far as the Developer’s Works have been the subject of a Certificate of Completion;

(c)	which arises from any consequences of war, invasion, act of foreign enemy, hostilities (whether war is declared or not), civil war, rebellion or revolution, insurrection or military or usurped power;

(d)	which is directly or indirectly caused by or arises out of pollution or contamination of buildings or other structures or of water or land or the atmosphere happening during the period of insurance, save that this exception shall not apply in respect of pollution or contamination caused by a sudden identifiable, unintended and unexpected incident which take place in its entirety at a specific moment in time and place during the period of insurance (all pollution or contamination which arises out of one incident being considered for the purpose of this insurance to have occurred at the time such incident takes place); or

(e)	which results in any costs or expenses being incurred by Alpha or in any other sums being payable by Alpha in respect of damages for breach of contract, except to the extent that such costs or expenses or damages would have attached in the absence of any contract,

26.	ASSIGNMENT

The Developer shall not assign charge underlet part with dispose of or otherwise deal with its rights obligations or interests under this Agreement without first obtaining the written consent of Alpha (not to be unreasonably withheld or delayed).

27.	NOTICES

27.1	General

27.1.1	Any demand notice or other communication or document to be made or delivered under this Agreement shall be made or delivered in writing and shall be treated as having been served if served in accordance with this clause 27.

27.1.2	Each demand notice communication or other document to be made on or delivered to any Party may (unless that Party has by fifteen (15) Working Days’ written notice to the other specified another address) be made or delivered to that Party at its registered office.

27.2	Mode of Service

27.2.1	Service of any demand notice or other communication or document to be made or delivered under this Agreement may be made:

27.2.2	by leaving it at the address for service referred to in clause 27.1.2; or

27.2.3	by sending it by prepaid first class letter (or by airmail if to or from an address outside the United Kingdom) through the post to the address for service referred to in clause 27.1.2.

27.3	Deemed service

27.3.1	Any notice demand or other communication or document shall be served or treated as served at the following times:

27.3.2	in the case of service personally in accordance with clause 27.2.2 at the time of such service; and

27.3.3	in the case of service by post in accordance with clause 27.2.3 at 9.00 a.m. on the Working Day next following the day on which it was posted (or if such day is not a Working Day on the Working Day next following) or in the case of service to or from an address outside the United Kingdom at 9.00 a.m. on the fourth (4th) day following the day on which it was posted.

27.4	Proof of service

In proving service of any demand notice communication or other document served by post it shall be sufficient to prove that such demand notice communication or other document was correctly addressed full postage paid and posted and in the case of personal service an affidavit of service shall be sworn by the person charged with such personal service and be delivered to the party on whom such service was made.

28.	THE DISPUTE RESOLUTION PROCEDURE

28.1	If a dispute (meaning for the purposes of the Dispute Resolution Procedure, any dispute or difference between the Parties relating to their rights or obligations under this Agreement), other than a dispute to which clause 21.4 applies, arises in relation to any aspect of this Agreement, the Developer and Alpha shall consult (but subject always to the ability of either Party to refer a dispute at any time to an Expert for determination in accordance with this clause) in good faith in an attempt to come to an agreement in relation to the disputed matter.

28.2	Either Party may give notice at any time of its intention to refer a dispute to an Expert for determination (“the Notice of Dispute”).  The Party referring a dispute to an Expert for determination shall be referred to as the Referring Party. The Party upon whom the Notice of Dispute is served shall be referred to as the Respondent. The Notice of Dispute shall include a brief statement of the issue or issues which it is desired to refer to the Expert and the redress sought.

28.3	The Parties may, within two (2) Working Days after the giving of the Notice of Dispute, agree upon an Expert.

28.4	If the Developer and Alpha are unable to agree on the identity of the Expert within two (2) Working Days of the giving of the Notice of Dispute, the Chairman for the time being of the Chartered Institute of Arbitrators shall appoint (upon application by either party) such Expert.

28.5	No later than five (5) Working Days from the appointment of the Expert, the Referring Party shall serve a Notice (“the Referral Notice”) upon the Expert.  The Referral Notice shall contain the undernoted information:

- the name of the Expert;

- the names and details of the Parties;

- a description of the nature and extent of the dispute and how and when it arose; and

- the relief, recourse or remedies sought by the Referring Party.

28.6	The Referral Notice shall be accompanied by copies of any documentation (whether contractual or otherwise) or correspondence which the Referring Party wishes to rely upon.

28.7	Within three (3) Working Days of referral of the dispute to him the Expert shall require the Respondent to submit in writing its response to the Referral Notice. The Expert shall, in his absolute discretion, consider whether a hearing is necessary in order to resolve the dispute.

28.8	In any event, the Expert shall provide both Parties with his written decision on the dispute within fifteen (15) Working Days of the dispute having been referred to the Expert (or such other period as the Parties may agree).  The Expert shall state reasons for his decision.  The Expert decision shall in the absence of manifest error be final and binding on both Parties who shall forthwith give effect to the decision.

28.9	The Expert’s fees and expenses of any reference shall be borne as the Expert shall specify or, in default, equally by the Parties on a joint and several liability basis.   Each Party shall bear its own costs arising out of the reference, including legal costs and the costs and expenses of any witnesses.

28.10	Notwithstanding any other provision in this Agreement, to the extent that the Construction Contracts (Northern Ireland) Order 1997 (as amended by the Construction Contracts (Amendment) Act (Northern Ireland) 2011) applies to this Agreement, either Party has the right at any time to refer a dispute arising under the Agreement for adjudication.  Part 1 of the Schedule to the Scheme for Construction Contracts in Northern Ireland Regulations (Northern Ireland) 1999 (as amended by the Scheme for Construction Contracts (Amendment) Regulations (Northern Ireland) 2012) shall apply to any such adjudication.

29.	DEFAULT

29.1	If the Developer or Guarantor commits any material breach of, or fails to observe and perform any of its obligations under this Agreement and the Developer fails to remedy the breach within a reasonable time after notice in writing from Alpha requiring the Developer to do so and as a consequence Alpha incurs expenditure, then the Developer or the Guarantor shall pay such expenditure, together with interest at the Agreed Rate, to Alpha within ten (10) Working Days of written demand.

29.2	The Developer and/or the Guarantor shall be treated for the purposes of this Agreement (but without limitation) as being in default if:

29.2.1	it has not remedied in all material respects a material breach of or failure to observe and perform any of its obligations under this Agreement after notice in writing from Alpha allowing it reasonable time to do so which at the time of the giving of the notice was not of such seriousness as to fall within the next clause below;

29.2.2	it has committed a breach of or failed to observe and perform its obligations under this Agreement which are individually or cumulatively of such seriousness as to permit Alpha to treat this Agreement as repudiated by breach;

29.2.3	it fails to proceed diligently with the Developer’s Works;

29.2.4	it goes into liquidation (except by way of reconstruction or amalgamation not in circumstances of insolvency) or a receiver is appointed to the Developer’s undertaking or any of its assets or a petition is made for the appointment of an administrator to the Developer’s undertaking or any of its assets or any notice of intention to appoint an administrator, or the filing at court of the prescribed documents in connection with the appointment of an administrator;

29.2.5	it commits an act of bankruptcy or enters into any arrangement or composition or any voluntary arrangement or compromise for the benefit of its creditors or the comments of a voluntary winding up in respect of the Developer for the purposes of amalgamation or reconstruction of a solvent company or the making of a petition of a winding up order;

29.2.6	it becomes unable or ceases to pay its debts as they become due;

29.2.7	it has not satisfied the Conditions Precedent by the Conditions Precedent Longstop Date;

29.2.8	notwithstanding the Developer’s Works are not complete by the Longstop Date.

29.3	Notice of default

29.3.1	If an event of default occurs which is not capable of remedy then Alpha may serve a notice of termination on the Developer.

29.3.2	If an event of default occurs which is capable of remedy then Alpha may give to the Developer a notice specifying the default and if the Developer continues such default for (or does not diligently commence to remedy the default within) twenty (20) Working Days after receipt of such notice or subsequently repeats such default at any time (whether previously repeated or not) then Alpha may serve notice of termination on the Developer at any time thereafter.

29.4	Alpha’s take-over rights

29.4.1	Following an event of default and service of notice of termination, Alpha may assume the responsibility of the Developer to its exclusion for the continuation and completion of the Developer’s Works.

29.4.2	If Alpha so requires by giving written notice to the Developer:

- (a)	the Developer shall vacate the Site within ten (10) Working Days of service of notice by Alpha requiring it to do so;

- (b)	the Developer shall procure that the Professional Team, all Contractors and all sub-contractors vacate the Site;

- (c)	Alpha may novate the Professional Team and/or employ and pay other persons to carry out and complete the Developer’s Works; and

- (d)	Alpha may enter upon the Site and use all temporary buildings, plant, tools, equipment, goods and materials intended for delivery to or placed on or adjacent to the Site and may purchase all materials and goods necessary for the carrying out and completion of the Developer’s Works.

29.5	If required by written notice from Alpha, the Developer shall assign to Alpha without payment the benefit of any agreement for the supply of materials, services or goods or for the execution of any work for the purposes of the completion of the Developer’s Works and Alpha may pay any members of the Professional Team, any Contractor and any supplier and sub-contractor for any services rendered, for materials and goods delivered and for works executed for the purposes of this Agreement (whether before or after the date of termination).

29.6	The Developer shall procure the delivery to Alpha of all drawings, specifications and all other documents and correspondence relating to the Site and/or the Developer’s Works reasonably required by Alpha including any held by third parties and the Developer shall assign, or procure the assignment to Alpha, of the copyright in or licence to use any documents relating to the Site and/or the Developer’s Works.

29.7	If, following an event of default and service of notice of termination, the cost to Alpha of completing the Developer’s Works is greater than it would have been but for the event of default and/or the termination, the Developer shall indemnify and hold Alpha harmless against such additional cost.

30.	MISCELLANEOUS

30.1	Further Assurance

The Parties hereby agree to do or cause to be done all actions and things and enter into any deed or document either severally or jointly with third parties which Alpha may reasonably consider necessary or desirable to give effect to this Agreement.

30.2	No Merger

Notwithstanding the completion of the Site Transfer this Agreement shall continue and remain in full force and effect in regard to anything remaining to be done performed or observed under this Agreement on the part of any of the parties hereto.

30.3	Interest on late payments

If any sum which is properly payable by one Party (“the Payer”) to another (“the Payee”) pursuant to this Agreement is not paid on the final date for payment as specified in any clause of this Agreement the Payer shall in addition pay to the Payee interest thereon at the Agreed Rate from the final date for payment until the date of payment.

30.4	Exclusion of Representations

Each Party acknowledges that it is entering into this Agreement without reliance on any warranty representations undertaking or statement of fact or opinion made to it by or on behalf of any other Party in relation to the subject matter of this Agreement other than as expressly contained in this Agreement or which have been made in writing prior to the date of this Agreement in the written replies given by the Developer’s Solicitors to all those written enquiries raised by Alpha’s Solicitors in relation to the Site prior to the date hereof.

30.5	Law and jurisdiction

This Agreement shall be governed by and construed in accordance with the law of Northern Ireland and the Parties irrevocably agree that the courts of Northern Ireland shall have jurisdiction to hear and determine any suit action or proceeding and to settle any disputes which may arise out of or in connection with this Agreement and for such purposes the Parties irrevocably submit to the jurisdiction of such courts.

30.6	General

30.6.1	This Agreement (once concluded) and Collateral Warranty constitute the only legally binding agreements between the Parties relating to the Scheme and no variation of this Agreement shall be effective unless made in writing signed by or on behalf of the Parties and expressed to be such a variation.

30.6.2	This Agreement may be executed in two or more counterparts and execution by each of the Parties of any one of such counterparts will constitute due execution of this Agreement.

30.6.3	Any remedy or right conferred by this Agreement on Alpha and/or the Developer for breach of this Agreement shall be in addition to and without prejudice to all other rights and remedies available to it.

30.6.4	No failure or delay by Alpha or the Developer or time or indulgence given by either of them in or before exercising any remedy or right under or in relation to this Agreement shall operate as a waiver of the same nor shall any single or partial exercise of any remedy or right preclude any further exercise of the same or the exercise of any other remedy or right.

30.6.5	No waiver by the Parties of any requirement of this Agreement or any remedy or right under this Agreement shall have effect unless given by notice in writing effectively signed by or on behalf of such Party.

30.6.6	No waiver of any particular breach of the provisions of this Agreement shall operate as a waiver of any repetition of such breach.

30.6.7	Nothing in this Agreement is intended to confer on any person any right to enforce any term of this Agreement which that person would not have had, but for the Contracts (Rights of Third Parties) Act 1999.

30.6.8	In entering into this Agreement, the Parties each acknowledge and agree that all aspects of the relationship among the Parties contemplated by this Agreement, including the performance of all obligations under this Agreement, will be governed by the fundamental principle of good faith and fair dealing.

31.	DETERMINATION

31.1.	Determination

If either the Developer or Alpha becomes entitled to determine this Agreement the following provisions of this clause 31 shall apply:-

31.1.1	Such determination on the part of Alpha may be exercised by written notice to the Developer; and

31.1.2	Such determination on the part of the Developer may be exercised by written notice to Alpha.

31.2	Determination to be without prejudice

The determination of this Agreement shall be without prejudice to any rights or remedies which may have accrued to any Party in respect of any sum then due or any prior breach non-observance or non-performance of any of the terms of this Agreement

THIS AGREEMENT has been duly executed as a deed on behalf of the parties on the day and year stated above

Administrative Details

Address:

Telephone:

Fax:				  [			]

For the Attention of:

Alpha Housing

Address:			Alpha Housing,

Telephone:

Fax:

For the attention of:

SCHEDULE 1

EMPLOYER’S REQUIREMENTS

Contents

1	Introduction and Mission Statement

2	Reference Documents and Client Objectives

3     	 External Environment

4      	Building Elements

5      	Mechanical and Electrical Installations

6	Internal and External Finishes

7	Samples

8	Handover and Defects

Appendices

Documents to review and consideration should be given to new developments

Appendix 1	Fire Design

Appendix 2	Additional Cat1 requirements

- Introduction and Mission Statement

Alpha Housing actively promotes the development of high-quality accommodation, which is designed to ensure integration into existing communities. The aim of this document (and associated documents) is to assist, provide guidance and set out the requirements and expectations of Alpha Housing for all its future developments to ensure excellence, innovation in design, high standards of construction is maintained and to standardise specification where possible.

Alpha Housing’s mission is to provide homes and services that help people flourish.

Buildings should be designed to have a minimum of 60 years’ life. Buildings are to be designed using low maintenance components and to provide a “home for life” for tenants regardless of change in circumstances. Consideration should be given to future ease of maintenance with special regard to access and servicing/cleaning of all elements.

All designs should highlight elements, which promote energy conservation, sustainability, and ease of maintenance. Particular attention should be paid to innovative new concepts, which may improve the design, efficiency or low maintenance of the property and improve the quality of living of residents.

This document is not a comprehensive design manual, and it is the duty of Developers to ensure all properties/schemes comply fully with the latest version of the regulations and standards to be met. This Design Guide is to be read in conjunction with the Client Requirements Performance Specification.

- Reference Documents and Client Objectives

As a minimum all new build properties must meet the general design requirements and comply with the Department for Communities Housing Association Guide

- Meet Department for Communities (DFC) Procurement and Social Housing Design Specifications

- Comply with Planning Permission conditions and any Planning Advisory Clauses

- Creating Place achieving quality in residential environments

- Achieve Secure By Design Accreditation – GOLD STANDARD

- Achieve Lifetime Homes Standards as referenced in the DFC Guide

- Meet fully and comply with all relevant Building Regulations

- The specification as set out in this Alpha Design Guide, Performance Specification, and associated documents

- Encompass Happi design principles in respect of Cat 1 Accommodation

- Comply with all fire regulations and any recommendations outlined in the fire strategy

- Achieve all consents in relation to Dfi Roads Service including road

- Adoption standards and adoption of public street lighting,

- Achieve all consents in relation to NI Water; all individual connection points for the storm/foul and water supply for each property to be to adoption standards and brought out to the adopted road and connected to the mains/network.

- Achieve all consents in relation to telephone gas and electricity providers

- All materials to relevant British Standards or an equivalent international standard & Codes of Practice relevant to the construction works at the time of construction.

- Adhere to all Health & Safety regulations. Construction (Design & Management) NI 2016

- Geotechnical Certification & TAS Approvals

- Any relevant consent to discharge to be evidenced with NIEA

- Comply with all contamination remediation works required

- Comply with Structural Warranty providers Technical Guidance Brief

Key design aspects of this are as follows:

Note: The section below on Energy and Sustainability will be amended in line with the new building regulations and the DfC guide requirements at a future date.

Energy and Sustainability (Nearly Zero-Energy Buildings)

Improving our energy efficiency is a key strategic objective for Alpha and forms part of a global effort to combat climate change. In the UK, the Government has signed up to various international commitments to reduce its CO2 emissions as it works towards achieving its statutory target under the Climate Change Act (2008) of an 80% reduction in CO2 emissions by 2050 compared with 1990 levels. These commitments, in which the housing sector will play a vital role, include the Energy Performance of Buildings Directive 2010/31/EU (EPBD recast) which is the main legislative instrument, at European level, for improving the energy efficiency of buildings. A key element of the EPBD is its requirement for all new buildings, including housing, to be ‘Nearly Zero-Energy Buildings’

Increasing the energy efficiency of homes is a vital way of mitigating the effects of climate change, reducing fuel poverty, and improving health. To achieve Nearly Zero Carbon status, Developers will be required to design and construct dwellings to achieve the following technical requirements:

- SAP Band ‘A’ (92-100)

- A minimum Fabric Energy Efficiency Standard (FEES)* of:
- 39 kWh/m2/year for apartment blocks and mid-terrace homes
- 46 kWh/m2/year for end terrace, semi-detached and detached homes

* FEES is the calculated maximum space heating and cooling energy demand for low energy homes. This is the amount of energy which would normally be needed to maintain comfortable internal temperatures and in a dwelling, this can be influenced by:

- Building fabric U-values

- Thermal bridging

- Air permeability

- Thermal mass

- External heat gain (solar)

- Internal heat gains e.g., from people or equipment

A FEES criterion is included to ensure that a good minimum standard for fabric (the longest-lasting part of a home) will be embedded in new homes availing of the multiplier. It is measured in kWh/m2/yr. and is therefore not affected by carbon emission factors for different fuel types. FEES allows flexibility in design approach and can be achieved in a variety of ways with different combinations of materials or product specifications.

Alpha will be required to provide evidence of achieving the above technical requirements by submitting a copy of the As-Built SAP reports for each dwelling type to DPG at Practical Completion (3rd tranche) stage.

Secured By Design Gold Standard

Secured by Design is a national initiative endorsed by the Association of Chief Police Officers (ACPO) and has the backing of the Home Office Crime Reduction Unit. This scheme awards formal recognition to housing developments whose design and construction incorporates Crime Prevention through Environmental Design measures.

The PSNI Architectural Liaison Service should be consulted during the design stage and Secured by Design certification should be obtained for each development on completion.

Secured By Design is required on all Alpha Housing schemes (unless otherwise stipulated in writing).

http://www.securedbydesign.com/

Considerate Constructors Scheme

All Alpha Housing developments are to be registered with the Considerate Constructors scheme prior to going on site as per DFC Guide. Proof of registration to be forwarded to Alpha Housing for audit purposes.

www.ccscheme.org.uk

Lifetime Homes

All new build properties must be designed to current Lifetime Homes Standards and including DFC LTH Additional Requirements unless otherwise stipulated by Alpha Housing. All 16 Criteria must be achieved.

https://www.designingbuildings.co.uk

Client Objectives

- Deliver quality, innovative schemes/properties

- Aspires to embrace and incorporate the 10 design principles set out in the HAPPI Housing our Ageing Population: Panel for Innovation Report 2009:

- Generous / flexible space standards.

- Natural light (including circulation spaces).

- Avoidance of internal corridors and single aspect dwellings for light and ventilation.

- ‘Care ready’ homes to accommodate emerging technologies.

- Circulation that avoids isolation and encourages interaction.

- Lively multi-purpose social spaces that link with the community.

- Engagement with the street.

- Energy efficient ‘green’ buildings.

- Adequate storage inside and outside home; and

10. Shared Surface design of outside spaces with pedestrian priority.

- Reduce Defects by inclusive design and using feedback from previous projects.

- Include local community and seek maximum buy in throughout project cycle. The Developer Design Teams must assist Alpha in undertaking community consultation by providing appropriate drawings/presentation boards, attending community consultation meetings and all other required work to complete the community consultation in line with the aims and objectives set out in the DFC guide including amending proposals if required as directed to address community concerns/comments.

- Site / External Environment

Site Appraisal

Consideration must be given to the proximity of the site in relation to public services such as shops, schools, chemists, public transport, and other community facilities. The development layout must be integrated with the local community/

Topography - Geotechnical and Topographical surveys should be undertaken at an early stage by a suitably qualified person and provided to the client.

Assessments should be carried out by direct investigation and examination of the ground, supplemented where necessary by results of laboratory testing on samples obtained. The Association should be notified of any hazards/contamination evident from the survey.

A copy of all documentation relating to the land quality shall be forwarded to the Association.

All investigations should include an assessment of site contamination.

A detailed land survey should also be undertaken, and consultants must assist in the preparation of transfer maps to assist in the acquisition of a site. The Association will require an overlay of the topographical survey with the land registry maps to be undertaken to confirm legal land title

The appraisal should take account of the potential hazards such as radon, methane, asbestos, gas, overhead power lines and contaminated land

Other issues to be included in the site appraisal include pedestrian and vehicular links, flora and fauna, current and future development of adjoining sites, orientation, privacy, views, and sustainability.

A copy of all documentation relating to the land quality shall be forwarded to the Association.

Schemes must be prepared in the context of relevant planning policies

The proposals should as far as possible be shown to.

- Integrate with supporting areas, buildings, and features

- Create attractive, user-friendly layouts with a ‘sense of place.’

- Have frontage dominated streetscapes, avoidance of backs and gables onto open spaces, roads, paths etc and have an attractive gateway and supervised open space

- Have rational, legible, safe vehicular/pedestrian circulation system with most streets leading to other streets, unobtrusive parking, and minimal pedestrian only routes, which, if necessary, should be supervised by dwelling frontages.

- Have attractive design features to individual dwellings, through a variety and detailing to a common theme.

- Have a clear demarcation of public and private spaces

- In considering the suitability of a site for development the Association’s aim is to generate a safe and secure environment that ensures residents, can live, work, and contribute to the local community.

Density

It is essential in the provision of social housing to have a balanced and proportionate dwelling density on sites.

Layout

Site layout and dwelling/building orientation must allow a convenient, safe, and attractive environment.

Consideration must be given to the surrounding area in terms of scale and character. Living rooms should overlook areas of interest or open space care must be taken to ensure privacy.

Pathways

All approaches to dwellings to be compliant Lifetime Homes and the DfC Housing Association Guide. Particular attention is drawn to the requirements for wheelchair users.

Main pathways should be overlooked by dwellings convenient and well-lit to ensure casual supervision.

Footpaths must be accessible to all residents including those who are wheelchair users:

- Easy gradients, preferable 1:20 and must not exceed 1:12

- Level rest areas are required within gradients which exceed 5 metres horizontally

- Pedestrian crossings of roadways must be clearly defined by contrasting colour and texture

- Pathways must be provided to car parking areas, where applicable, to the bin store and to external drying facilities

- There should be no sharing of footpaths between dwellings

- Dwelling access paths and rear paths require a clear width and be compliant with the DfC Housing Association and Lifetime Home Guide

- All external pathways to be brushed concrete finish with slip resistant surface to rear. Communal decorative concrete with a natural aggregate finish to be provided.

- Driveways & front paths to be bitmac finish consisting of a base course and wearing course. One course will not be acceptable.

- Any areas in the public domain which are to be adopted to be constructed to Dfi standards. The developer retains control of the Roads/street lighting/drainage until adoption takes place.

- Use of mulch, bark, loose gravel, concrete slabs or grass seed is not acceptable.

Roads

- The design of roads within a residential development must reduce speed and every effort must be made to ensure the safety of pedestrians and cyclists.

- The Association requires all roads to be provided to adoption standards. Roads, pathways, and open space should be appropriate for their likely use and clearly defined as public and private space.

- Consultants are responsible for liaising with Roads Service and all necessary utility companies to ensure standards are to an acceptable level and achieve adoption.

- Vehicle and pedestrian access should be integrated within the overall design of a scheme with consideration afforded to the needs of residents with regards to safety, convenience, security, and scale.

Car Parking

- Car Parking should be adequate for the needs of residents, staff and visitors and be both convenient and secure. Distance from car parking to dwelling to be kept to the minimum

- The provision of car parking must be in accordance with the Planning Service and DFE /DFI / DFC LTH Standards.

- Adequate and convenient open hard-standing car parking should ideally be located in-curtilage,

- Within apartment developments, in addition to the DfC Housing Association Guide and Lifetime Homes requirements the following is required:-

- Within the carparking bays the infrastructure should be provided to allow for the future installation of charging points

- Individual spaces must be clearly marked out, as should spaces for wheelchair users.

- Good lighting is required in all parking areas.

- In-curtilage car parking space or a percentage (minimum 25%) of communal car parking capable of enlargement to 3.3m wide.

Landscaping

- Creating beautiful outdoor social spaces, promoting sustainability, and improving quality of life are important elements of Alpha Housing Associations vision. It is therefore necessary that approval must be sought from the Association on an individual scheme basis of the landscape design proposals.

- The landscape designer should consider steps to improve the biodiversity of the site e.g.  incorporating hedge rows and wildflower planting. Promote individual species such as providing swift boxes.

- A Contractor appointed Landscape designer will be required to design a comprehensive and detailed planting schedule for the scheme/ dwellings. A maintenance schedule for the duration of the defect period is to be included. This will require approval by the Association.

- Landscape design should blend hard and soft landscape treatments to achieve an attractive environment.  Pathways to the front and sides of dwellings and communal areas shall be decorative concrete with a natural aggregate finish. Unless permeability is required to achieve statutory requirements in which case approved permeable bitmac or paving should be provided as agreed with the Association.

- Communal planting areas must be fully maintained by the landscape contractor for 12 months after handover of the development or completion of planting whichever is the later.  The maintenance programme to be agreed with Alpha prior to handover.  Any costs for maintenance service must be included.

- Where appropriate, existing landscape features should be retained to help give the site maturity. Existing trees and mature bushes should be protected during the construction phase.

- Landscape proposals must make use of shrubs, plant and trees species should be native and wildlife friendly which are suitable to the site environment and soil conditions. Soft landscaping should be durable, low maintenance and attractive. It should be carried out at times, most beneficial to the plant’s growth and survival.

- All landscaped areas, and private gardens, both front and rear, should be fully accessible to all and be either level or gently sloping, not exceeding 1:20

- All landscaped areas, and private gardens, both front and rear, should be prepared. A suitable weed prevention barrier installed.

- Rolled turf is required for any grassed areas.

- Adequate topsoil should be provided with a minimum depth of 150mm and suitable quality to promote strong plant growth. All topsoil should be quality screened free of roots, perennial weeds, large stones, and rubble.

- In Category 1 schemes, the design should ideally include external private open space for each dwelling using private garden spaces or balconies. Balconies should have a minimum depth and width of 1500mm. Each ground floor apartment should have its own external space of 6m2 and level access from the home.

Fencing and Boundary Walls (Comply Fully with Secured By Design Gold Requirements)

- Site perimeter fence/ wall boundary treatment to be included regardless of existing adjoining property boundary

- All boundary treatment must comply with secure by design standards and planning approved   drawings. Detail boundary treatments will be required to be presented to Alpha at detailed design and application for project approval stage.

- Any railings to be mild steel hot dipped galvanized finish

- Brick walls must be at lease 225mm thick with piers at appropriate intervals.

- Gates should be the same height as the adjoining fence and must provide a clear opening width of 900mm.

- Gates should not be fixed directly on to the brick but on to independent steel gate posts which should be concreted.

- Rear and side fencing should be as a minimum height 1800mm close rounded double boarded decorative timber bolted to concrete posts with no exposed threaded bolts. Must be approved by the Association. An illustration can be provided by the Association.

- Where in-curtilage parking is provided driveways should be of sufficient layout to permit inward opening of gates.

External/ Internal Clothes Drying

Adequate space and paved access should be provided to external rotary clothes drying line in rear gardens of houses and a compound should be provided for communal drying in apartments schemes, shielded from amenity space.

In apartments provision should be made for internal drying area.

Waste/ Refuse Bins

- Waste/ Refuse bins to be included, supplied, and numbered by the contractor / developer as per the Local Authority Cleansing Department requirements

Bin Storage

- Hardstanding to be provided preferably at the side or rear of the dwelling to accommodate 3 wheelie bins for refuse, food waste and recycling

- The location of wheelie bin storage should be screened and visually unobtrusive

- Pathways of appropriate width are provided from the hardstanding to the collection point by the refuse collection vehicles.

Drainage

- Appointed Civil Engineer Consultant to design main drainage layout to N.I. Water adoptable standards. Please note that all applications should be made in good time.

- CCTV survey will be required for all drainage.

- In curtilage drainage to be designed and compliant Part N Building Regs.

- Note all condensate pipes to be terminated internally into appropriate system.

Signage

- Street name signs as per local authority requirements.

- Scheme name plaque as per Alpha’s design.

- All signage to be powder coated aluminium.

- At apartment schemes all signs should be adequate for the need group and the positioning approved by Alpha

Canopies

- Canopies or recessed thresholds are to be provided at all main entrances as per Lifetime Home Requirements. The design of the canopies is to be approved by the Association.

- Building Elements

Substructures

Sub Structures to be Designed by the Developer’s Structural and Civil Engineers. They must meet Building Control Requirements and Structural Defects Warranty Requirements. The Structural Defects Warranty will be taken out by the Developer and cover the warranty for 10 years.

The foundations shall be constructed to Structural Engineers Specification. If design requires piling, collateral warranties will be required from specialist sub-contractors.

The foundation shall be designed to suit the ground conditions and any hazards revealed by the results of the land quality surveys.

Concrete samples shall be taken in the presence of the Association’s Clerk of Works and tested at an approved laboratory. A copy of all test results shall be kept on site, the originals shall be forwarded to the Association upon receipt from the laboratory.

All precast concrete to be CE marked and supplied by accredited manufacturers.

Ground Floor Slabs

The type of ground floor slab construction shall be specified and signed off by a suitable qualified structural engineer.

Suspended / precast floor slabs or floor ‘T’ beams to be specialist sub-contractor designed and manufacturer collateral warranty is required

Superstructure

Brick work

All structural brickwork must comply with current British Standards or an equivalent international standard and Codes of Practice. Sample panels of 2m2 shall be required for brick selection.

Preference is clay bricks must be wire-cut, with samples provided for client approval.

Timber and Concrete Upper Floors

To be constructed in accordance with engineers’ drawings

All external surfaces i.e., facing brick or render colour to be discussed with Alpha and samples provided prior to construction commencing.

External Timber Framed Walls

Timber frame construction by client approval only. Please note that it is our preferred option that all apartments are to be of traditional masonry.

The design shall comply with all relevant statutory requirements

Roofs

All roofs to main buildings should preferably be pitched and covered in concrete tiles or slates.

Roof tile selection to be standardised to facilitate future maintenance.

The Association must approve a sample roof tile/ slate.

Ridges, hips, and verges shall be mechanically fixed with dry verge cloaking

The Association prefers seamless gutters and down pipes, fascia’s eaves and soffits preferably be of self-finish maintenance free finish. Where timber is used, it should be pressure treated with an appropriate finish. Soffit boards, where used, should preferably be self-finisher Supalux or Master board, or stained WBP plywood

Traditional synthetic lead should be provided. Samples to be provided to Alpha for approval.

Access Hatches

To be provided and located to allow access to the roof space and other equipment for maintenance purposes.

The use of a proprietary hatch will be permitted, suitably sized and must have an integrated latch and access pole. In apartment schemes roof hatches should be lockable.

Roof space should have a suitable low energy lighting and an access platform (min 2.0m x 2.0m). A raised 600mm gangway above ceiling insulation (in the case of cold roof construction) must be provided to access any serviceable equipment in attic space.

Stairs

- The use of winders and tapered treads should be avoided. Open tread staircases shall not be used. Open balustrade can be used but this should consist of vertical balusters, not horizontal rails.

- The stairs should be installed in one straight flight (wherever possible) and be sufficiently wide to accept the installation of a stair lift.

Lifts

- A traction lifts of 1400mm deep and 1100mm wide (minimum) must be provided to accommodation with one of more storeys. Two independently operating lifts should be provided in blocks exceeding 4 storeys in height.  A platform lift is NOT acceptable.  Refer to separate specification.

- At least 1 metre per second travel speed.

- The open protocol autodialler must not restrict communication to a single organisation. After power outage or lift breakdown the autodialler used must not revert back to the original factory settings leaving schemes not covered with outside contact centre. Closed protocol autodialler is not acceptable. The autodialler specification must - Allow full compliance with EN81-28 and EN81-70; Backlit LCD display for programming and status information; Easy programming; Stand-alone battery back-up of complete system including GSM (if using); Ability to program and reprogram installed units.

Windows

All approved window samples and obscure glazing to be retained on site during construction period.

Windows and glazing units to be hermetically sealed to meet minimum required u-Value, to be SBD standards

All manufacturing joints must be welded Window design shall be simple and functional, with preference for outward opening casements and fanlight ventilation where possible.

Windows shall preferably be manufactured from PVC-U. Softwood/Hardwood windows shall be considered on planning or costs grounds but will be subject to Association approval.

Windows shall be designed and specified to consider the location, climate condition, planning requirements, Secure by Design requirements and general environmental factors such as noise.

Windows to have internally glazed beads for ease of maintenance.

Apartment living room glazing shall preferably be full length. If leading to a balcony the door threshold should be level with the living room.

All windows shall be fitted with opening restrictors, limiting opening to 100mm

An escape window shall be provided as specified by the Building Regulations.

Window handle height should be in accordance with Lifetime Homes requirements.

Hinges and fastenings of opening lights shall be of heavy duty and of the type that prevents them from being opened from the outside when in the closed position.

Handles to kitchen windows to be easily accessible.

All opening windows are to be fitted with lockable fasteners. If the locking mechanism is key operated, then the same key pattern shall be used for the entire dwelling. Key operated locks are not permitted on escape windows. Glazing strip to be included.

All uPVC windows to be steel or aluminium reinforced internally.

Trickle vents shall be incorporated in the body of the frame with suitable controls and a minimum free flow as determined by the Building Regulations.

The Association shall determine the colour of PVC-U windows.

Windows shall comply with minimum U value requirements as set out in current NI Building Regulation

Windowsills to be 18mm thick MDF. All sill to be approved by the Association.

A 10-year guarantee is required for hinges, frames and handles to be provided at handover.

No transoms at eye level.

Glazing to all windows shall incorporate a condensation channel.

Glazing to all toilets/ bathroom to have obscure glass to approved pattern.

External Doors

All External Doors of houses and Entrance Doors and Main apartment doors in schemes shall be Secured by Design Compliant.

Entrance doors must have SBD approval and been tested as a 'set' and have all furniture / ironmongery in the set, including door chains and letter boxes if required

All external door frames shall in corporate neoprene weather stripping and be bedded and pointed in a mastic compound and comply with minimum U value requirements as set out in current NI Building Regulations

Thumb turn locks should be installed on the front and rear doors to facilitate easy escape.

Must be SBD compliant and ironmongery to include such as spy hole and door chain.

All glazing to external doors shall be double-glazing. Where required laminated glass shall be incorporated into the double-glazing units

Glazing to rear doors shall be “obscure” and shall not exceed half of the door area.

Glazing to front doors shall be “obscure” and shall be in small panes not exceeding a quarter of the total door area.

The detailed specification of the external doors/door set shall be considered in the architect’s specification of the employer’s requirements.

Front and rear composite door sets should incorporate a multipoint locking system. All apartment block external doors are to be fitted with electronic multipoint locking mechanisms with both door and lock to be SBD accredited and fire regulation certificate provided

Front and back door thresholds to have an eco-drainage channel fitted with a metal grill heal guard

Internal Doors

All doors should comply with all relevant statutory requirements.

All Internal doors shall be solid doors, either flush type, hardwood veneered with hardwood lipping and a factory applied finish. * or panel type doors with a painted finish, subject to client approval

Internal thresholds are not to be provided.

All communal and flat entrance doors should be fire doors.

Fire doors shall be closed with an appropriate door closure as required by Building Control. Smoke seals and intumescent strips shall also be used where required. Stops to frames housing a fire door shall be of the required thickness and be glued and screwed to the frame in accordance with the relevant Regulations.

Ironmongery

All ironmongery should meet DDA Standards and be approved by the Association.

Reference should be made to the Secure by Design requirements, DfC Housing Association Guide and Lifetime Home Standards

The finish to the ironmongery is dependent upon the scheme/environment.

Keys

Front and rear doors to be keyed common in houses and 3 no keys provided to resident for each lock

Residents of apartments to be provided with 3 No. keys required for apartment main door and fob for main entrances, bin stores and carpark as required

A master key system will be required for communal stores/ areas in apartment scheme

Internal Elements

1st Fix

    - Mechanical, Electrical and Ventilation marking up of each property type must be completed for client approval before 1st fix commences.

    - Plumbing & heating manifolds to be located within HP or a store. 1st fix drainage provision for future appliance in kitchen and future shower in WC except for apartments when the future shower drainage will be in the bathroom.

2nd Fix

- All internal doors to be 40mm solid wood doors All internal ironmongery to be presented for client approval. Agreed door type to be presented for client approval. Skirting to be presented for client approval. Architraves to be presented for client approval and to match skirting,

- Door handles to be bolt through.

- Tubular latches are not acceptable.

Stores and Wardrobes

Every dwelling should have designated storage space that is easily accessible.

Stores should be located off circulation areas, and shelving provided. Wardrobes to be fitted with shelving and chrome hanging rail. Ventilated in the form of undercut door provided, and heating provision in linen / HP.

Meet the DfC Housing Association Guide and Lifetime Home Standards.

Kitchens

Kitchens must meet the space requirements to DFC Guide Table 2. In addition to the minimum Standards for Kitchen Storage and Appliance Spaces an additional future appliance cupboard will be required, incorporating the necessary electrical and plumbing connections.

Kitchen Manufacturer to provide plan and elevation drawings of each kitchen type

All floor base unit carcasses shall be composed of 18mm melamine faced chipboard i.e., gables, bottoms, and shelves.

Plinth height shall be 160mm and recessed back 40mm.

Worktop height to be 910mm (800mm in the case of wheelchair kitchens) depth to be 600mm.

Work top shall be 40mm chipboard bonded and coloured laminate to top with front edge post formed.

A 100mm upstand from the worktop is required

A minimum 6 No. sample worktop, doors and handles shall be provided for selection.

Cupboards shall have wood grain effect melamine face board (3.2mm) backs.

Doors shall be 5-piece vinyl wrap door. Top of doors detailed to ensure no water remains trapped.

Hinges shall be 180 degrees good quality with soft closing mechanism.

Drawers shall be Blum metal box with 15mm melamine base (including cutlery tray). Drawer to be the same construction as doors.

Wall units to be 710mm high and to the same construction as the floor units. Also have two shelves.

Toe space shall be plywood laminate to match door colour.

Infill panels and gable ends exposed to be made from matching melamine faced chipboard and made to match the doors.

Corner, base, and wall mounted units to be fully accessible, i.e., no dead space. They shall be double opening doors without a front corner post

Handles to be bolt through fixed

All base units to have adjustable feet with removable plinths

I no. wall unit to be lockable as a medicine cupboard

All cooker extractor fan shall be stainless stell chimney type with extendable chimney to fit variable veiling heights. Emission rates as per Building Regs. All ducting is to be concealed and match the kitchen units.

Unit to accommodate tall fridge / freezer.

All joints in work tops to be metal trimmed. Jointing to be ‘Masons mitre’ connected with dog bolts and exposed edges to have aluminium end capping strips. Worktop to have double end capping strips at fridge location to facilitate removal of worktop section to accommodate tall fridge freezer.

All sinks to be kite marked. Preferably 1 ½ bowl, size gauge and bowl depth to be agreed

Taps to be single pillar lever action mixer taps

Underside of sinks to be insulated.

Kitchen Tiling, and Flooring see Finishes section of this guide

Bathrooms and WC

Please refer to the DFC Housing Association Guide and Lifetime Home Standards in respect of the requirements.

Sanitary fitting shall consist of a white vitreous China cistern, back to wall WC pan and a white toilet seat. White vitreous China wash hand basin and white enamelled steel baths (non-slip surfaces in baths with stainless steel lever taps).

All sanitary ware to be presented for approval by the Association

Walls in bathrooms and WCs should be capable of taking handholds

WCs shall be screwed to the floor and sealed using a silicone building sealant. Cementing is not acceptable to the Association.

WCs shall have heavy duty white toilet seat and cover, fixed to the WC with heavy-duty stainless-steel hinges.

Push button flush mechanisms must be used.

Low level ceramic cisterns are to be used.

Wash hand basins shall be supported on vitreous China pedestals and screw fixed to the wall directly or on brackets.

Wash hand basins shall be no less than 510x420 except in separate cloakrooms where a smaller basin will be considered.

In Cat 1 accommodation the bathroom is to be designed as a “wet room” with suitable slip resistant floor tiling.

In Cat 1 accommodation where possible all bathrooms to have Jack and Jill with doors opening to the double bedroom and hallway.

Thermostatic showers including tanking and tiling are to be fitted to General Needs Housing, Cat 1 and Wheelchair apartment bathrooms.

Where baths are provided baths shall be 1700 X 700mm flat bottomed slip resistant with integral hand grips be 1.5mm gauge pressed steel white enamelled to British Standards or an internationally recognised equivalent standard complete with side and end panels. The bath hand/shower mixer hot and cold taps shall be lever action. Showers mixer units over baths must be thermostatically controlled and have a short hose of 500mm maximum.

Specification on Fixtures and fittings to bathrooms and WC to be confirmed by client but will include a mirror (60x80 cm) with shaver point, a toilet roll holder, a heated towel rail in lieu of radiator (subject to mechanical consultant approval), and a floor to ceiling glass shower screen.

Future Level deck showers shall have a suitable gully trap 1300 x 800. (sealed for future use)

All taps to be lever operated

All walls to be PVA sealed before tiling

TMVs to all hot water connections to bath, wash basin and sinks

Bathroom Tiling, and Flooring

see Finishes section of this guide

Shower Formers

Level deck downstairs showers to be provided as level access shower tray formers minimum 800 x 1300mm. Samples to be provided to the association for approval.

5	Mechanical and Electric Installations

Heating Systems

The heating system should be designed to the form of construction and take account of the thermal capacity of the building and be related to the expected use and occupancy and the availability of fuel source.

Gas heating

A gas “a “rated Condensing boiler to be approved by Association. A 10-year warranty is required. Gas Condensing Combi Boilers sized to suit the size of each unit and capable of providing enough hot water flow to showers and taps.

Boiler make and model to be accepted and agreed with the Association.

The boiler shall be wall mounted condensing regular type manufactured and specified according to the Boiler Efficiency Directive 92/42/EEC. Boiler installer shall be Gas Safe registered for all points of the installation. The boiler shall be complete with the following.

- A heat cell manufactured from 90% aluminium and 10% silicon, delivering higher efficiency and reliability.

- A 2-year parts and labour warranty.

- A 10-year manufacturer backed warranty on all elements of the boiler, e.g. primary heat exchanger.

- Built in frost protection.

- Have a maximum flow temperature of 82 degrees.

- 22mm compression fitting on flow & return.

- Full range of flexible fluing options in 60/100mm and 80/125mm including plume detector as standard.

- Plume management kit

- Integral High Head pump.

Boiler and parts must be available through mainline and independent merchants with a maximum 5-day lead time.

Boilers will be fitted on the inside of external walls within kitchen units.

The heating control thermostat should ideally be sited in the living area, away from any direct heat source and easily accessible. Thermostatic valves shall be provided.

Heating programme to be located in the kitchen/dining area.

The heating system and controls should be fully automated and have a facility to be operable through an App.

A micro bore system will not be accepted.

Boiler controls should be of a type easily operated by tenant.

Stopcocks to be of the easy clean, screw down pattern with integral drain cock with capillary or compression ends. Stopcocks shall be located below sink level in each kitchen where practical

The contractor shall supply and install a Surestop stopcock on the incoming water main connection to each dwelling. The stop cock shall be complete with remote water switch including a 6m tubing system. for wheelchair and cat1 properties only .

Bib taps are to be fitted to all houses and to apartment bin stores with associated drainage gully.

All rainwater pipes should discharge into gullies and be aluminium seamless. Deep flow gutters should be considered where appropriate.

Pipe work behind wash hand basin etc. should not be boxed in. Where boxing is necessary, provision shall be made for access.

The water supply shall be protected by an electronic scale inhibitor such as “hydro flow.”

A triple trap shall be installed below the sink unit to facilitate the installation of a washing machine and dishwasher.

A landlord metered water supply shall be provided in communal areas where provision is made for cleaning equipment and facilities. This would normally be in the form of a “Belfast” sink or similar.

At least one external tap to be provided for external use.

Hot water supply provided in communal cleaner’s store and coffee dock areas.

Radiators

All radiators shall be panel radiators manufactured and tested to BS EN 442. Each radiator shall carry the BS Kite mark certifying independent approval of heat output and verifying production under British Standards or an internationally recognised equivalent standard . All radiators to comply with British Standards or an internationally recognised equivalent standard and be Kite Marked.

All radiators shall have central connections to the underside of the radiator and equipped with an integrated valve arrangement. Each radiator shall have an integral air vent and TRV both top end connections. The exception to this is where a room thermostat is fitted; this room shall have handwheel valves in lieu of TRVs. The height of the TRVs must comply with lifetime home requirements.

All radiator components must be available from a local supply chain.

Electrical

Electrical layout as per M&E Consultant approved drawings.

M&E Consultants to certify that drawings and installation is compliant to the most recent Standards

The electrical layout must be compatible with the furniture layout in each room.

Consideration should be given to typical minimum requirements in the table below.

| Location | Requirement |
| --- | --- |
| Hallway | 2 x 13A twin socket outlets. 1 data point. 3 gang switches for ext light, 2 way for hall, 2 way to landing. Ext light to be wired through photocell for dusk/dawn operation. Single gang 2-way switch for hall/pendant x 2. Doorbell sounder. Future stair chair lift charging supply. |
| Living room | 4 x 13A twin socket outlets (2 to be positioned beside TV point) 1 x 13A DP indicating unswitch socket for focal point fire. 1 TV point. 1 phone point (next to TV point). Single gang light switch/pendant. Room stat. Smoke detector. 1 no. double data point. Future through floor lift. Smoke detector |
| Large store | CU, future intruder alarm, NIE keypad wiring, 13A twin socket outlet. Single gang light switch/ fitting |
| Kitchen | 4 x 13A twin socket outlets. Supply for cooker, boiler, extract, washing machine, future appliance, 1 unswitched socket for fridge to be provided at low level, heating programmer, immersion with timing facility and MVHR where applicable. All sockets to provide engraving. Single gang 2-way light switch/light, 2 gang switch ext light & 2 way for kitchen. Heat detector, CO2 detector, carbon monoxide sensor/detector located at boiler |
| Kitchen / dining room | 2 no. 13a twin socket outlets. |
| Bathroom and WC/ Future Shower Room | Shaver socket in all bathrooms, mirror pull switch. 1 no. extract fan. Capable of 6 air changes per hour. |
| HP | Immersion outlet, pull switch/2d luminaries. Motorised valves circuit |
| Main/double bedroom | 3 x 13A twin socket outlets. 1 TV point. 2 x data point Room stat. Single gang light switch. Supply future tracking hoist from bathroom to bedroom. Smoke detector |
| Single bedroom | 2 x 13A twin socket outlets. 1 TV point. 1 telephone point. Single gang light switch/ 1 x data point. Smoke detector |
| Landing | Smoke detector, Co2 detector, 1X 13a twin socket, Single gang intermediate light switch/ |
| Roof space | Pendant should be provided with the switch located in the landing. Power supply for MVHR unit. |

The contractor shall provide a complete earthing and bonding system in accordance with the current Edition of the IEE Wiring Regulation.

Switches shall be of the flush rocker pattern with polycarbonate or PVC finish. Where possible lighting shall be locally switched.

Generally, switches shall be installed 1000mm above floor level in all dwellings and sockets shall be installed at 600mm AFFL. Thermostat height should be 1200mm from FFL. The heights of each will be agreed at the marking out meeting and in accordance with the DfC guide and Lifetime Home Standards.

Accessories mounted above worktops shall be 150mm above worktop level. Consider positioning for height of upstand in kitchen.

External luminaries shall be provided over all entrances be vandal resistant and approved by the client.

External entrances should be illuminated using fully diffused luminaries activated by a dawn to dusk timer or by detecting motion and as determined by Secure By Design Standards

Electrical sockets in communal areas in apartment blocks to be on a boost time switch and located in the cleaner’s store

Living Room			1 no. pendant light

Kitchen			1 no. surface mounted LED light strip

1 No. plate switch – 1 No. cooker hood

or

1 No. 13A fused (5A), indicating switched, connection unit – cooker hood

Store				1 No. pendant light

Bedrooms			1 No. pendant light

Bathroom			1 no pull cord – surface enclosed bathroom fitting

Hall				2 no. pendant light

Boiler				Power supply/controls as necessary

Landing			1 no. pendant light

Roof space			1 no. pendant light

The 13A socket outlets shall be wired in two ring circuits and shall be protected by a 30Ma RCD in the consumer unit.

Consumer units must have single module combined AFDD & R. C.B O’s. Please note there are to be a minimum of 4 spare ways.

Consumer control units; sheet iron-clad; 18th Edition; main switch; 15 ways with 100 Amp DP switch; single module combined AFDD & R. C.B O's - 4 No 5 amp, 3 No 15 amp, 4 No 30 amp, 1 No 40 amp, 2 No spare, identification labels; 16 SMM split concentric cables, BS 4553 as tails to meter.

The electrical Engineering Installation shall be fully tested, commissioned, and left safe.

All lighting points to be provided with appropriate bulbs or lamps.

Fire Design

Please refer to the attached Fire Safety Design Guide attached

TV Aerials / Satellite systems

Within Houses

Provision should be made for roof space TV installation and full fibre to be installed where available.

- Mechanical ventilation

Mechanical ventilation shall be provided to each bathroom, kitchen and ground floor WC designed to meet the requirements of the Building Control Regulations for Northern Ireland.

All areas shall be ventilated using wall mounted extract fans with an external grille to match the colour of the external brickwork.

Ventilation fans mounted near baths shall be the extra low voltage type to meet with the requirements of the current IEE Regulations.

The Electrical Contractor shall be a member of the National Inspection Council for Electrical Installation Contracting and/or a member of the Electrical Contractors Association and Sparksafe registered.

The consumer unit should have a suitable RCD installed to provide earth leakage protection to the installation.

Emergency Lighting

Please refer to Fire Design Guide attached. Emergency Lighting shall be installed in accordance with the BS and ICEL Standards (current editions) and the requirements of the Fire Consultant.

CCTV

CCTV is required to cover all communal areas within apartments blocks for example, internal and external of each entrance, communal corridors and stairwells, bin storage areas and the external perimeter of the building as Associations management requirements. CCTV shall have the facility to be remotely monitored via internet connection. Recorder shall have the capacity to hold footage from all cameras for a period of not less than 31 days. Recorders shall have the facility to serve all cameras plus an additional 25% spare for future expansion.  All signage must be clearly visible and GDPR Compliant.

Audio-Visual Door Entry System within Apartment Blocks.

All entrance doors into communal blocks to be access controlled featuring automatic opening devices to any internal doors leading to the lift. All apartment block external doors are to be fitted with electronic multi point locking mechanism with both the door and lock to be SBD accredited.

An audio-visual door entry system shall be provided to each apartment block to facilitate communication between the main entrance door and each apartment. Adjacent to the main entrance door a call panel shall be provided which shall feature an integrated digital keypad and colour wide angle camera. Within each apartment a colour LCD tablet style video monitor handset shall be provided in the hall or living room, and capable of conversion to a desk mounted version The system shall allow communication between the main entrance and the apartment with the facility for the tenant to remotely release the locking mechanism of the main entrance door. Where the doors opening is automated this remote release shall also engage the door operator to drive the door open. The digital keypad as part of the audio-visual system shall also have the facility to accept input of two 4-digit codes. On entering either code the door locking mechanism shall be released and where automated doors shall be driven open. One code shall be operational 24 hour with the other code for trade use between pre-set times that shall be confirmed (typically 8am to 5pm Monday - Saturday). A telecare call system connected to 3rd party call centre shall be provided to all apartment blocks. Within general needs apartments blocks this system shall comprise of an external managers call point; internal managers call point and a key safe. The external managers call point is to facilitate communication off site with a call centre who will have the ability to remotely release the main entrance door. The internal managers call point is to again facilitate communication off site with the call centre who will have the ability to remotely release the key safe. Both the internal managers call point and key safe should be located within the main entrance lobby of each apartment block. provided). Within all apartment blocks the communal fire alarm system shall be interfaced to the telecare call system to notify a call centre of any event in the fire alarm system. All Apartment blocks shall have all main entrance doors automated. Door access system to be networked and compatible with the existing Alpha Housing Association across all schemes. Wi-fi will be required. Overhead door actuators shall be provided on the secure side of each door fixed to the door frame with an arm from the actuator to be secured to the door. Entry shall be controlled by the audio-visual door access system or by the telecare call system with both systems beings interfaced to the door automation so either can drive the door open. Egress shall be by a DDA type request to exit button that shall be located clear of the door swing in a position suitable for wheelchair users. Where door automation is provided, door locking mechanisms shall be controlled by the automation actuator to ensure the door does not try to drive open until the lock as fully disengaged. Door automation actuators shall be a semi-automatic type that if the door is pushed it will move freely without putting stress on the actuator system. Should the door be pushed then released the progress of the opening actuator shall take over and continue to drive the door open. Apartment block main entrance doors that are electronically locked that all have the facility to be manually unlocked from outside by key. A key safe shall be in a discrete location on the perimeter of the building to house a key for opening the door. Pedestrian gates were automated shall be controlled by fob for entry and a DDA style request to exit button for egress. Both the audio-visual door entry system and telecare call systems shall be extended to any pedestrian gate to provide a facility for visitors to contact apartments for entry, for entry by use of a 4-pin code as described previously or for a visitor to communicate with Telecare who may also grant access. Vehicular gates shall be controlled by remote fob for both entrance and egress. In addition, vehicular gates shall be interfaced to the fire alarm system to be driven open in the event an alarm activation. Fobs for pedestrian gate access shall be provided as 2nr per apartment plus 25% spare (minimum quantity of 10 spare fobs to be provided). Fobs for vehicular gates to be provided to reflect the parking ration of the scheme plus extra.

6.	Internal Finishes

Flooring in houses

Kitchens to have approved slip resistant safety flooring Standard R rating (full range to be made available for selection) Flooring to be extend below units and be wall to wall.

Bathrooms/WCs- approved safety flooring slip resistant and low-profile shower tray.

Downstairs toilet & shower room to have wet foot traffic slip resistant.

Flooring in apartments

Communal areas to have approved slip resistant safety tiles and communal staircases in apartment blocks to have approved slip resistant safety flooring.

Matwells should be provided at entrances in communal areas with coir matting or equivalent.

Kitchen and Bathrooms to have approved safety / slip resistant tiling.

Association to approve samples.

General Information on vinyl flooring

All seams to be heat welded and coved to form skirting in bathrooms and wet rooms. Flooring to be installed to in accordance with current BS to include full hydrometer testing of floors. Laying of floor finishes will be judged as acceptance, by the contractor, of the suitability and readiness of the screed/sub-floor.

Adhesives shall be approved by the manufacturer. Initial cleaning shall be in accordance with manufacturer’s instructions.

Colours and patterns to be approved by client.

Ceramic Tiles/ Panelling

Tiling shall include all colour matched PVC capping, corner, and edge trims. (Samples are to be provided to the Association).

Tiles are to be located as follows:

Bathrooms – bath and shower walls to be uPVC wall cladding panelling. Samples to be provided to Association for approval.

Showers- where showers, or shower taps, are provided all tiling shall extend wall to ceiling.

Splashbacks

Splashbacks to be provided in lieu of tiles in kitchen areas and meet any environmental requirements and to be approved by Alpha Housing Association

Painting

All colour schemes must be agreed with Alpha Housing Association.

All woodwork ceilings and all internal walls to be painted prior to handover in ALL areas throughout the building and All rooms in internal apartments and houses. Colours to be chosen prior to painting commencing. Alpha will require a full finishes schedule.

The Association will require the ability to use up to four different paint colours for the walls to each property. The extent of this will depend on the size of development and client group.

All internal woodwork will be painted or stained. Painted joinery shall be primed, two undercoats and one gloss coat. Stained timber shall be treated with one coat base stain and two coats finish stain – or similar as approved by specified manufacturers/product.

In general, external timber doors shall be finished with one coat base stain and two coats finish stain.

External Finishes

Rendered walls shall be sand and cement render with external grade paint finish applied. Colour to be determined by the Association and in accordance with planning approval.

Post Boxes

A “Bank” of lockable post boxes is to be located in the entrance of an apartment block lobby and 2 no sets of keys provided for each box and be approved by Secured by Design.

Additional items

Doorstops to be provided to doors where necessary to prevent damage to walls.

Coat hooks should be provided

Letter plates shall be fixed in an accessible position and not at the bottom of the door to comply with Secure by design, Fire and Building Regulations

NIE & Gas meter cabinets to be recessed into brick/block superstructure.

Internal Joinery

Skirting to be ogee, bevelled or square profile 94mm X 19mm redwood or MDF as agreed. Architraves to be ogee, bevelled or square profile to match skirting, 69mm X 19mm redwood or MDF to be approved by client.

Window boards shall be softwood, MDF, or another approved maintenance material. They should extend beyond the window opening by 50mm and proud of the wall by 25mm. The external edge should be rounded.

Wheelchair Housing

All Alphas wheelchair housing must meet all criteria set out in the DFC Guide and any additional items recommended by Occupational Therapists and approved by NIHE DPG.

7.	Samples

Samples schedule refer to the table below;

ITEM

Facing brickwork and/or self-coloured render panels

Roof tiles

Windows

Lifts

External Door set

Internal Doors

Ironmongery

Canopies

Newels, handrails and balustrades, skirting

Slip Resistant floor coverings including tiles and carpets

uPVC wall cladding panelling

Kitchen furniture components (carcasses, doors worktops, handles, tiles, upstands, and splashbacks) 6 samples to be provided

Colour schemes

External paving

External and internal light fittings

Sanitary ware & fittings including mirror

Heating controls

Gutters, downpipes, fascia’s, soffits

Door entry and handset controls

It should be noted that this list is not exhaustive, and the client reserves the right to request additional samples

8.	Handover

Handover, Practical Completion and Defects as per Alphas Procedures.

# Fire Safety Design Guide

# Alpha Housing Association

# Appendix 1

# 1.0 General

The design and construction of an Alpha Housing property should meet the current standards as set out in the Building Regulations (Northern Ireland) 2012 (as amended), Technical Booklet E: 2012 – Fire Safety (as amended) and all relevant British Standards or equivalent international standards, and approved Codes of practice. All materials and products should be certified as suitable for their application and installed strictly in accordance with the manufacturer’s recommendations.

A Fire Strategy should be completed by a competent Fire Engineer for all dwellings, which are to be occupied by tenant category Cat. 1, complex needs/wheelchair accessible dwellings and all apartment blocks.  The strategies should ensure that the premises are suitable for use as social housing, taking account of the relevant tenant category, and include all of the measures outlined in this guide.  A copy of the Strategy should be made available as early as practical for review by Alpha Housings appointed Fire Engineer.

All fire detection, alarm systems and devices must use standard equipment and be open protocol available freely from more than one source to ensure continuity of systems, efficient maintenance, control of software and engineering access.

Carbon monoxide detectors should adjacent to any combustion appliance within any building or enclosure to comply to BS EN 50291 and be located as per BS EN 50292 and the manufacturers recommendations.

All BS5839-6 fire alarm devices shall be provided from a single manufacturer, single range. All devices shall be hard wired but feature integral sealed 10-year lithium battery backup. Lifespan of all BS5839-6 devices is to be manufactured rated at 10 years.

Each dwelling shall be provided with a main powered alarm control switch. This main powered alarm control switch shall incorporate Locate, Test and Silence functions and mains failure warning. All functions shall be operable from floor level. Mains powered Relay module (1no.) shall be rated up to 240V AC / 5 Amps and operate on receipt of a signal from the interconnect line of a Smoke, Heat or CO alarm to shut down the mechanical plant. The switch shall be within a cupboard or other area agreed with the Development Officer where is easily accessible to adults but other of sight of children to avoid nuisance alarms.

The Fire Strategy should detail how suitable facilities and access is provided for the fire service.

## 1.1 General needs dwelling

Dwellings should be designed and constructed to support a ‘simultaneous’ evacuation strategy.

Within each dwelling, a standalone domestic fire alarm system complying with BS 5839-6:2019 of at least Grade D Category LD2 standard should be provided, this should include –

- Heat detection within kitchen area.

- Smoke detection within the living area, hallway and each bedroom.

- The smoke alarms should comply with BS 5446-1 and heat alarms should comply with BS 5446-2 and be installed in accordance with paragraphs 2.25 to 2.32 of Technical Booklet E: 2012.

## 1.2 General needs apartments

All Alpha Housing apartment developments should comply with the recommendations of ‘BS 9991- Fire safety in the design, management and use of residential buildings – Code of practice’ (taking account of the specific additional requirements for N Ireland, with reference to the cited standard BS 5588:1) and the provisions of the Building Safety Bill as and when enacted.

Purpose built apartment developments should be designed and constructed to support a ‘stay-put’ evacuation strategy.

Within each general needs apartment, a standalone domestic fire alarm system complying with BS 5839-6:2019 of at least Grade D Category LD2 standard should be provided, this should include –

- Heat detection within kitchen area.

- Smoke detection within the living area, hallway and each bedroom.

- The smoke alarms should comply with BS 5446-1 and heat alarms should comply with BS 5446-2 and be installed in accordance with paragraphs 2.25 to 2.32 of Technical Booklet E: 2012.

Any active fire safety system within an apartment block, will be activated by a suitable silent ‘BS 5839:1 fire detection system’.  Where such a system is installed, detection shall be provided within the common escape routes, service areas and common facilities; it typically, should not include sounders or manual call points.  Exceptionally, where Alpha schemes incorporate common facilities, e.g., lounges or communal roof gardens, we will require audible/visual alarm signal in such zones. In addition, a single heat detector shall be provided as part of this Part 1 system within the entrance hallway of each flat.  This BS 5839:1 system should be designed and installed, such that it shall:

- activate the fire safety systems (where provided), e.g. ground the lift, release door security devices, open automatic smoke vents, close dampers etc.

- summon the fire and rescue service (facilities should be provided for the automatic transmission of alarm signals to an alarm receiving centre) in the event of a fire within the common areas, or where a significant fire occurs within an apartment.

- The automatic transmission of the alarm signal shall be linked back to an nominated Alarm Receiving Centre, (Connect 24), via a dedicated copper phone line and GSM sim.

- includes a ‘Staff only test switch’, to facilitate in-house testing of the system.

- the specialist installer is to be certified to NACOSS Fire Gold and BAFE SP203-1.

Where the height of the building exceeds 11.0 m to the uppermost floor, Alpha Housing require the installation of a BS 8629:2019 Fire Service Manual Evacuation Alert System to be installed.

## 1.3 Additional measures for Cat. 1 – Active Elderly Accommodation

In addition to the matters detailed above, Category 1 Active Elderly block of flats should be classified as sheltered housing. In accordance with the NFCC Guide, sheltered housing is defined as ‘housing in which residents live independently in self-contained accommodation, as in a block of flats for those with general needs, but the building is predominately occupied by, and promoted to, people who are of a defined age or vulnerability. Such housing usually includes special features to address the particular needs of residents.’

Within each apartment, a standalone domestic fire alarm system complying with BS 5839-6:2019 of at least Grade D Category LD1 standard should be provided.

Each flat should feature a social (“Telecare”) alarm system to enable communication between residents and someone on or off-site. Another feature of such premises is that, like general needs blocks of flats, they are not staffed to provide assistance to residents to evacuate in case of fire. The fire detection within a flat has a significant part to play in this respect. Early attendance by the fire and rescue service is achieved by arranging for transmission of this detection to an alarm receiving centre, normally via a social alarm (“Telecare”) system. The warden call system shall share the copper phone line with the fire alarm system. In the event of a failure of this line this shall notify the Alarm Receiving Centre (Connect 24) by use of the GSM connection.

Over time the ability of Cat. 1 active elderly tenants can change.  The infrastructure (cabling) should be provided to facilitate the future installation of ‘swing-free’ self-closing devices to internal apartment hallways. Where active elderly apartments are on the ground floor (and a door has not been provided from the apartment leading directly to the outside space/garden), consideration should be given when designing window structural openings and external landscaping, to ensure at least one window is readily adapted, to accommodate the installation of a future external door.

Normally, Cat. 1 tenants upon occupation are ‘active’ and capable of self-evacuation.  However, over time their abilities can change.  Where this occurs, a person-centred approach may identify value in such systems to protect individual residents who are deemed especially vulnerable. In such cases, one option to address their vulnerability may be to provide a domestic fire suppression system within their single flat.

## 1.4 Additional measures for complex needs/wheelchair accommodation

In addition to the matters detailed above, where possible complex needs/wheelchair accommodation should, be sighted on the ground floor, with an exit door (fitted with an EOD) leading directly to the outside space/garden, to avoid the need for complex needs tenants to evacuate through the common areas.

The internal hallway of complex needs/wheelchair accommodation should be protected with FD30s fire doors with ‘swing-free’ self-closing devices, interlinked to the BS 5839: 6 fire alarm system.

The NFCC Guide strongly recommends sprinkler or watermist protection for all new sheltered housing.  Where the characteristics of individual residents are know, a person-centred approach may identify value in such systems to protect individual residents who are deemed especially vulnerable. However, sprinkler or watermist systems, if installed throughout a building, provide an effective means of ‘future proofing’ the building containing vulnerable residents. Accordingly, it is strongly recommended that sprinkler or watermist protection be provided in all new sheltered care housing, where the tenants are vulnerable, i.e. within complex needs and/or wheelchair accommodation.

## 1.5 Apartment blocks design and construction

The design and construction of the apartment buildings should be such, that the installation of boiler flue pipes, extract ventilation, domestic ventilation system ducts etc. do not compromise the integrity of protected apartment entrance hallways (where provided) or any other fire-resistant construction.

- Fire doors should be installed strictly in accordance with their respective test certification, and to BS 476: 22 and BS EN 1643.  Self-closing devices shall be in accordance with BS EN 1154.

- In addition to any inspections by the client, their representative or COW, the adequacy of the structural fire safety compartmentation shall be unconditionally certified by the main contractor prior to handover and 3rd party accredited firm

- The layout should be such that stores, or other ancillary accommodation does not open directly into staircase enclosures. The incoming electric and gas meters should not be located within the common escape routes.

- In addition to the normal domestic artificial lighting, emergency lighting shall be provided throughout the common areas serving the apartments, including the external ancillary areas. The emergency lighting installation shall comply with BS 5266-1 and the requirements of BS 5266-8 and BS    EN 1838, and it should provide illumination for three hours in the event of power failure. Exits routes should be clearly marked with the appropriate sign complying with BS 5499-1.

- The use of combustible materials on the external wall façade (including balconies) should be avoided in all residential buildings regardless of height, unless where expressly agreed by the client. Where the height of the uppermost floor exceeds 11.0 m, the use of any combustible material is strictly prohibited in the external wall construction.

- In all Alpha Housing apartment blocks, a ‘premises information box’ should be provided adjacent to the fire alarm control panel, this can be of great assistance to the fire and rescue service. It is normal practice for building specific information to be made available to the fire and rescue service in the event of fire, including evacuation plans.

- A fire alarm zone chart should be provided, framed, and mounted adjacent to each communal fire alarm control panel.

- A Secured by Design approved key code key safe positioned externally beside main entrance doors to facilitate Fire Service brigade access.

- Clear signage to be provided at each stair landing within the building to indicate the floor level (to assist firefighters in the event of a fire).

- The mobility scooters and their chargers should be in accordance with BS EN 12184: 2014. Solutions for possible locations of mobility scooter charging stations should meet the recommendations set out on the NFCC Specialized Housing Guide.

Appendix 2

Additional Category 1 requirements

- General

Alpha requires additional consideration for category 1 requirements as part of their over 55s housing corporate strategy. These additional requirements should be designed and costed for the Association prior to contact stage. Subject to NIHE funding and planning permission.

Landscaping will be thoughtfully designed, improved, and maintained to enhance the health and well-being of Alpha Housing residents and visitors to Alpha Housing sites. This includes creating more opportunities for social interaction and fostering connections with nature.

Nature-based solutions will guide the design, enhancement, and upkeep of Alpha Housing sites to increase the availability of ecosystem services both on-site and in surrounding areas.

All new developments should incorporate high-quality green spaces that promote social interaction within landscaped areas, such as accessible terraces, rooftop gardens, courtyards, and building surroundings, tailored to specific needs identified for each site. These spaces should establish a sense of place, facilitate a connection with nature, and promote health and well-being. Examples include planting near high-traffic areas and entrances to provide views of nature, as well as using diverse plantings that add colour, texture, scent, movement, and visual interest. Consideration to include bird boxes and bee hotels.

2.0 Design Elements

Enhanced landscaping to incorporate decorative concrete with a natural aggregate finish, along with native tree and shrub species, designed to blend seamlessly with the natural environment. This approach supports local biodiversity and sustainability by using plants that are well-suited to the area’s climate and ecosystem.

Communal WC to be provided to lifetime home standards.

Communal outdoor seating areas to be provided with comfortable garden furniture and ambient outdoor lighting, providing a welcoming space for tenants to relax, socialise, or enjoy the outdoors at any time of day or evening.

Coffee dock area - A casual space where tenants can relax and chat, helping build a sense of community and connection with neighbours. Wifi to be provided so tenants can feel comfortable and stay connected. These areas are designed to foster community interaction and enhance the overall living experience.

The Happi principles focus on creating homes that offer generous and flexible spaces. This includes larger floor areas with separate utility room/drying areas, balconies, and more natural light, all designed to enhance tenants’ comfort and well-being. These features promote a healthier, more adaptable living environment, allowing for greater freedom in how spaces are used and enjoyed.

The bathroom features upgraded finishes, this includes fully tiled floor. Additionally, it should be equipped with a sleek glass shower door, illuminated mirrors, adding a modern touch while enhancing both functionality and aesthetics. Modern internal finishes that improve both the aesthetics and durability of the living areas.

Enhanced internal lighting to include energy-efficient LED downlighters.

Scooter storage to provide automatic control systems to include smart technology.

SCHEDULE 2

SITE PLAN

SCHEDULE 3

SITE TRANSFER

SCHEDULE 4

SPECIFICATION

SCHEDULE 5

CONTRACT SUM ANALYSIS

SCHEDULE 6

Part I

FORM OF COLLATERAL WARRANTY – sub contractors

SUBCONTRACTOR COLLATERAL WARRANTY

Dated this                  day of                             20

## [SUB-CONTRACTOR]

and

ALPHA HOUSING ASSOCIATION

and

[MAIN CONTRACTOR]

SUB-CONTRACTOR’S WARRANTY

- THIS DEED is made on							20

- BETWEEN

- (1)	[SUB-CONTRACTOR]  whose registered office is at [                                                                          ] (the “Sub-Contractor”);

- (2)	ALPHA HOUSING ASSOCIATION whose registered office is (the [ [       [                                                                          ] the "Beneficiary”);

- (3)	[MAIN CONTRACTOR] whose registered office is at [                                                                          ] (the “Main Contractor”)

- NOW THIS DEED WITNESSES in consideration of the sum of £10.00 paid by the Beneficiary to the Sub-Contractor, receipt of which the Sub-Contractor acknowledges, as follows:

- 1.	INTERPRETATION

  - In this Deed:

- “Building Contract”	means the contract dated [                ] and made between (1) the Beneficiary] and (2) the Main Contractor for the Development;

- “Development”	means [                                                ];

- “Property”	means the site upon which the construction works for the Development are to be carried out at [                                                         ];

- “Sub-Contract”	means the sub-contract dated [                      ] and made between (1) the Main Contractor and (2) the Sub-Contractor for the carrying out of the Sub-Contract Works;

- “Sub-Contract Works”	means the works including any design obligations comprising [                            ] more particularly described in the Sub-Contract.

1.2	In interpreting this Deed:

    - if any party to this Deed is a partnership then the provisions of this Deed will bind each and every such partner jointly and severally;

    - references to the singular shall be deemed to include the plural (and vice versa) and reference to a “person” shall be deemed to include any individual firm unincorporated association or body corporate;

    - references to the Beneficiary shall be deemed to include its successors in title and assignees;

1.2.4	any reference to any enactment includes any consolidation, re-enactment, amendment or replacement of it and any subordinate legislation under it;

1.2.5	headings to Clauses shall be disregarded.

2.	GENERAL

  - The Employer has by the Building Contract employed the Main Contractor to carry out and complete the [design and] construction of the Development.

  - By the Sub-Contract the Main Contractor has appointed the Sub-Contractor to carry out and complete the Sub-Contract Works at the Development on the terms set out therein.

2.4	The Sub-Contractor has agreed to enter into this Deed with the Beneficiary.

3.	SKILL AND CARE

The Sub-Contractor undertakes with and warrants to the Beneficiary that:

  - it has observed and performed and will observe and perform its obligations under the Sub-Contract and without prejudice to the generality of the foregoing insofar as the Sub-Contractor is required by the Sub-Contract to:-

- 3.1.1	design any part of the Development;

      - select materials for incorporation into the Development; or

    - ensure compliance of any part of the Development with a performance specification;

in so doing the Sub-Contractor has used and will continue to use all the reasonable skill, care, diligence and attention to be expected of a competent and fully qualified member of the Sub-Contractor’s trade experienced in carrying out works and services the like of those undertaken or to be undertaken by the Sub-Contractor under the Sub-Contract for works of a similar nature, value, complexity and timescale to the Development;

3.2	it has not specified or used nor will it specify for use or use any products or materials in the Development which at the time of use:

3.2.1	do not conform with British or equivalent international standards or Codes of Practice; or

3.2.2	are generally known within the Sub-Contractor’s trade to be deleterious, in the particular circumstances in which they are specified for use, to health and safety and/or the durability of the Development;

4.	OBLIGATIONS PRIOR TO TERMINATION OF THE SUB-CONTRACT BY THE SUB-CONTRACTOR

4.1	The Sub-Contractor covenants with the Beneficiary that it will not exercise nor seek to exercise any right of termination of its employment under the Sub-Contract or to discontinue the performance of any of its obligations thereunder for any reason whatsoever (including any breach on the part of the Main Contractor) without giving not less than 28 days written notice of its intention to do so to the Beneficiary and specifying the grounds for the proposed termination or discontinuance.

4.2	Any period stipulated in the Sub-Contract for the exercise of a right of termination by the Sub-Contractor of its employment under the Sub-Contract or to discontinue the performance of any of its obligations thereunder shall, nevertheless, be extended as may be necessary to take account of the period of notice required under Clause 4.1.

  - The right of the Sub-Contractor to terminate its employment under the Sub-Contract or to discontinue to discharge its obligations thereunder shall cease within the period of 28 days referred to in Clause 4.1 if the Beneficiary shall give notice to the Sub-Contractor:-

4.3.1	requiring the Sub-Contractor to continue its obligations under the Sub Contract with the Beneficiary or its nominee; and

    - acknowledging that the Beneficiary or its nominee will assume all the obligations of the Main Contractor under the Sub-Contract; and

4.3.3	undertaking that the Beneficiary or its nominee will discharge all payments which may subsequently become due to the Sub-Contractor under the terms of the Sub-Contract and will pay to the Sub-Contractor any sums which have been due and payable to it under the Sub-Contract but which remain unpaid.

4.4	Upon service by the Beneficiary or its nominee of a notice complying with the requirements of Clause 4.3 the Sub-Contract will continue in full force and effect as if the same had been entered into between the Sub-Contractor and the Beneficiary or its nominee to the exclusion of the Main Contractor.

4.5	Compliance by the Sub-Contractor with the provisions of this Clause 4 will not be treated as a waiver of any breach on the part of the Main Contractor giving rise to the right of termination nor otherwise prevent the Sub-Contractor from exercising its rights after the expiration of the notice issued pursuant to Clause 4.1 unless the rights of termination have ceased under the provisions of Clause 4.3.

4.6	This Clause 4 shall cease to have effect upon the prior exercise by any third person of any similar rights of substitution contained in any other agreement concerning the Development and entered into between the Sub-Contractor and such person.

5.	BENEFICIARY’S RIGHTS IN RELATION TO THE SUB-CONTRACT

5.1	Notwithstanding that as between the Main Contractor and the Sub-Contractor the Sub-Contractor’s right of termination of its employment under the Sub-Contract may not have arisen the provisions of Clause 4.4 shall also apply if the Beneficiary gives notice to the Main Contractor and to the Sub-Contractor to the effect that the Beneficiary wishes the provisions of Clause 4.4 to apply and the Beneficiary or its nominee complies with the requirements of Clause 4.3.

5.2	The Sub-Contractor shall not be concerned, or required to enquire whether, and shall be bound to assume that as between the Main Contractor and the Beneficiary the circumstances have arisen permitting the Beneficiary to give notice under Clause 5.1.

5.3	This Clause 5 shall cease to have effect upon the prior exercise by any third person of any similar rights of substitution contained in any other agreement concerning the Development and entered into between the Sub-Contractor and such person.

6.	SUB-CONTRACTOR’S POSITION

By acting in accordance with Clauses 4 and 5 the Sub-Contractor shall not incur any liability to the Main Contractor.

7.	COPYRIGHT

7.1	The copyright in all drawings, reports, specifications, bills of quantities, calculations and other similar documents provided by the Sub-Contractor in connection with the Development shall remain vested in the Sub-Contractor but the Sub-Contractor grants to the Beneficiary and its nominees a non-exclusive irrevocable royalty free licence to copy and use such drawings and other documents and to reproduce the designs contained in them for any purpose related to the Development including (but without limitation) the construction, completion, maintenance, letting, promotion, advertisement, reinstatement, extension and repair of the Development.  Such licence shall include a licence to grant sub-licences and to transfer the same to third parties.

7.2	The Sub-Contractor shall not be liable for any such use by the Beneficiary or its nominees of any drawings and other documents for any purpose other than that for which they were originally prepared by the Sub-Contractor.

7.3	The Beneficiary shall on written request and upon paying a reasonable copying charge therefor, be entitled to be supplied by the Sub-Contractor with copies of the drawings and other items referred to in Clause 7.1.

8.	INDEMNITY INSURANCE

8.1	The Sub-Contractor shall maintain professional indemnity insurance covering (inter alia) all its design liability hereunder upon customary and usual terms and conditions prevailing for the time being in the insurance market, and with reputable insurers lawfully carrying on such insurance business in the United Kingdom, in an amount of not less than £1,000,000 (One million pounds) for any one occurrence or series of occurrences arising out of any one event for a period beginning now and ending 12 years after the date of completion of the Development, provided always that such insurance is available at commercially reasonable rates. The said terms and conditions shall not include any term or condition which might adversely affect the rights of any person to recover from the insurers pursuant to the Third Parties (Rights Against Insurers) Act (Northern Ireland) 1930, or any amendment or re-enactment thereof.

8.2	Any increased or additional premium required by insurers by reason of the Sub-Contractor’s own claims record or other acts, omissions, matters or things particular to the Sub-Contractor shall be deemed to be within commercially reasonable rates.

8.3	The Sub-Contractor shall immediately inform the Beneficiary if such insurance ceases to be available at commercially reasonable rates in order that the Sub-Contractor and the Beneficiary can discuss means of best protecting the respective positions of the Beneficiary and the Sub-Contractor in respect of the Development in the absence of such insurance.

8.4	The Sub-Contractor shall fully co-operate with any measures reasonably required by the Beneficiary, including (without limitation) completing any proposals for insurance and associated documents, maintaining such insurance at rates above commercially reasonable rates if the Beneficiary undertakes in writing to reimburse the Sub-Contractor in respect of the net cost of such insurance to the Sub-Contractor above commercially reasonable rates or, if the Beneficiary effects such insurance at rates at or above commercially reasonable rates, reimbursing the Beneficiary in respect of what the net cost of such insurance to the Beneficiary would have been at commercially reasonable-rates.

8.5	As and when reasonably requested to do so by the Beneficiary the Sub-Contractor shall produce for inspection reasonable documentary evidence that its professional indemnity insurance is being maintained.

8.6	The above obligations in respect of professional indemnity insurance shall continue notwithstanding termination of this Deed for any reason whatsoever, including (without limitation) breach by the Beneficiary.

9.	LIABILITY PERIOD

The obligations of the Sub-Contractor under this Deed shall cease 12 years from the date of completion of the Development save in respect of any claim under this Deed where proceedings have been issued during such 12 year period.

10.	ASSIGNMENT

10.1	The Sub-Contractor consents to the benefit of this Deed being assigned twice only PROVIDED ALWAYS that the maximum number of two assignments referred to above shall not be affected by assignments by way of security and assignments to and from subsidiary or other associated companies within the same group of companies as the Beneficiary so long as such assignee company remains within the same group of companies as the Beneficiary.

10.2	The Sub-Contractor shall not be entitled to contend that any person to whom this Deed is assigned in accordance with Clause 10.1 is precluded from recovering under this Deed any loss incurred by such assignee resulting from any breach of this Deed (whenever happening), by reason that such person is an assignee and not a named promisee under this Deed.

11.	NOTICES

11.1	Any notice required to be given under this Deed shall be in writing and service shall be effected at the relevant address shown on the first page of this Deed (or at such other address as the party may hereafter specify in writing for this purpose) and service shall be effected by one of the following methods:

11.1.1	personally (in which case service shall be effected on delivery);

11.1.2	by first class pre-paid post (in which case service shall be effected on the second business day following posting); or

11.1.3	by facsimile (in which case service shall be effected on dispatch)

12.	EXTRANEOUS RIGHTS

  - This Deed shall not negate or diminish any duty or liability otherwise owed by the Sub-Contractor to the Beneficiary.

12.2	No approval or inspection of the Development or of any designs or specifications and no testing of any work or materials by or on behalf of the Beneficiary and no omission to inspect or test shall negate or diminish any duty or liability of the Sub-Contractor arising under this Deed.

12.3	This Deed may be executed in any number of counterparts all of which when taken together shall constitute one and the same instrument.

12.4	This Deed does not create any right enforceable by any person not a party to it (whether pursuant to the Contracts (Rights of Third Parties) Act 1999 or otherwise) except that a person who is the successor to or the permitted assignee of the rights of the Beneficiary is deemed to be a party to this Deed.

13.	GOVERNING LAW

This Deed is subject in all respects to the law of Northern Ireland and the Northern Irish Courts shall have exclusive jurisdiction with regard to all matters arising under or in connection with it.

EXECUTED AS A DEED by the parties on the date which first appears in this Deed.

We undertake to execute this deed with Sub-Contractors as required by the Employer.

EXECUTED AND DELIVERED AS A DEED BY THE MAIN CONTRACTOR

hereinbefore mentioned namely ____________________________________________

by affixing hereto its common seal

in the presence of:

OR ____________________________________________________________________________

acting by a director and its secretary*/two directors* whose signatures are here subscribed:

namely __________________________________________________________________

[Signature]________________________________________________________ DIRECTOR

and _____________________________________________________________________

[Signature]_______________________________________________ SECRETARY/DIRECTOR*

DATE:

EXECUTED AND DELIVERED AS A DEED BY THE SUB-CONTRACTOR

hereinbefore mentioned namely ____________________________________________

by affixing hereto its common seal

in the presence of:

OR ____________________________________________________________________________

acting by a director and its secretary*/two directors* whose signatures are here subscribed:

namely __________________________________________________________________

[Signature]_________________________________________________________ DIRECTOR

and ____________________________________________________________________

[Signature]_______________________________________________SECRETARY/DIRECTOR*

DATE: ____________________________________________________________________________

EXECUTED AND DELIVERED AS A DEED BY THE BENIFICIARY [ALPHA HOUSING ASSOCIATION LTD]

hereinbefore mentioned namely ____________________________________________

by affixing hereto its common seal

in the presence of:

OR ____________________________________________________________________________

acting by a director and its secretary*/two directors* whose signatures are here subscribed:

namely __________________________________________________________________

[Signature]________________________________________________________ DIRECTOR

and _____________________________________________________________________

[Signature]_______________________________________________ SECRETARY/DIRECTOR*

DATE:_____________________________________________________________________________

Part II

Contractor’s Warranty

Deed of Warranty

THIS DEED is made on [insert date]

BETWEEN:

- [insert] [(registered number [insert])] [whose registered office is at] [of] [insert] (“Beneficiary”) which expression includes its permitted assignees;

- [insert] [(registered number [insert])] [whose registered office is at] [of] [insert] (“Consultant”); and

- [EMPLOYER (Pre-Novation)] [CONTRACTOR (Post-Novation)] (registered number [insert]) [whose registered office is at] [of] [insert] (“Employer/Contractor”)]].

WHEREAS:

- [The Beneficiary] [The Employer] [[insert] (“Employer”)] has [engaged the Consultant] under an agreement in writing dated [insert] (“Appointment”) in relation to the design and construction of [insert] at [insert] (“Project”)

- The [Employer] [Beneficiary] has engaged [the Contractor] [[insert] (“Contractor”)] under an agreement in writing dated [insert] (“Building Contract”) in relation to the Project

(C)	The [Employer] [Beneficiary] has novated the Appointment to the Contractor]

(C/D)	[recite nature of Beneficiary’s interest]

(D/E)	The Consultant has agreed to enter into this Deed for the benefit of the Beneficiary

WITNESSES:

- DUTY OF CARE

The Consultant covenants with the Beneficiary that it has performed and will continue to perform all of its obligations under the Appointment in accordance with all the terms and conditions thereof.

- COPYRIGHT

  - Copyright in the Documents (as defined in the Appointment) shall be retained by the Consultant but the Consultant hereby grants to the Beneficiary a royalty-free irrevocable non­exclusive licence to copy and use all or any of the Documents and to reproduce the same for any purpose whatsoever relating to the Project.  Such licence shall be assignable and shall include the right to grant sub-licences.  The Consultant will not be liable for any use of the Documents for any purpose other than that for which the same are or were prepared and/or provided.

  - The Consultant shall (if so requested by the Beneficiary at any time) give the Beneficiary access to and/or provide copies of all or any of the Documents referred to in clause 2.1 (subject to the Beneficiary being responsible for the Consultant's reasonable copying costs).

- INSURANCE

  - The Consultant confirms that it maintains and shall maintain professional indemnity insurance with an insurer or underwriter of good repute covering the Consultant's obligations under this Deed on the basis of and with an indemnity limit of not less than the amount stated in schedule 1 of the Appointment until 12 years from the date of Practical Completion (as defined in the Building Contract) (or 12 years from the date of termination of the Appointment if earlier) provided that such insurance remains generally available to members of the Consultant's profession in the UK insurance market at commercially reasonable rates and terms.

  - The Consultant shall notify the Beneficiary immediately if such insurance ceases to be available and shall co-operate with the Beneficiary to discuss the best means of protecting their respective interests in such circumstances and shall at the Beneficiary's option maintain such insurance above commercially reasonably rates if the Beneficiary undertakes in writing to reimburse the Consultant in respect of the net cost of such insurance above commercially reasonably rates or again at the Beneficiary's option the Consultant shall obtain in respect of any relevant period such reduced cover (if any) as is available and as would be fair and reasonable in the circumstances for the Consultant to obtain.

  - The Consultant shall as and when reasonably required by the Beneficiary to do so provide satisfactory documentary evidence to the Beneficiary that the insurance referred to in this clause 3 is being maintained.

- ASSIGNMENT

  - The Beneficiary (which for the purposes only of this clause 4.1 shall mean the person named as the first party to this Deed only) may assign the benefit of this Deed and such assignee may then assign the benefit of this Deed in each case by way of absolute legal assignment to any person acquiring an interest in the Project without the consent of the Consultant being required. Subject to clause 4.2 any assignments additional to those provided by this clause shall only be permitted with the consent of the Consultant (which consent shall not be unreasonably withheld or delayed).

  - The benefit of this Deed may be assigned:

    - by way of security and/or by way of re-assignment on redemption by or to the Beneficiary; and/or

    - to any company which is a member of the same group of companies as the Beneficiary

which assignment(s) shall not count as an assignment for the purposes of clause 4.1.

- NON-WAIVER

The liability of the Consultant under this Deed shall not be modified released diminished or in any way affected by any independent inspection investigation or enquiry into any relevant matter which may be made or carried out by or for the Beneficiary nor by any failure or omission to carry out any such inspection investigation or enquiry nor by the appointment by the Beneficiary of any independent firm company or party whatsoever to review the progress of or otherwise report to the Beneficiary in respect of the Project nor by any action or omission of any such firm company or party whether or not such action or omission might give rise to any independent liability of such firm company or party to the Beneficiary.

- CONTINUING EFFECT

Notwithstanding the completion of the Project the provisions of this Deed shall continue to have effect as between the Consultant and the Beneficiary.

- CONSULTANT'S LIABILITY

  - No proceedings in respect of the Consultant's liability under this Deed may be commenced more than 12 years after the date of Practical Completion of the Project under the Building Contract.

  - Subject to clause 7.3 below the Consultant shall:

    - owe the same but no greater duties to the Beneficiary than it would owe to the Beneficiary if the Beneficiary was jointly named as the employer under the Appointment; and

    - be entitled in any action or proceedings by the Beneficiary under this Deed to rely on any limitation in the Appointment and to raise the equivalent rights in defence of liability as it would have against the Beneficiary if the Beneficiary was jointly named as the employer under the Appointment

  - Nothing in clause 7.2 shall entitle the Consultant to contend in any action or proceedings that the Beneficiary can only recover reduced or nominal damages because the employer under the Appointment has suffered no loss or a loss that is less than that actually suffered by the Beneficiary or to raise against the Beneficiary any set off or counterclaim that the Consultant would be entitled to raise against the employer under the Appointment.

- CONTRACTS (RIGHTS OF THIRD PARTIES) ACT 1999

A person who is not party to this Deed shall have no right under the Contracts (Rights of Third Parties) Act 1999 to rely upon or enforce any term of this Deed.

- DISPUTES

  - The Beneficiary and the Consultant hereby agree that any and all disputes as to the construction interpretation validity and application of this Deed and any and all matters or things of whatsoever nature arising out of or in connection therewith shall be governed by and construed in accordance with the law of England.

  - Save in relation to any enforcement proceedings the Beneficiary and the Consultant irrevocably submit to the exclusive jurisdiction of the English courts over any claim dispute or matter arising under or in connection with this Deed.

- NOTICES

Any notices given under this Deed shall be in writing and may be served by hand or by prepaid special delivery post or recorded delivery addressed to the party to whom it is given Such notice to be served in the case of a Corporation to its registered office for the time being In any other case notice may be served at the address hereinbefore set out or such other address as may be notified by the relevant party to the other party and any notice so given by prepaid special delivery or recorded post shall be deemed to have been served 48 hours after the time of posting and any notice delivered by hand shall be deemed to have been served immediately upon delivery.

- CONFIRMATION OF AGREEMENT - FUND/PURCHASER[/EMPLOYER] WARRANTY ONLY

The [Employer] [Contractor] has joined in this Deed to confirm its agreement to the arrangements made and contemplated by it.

- DETERMINATION BY THE CONSULTANT – FUND/PURCHASER[EMPLOYER] WARRANTY ONLY

  - The Consultant warrants to the Beneficiary that it shall not terminate or treat as terminated the Appointment or discontinue the performance of any of its services or obligations under the Appointment without first giving to the Beneficiary not less than 28 days' prior notice of the Consultant's intention to do so specifying the grounds for so doing. For the avoidance of doubt temporary suspension under Section 112 of the Housing Grants (Construction & Regeneration) Act 1996 or paragraph 7 of schedule 3 of the Appointment shall not constitute discontinuance but the Consultant shall notify the Beneficiary immediately such temporary suspension commences.

  - If the Beneficiary serves on the Consultant a notice in accordance with clause 12.3 the Consultant shall not terminate or treat as terminated the Appointment or discontinue the performance of any of its services or obligations under the Appointment but service of such notice shall not prejudice any other right or remedy the Consultant may have under or in connection with the Appointment.

  - Unless the employment of the Consultant shall have terminated previously (and whether or not the Consultant shall have served notice on the Beneficiary pursuant to clause 12.1) if the Beneficiary serves upon the Consultant a notice to do so the Consultant shall thereafter accept the instructions of the Beneficiary or its appointee to the exclusion of the Employer under and in connection with the Appointment.

  - As against the Employer and the Beneficiary the Consultant shall be entitled and obliged to rely upon and to comply with such notice served by the Beneficiary under clause 12.3 and shall not make any enquiry into the entitlement of the Beneficiary as against the Company to serve such notice.

  - As from the date of service of notice under clause 12.3 the Beneficiary or its appointee shall assume all the rights and perform all the obligations of the Employer under the Appointment provided that this shall not affect or derogate from any right of action the Employer may have against the Consultant in respect of any breach of duty of the Consultant under or in connection with the Appointment happening prior to the date of service of notice by the Beneficiary under clause 12.3.

  - Within 21 days after serving notice under clause 12.3 the Beneficiary shall pay to the Consultant an amount equal to the fees and disbursements then owing to the Consultant under the Appointment.

  - If the employment of the Consultant under the Appointment is terminated before service of any notice under clause 12.3 then if required to do so by notice served by the Beneficiary not later than 12 weeks after the date of such termination the Consultant shall enter into a new agreement with the Beneficiary or its appointee on the same terms as the Appointment but with such revisions as the Beneficiary shall reasonably require and the Consultant may approve acting reasonably to reflect altered circumstances Forthwith upon the execution of such new agreement the Beneficiary shall pay to the Consultant an amount equal to the fees and disbursements (excluding cancellation fees) then owing to the Consultant under the Appointment.

- FURTHER WARRANTIES - FUND/PURCHASER[/EMPLOYER] WARRANTY ONLY

The Consultant shall as the Beneficiary may at any time or times require (and whether before or after completion of the Services (as defined in the Appointment) or the termination of the Consultant's engagement under the Appointment) execute and deliver to the Beneficiary within 14 days of receipt of engrossments from the Beneficiary a deed or deeds of collateral warranty in favour of any party (excluding the Beneficiary) in whose favour the Consultant may have been required to execute a deed of warranty under the Appointment (save where such deed of warranty has already been requested and executed by the Consultant).

IN WITNESS whereof this document has been executed and delivered as a Deed the day and year first before written

EXECUTED AS A DEED by the parties on the date which first appears in this Deed.

We undertake to execute this deed with Sub-Contractors as required by the Employer.

EXECUTED AND DELIVERED AS A DEED BY THE CONSULTANT

hereinbefore mentioned namely ____________________________________________

by affixing hereto its common seal

in the presence of:

OR ____________________________________________________________________________

acting by a director and its secretary*/two directors* whose signatures are here subscribed:

namely __________________________________________________________________

[Signature]________________________________________________________ DIRECTOR

and _____________________________________________________________________

[Signature]_______________________________________________ SECRETARY/DIRECTOR*

DATE:

EXECUTED AND DELIVERED AS A DEED BY THE EMPLOYER (Pre-Novation) / CONTRACTOR (Post-Novation)

hereinbefore mentioned namely ____________________________________________

by affixing hereto its common seal

in the presence of:

OR ____________________________________________________________________________

acting by a director and its secretary*/two directors* whose signatures are here subscribed:

namely __________________________________________________________________

[Signature]_________________________________________________________ DIRECTOR

and ____________________________________________________________________

[Signature]_______________________________________________SECRETARY/DIRECTOR*

DATE: ____________________________________________________________________________

EXECUTED AND DELIVERED AS A DEED BY THE BENIFICIARY [ALPHA HOUSING ASSOCIATION LTD]

hereinbefore mentioned namely ____________________________________________

by affixing hereto its common seal

in the presence of:

OR ____________________________________________________________________________

acting by a director and its secretary*/two directors* whose signatures are here subscribed:

namely __________________________________________________________________

[Signature]________________________________________________________ DIRECTOR

and _____________________________________________________________________

[Signature]_______________________________________________ SECRETARY/DIRECTOR*

DATE:_____________________________________________________________________________

Part III

Architect’s Warranty

Dated				20

(1)

ALPHA HOUSING NORTHERN IRELAND LIMITED  (2)

_____________________________________

CONSULTANT’S DEED OF WARRANTY

in favour of an owner of a development at

Contents

Memorandum

Clause

1	Duty of care

2	Professional indemnity insurance

3	Assignment

4	Copyright

5	Extraneous rights

6	Contracts (Rights of Third Parties) Act 1999

7	Expiry of warranty

8	Service of notice

9	Governing law and interpretation

Memorandum

Date of this Deed				day of			20

Developer

Contractor

Beneficiary	ALPHA HOUSING NORTHERN IRELAND LIMITED (Company No. NP) whose registered office is situate at       .

Consultant’s profession	Architects

Development	Construction of [       ]

Site

Date of Appointment			day of				20

Date of Building Contract			day of				20

Beneficiary’s interest	Owner of the Development

Clause 2:  (Professional	(a)	Limit of indemnity: not less than £

Indemnity insurance)		£5,000,000.00 for any occurrence or series of occurrences arising out of each and every event

(b)	Excess: not exceeding £1,000.00.

Parties

(1)	The Consultant

(2)	The Beneficiary

WHEREAS

(A)	The “[Contractor]” “[Developer]” and the Consultant have entered into an appointment (Appointment) under which the Consultant has agreed to perform certain services (Services) and to perform certain other obligations in connection with the Development (which expression includes the Site and the works (Works) constructed or to be constructed on or adjacent to the Site or either of them as the case requires).

(B)	The Beneficiary and the Contractor have entered into a building contract (Building Contract) under which the Contractor has agreed to design or complete the design of and to construct the Works.

IT IS AGREED in consideration of the sum of £1.00 paid by the Beneficiary, receipt of which the Consultant acknowledges, as follows:

1.	Duty of Care

The Consultant warrants to the Beneficiary that it has performed and/or subject to the terms of the Appointment shall perform the Services and its other obligations under the Appointment, and that in doing so it has used and/or shall use all the professional skill and care and diligence reasonably to be expected of suitably qualified and experienced consultants undertaking duties similar to the Services in relation to projects similar to the Development.

2.	Professional indemnity insurance

2.1	The Consultant warrants to the Beneficiary that there is in force a policy of professional indemnity insurance covering the liabilities of the Consultant for negligence under the Appointment and this Deed, conforming to the relevant requirements specified in the Memorandum.  The Consultant agrees to maintain such insurance at all times until 12 years after the practical completion of the Development under the Building Contract (or if sooner until 12 years after the termination of the employment of the Consultant under the Appointment), provided such insurance is available on commercially reasonable terms having regard (inter alia) to premiums required and policy terms obtainable.

2.2	If for any period such insurance is not available on commercially reasonable terms, the Consultant shall forthwith inform the Beneficiary, and shall obtain in respect of such period such reduced level of professional indemnity insurance as is available and as would be fair and reasonable in the circumstances for the Consultant to obtain.  Any increased or additional premium required by insurers because of the Consultant's claims record or other acts, omissions, matters or things particular to the Consultant shall be deemed to be within commercially reasonable rates

2.3	Whenever reasonably required to do so by the Beneficiary, the Consultant shall provide to the Beneficiary documentary evidence that the insurance required under this Deed is being maintained.

3.	Assignment

3.1	The Beneficiary may assign all of its rights under this Deed:

(a)	to any Mortgagee and by way of re-assignment on redemption; and

(b)	by absolute assignment to any Group Company of the Beneficiary; and

(c)	by absolute assignment on two other occasions only without counting as an assignment under clause 3.1 (a) or 3.1 (b).

3.2	In this Deed references to the Beneficiary include where the context admits its permitted assignees, but not so as to permit more than two assignments under clause 3.1(c).

3.3	The Consultant shall not be entitled to contend that any person to whom this Deed is assigned in accordance with clause 3.1 is precluded from recovering under this Deed any loss incurred by such assignee resulting from any breach of this Deed, (whenever happening) by reason that such person is an assignee and not a named promisee hereunder.

4.	Copyright

4.1	The Consultant grants to the Beneficiary an irrevocable, non-exclusive royalty-free licence to use and reproduce any drawings, calculations, specifications and/or other documents produced by the Consultant under the Appointment and any designs contained in them (Documents) for any purpose connected with the Development (other than by the reproduction of any such designs in any extension to the Development) and to grant sub-licences in the terms of this licence, but copyright in the Documents shall remain vested in the Consultant.  The Consultant will not be liable for any use of the Documents for any purposes other than those for which the same are or were produced.  The Beneficiary shall on written request and upon paying a reasonable copying charge, be entitled to be supplied by the Consultant with full and property copies of the Documents.

4.2	The Consultant warrants to the Beneficiary that the use of the Documents for the purpose of the Development will not infringe the rights of any third person.

4.3	The Consultant agrees to waive any right to be identified as author of the Documents in accordance with section 77, Copyright Designs and Patents Act 1988 and any right not to have the Documents subjected to derogatory treatment in accordance with section 80 of that Act as against the Beneficiary or any licensee or assignee of the Beneficiary.

5.	Extraneous rights

5.1	This Deed shall not negate or diminish any duty or liability otherwise owed by the Consultant to the Beneficiary.

5.2	No approval or inspection of the Development or of any designs or specifications and no testing of any work or materials by or on behalf of the Beneficiary and no omission to inspect or test shall negate or diminish any duty or liability of the Consultant arising under this Deed.

6.	Contracts (Rights of Third Parties) Act 1999

This Deed is not intended to confer any rights on any third party pursuant to the Contracts (Rights of Third Parties) Act 1999.

7.	Expiry of warranty

No proceedings shall be commenced against the Consultant under this Deed more than 12 years after the practical completion of the Development under the Building Contract (or, if earlier, more than 12 years after the employment of the Consultant under the Appointment is terminated).

8.	Service of notice

Any notice to be served under this Deed must be in writing and must be served by hand or by recorded delivery, and in the case of a corporation must be served at its registered office for the time being.  In any other case notice may be served at any address for the time being of the person to be served.  Service shall take effect, if given by hand, on the date of delivery.  If given by post, it shall take effect 2 days after posting, excluding Saturdays, Sundays and statutory holidays.

9.	Governing law and interpretation

9.1	The law of this Deed is Northern Ireland law and the courts of Northern Ireland shall have jurisdiction with regard to all matters arising under it.

9.2	The Memorandum is part of this Deed and the definitions given in the Memorandum and in the Recitals apply to this Deed.

9.3	In this Deed:

(a)	Group Company means any subsidiary company or holding company of the Beneficiary, or another subsidiary or holding company of such company, as subsidiary and holding company are defined in Article 4 of The Companies (NI) Order 1986;

(b)	Mortgagee means a person having or acquiring a mortgage or charge over the Development or any part of it;

(c)	Purchaser means a person having or acquiring a freehold interest in the Development or any part of it, or a purchaser for a capital consideration of a leasehold interest; and

9.4	In this Deed:

(a)	Development includes part of the Development;

(b)	Person includes a firm and any entity having legal capacity;

(c)	any term importing gender shall include any gender;

(d)	any term importing the singular includes the plural and vice versa; and

(e)	any reference to any clause or schedule or appendix is a reference to such clause or schedule or appendix of or to this Deed.

9.5	For the purposes of clause 1 (Duty of care), references to the Appointment include any previous appointment of the Consultant by the Developer (whether or not in writing) to provide services of the kind mentioned in the Appointment in connection with the Development.

9.6	Clause headings do not form part of or affect the interpretation of this Deed.

Executed and delivered as a deed:

Signed as a deed and delivered by			}

}

}

…………………………………………….		}

Witness Signature					}

}

…………………………………………….		}

Print name						}

[OR]

Executed as a deed by					}	…………………………..

[The Consultant]					}	Director

by the signature of a director 				}	…………………………..

}	Print name

}

[OR]

Signed as a deed and delivered by			}	…………………………..

[LLP}							}	Member

}

}	…………………………..

}	Print name

}

}	…………………………..

}	Member

}

}	…………………………..

}	Print name

SCHEDULE 7

PROJECT EXECUTION PLAN

SCHEDULE 8

ALPHA’S PROCEDURES

Handover & Practical Completion Procedure

1 PURPOSE

To ensure that there is a smooth transition of responsibilities at handover of new build and rehabilitated dwellings on reaching Practical Completion

To ensure that there is clarity in term of roles and responsibility between all Association staff involved.

2 SCOPE

This procedure provides guidance for the snagging and handover of dwellings reaching Practical Completion.

3 ROLES AND RESPONSIBILTIES

Development Department

- Agree date of handover

- Consult with the Housing, Asset and Finance Departments

- Co-ordinate all pre-handover snagging

- Ensure completion of administrative duties prior to handover

- Formally accept handover from the Main Contractor

- Forward a copy of the Certificate of Practical Completion to relevant departments

- Process Practical Completion tranche claim and forward to DPG and copy in Finance Department

Housing Department

- Agree date of handover

- Agree tenant viewing days

- Attend demonstrations and handover meeting

Assets Department

- Attend demonstrations and handover meeting

- Undertake pre-handover snagging with CoW & Employers Agent

- Invite MTC Heating Maintenance contractor to snagging

- Arrange Fire Strategy pre completion inspections with Contractor

- Sign off receipt of Health and Safety, Operation Manuals and Servicing and Maintenance schedule

- Complete electricity and gas readings on the day of handover.

- In conjunction with the Development team ensure that all Certification is in place prior to commencement of 1st snagging Inspection (or at least 2 weeks prior to the handover date).

Clerk of Works

- Undertake snagging and final inspections

- Ensure snagging has been completed prior to handover and if applicable advise the relevant Departments of any issues that may delay handover and advise on appropriate actions that maybe required i.e., cancellation / delay of the handover.

- Agree date of and attend handover meeting

4 PROCEDURE

3 months prior to Practical Completion the Development Department will :

- Invite the relevant Housing and Assets personnel to attend site meetings.

- Arrange with Finance, Housing and Assets to agree final rents and service charges.

- Identify those components which require servicing contracts as per the attached maintenance schedule Appendix 1

8 weeks prior to handover the Development Department will:

- Provide all property input data for entry onto the internal accounting and management system. This information should be circulated to all departments.

6 weeks prior to handover the Development Department will :

- Provide confirmation to Housing and Assets that the Contractor gas given their six week notice for practical completion.

- The date of handover shall be agreed between the appropriate members of staff, the Employers Agent, the Clerk of Works, and the Main Contractor.

- Alpha will only accept handovers on Tuesday, Wednesday or Thursdays. Any agreed handover shall be at least to two weeks clear of any major public holiday. These dates can be amended only with the agreement of Housing Management.

- Housing and Contractor to arrange a tenant viewing day.

Snagging

The Employers Agent and Clerk of Works in conjunction with the Assets are responsible for checking the building prior to handover and preparing a snagging list.

The first snagging will take place 3 weeks and two days prior to the date of

handover:

- Formal snagging lists are to be issued to the Main Contractor by the Employers Agent/Clerk of Works within 48 hours of being undertaken.

- All M&E equipment is to be commissioned in order that snagging can commence.

The second snagging will take place one week and two days prior to the date of handover:

This can only proceed on receipt of Building Control Completion Certificates.

The Clerk of Works & Employers Agent will check the snag list for all completed items.The Employers Agent/Clerk of Works will issue a list of outstanding items to the Main Contractor within 24 hours of snagging being undertaken.

Information Required Prior to Handover

The following documents (one hard copy and one electronic copy), including where appropriate certificates/guarantees, for each Dwelling will be provided by the Developer to Alpha on or before the Completion Date save the items in bold which must be supplied by the Developer to Alpha at least two weeks before the Completion Date

- Tenancy Pack for each Residential Unit

- Health and Safety File (Drawings/ Certificates /Approvals/ Risk Registers etc.)

- Two sets of As-built architectural, Civils, Electrical, Mechanical and Structural drawings as completed in paper format and in digital format.

- Intellectual Property Licence

- Operational & Maintenance Manuals

- Operational & Maintenance drawings - Electrical Contractor

- Operational & Maintenance drawings - Mechanical Contractor

- Operational & Maintenance drawings - Principal Contractor

- Stamped Planning Approval including drawings, approval form with conditions and informatives, application and approval of any non-material changes

- Planning Condition Discharge Statement

- If applicable a certificate by any report provider confirming that 
all the works recommended in the Environmental Reports have been satisfactorily completed

- Site Layout showing site numbers and postal addresses

- Practical (or Sectional) Completion Certificate

- Building Control Completion Certificates for each Residential Unit

- All Collateral warranties

- Structural & Defects Liability Insurance documentation

- Structural Insurance Certificate for each Residential Unit

- Article 32 Roads Service agreement if applicable

- TAS approval if applicable

- Preliminary Road Adoption Certificate if applicable

- Final Adoption Certificate and testing Certificate if applicable

- Article 161 or 163 Agreement if applicable

- Article 154 sewer requisition if applicable

- NI Water Preliminary Inspection Certificate as soon as available if applicable

- NI Water Final Adoption Certificate if applicable

- DFI Preliminary and Final Inspection Certificate as soon as available if applicable

- Secured by Design Certificate

- Secured by Design Certificates for Windows and Doors (windows to have sticker applied to confirm SBD certification)

- Gas Safety Certificate i.e., CP12 for each Residential Unit or equivalent if oil heating

- Boiler warranties (including registration)

- Installation Certificates - Unvented Hot Water Storage Systems and Warranties

- Carbon Monoxide Detection Certificates

- Smoke alarm test certificate

- NICEIC Electrical Test Certificates for each Dwelling

- Fire Alarm Test Certificates for each Dwelling

- Energy Performance Certificates

- Full SAP Calculations printout

- Air Leakage Test Report

- Warranties for all installed equipment

- Contractors Tenant Pack explaining operational, and maintenance of items installed in the house/ apartment

- Heating Test Certificates

- If applicable 10-year guarantee for bonded bead insulation

- If applicable MVHR commissioning certificates

- If applicable Collateral Warranties for the benefit of Alpha from the providers of the Environmental Reports in the format recommended by their professional body or failing same as recommended by or acceptable to the Royal Institute of Chartered Surveyors

- Lift commissioning certificate and warranty

- Energy Performance Certificate

Pre-Handover Meeting

One week prior to the date of handover:

- The contractor will demonstrate the building services, to the relevant Housing and Assets personnel.

- Development will complete and update property information sheets and issue to all Departments.

- The final snagging inspection will take place; the Clerk of Works, Employers Agent and Assets representative to attend the final check of the snag list.

- The Assets and Development team shall also ensure that all final drawings, Health and Safety file and service manuals, certifications are duly received by the Association and signed off by the relevant consultants.

- The Development team will ensure that the Finance Department have been informed that responsibility for the building insurance will pass to Alpha on the date of handover

- NIE Change in Responsibility forms have been completed prior to readings being recorded on morning of handover.

- Gas cards have been completed prior to readings being recorded if applicable on morning of handover.

- Royal Mail has been contacted to ensure that postal addresses / postcodes are made live on the date of handover.

- Design Team to ensure and confirm that all statutory requirements e.g., planning requirements / building control have been met

Day of Handover

- The Employers Agent is responsible for listing any outstanding snagging items on the Practical Completion Certificate along with an action plan for completion and ensuring that the work is completed by the Main Contractor.

- Assets will complete handover checks and forward details of the main contractors and subcontractors telephone numbers and emergency out of hours contact details to all departments and to Connect 24.

- At handover, the Contractor is advised of Alpha Housing protocol following No Action from Contractor to reported Defects during the Defects Liability Period, including checking all out of hours numbers. No action will result in Alpha Housing attending to the reported Defect without prior warning the cost of any resultant works will be deducted from the next/ final payment.

- Assets will forward completed electricity and gas cards readings to the relevant utility provider and pass a record of the gas readings on day of handover to Housing

- Housing shall be available to collect all keys, NIE cards, Gas cards and tenant information packs for heating systems, door-entry systems and warden call/alarm systems as required.

- General Waste bin, recycle bins and washing lines should be left in the living room/Garden of the properties which are handing over.

- On the date of handover, the Employers Agent shall issue a Certificate of Practical or Partial Completion to the Association.

- Development will issue a copy of the Certificate of Practical Completion to the Assets for their records.

- The appropriate member of staff shall process the final tranche claim to the DPG in accordance with Housing Association Guide. Check that previous certification at acquisition and start on site stages are still valid and any issues highlighted in the Project Approval Annex response have been actioned.

- Housing to arrange for tenant satisfaction survey on completed developments to be conducted and any development related comments passed to Development for continuous improvement / lessons learned information.

Defects Liability PEriod

1.0 Purpose

- To ensure that all defects are dealt with in accordance with the procedures laid down by the DFC Housing Association Guide;

- To ensure that there is clarity in terms of roles and responsibility between the Development and Assets Teams;

- To ensure that defects are undertaken by the Main Contractor and that Assets do not assign the work to 3rd parties.

- To ensure that all snagging and defects procedures, as agreed between Teams, are being implemented.

- To ensure clarity on allocation of costs in cases of defects and repairs due to incorrect operation by service user; and

- To ensure that Development establish the defect procedures for Assets to implement during the defect’s correction period.

2.0 Scope

This procedure provides guidance for the administration of defects during the 12-month defect correction period. It should be read in conjunction with Handover and Practical Completion Procedures.

3.0 Roles and Responsibilities

3.1 Departmental Roles & Responsibilities:

Development Team

- Facilitate the implementation of the Defects Procedures and liaise with the Main Contractor and the Assets Team to ensure that all Defects are addressed within the agreed timescales.

- Out of hours defects will be addressed via Connect 24, the scheme upon handover should be notified to Connect 24.

- Ensure that both the Employers Agent and the Main Contractor are aware of the Associations policy for defects to ensure they are compliant with same during the defects correction period.

- Manage any non-performance issues as reported by Assets.

- Formally handover unit to Assets Team, who have the responsibility for the Maintenance of the unit.

Assets Team

- Manage internal communication and administration to ensure defects policy can be implemented.

- Advise Development of any issues regarding defects or latent defects.

- Advise Development by email or telephone of any non-performance issues complete with evidence of same.

- Appropriate management of all reported defects which are reported during the 12-month defect period, ensuring these are responded to within the agreed timescales, ensuring the defects are checked on a weekly basis and any issues which have not been attended to are highlighted to the Employers Agent in order that they can raise these issue directly with the Contractor to ensure the issue is closed promptly.

- Undertake end of defect correction period inspections and issue a defect schedule a minimum of 20 working days prior to the defect date.

- At the End of DCP to manage internal communication, to notify all relevant parties that the unit is out of defects i.e. Housing and Connect 24.

3.2 Individual Roles and Responsibilities:

Development Team

- Responsible for advising and preparing a report to SMT on items that are classed as a major or latent defect.

- Responsible for liaising with the Housing and Assets Teams to ensure that, all reasonable efforts are expended to resolve defects quickly with minimal inconvenience to the tenant.

- Overall responsibility for ensuring the defects policy is implemented.

- Liaise with Assets Team throughout defects period, but in particular before the end of 12 months defect correction period to identify any issues which may not have been included within the defects inspection but require addressing prior to the end of the last defect correction period.

- Ensure that Employers Agent issues the Defects Certificate at the later of the defects date (12 months from PC) or the end of the last defect correction period.

- Advise the Assets Team when the units are out of the defects period.

- Advising on lessons learned and on any items that may require further discussions (i.e. specification, materials not fit for purpose)

- Ensure all records are kept on Development electronic filing system.

Employers Agent

- Ensure delivery of Alpha’s defects policy in the format provided.

- Ensure adequate resources are available to implement policy.

- Ensure items requiring service at end of defects period are serviced.

- Employers Agent to make Contractor aware that any scheduled equipment servicing not completed within 10th month of Defect Period will be completed by Alpha and cost recouped deducted from Him/Her.

- Ensure defects reported are actioned within agreed time scales.

- Undertake final snagging with the CoW & Assets Team at the end of the defect’s liability period.

- Ensure the end of defects period is completed within 12 months of projects handover.

- Provide Alpha with a formal notification when the building is out of the Defects Period (the last defect correction date) This may well be in advance and agreement of the Statement of Account and will be the date when the Assets Team commence Assets of the unit.

Assets Team

- Ensure that all defects are reported directly through to the relevant Contractor.

- Ensure that defects are not incorrectly actioned as repair work and therefore billed to Alpha’s Assets contractors.

- Ensure appropriate management of all reported defects during the 12-month defect period, ensuring these are responded to within the agreed timescales, and that any issues which have not been attended to are highlighted to the Employers Agent in order that they can be raised directly with the Contractor to ensure that issues are closed promptly.

- Ensure the Employers Agent makes the Contractor aware that any scheduled equipment servicing not completed within 10th month of Defect Period will be completed by Alpha and cost recouped from Contractor.

- Facilitate the CoW for the formal “End of Defects” snagging at least 9 weeks prior to end of the 12 months defect period.

- Ensure that all defects reported are identified in terms of priority of response.

- Discuss and record any issues or concerns with Development Team & CoW within 1 weeks of receipt.

- At the end of the defects period, provide Development with a report on any repetitive defects issues that should be noted.

- At the end of defects period provide Development with a synopsis of key defect issues in order that these can be used for continuous improvement.

- Attend the end of defect inspection with the relevant MTC Heating Contractor, CoW, Employers Agent, and formally accept the building as being complete.

- Notify the relevant parties within the Teams that the building is out of defects period including Connect 24.

- Inform Development immediately if there are any issues which may be a potential latent defect.

- When notification of a defect is received, assess same and liaise with contractor as necessary (bearing in mind the priority / severity of the issue and when it was reported i.e. Friday afternoon).

- Contact tenant directly to check if defect has been addressed within the noted response time.

- Act on any unattended notified defect in order to have the defect corrected by MTC (uncorrected defects will be covered under the contract).

- Set clear dates in advance for the End of Defects snagging, at least 9 weeks prior to the defect date and End of Defects Final Check.

- Assets to attend the first end of defects with their MTC Heating contractor

- Assets must contact tenants to advise of initial End of Defects Inspections 9 weeks prior to Defects Date.

- Ensure that within 20 days of the Defect Date final snagging with the Employers Agent and CoW is undertaken.

  - Contractor to arrange for any equipment, e.g. boilers, MVHR which require servicing, to be undertaken within the tenth month of Defect Correction period.  Boilers must be serviced prior to the expiry of current Safety Certificate, which is completed at commissioning stage. In some situations, boilers may have been serviced earlier than 10 months prior to handover i.e. handover may have been delayed.  If this is the case, then arrangements should commence for the boilers to be serviced 10 months after the date they were originally commissioned.

  - Ensure items requiring service at the end of defects period are serviced.

  - Work with the Employers Agent to encourage the contractor to address all notified defects by the Defects Date i.e. 52 weeks from Completion.

Contractor

- Adhere to the Contractors Code of Conduct.

- To undertake action within agreed timescales and in accordance with Alpha’s response targets.

- Ensure all ‘no access’ visits are reported back to Assets Team and Employers Agent.

- Each defect should be listed as to the problem found, action taken and whether it is chargeable or not.

- Chargeable items can be recouped from Alpha on confirmation from the Employers Agent that the item is rechargeable.

4.0 Definitions

| DFC: | Department for Communities |
| --- | --- |
| Contractors Code of Conduct | Code of Conduct is to provide the contractor with the details of the expectations of Alpha Housing Association in the provision of defects services to its tenants. |
| Site/Scheme: | Land or property being developed |
| Practical Completion: | When all scheduled work to the property has been undertaken by the Developer and allocations will soon proceed |
| Completion Date: | Date when the development should complete |
| D D | Defects Date – Usually 52 weeks from Practical Completion |

Defects Correction Period Procedure - Summary

| PROJECT STAGE | TIME PERIOD | MEETING | PURPOSE | ATTENDEES | DOCUMENTS TO BE ISSUED |
| --- | --- | --- | --- | --- | --- |
| Defects Period | For 12 months after handover |  | Assets responsible for taking calls relating to defects and reporting same to the contractor in line with defects procedure. And responsible for reviewing the defects on a weekly basis and chasing up any unattended defects to the Contractor for action. Main Contractor responsible for all defects for 12-month period – both chargeable and non-chargeable items. | Assets, EA, Contractor | Defect Notification |
| End of Defects Correction period | Wk -9 before end of Defects Correction period |  | Assets responsible for issuing a formal timeline for End of Defects Correction Period process to Contractor, Employers Agent, CoW | COW, Assets, EA | Issue formal timeline |
| End of Defects Liability period | Wk -9 before end of Defects Liability period |  | HO & AO responsible for advising of any defect not previously recorded | HO, AO | List of unrecorded defects issued to EA |
| End of Defects Correction period | Wk -9 Monday before end of Defects Liability period | Tenant letters re admission | Assets writes to tenants to advise of End of Defects Inspections. Assets advises HO for information | AO & HO | Letters re access |
| End of Defects Correction period 1st inspection | Wk -7 Wed before end of Defects Liability period | On site | Inspection of units at end of defects correction period, to prepare a list any defects and the required action | CoW, AO, EA & Contractor | List prepared of defects to be undertaken as part of end of defects correction period. List formally issued to Contractor within 48 hrs). Works to be completed within a 20 working day period. |
| End of Defects Correction period Non Access Inspection | Wk -6 Wed before end of Defects Liability period | On site | Inspections of any units where access had been unavailable in previous week | CoW, AO, EA & Contractor | As above |
| End of Defects Correction period | Wk -1 Wed before end of Defects Liability period | On site | Defects list checked off for completion | CoW, AO, EA & Contractor | Any defect not actioned to be noted and works costed for completion by another contractor |
| End of Defects Correction period | 52 weeks from handover Wed |  | Building out of defects period and formal transfer to Assets. | CoW & AO | Assets issues Formal letter re End of defects and lists any o/s item |
| End of Defects Correction period | 52 weeks from handover |  | HO to complete the Tenant Satisfaction Surveys at the same time as the initial end of defect inspection | HO | Surveys saved to electronic filing system. |
| Statement of Account | 8 wks from handover |  | Development responsible for working with Employers Agent for issue of Statement of Account. All defects to be completed. Any issues preventing the issue of Statement of Account to be brought to the attention of the DD | Development Team | Issue of Statement of Account and release of retention monies |
| Post Project Evaluation | 52 wks from handover |  | Development responsible for completing PPE and submitting to DFC in the required format. | Development | Saved to electronic filing system. |

# CONTRACTOR’S CODE OF CONDUCT

EMPLOYER’S REQUIREMENTS FOR CONTRACTORS RESPONSE TO DEALING WITH DEFECTS ETC ARISING DURING THE DEFECTS LIABILITY PERIOD

# Statement of Intent

Alpha Housing Association and the contractor work together throughout the contract and strive to provide high quality, defects free attractive homes.

All properties are subject to a defects liability period, and through this document it is hoped that a process for attending to defects in the 12 months between handover and the final defects inspection can be clearly defined.

The aim of the Code of Conduct is to provide the contractor with the details of the expectations of Alpha Housing Association in the provision of services to its tenants covering the following: -

- Response Times

- Quality of Service

- Relationship with Tenants

- Relationship with Alpha

## RESPONSE TIMES

Alpha Housing Association has defined below the work which should be completed within the defects liability period.  These repairs have all been given a response time which we expect the contractor to comply with.  Failure to comply without providing justification to Alpha will result in the Employer/ Client obtaining the service of ‘others’ to correct the unattended defects.  The cost of these unattended defects will be deducted from monies due to the Contractor/ Developer.  A seven day notice will be issued informing the Contractor/Developer that the Employer/Client has made good the defect.  For NEC 3 or 4 Contracts defects will be dealt with in accordance with Core Clause 4 of the Contract.

The Contractor/Developer will be notified of each of the defects, which will detail the date the work should be completed.  If the work cannot be completed within this defined timescale or subsequent visits to the property are required, both the tenant and Alpha must be advised.  The contractor will be required to provide a monthly report detailing the number of defects reports issued, date work commenced, date work completed, any comments on cause of defect etc.  The contractor is able to bill Alpha for any abortive work providing they advise Alpha immediately.

Below are the categories of defects and the timescales they should be responded to.

## EMERGENCY WORK - 24 HOURS

No heating

No water

No electricity

Burst pipes

Broken W.C. i.e. not flushing or health and safety hazard

Any health and safety issue

Blocked drains

Warden call or fire alarm panel faults

Emergency lighting not operating

Fire exits not opening

## URGENT WORK – 4 WORKING DAYS

Some sockets not working

Some radiators not heating

Timeclock defective but still able to use manual heating controls

Front door and back doors sticking (fire exit)

Roof tiles missing or dislodged

Blocked baths, sinks etc.

Restrictor stays missing

## ROUTINE WORK – 20 WORKING DAYS

Leaking gutters

Defective kitchen doors and/or handles

Defective internal door handles, hinges, easing doors etc.

Clipping pipes

## END OF DEFECTS PERIOD

Easing and adjusting doors, keepers etc.

Filing in settlement cracks

Provision of additional sealant around windows, skirting etc. due to any drying out

Sealing any joints in gutters and downpipes

First inspection of gas/oil boilers

First service of fire alarms, fire extinguishers, burglar alarms

Welding any loose joints in vinyl flooring

The contractor must commence the making good defects work within 21 days of receiving the work schedules.  The making good schedule will be issued a minimum of twenty working  days before  the 12 months liability period has ended.

QUALITY OF SERVICE

- Contractors must adhere to the requirements of the Health and Safety at Work Act 1974 and also follow these basic guidelines:

- provide adequate resources to ensure that proper provision can be made for Health and Safety.

- adequate training has been provided to those persons carrying out the work at Alpha’s properties.

- all plant machinery and equipment used should be safe and maintained properly and sited safely.

- Alpha should be notified if the contractor finds something which they consider potentially or imminently dangerous.

- All repairs completed must be of an acceptable quality to Alpha.  All complaints of dissatisfaction must be fully investigated and resolved.  The work should comply with that which is specified on the works order, where this is not feasible Alpha should be contacted.

RELATIONSHIP WITH TENANTS

- All tenants must be given notice of when the work will commence.

- All dwellings must be kept secure at all times.

- Workmen should not smoke, work under the influence of alcohol, use offensive language, play radios or use the tenants’ facilities without permission.

- Contractors must not comment to the tenant with regard to the original installation, make and model of any appliance, materials used in the construction of the properties.  Nor should they comment about other work completed with any of Alpha’s accommodation or other tenants.

- Where a tenant becomes difficult or will not provide access, the contractor should leave and contact Alpha immediately.

RELATIONSHIP WITH ALPHA

- The contractor should communicate any problems immediately to Alpha with regard to access; abortive calls or repairs which cannot be full remedied in one visit and so will not meet the defined response times.  A new completion date must be confirmed.

- The contractor must return one copy of the works order signed and dated by both the work operative and the tenant.

- The contractor should provide monthly reports within the agreed timescale.

- The contractor must have adequate staff to provide a high quality service and meet all the response times.

### The above standard is applicable to all the work being completed in the dwelling whether by the main contractor or sub-contractor.  The contractor’s performance will be reviewed on an ongoing.

Maintenance Schedule

Scheme Name

| Item | Installer Details | Date of Commissioning | Is servicing included during the 12 months defects period | If servicing included please give no. of visits per year. | Notes/ Comments |
| --- | --- | --- | --- | --- | --- |
| _ no. of gas boilers |  |  |  |  |  |
| _ no of communal boilers |  |  |  |  |  |
| _ no of smoke alarms |  |  |  |  |  |
| _ no of carbon monoxide alarms |  |  |  |  |  |
| _ No. of communal water heaters |  |  |  |  |  |
| _ No of fire panels |  |  |  |  |  |
| _No. of emergency lights |  |  |  |  |  |
| _No of lifts |  |  |  |  |  |
| _ No of door entry systems |  |  |  |  |  |
| _ No of Automatic doors |  |  |  |  |  |
| _no of smoke vents |  |  |  |  |  |
| Details of card for lift line |  |  |  |  |  |
| Details of CCTV Equipment including details of number of monitors and cameras |  |  |  |  |  |
| Landscaping and grass cutting |  |  |  |  |  |

SCHEDULE 9

CONTRACT ADDENDUM

SUSTAINABILITY REPORT

At every monthly progress meeting thereafter, the Contractor submits to the Employer the following deliverables in support of the sustainability requirements:

The Developer/Contractor must complete the CSR monthly to confirm its sustainability requirements and which includes the following:

- Reporting on social, economic and environmental requirements and KPIs;

- Report on payment of Subcontractors; and

- the Contractor’s Health and Safety Report (using the GCH&SOG reporting template);

The above reports must be updated by the Developer/Contractor monthly, detailing the changes from the last reports.

The Contractor must cooperate with the Employer and provide all information necessary to review its progress towards meeting the sustainability requirements.

The Contractor submits to the Employer a final CSR by the Completion Date as evidence that requirements have been complied with.

Considerate Constructors Scheme

The Developer/Contractor shall register the site and pay the associated fee with the Considerate Constructors’ Scheme (CCS) see: https://www.ccscheme.org.uk/

The Developer/Contractor shall take the necessary measures to ensure that the site receives a Certificate of Performance Beyond Compliance after assessment under the CCS scheme.

Equality of Opportunity

The Developer/Contractor shall comply with all applicable fair employment, equality of treatment and anti-discrimination legislation, including in particular, the Employment (Northern Ireland) Order 2002, the Fair Employment and Treatment (Northern Ireland) Order 1998, the Sex Discrimination (Northern Ireland) Order 1976 and 1988, the Employment Equality (Sexual Orientation) Regulations (Northern Ireland) 2003, the Equal Pay Act (Northern Ireland) 1970, the Disability Discrimination Act 1995, the Race Relations (Northern Ireland) Order 1997, the Employment Relations (Northern Ireland) Order 1999 and the Employment Rights (Northern Ireland) Order 1996. The Developer/Contractor ensures that in its employment policies and practices and in the delivery of the works and services required under this Contract it has due regard to the need to promote equality of treatment and opportunity between:

- persons of different religious beliefs or political opinions;

- men and women or married and unmarried persons;

- persons with and without dependants (including women who are pregnant or on maternity leave and men on paternity leave);

- persons of different racial groups (within the meaning of the Race Relations Northern Ireland) Order 1997);

- persons with and without a disability (within the meaning of the Disability Discrimination Act 1995);

- persons of different ages; and

- persons of differing sexual orientation.

The Developer/Contractor takes all reasonable steps to ensure the observance of the provisions of the above clause by all servants, agents, employees, consultants and Sub-Contractors of the Developer/Contractor.

The Developer/Contractor acts, and ensures that its supply chain members act, in a way that is compatible with the Convention rights within the meaning of Section 1 of the Human Rights Act 1998. The Developer/Contractor shall indemnify the Employer against breaches of the Act by the Developer/Contractor.

Modern Slavery

The Developer/Contractor shall ensure that the Developer/Contractor and its supply chain:

- do not engage in any activity, practice or conduct which constitutes an offence under the Modern Slavery Act (MSA) 2015; and

- comply with all applicable anti-slavery and human trafficking laws, statutes, regulations and codes that are in force from time to time, including, but not limited to, the MSA 2015.

In performing its obligations under the contract, the Developer/Contractor shall ensure it:

- develops and maintains throughout the contract period a human rights policy which must be approved at board level and published on the Developer/Contractor’s website. The policy must detail procedures to ensure the Developer/Contractor’s compliance with the MSA 2015 in accordance with any requirements of the MSA 2015;

- provides within 30 days of contract award, a copy of its human rights policy and the processes it has in place which demonstrates that its activities give due consideration to human rights;

- includes in its contracts with its Subcontractors and supply chain anti-slavery and human trafficking provisions that are at least as onerous and carry the same liability as that set out in this clause;

- monitors and reviews contracts / subcontracts identified as having a high risk to human rights and puts in place appropriate measures to ensure the protection of human rights; and

- includes Modern Slavery and Protection of Human Rights as a standing agenda item at monthly progress meetings and meetings with its supply chain.

The Developer/Contractor shall indemnify the Employer against any losses, liabilities, damages, costs (including, but not limited to, legal fees) and expenses incurred by the Developer/Contractor as a result of the Developer/Contractor and/or its supply chain breaching the requirements of the MSA 2015.

Data Protection

The Developer/Contractor and its supply chain are to comply with all data protection legislation as follows:

- the UK General Data Protection Regulation (UK GDPR) and the Data Protection Act 2018, as amended from time to time;

- the DPA 2018 to the extent that it relates to processing of personal data and privacy;

- all applicable Law about the processing of personal data and privacy.

The GDPR applies to the processing of personal data. The Developer/Contractor must comply with the following requirements where personal data shall be processed:

- The following terms used in this section of the Works Information have the definitions given to them in the GDPR.

- The Data is personal data.

- The Employer is the controller.

- The Developer/Contractor is the processor.

- The Developer/Contractor processes the Data only in accordance with the Data Sharing Agreement and in compliance with the requirements of the GDPR.

- The Developer/Contractor obtains written commitments to confidentiality from persons authorised to process the Data and requires them not to process the Data except in accordance with the Data Sharing Agreement.

- The Developer/Contractor implements technical and organisational measures to maintain a level of security of the Data appropriate to the risk presented by processing.

- The Developer/Contractor includes in any subcontract which involves the processing of Data the same requirements for Data processing to those in this contract. Further sub-subcontracting which involves the processing of Data is not made without the agreement of the Employer.

- The Developer/Contractor assists the Employer by appropriate technical and organisational measures for the fulfilment of the Employer’s obligation under the GDPR.

- In accordance with the instruction of the Employer the Developer/Contractor deletes or returns the Data to the Employer before the defects date.

- The Developer/Contractor makes available to the Employer information necessary to demonstrate compliance with the requirements for processing the Data.

- The Developer/Contractor assists in audits, including inspections, conducted by or on behalf of the Employer.

- The Developer/Contractor immediately informs the Employer if it believes that an instruction infringes the GDPR or data protection provisions

- If instructed by the Employer the Developer/Contractor assists the Employer to ensure compliance with its obligations under the GDPR.

SUSTAINABLE TIMBER

All timber and wood derived products acquired by the Developer/Contractor and supply chain for use in the performance of the contract shall be certified as legal and sustainable from a scheme or schemes which are recognised as delivering NI and UK Government requirements for timber procurement.

- The Developer/Contractor shall comply with Procurement Guidance Note 04/06:

https://www.finance-ni.gov.uk/publications/pgn-0406-procurement-timber-and-wood-products

- The Developer/Contractor shall comply with UK Timber Procurement Policy (TPP) guidance and support:

https://www.gov.uk/government/collections/timber-procurement-policy-tpp-guidance-and-support

- The Developer/Contractor shall comply with UK Government Buying standards for wood products:

https://www.gov.uk/government/uploads/system/uploads/attachment_data/file/339920/GOV.UK_GBS_for_wood_products.pdf

Acceptable certification schemes are listed at the above links.

The Developer/Contractor, at the request of the Employer shall supply evidence that it has procured timber and wood products that are certified as legal and sustainable in accordance with the guidance contained within the NI and UK Government requirements.

- For example: Forest Stewardship Council (FSC); Programme for the Endorsement of Forest Certification (PEFC); Canadian Standards Association & Sustainable Forestry Initiative with certified products containing >70% certified raw material are acceptable schemes.

The acceptance of procurement procedures followed by the Developer/Contractor are as follows:-

- Timber procurement procedures regarding chain of custody. The following is required for Category A evidence using a Certification Scheme. The certificate is acceptable if all of the points below are satisfied:

- The timber is certified under one of the approved schemes;

- The product is covered by the scope of the certificate;

- The certificate is current with regard to its time period; and

- The certificate is issued by the company selling the product to the Developer/Contractor.

EXECUTED as a deed by

in the presence of:

EXECUTED as a deed by

in the presence of:

EXECUTED as a deed by

in the presence of:

EXECUTED as a deed by

acting by a director

in the presence of:

EXECUTED as a deed by

acting by a director

in the presence of:

SCHEDULE 9

Social Value

- Background

## The Northern Ireland Civil Service and its associated agencies are committed to the promotion of social inclusion and equal opportunities as key objectives in the Sustainable Development Strategy for Northern Ireland. They want to promote a fair and inclusive jobs market in which every individual can participate to achieve their full potential, both as a way of maximising value for money from its investment in these services and to get more people working in better jobs, who can deliver future Government investment and help attract inward investment.

## To help achieve these objectives and address the strategic aims of the Contracting Authority, it is required that the successful Contractor will, as a condition of contract, deliver measurable social value outcomes as set out below.

# 2.0	Social Value Points Target

# The Contractor must provide social value initiatives to a minimum value of 100 social value points per £1m of contract value (and pro-rata).  The social value initiatives which are eligible for inclusion on this contract are outlined in the Social Value Point Matrix at 3.0.

# The Contractor may provide a mix of all eligible social initiatives in the matrix or may provide only one or a subset of the eligible social value initiatives, based on business need and providing the overall social value points target is met.

The Contractor must only count towards their Social Value points target those activities that have been delivered as a direct result of the social considerations requirements set out in this Schedule.

- Social Value Points Matrix

| - Social consideration | - Amount | - Buy Social points (pro-rata) |
| --- | --- | --- |
| - Paid employment for people who are considered to be disadvantaged in the labour market. | - 52 person weeks FTE (Build) | - 75 |
| - Paid employment for people who have a disability. | - 52 person weeks FTE (Build) | - 90 |
| - Paid employment for people who are eligible for a priority group detailed below. | - 52 person weeks FTE (Build) | - 90 |
| - Paid employment for Apprentices. | - 52 person weeks FTE (Build) | - 75 |
| - Paid employment Student Placements/Professional Trainees. | - 52 person weeks FTE (Build) | - 50 |
| - Continued Employment for someone who has completed their 52 week period. | - 52 person weeks FTE (Build) | - 20 |
| - Unwaged work experience placements for people who are considered to be disadvantaged in the labour market. | - 4 weeks of FTE | - 10 |
| - Unwaged work experience placements for people who have a disability. | - 4 weeks of FTE | - 15 |
| - Unwaged work experience placements for people who are eligible for a priority group detailed below. | - 4 weeks of FTE | - 15 |
| - Skills development and educational attainment for people who are considered to be disadvantaged in the labour market. | - 8 hours of activity | - 10 |
| - Skills development and educational attainment for people who have a disability | - 8 hours of activity | - 15 |
| - Skills development and educational attainment for people who are eligible for a priority group detailed below. | - 8 hours of activity | - 15 |
| - Working with the Voluntary, Community, Social Enterprise (VCSE) Sector - business development and knowledge sharing. | - 8 hours of activity | - 10 |
| - Inclusion of Social and Micro Enterprises in the contract’s supply chain | - Inclusion of at least one Social or Micro Enterprise in the supply chain. | - 20 |
| - In-work progression and skills development | - 1 Strategy | - 10 |
| - Fair Work strategy for the contract | - 1 Strategy | - 10 |
| - Human Rights strategy for the contract including Ethical Supply chain | - 1 Strategy | - 10 |
| - Supply Chain Resilience and Capacity strategy for the contract | - 1 Strategy | - 10 |
| - Environmental Strategy for the contract including Carbon Reduction. | - 1 Strategy | - 10 |
| - Waste and Resource Efficiencies in the delivery of the contract. | - 1 VCSE organisation - 1 SME - 1 business | - 20 - 15 - 10 |
| - Environmental Awareness Initiatives | - 8 hours of support or improvement | - 10 |
| - Health and Wellbeing strategy for the staff employed on the contract, including Equality, Diversity and Inclusion | - 1 Strategy | - 10 |
| - Health and Wellbeing initiatives | - 8 hours of support | - 10 |
| - Community engagement activities to determine the most relevant artwork or cultural activities. | - 8 hours of activity | - 10 |

## 4.0 Supplier Guidance

## 4.1	Paid Employment Opportunities

The delivery of paid employment for people who face barriers to employment. The Supplier must ensure that they satisfy one of the following categories:

- a person who is in education or has left education in the last 12 months and is seeking employment; or

- person aged under 25 that has been unemployed for more than 26 weeks and is seeking employment;

- person aged over 25 that has been unemployed for more than 52 weeks and is seeking employment;

- people who are underrepresented and new to the sector and are seeking employment;

- people with a disability;

- student placements;

- apprentices working on the contract;

- professional trainees;

- people who meet the conditions of the Contracting Authority’s Priority Groups, as set out at clause 4.1.2 and are seeking employment;

- another person who faces barriers to employment or who is at risk of social exclusion and is seeking employment, as accepted by the Authority, at the Authority’s discretion

4.1.2	Contracting Authority’s Priority Groups [remove if not appropriate]

For a person to qualify as a member of the Contracting Authority’s Priority Groups, the Contractor must ensure that they satisfy one of the following categories:

- People at risk of re-offending

- Female apprentices in construction roles

- Looked After Child/Care leaver

Each employment opportunity can be counted towards the Social Value Points target for up to 52 person weeks (*with the exception of Apprentices), where the definition of a person-week is the equivalent of one person working for 5 days.

After 52 weeks, if the person continues to be employed on the contract they can be moved to the ‘Continued Employment’ category where they will continue to count towards the target at a lower points value.

*Apprentices can be counted towards the Social Value Points target for the duration of their time working on the contract.

Each employment vacancy must be notified to Jobcentre Online (www.jobcentreonline.com) and one or more organisations registered on the Social Value Unit website (www.buysocialni.org/contractors/find-a-broker/) and/or equivalent agencies named by or agreed with the Authority for this purpose. Sufficient time must be allowed for information on vacancies to be made available and applications submitted.

Support and Training

Each beneficiary must be:

- provided with the opportunity to obtain training and accreditation relevant to the tasks they are expected to perform;

- asked if they would like to receive support with numeracy, literacy and information technology, and those that do must be signposted to sources of training and accreditation for these Essential Skills; and

- supported in undertaking training e.g. through flexible working arrangements, where practicable.

The costs of training and accreditation/registration must be covered by the Supplier either directly or through public or industry sources that they identify.

## 4.2	Unwaged work experience placements

The delivery of unwaged work experience placements for:

- people who face barriers to employment and/or who are located in deprived area. This can include people who are long-term unemployed, people who are located in deprived areas, people who have a disability and people who are underrepresented in the contracts workforce.

- people who meet the Contracting Authority’s priority groups, as set out at 4.1.2. [remove if not appropriate].

The Supplier is to provide work placement participants with meaningful work experience, training and development which will enhance their opportunities for future employment.

Each unpaid work placement opportunity must be notified to one or more organisations registered on the Social Value Unit website (https://buysocialni.org/contractors/find-a-broker/) and/or equivalent agencies named by or agreed with the Authority for this purpose.

## 4.3	Skills development and educational attainment

The delivery of skills development and educational attainment support in areas related to the contract to a school or organisation within the Voluntary, Community and Social Enterprise sector to aid the career development of:

- people who are considered to be disadvantaged in the labour market or at risk of social exclusion. This can include people who are long-term unemployed, people who are located in deprived areas, people who have a disability and people who are underrepresented in the contracts workforce.

- people who meet the Contracting Authority’s priority groups, as set out at 4.1.2. [remove if not appropriate]

This support can include vocational talks, curriculum support, careers guidance, workplace visits, mentoring or as otherwise agreed by the Authority.  The Supplier shall agree the scope of activities with the Authority prior to delivery.

Each opportunity must be notified to one or more organisations registered on the Social Value Unit website (https://buysocialni.org/contractors/find-a-broker/) and/or equivalent agencies named by or agreed with the Authority for this purpose.

## 4.4	Inclusion of Social and Micro Enterprises in the contract’s supply chain

The Supplier will include social enterprises or micro businesses that are within their first 48 months of trading in the supply chain, in relation to any sub-contracting or other business opportunities available as a result of this contract. The Supplier should ensure this is a meaningful opportunity for the social enterprise or micro business.  Each social or micro enterprise included within the supply chain will be eligible for achieving the points against this initiative rather than each contract with the enterprise.

Social Enterprise NI (SENI) (https://www.socialenterpriseni.org) is the representative body for social enterprises in Northern Ireland. SENI connect, support, develop and sustain vibrant businesses to create social change. SENI can provide advice and guidance to help businesses who want to explore opportunities to work with social enterprises in Northern Ireland.

Any action taken by the Authority or their agents to broker relationships between the Supplier and local individuals/firms/agencies does not imply and should not be deemed to imply that they or their agents consider the individual/firm/agency as suitable for engagement by the Supplier.

## 4.5	Business development and knowledge sharing

The Supplier will deliver skilled advice in an area related to the contract to:

- an organisation/organisations within the Voluntary, Community and Social Enterprise (VCSE) sector.

- micro businesses that are within their first 48 months of trading

This may include: mentoring, training, advice or other professional voluntary services or equivalent initiatives as agreed with the Authority, at the Authority’s discretion. The Supplier shall agree the scope of activities with the Authority prior to delivery.

Each skilled advice opportunity must be notified to one or more organisations registered on the Social Value Unit website (https://buysocialni.org/contractors/find-a-broker/) and/or equivalent agencies named by or agreed with the Authority for this purpose.

4.6	Fair Work Practices

The New Decade, New Approach Deal emphasised the importance of access to good jobs, where workers have a voice that provides a level of autonomy, a decent income, security of tenure, satisfying work in the right quantities and decent working conditions. Creating good jobs and protecting workers’ rights impacts upon better health and wellbeing by tackling inequalities, building self-efficacy, and combating poverty and also helps employers to attract and retain the talent they need to grow and thrive.

The Supplier will develop, implement and maintain a fair work practices policy in relation to this contract which demonstrates the Supplier’s commitment to ensuring that workers employed on this contract are treated fairly, humanely and equitably.  This should be submitted within Click here to enter text. days of contract award.

The Fair Work Policy must at least include and address among other things:

- employment terms and conditions, including pay, job security, minimum guaranteed hours

- working environment, including health, safety and wellbeing, social support and cohesion, employee voice and representation and work life balance

- skills development, including opportunities for progression

- fair shift arrangements including adequate rest breaks

- processes for identifying and managing the risks of modern slavery in the delivery of the Contract, including in the supply chain; and

- other initiatives that tackle inequality, promote staff welfare and support staff wellbeing.

The Supplier shall submit an annual progress report to the Authority. The report shall be in writing and shall detail the actions taken by the Supplier and its sub Suppliers (if any) to implement the Fair Work strategy in the delivery of the Contract, as well as setting out quarterly actions for the year ahead.

The Authority reserves the right to survey workers on workforce matters such as access to terms and conditions, staff policies such as grievance procedures and how payment for services is managed.

4.7	Human Rights Strategy Including Supply Chain

Doing business with respect for human rights is linked to business opportunities such as: improved employee retention and recruitment rates; greater access to customers and buyers who increasingly value ethical practices; and, improved relationships with workers, communities and stakeholders, resulting in a stronger business reputation.

The Supplier will develop, implement and maintain a human rights policy in relation to work carried out on this contract.

Within Click here to enter text. days of contract commencement, Suppliers must provide a copy of this human rights policy, and the processes they have in place which demonstrate that their activities, including those within their supply chain, in relation to this contract show a consideration to human rights.  Supplier guidance related to human rights policies and due diligence is available at: https://buysocialni.org/Suppliers/Supplier-resources/

The Supplier shall submit an annual progress report to the Authority. The report shall be in writing and shall detail the steps taken by the Supplier and its sub Suppliers (if any) to implement the human rights policy and procedures on the Contract.

The Authority reserves the right to inspect supply chain audits, survey workers on workforce matters such as access to terms and conditions and staff policies such as grievance procedures and request information on how payment for services is managed.

4.8	Supply chain resilience and capacity

As set out in the Programme for Government, the Executive aim to develop a regionally balanced economy that is globally competitive and carbon neutral and to build a place where everyone can reach their potential. The Executive’s Green Growth Strategy aims to ensure the sustainability of Northern Ireland’s natural environment, while fostering the necessary conditions for innovation, investment and competition that can give rise to new sources of economic growth, while building resilient ecosystems.  By doing so, we can create jobs, reduce carbon, enhance profitability, lower waste, increase efficiency and protect our environment and climate for future generations.

The Supplier will develop, implement and maintain a strategy to continuously monitor and improve the supply chain’s resilience and capacity on this Contract. This should be provided within Click here to enter text. days of award of the Contract and must at least include and address among other things the Supplier’s actions to:

- Modernise delivery by increasing circular solutions throughout the supply chain.

- Promote and support innovation throughout the supply chain to deliver more sustainable goods and services.

- Demonstrate collaboration and knowledge sharing throughout the supply chain to support economic growth and encourage ethical and resilient business.

- Maximise security of supply on the contract, for example, by minimising proximity of supply chains to point of delivery.

- Employ low or zero-carbon practices and materials on the contract and support the contract’s supply chain to minimise carbon footprint and emissions.

At end of year review meetings, the Supplier will submit an annual progress report to the Authority, detailing the progress made in relation to the Supply Chain Resilience and Capacity Strategy and setting out the quarterly actions for the year ahead.

The report shall be in writing and shall detail the steps taken by the Supplier and its sub Suppliers (if any) to implement the Supply Chain Resilience and Capacity Strategy on the Contract. The Authority reserves the right to request an updated progress report at interims throughout the Contract.

4.9	Environmental Strategy including Reducing Carbon

As set out in the Programme for Government, the Executive aim to develop a regionally balanced economy that is globally competitive and carbon neutral and to build a place where everyone can reach their potential.  The Executive’s Green Growth Strategy aims to ensure the sustainability of Northern Ireland’s natural environment, while fostering the necessary conditions for innovation, investment and competition that can give rise to new sources of economic growth, while building resilient ecosystems.  By doing so, we can create jobs, reduce carbon, enhance profitability, lower waste, increase efficiency and protect our environment and climate for future generations.

The Supplier will develop a sound proactive environmental approach in the delivery of this Contract, designed to minimise harm to the environment by:

- conserving energy and minimising carbon emissions and identifying opportunities to increase the amount of renewable energy used on the Contract;

- conserving materials such as wood, paper and other natural resources;

- minimising packaging and waste, and using compostable, reusable or recyclable options;

- phasing out the use of single-use resources, instead re-using (where possible), recycling or using recycled resources;

- promoting circular economy outcomes through extending the useful life, reusing, refurbishing and reconditioning products used to deliver this Contract;

- phasing out the use of ozone depleting substances and minimising the release of greenhouse gases, volatile organic compounds and other substances damaging to health and the environment;

- raising awareness of the environmental impacts related to the Contract amongst the Supplier’s workforce and encouraging environmentally conscious behaviours within the workplace including the use of sustainable methods of transport for commuting.

The Supplier will develop, implement and maintain an Environmental Strategy detailing their environmental commitments in relation to this Contract. The Strategy will set out the processes and actions that the Supplier will undertake to demonstrate that their activities in relation to this contract show a consideration to the environment and a commitment to continually reduce the contract’s impact on the environment.  This should be provided within Click here to enter text. days of contract award.

The Supplier shall submit an annual progress report to the Authority, detailing the progress made in relation to the Environmental Strategy and setting out the quarterly actions for the year ahead.  The report shall be in writing and shall detail the steps taken by the Supplier and its sub Suppliers (if any) to implement the environmental improvements on the Contract.  The Authority reserves the right to request an updated progress report at interims throughout the contract.

4.10 Waste and Resource Efficiencies in the delivery of the contract

Moving towards a more circular economy will reduce our demand for virgin materials and reduce our greenhouse gas emissions, by keeping resources in use as long as possible, extracting maximum value from them, minimizing waste and promoting resource efficiency.  Companies that manage their business waste efficiently achieve significant cost and energy savings.  In doing so they also make a contribution to tackling climate change. Reuse, repair, remanufacture and recycle are key components of the circular economy with the focus being to retain as much value as possible in line with the waste hierarchy.

The Supplier will take measures to actively reduce waste and transfer business waste, unwanted materials and by-products (both bio-based and technical materials) from the contract’s supply chain to be reused, repaired recycled, reprocessed and repackaged by another organisation.

Reuse and repair organisations work to do more with less, to make better use of available resources and to reduce waste while promoting new forms of employment and tackling inequality.  A directory of reuse and repair organisations can be found at www.ni-rn.com/reuse-and-repair-near-me/.

Invest NI’s Resource Matching Service (https://www.investni.com/support-for-business/resource-matching-service) provide advice and guidance to help businesses achieve resource matching solutions specific to their resource and waste management needs.

Any action taken by the Authority or their agents to broker relationships between the Supplier and local individuals/firms/agencies does not imply and should not be deemed to imply that they or their agents consider the individual/firm/agency as suitable for engagement by the Supplier.

4.11 Environmental Awareness Initiatives

The delivery of environmental awareness initiatives in areas related to the Contract designed to influence staff, suppliers, customers and communities through the delivery of the contract to support environmental protection and improvement.

Activities may include: delivery of training to the contract workforce to promote environmental awareness in the performance of the contract; partnering/collaborating in engaging with the community in relation to the performance of the contract, to support environmental objectives; volunteering opportunities for the contract workforce, e.g. undertaking activities that encourage direct positive impact; supply chain events to raise awareness of environmental issues in relation to the contract; or equivalent initiative as agreed with the Authority, at the Authority’s discretion. The Supplier shall agree the scope of activities with the Authority prior to delivery.

Each opportunity must be notified to one or more organisations registered on the Social Value Unit website (https://buysocialni.org/contractors/find-a-broker/) and/or equivalent agencies named by or agreed with the Authority for this purpose.

4.12	Health and Wellbeing for existing employees

The Public Health Agency (PHA) recognises that using the workplace as a setting to promote and support health and wellbeing makes good business sense and has many benefits for both employers and employees which is especially important as workplaces emerge from the COVID-19 pandemic. According to the World Health Organisation, the definition of a healthy workforce is: ‘... one in which workers and managers collaborate to use a continual improvement process to protect and promote the health, safety and wellbeing of all workers and the sustainability of the workplace’.

The Supplier will develop, implement and maintain a Health and Wellbeing strategy to continuously support and improve the health and wellbeing of employees engaged on this Contract.

The strategy should be provided within Click here to enter text. days of award of the Contract and must at least include and address among other things the Supplier’s actions to:

- engage with employees working on the Contract to determine the most important health and wellbeing issues to address;

- implement measures to improve employee retention levels;

- reduce stigma, increase awareness of health and well-being issues and provide adequate training for employees and managers engaged on the Contract;

- ensure a safe and healthy physical work environment on the Contract;

- promote a positive psychosocial work environment and prevent stress at work;

- support employees to use personal health resources in the workplace and adopt a healthier lifestyle;

- support the health and wellbeing of employees working remotely on the Contract;

- increase awareness of equality, diversity and inclusion issues within the contract workforce and provide adequate training for employees and managers engaged on the Contract;

- adopt inclusive and accessible recruitment practices to increase equality, diversity and inclusion of the contract workforce;

- identify and address inequality in employment, skills and pay in the contract workforce; and,

- support all employees working on the Contract, including those with mental health problems, to remain in and thrive through work.

At end of year review meetings, the Supplier will submit an annual progress report to the Authority, detailing the progress made in relation to the Health and Wellbeing Strategy and setting out the quarterly actions for the year ahead. The report shall be in writing and shall detail the steps taken by the Supplier and its sub-Suppliers (if any) to implement the Health and Wellbeing Strategy on the Contract. The Authority reserves the right to request an updated progress report at interims throughout the Contract.

4.13	Health and Wellbeing Initiatives

The Supplier will deliver initiatives that are designed to influence staff, suppliers, customers and communities through the delivery of the contract to support health and wellbeing, including physical and mental health.

This may include: coaching, training, advice or other equivalent initiatives as agreed with the Authority, at the Authority’s discretion.

The Supplier shall agree the scope of activities with the Authority prior to delivery.

## 4.14	Community engagement activities to determine the most relevant artwork or cultural activities.

The Supplier will deliver initiatives that are designed engage with communities to determine the most relevant artwork or cultural activities that should be delivered through the contract.

The Supplier shall agree the scope of activities with the Authority prior to delivery.

# General requirements

## 5.0	Positive Action to maximise employment opportunities

All employment vacancies on the contract are to be notified by the Supplier to www.jobcentreonline.com and one or more organisations registered on the Buy Social website (https://buysocialni.org/contractors/find-a-broker/) and other agencies named by or agreed with the Authority for this purpose. Sufficient time must be allowed for information on vacancies to be made available and applications submitted.

## 6.0	Security clearance

The Supplier shall obtain security clearance for all persons visiting the workplace in relation to employment, work experience or site visits to the same standard as all other personnel involved in the contract in accordance with the Contract Information.

## 7.0	Data Protection

Where the Supplier has selected to provide paid employment opportunities for people who face barriers to employment the following Data Protection arrangements will apply.

A Data Protection Consent Form (as provided) must be completed by each person in the Supplier’s Social Value Monitoring Report and therefore counted towards the Social Value target for the contract. Consent shall be provided on a voluntary basis and can be withdrawn at any time (as noted within the Data Protection Consent Form). Completed Consent Forms must be sent to the Strategic Investment Board.  Notwithstanding the above, the Supplier shall ensure it satisfies itself in respect of its obligations under the Data Protection Act 2018 (as may be amended from time to time) and the General Data Protection Regulation (GDPR).

The Supplier, at contract award, shall enter into a Data Processing Agreement with the Strategic Investment Board. This is to enable the sharing of personal information (provided in the Social Value Monitoring Report) for the purposes of checking and verification.

The Supplier must only engage a Sub-processor, in relation to the Social Value requirements, with the prior consent of the Strategic Investment Board and must enter into a Data Processing Agreement with any Sub-processor with whom the information in the Supplier’s Social Value Monitoring Report is shared.

## 8.0	Health and Safety

It is the responsibility of the Supplier to ensure that persons recruited or otherwise visiting the worksite in relation to the social consideration requirements has or is supported to obtain the necessary health and safety accreditation or other appropriate measures and appropriate personal protective equipment if necessary.

## 9.0	Costs

The Supplier shall deliver the social value requirements within their tender sum (omitting any grants or other public funding that will be obtained to offset the costs of delivering the social value requirements).

## 10.0	The Authority’s Support Activities

Organisations delivering employability, education and skills training are listed on the Social Value Unit website (https://buysocialni.org/contractors/find-a-broker/) established for the purpose of helping Suppliers identify social value beneficiaries.  However, this action does not comprise or imply any promise on the part of the Authority or their agents to provide suitable services.  Responsibility for sourcing social value beneficiaries remains with the Supplier.

Any action taken by the Authority or their agents to broker relationships between the Supplier and local individuals/firms/agencies does not imply and should not be deemed to imply that they or their agents consider the individual/firm/agency as suitable for engagement by the Supplier.

## 11.0	Sub-contractors

It is the Supplier’s responsibility to develop a working method and where necessary secure sub-contractor co-operation in order to achieve the Authority’s social consideration requirements.

## 12.0	Monitoring Information

The Supplier shall provide a completed Social Value Monitoring Report every month using the Social Value online monitoring system. The Authority retains the right to request interim reports.

This Report will include, subject to the initiatives selected for delivery by the Supplier and Data Protection

- the value of services invoiced to date;

- a listing of all of the people who face barriers to employment who have been employed on the contract, which barrier to employment category they meet and the number of FTE weeks they have delivered since their employment;

- the number of weeks of unwaged work experience delivered and details of which barrier to employment category each beneficiary meets;

- details of skills development and educational attainment activities delivered, including brief description of activity and hours of support provided;

- details of business development and knowledge sharing initiatives delivered, including details of the organisation(s), brief description of activity and hours of support provided;

- details of any Social Enterprises or Micro Enterprises that have been included in the supply chain; and,

- the actions being undertaken to address any problems identified.

The Supplier shall provide all information necessary, including obtaining it from sub Suppliers and agencies, and cooperate with the Authority's Project Manager to review progress on delivering the overall Social Value requirements.

The Supplier should not record any activities on the Social Value Monitoring Reports to the extent that they are delivered [wholly or in part] for a purpose other than satisfying the requirements specified in this Schedule.